## Sheet1
ID | TaskType | Label | PlannedStart | PlannedEnd | ActualStart | ActualEnd | Float | Status | File
SI---1P2A559 | TT_Task | DESIGN PHASE PIPING SUPPORTS ON RACK LOT3 | 06/08/2021 | 02/09/2021 | 06/08/2021 | 02/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI---1P2A558 | TT_Task | DESIGN PHASE PIPING SUPPORTS ON RACK LOT2 | 09/07/2021 | 05/08/2021 | 09/07/2021 | 05/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI---1P2A557 | TT_Task | DESIGN PHASE PIPING SUPPORTS ON RACK LOT1 | 11/06/2021 | 08/07/2021 | 11/06/2021 | 08/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI---1P2A556 | TT_Task | FABRICATION ISOMETRICS ON RACK LOT3 | 03/09/2021 | 01/10/2021 | 03/09/2021 | 01/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI---1P2A555 | TT_Task | PIPE SUPPORTS DOCUMENTATION ON RACK LOT3 | 03/09/2021 | 01/10/2021 | 03/09/2021 | 01/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI---1P2A554 | TT_FinMile | (M2) LOT3-GR.5(ZTB,ZTM-MAV,ZTM-MAW,ZTE/ZTP)(FInal Data for Piping design needed) | 10/06/2021 | 10/06/2021 | 10/06/2021 | 10/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI---1P2A553 | TT_FinMile | (M2) LOT3-GR.4(GHD,GKB,GMx,QFB,SCB,SGA,MAA/B/C)(FInal Data for Piping design needed) | 03/06/2021 | 03/06/2021 | 03/06/2021 | 03/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI---1P2A552 | TT_FinMile | (M2) LOT3-GR.3(MAJ,MAN,MAV,LCW,MAX,LCE,GHC,HSJ)(FInal Data for Piping design needed) | 20/05/2021 | 20/05/2021 | 20/05/2021 | 20/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI---1P2A551 | TT_FinMile | (M2) LOT3-GR.2(EKT,EKG,LCA10,LCA30,LCL,LDK10,MAG,MAG50,MAW,MAM,MAL)(FInal Data for Piping design needed) | 06/05/2021 | 06/05/2021 | 06/05/2021 | 06/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI---1P2A550 | TT_FinMile | (M2) LOT3-GR.1(ZTB,ZTM-MAV,ZTM-MAW,ZTE/ZTP)(FInal Data for Piping design needed) | 22/04/2021 | 22/04/2021 | 22/04/2021 | 22/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI---1P2A549 | TT_Task | FABRICATION ISOMETRICS ON RACK LOT2 | 06/08/2021 | 01/09/2021 | 06/08/2021 | 01/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI---1P2A548 | TT_FinMile | (M2) LOT2-GR.5(ZTB,ZTM-MAV,ZTM-MAW,ZTE/ZTP)(FInal Data for Piping design needed) | 10/06/2021 | 10/06/2021 | 10/06/2021 | 10/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI---1P2A547 | TT_FinMile | (M2) LOT2-GR.4(GHD,GKB,GMx,QFB,SCB,SGA,MAA/B/C)(FInal Data for Piping design needed) | 03/06/2021 | 03/06/2021 | 03/06/2021 | 03/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI---1P2A546 | TT_FinMile | (M2) LOT2-GR.3(MAJ,MAN,MAV,LCW,MAX,LCE,GHC,HSJ)(FInal Data for Piping design needed) | 20/05/2021 | 20/05/2021 | 20/05/2021 | 20/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI---1P2A545 | TT_FinMile | (M2) LOT2-GR.2(EKT,EKG,LCA10,LCA30,LCL,LDK10,MAG,MAG50,MAW,MAM,MAL)(FInal Data for Piping design needed) | 06/05/2021 | 06/05/2021 | 06/05/2021 | 06/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI---1P2A544 | TT_FinMile | (M2) LOT2-GR.1(ZTB,ZTM-MAV,ZTM-MAW,ZTE/ZTP)(FInal Data for Piping design needed) | 22/04/2021 | 22/04/2021 | 22/04/2021 | 22/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI---1P2A543 | TT_Task | FABRICATION ISOMETRICS ON RACK LOT1 | 09/07/2021 | 01/08/2021 | 09/07/2021 | 01/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI---1P2A542 | TT_FinMile | (M2) LOT1-GR.5(ZTB,ZTM-MAV,ZTM-MAW,ZTE/ZTP)(FInal Data for Piping design needed) | 10/06/2021 | 10/06/2021 | 10/06/2021 | 10/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI---1P2A541 | TT_FinMile | (M2) LOT1-GR.4(GHD,GKB,GMx,QFB,SCB,SGA,MAA/B/C)(FInal Data for Piping design needed) | 03/06/2021 | 03/06/2021 | 03/06/2021 | 03/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI---1P2A540 | TT_FinMile | (M2) LOT1-GR.3(MAJ,MAN,MAV,LCW,MAX,LCE,GHC,HSJ)(FInal Data for Piping design needed) | 20/05/2021 | 20/05/2021 | 20/05/2021 | 20/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI---1P2A539 | TT_FinMile | (M2) LOT1-GR.2(EKT,EKG,LCA10,LCA30,LCL,LDK10,MAG,MAG50,MAW,MAM,MAL)(FInal Data for Piping design needed) | 06/05/2021 | 06/05/2021 | 06/05/2021 | 06/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI---1P2A538 | TT_FinMile | (M2) LOT1-GR.1(LAB,LBX,PAB10,PAB20)(FInal Data for Piping design needed) | 22/04/2021 | 22/04/2021 | 22/04/2021 | 22/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI---1P2A537 | TT_FinMile | (M2) LOT7-GR.4(GHD,GKB,GMx,QFB,SCB,SGA,MAA/B/C)(FInal Data for Piping design needed) | 03/06/2021 | 03/06/2021 | 03/06/2021 | 03/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI---1P2A536 | TT_FinMile | (M2) LOT7-GR.1(LAB,LBX,PAB10,PAB20)(FInal Data for Piping design needed) | 22/04/2021 | 22/04/2021 | 22/04/2021 | 22/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI---1P2A535 | TT_FinMile | (M2) LOT6-GR.5(ZTB,ZTM-MAV,ZTM-MAW,ZTE/ZTP)(FInal Data for Piping design needed) | 10/06/2021 | 10/06/2021 | 10/06/2021 | 10/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI---1P2A534 | TT_FinMile | (M2) LOT6-GR.4(GHD,GKB,GMx,QFB,SCB,SGA,MAA/B/C)(FInal Data for Piping design needed) | 03/06/2021 | 03/06/2021 | 03/06/2021 | 03/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI---1P2A533 | TT_FinMile | (M2) LOT6-GR.3(MAJ,MAN,MAV,LCW,MAX,LCE,GHC,HSJ)(FInal Data for Piping design needed) | 20/05/2021 | 20/05/2021 | 20/05/2021 | 20/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI---1P2A532 | TT_FinMile | (M2) LOT6-GR.2(EKT,EKG,LCA10,LCA30,LCL,LDK10,MAG,MAG50,MAW,MAM,MAL)(FInal Data for Piping design needed) | 06/05/2021 | 06/05/2021 | 06/05/2021 | 06/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI---1P2A531 | TT_FinMile | (M2) LOT6-GR.1(LAB,LBx,PAB10,PAB20)(FInal Data for Piping design needed) | 22/04/2021 | 22/04/2021 | 22/04/2021 | 22/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI---1P2A530 | TT_FinMile | (M2) LOT5-GR.5(ZTB,ZTM-MAV,ZTM-MAW,ZTE/ZTP)(FInal Data for Piping design needed) | 10/06/2021 | 10/06/2021 | 10/06/2021 | 10/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI---1P2A529 | TT_FinMile | (M2) LOT4-Gr.3(MAJ,MAN,MAV,LCW,MAX,LCE,GHC,HSJ)(Final PID's) | 20/05/2021 | 20/05/2021 | 20/05/2021 | 20/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI---1P2A528 | TT_FinMile | (M2) LOT4-Gr.2(EKT,EKG,LCA10,LCA30,LCL,LDK10,MAG,MAG50,MAW,MAM,MAL)(Final PID's) | 31/05/2021 | 31/05/2021 | 31/05/2021 | 31/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--HA-2-94 | TT_Mile | FULL ENGINEERING RELEASE HRSG FOR BUILDING BLOCK ENGINEERING (no Hardware Order before NTP) | 13/11/2020 | 13/11/2020 | 13/11/2020 | 13/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--C--2E87 | TT_Mile | 2. Order PLACED of BOP IC CABLES (CONTRACT INTO FORCE) (LOT2) | 19/02/2022 | 19/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--CP-4-30 | TT_Task | TRANSPORT BOP IC CABLES (LOT2) | 11/12/2022 | 04/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--C--4-14 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION BOP IC CABLES (LOT2) | 04/06/2022 | 01/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--C--3-74 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) BOP IC CABLES (LOT2) | 03/06/2022 | 03/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--C--3E84 | TT_Task | DETAIL DESIGN / MANUFACTURING/ SHOP TEST FOR BOP IC CABLES (LOT2) | 19/02/2022 | 03/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--C--3E85 | TT_FinMile | (RFS) READY FOR SHIPMENT BOP IC CABLES (LOT2) | 01/07/2022 | 01/07/2022 |  |  | 1296 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK4-42 | TT_FinMile | (OTD-OS) ON SITE IC CABLES 20/00BZK (LOT2) | 04/02/2023 | 04/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--C--2E85 | TT_Mile | 1. Order PLACED of BOP IC CABLES (CONTRACT INTO FORCE) (LOT1) | 11/12/2021 | 11/12/2021 | 11/12/2021 | 11/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--C--2E84 | TT_Task | Order of BOP IC CABLES (PREPARATION RFQ/QUOTATION STAGE) | 28/08/2021 | 10/12/2021 | 28/08/2021 | 10/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--C--2B83 | TT_FinMile | (DF) HANDOVER T3000 DB complete and hand over | 28/08/2022 | 28/08/2022 |  |  | 1360 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--C--2C71 | TT_Mile | (DF) T3000 Software ready | 02/08/2022 | 02/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--C--2B82 | TT_Task | SW ENGINEERING BOP IC, T3000 DB MERGING non Fail Safe | 07/02/2022 | 03/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--C--2B81 | TT_Task | Filling Meas/Consumer list IC tasks | 26/03/2021 | 15/07/2021 | 26/03/2021 | 15/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--LOG4-10 | TT_Mile | START FIRST SHIPMENTS BY LOGISTICS CONTRACTOR | 14/07/2021 | 14/07/2021 | 14/07/2021 | 14/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--LOG2-40 | TT_Task | REVIEW OF QUOTATIONS PREPARATION OF BID COMPARISON SHEET LOGISTICS CONTRACT | 16/04/2021 | 06/05/2021 | 16/04/2021 | 06/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--LOG4-30 | TT_Mile | START FIRST TRANSPORT TO SITE (HEAVY LOADS) | 08/12/2021 | 08/12/2021 | 08/12/2021 | 08/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--LOG2-80 | TT_Mile | CONTRACT INTO FORCE TRANSPORT LOGISTICS | 11/06/2021 | 11/06/2021 | 11/06/2021 | 11/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--LOG2-70 | TT_Task | CONTRACT AWARD LOGISTICS CONTRACT (SOURCING BOARD / FINAL CONTRACT DOCUMENTS) | 28/05/2021 | 10/06/2021 | 28/05/2021 | 10/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--LOG2-10 | TT_FinMile | RECEIVE COLLI LIST (INCL. SOURCING CONCEPT / INCOTERMS) | 25/02/2021 | 25/02/2021 | 25/02/2021 | 25/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--LOG2-50 | TT_Mile | SHORTLIST READY FOR LOGISTICS CONTRACT | 07/05/2021 | 07/05/2021 | 07/05/2021 | 07/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--LOG2-30 | TT_Task | QUOTATION STAGE LOGISTICS CONTRACT | 19/03/2021 | 15/04/2021 | 19/03/2021 | 15/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--LOG2-20 | TT_Task | PREPARATION RFQ LOGISTICS CONTRACT | 26/02/2021 | 18/03/2021 | 26/02/2021 | 18/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--LOG2-60 | TT_Task | CONTRACTUAL CLARIFICATION, QUALIFICATION AND FINAL EVALUATION | 07/05/2021 | 27/05/2021 | 07/05/2021 | 27/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--LOG4-20 | TT_Task | PREPARATION PERIOD FOR LOGISTICS CONTRACTOR (HEAVY LOADS) | 11/06/2021 | 07/12/2021 | 11/06/2021 | 07/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--PEI7-20 | TT_Mile | START IC ERECTION WORKS ON SITE | 24/06/2022 | 24/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--PEE7-20 | TT_Mile | START ELECTRICAL ERECTION WORKS ON SITE | 03/04/2022 | 03/04/2022 |  |  | 88 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--PEM6-20 | TT_Mile | START MECHANICAL ERECTION WORKS ON SITE | 16/01/2022 | 16/01/2022 |  |  | 768 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7-165 | TT_Task | ERECTION CABLE TRAYS FOR 20UMCL1Y | 25/05/2022 | 28/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7-10 | TT_Task | ERECTION CABLE TRAYS FOR 20MAG50Y | 29/06/2022 | 19/07/2022 |  |  | 1320 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MPB2A94 | TT_Mile | CONTRACT INTO FORCE ENCLOSURE 20MPB | 25/06/2021 | 25/06/2021 | 25/06/2021 | 25/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MPB2A93 | TT_Task | QUOTATION STAGE ENCLOSURE 20MPB | 07/05/2021 | 24/06/2021 | 07/05/2021 | 24/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MPB2A92 | TT_Task | PREPARE TEC RFQ ENCLOSURE 20MPB | 29/03/2021 | 06/05/2021 | 29/03/2021 | 06/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MPB3A93 | TT_FinMile | (RFS) READY FOR SHIPMENT ENCLOSURE 20MPB | 12/07/2022 | 12/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MPB3A92 | TT_Task | DETAIL DESIGN / FABRICATION DESIGN ENCLOSURE 20MPB | 09/09/2021 | 01/12/2021 | 09/09/2021 | 01/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MPB4-43 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION ENCLOSURE 20MPB | 15/06/2022 | 12/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MPB3-83 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) ENCLOSURE 20MPB | 14/06/2022 | 14/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MPB4A43 | TT_FinMile | (OTD-OS) ON SITE ENCLOSURE 20MPB | 05/10/2022 | 05/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--PM-2-90 | TT_FinMile | (DF) 90% DESIGN REVIEW | 14/02/2022 | 14/02/2022 |  |  | 528 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--PM-2-60 | TT_FinMile | (DF) 60% DESIGN REVIEW | 14/10/2021 | 14/10/2021 | 14/10/2021 | 14/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--PM-2-30 | TT_FinMile | (DF) 30% DESIGN REVIEW | 30/04/2021 | 30/04/2021 | 30/04/2021 | 30/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---2M61 | TT_Mile | PROJECT SPECIFIC CHECKUP IF PM80 AND / OR LNTP ARE NECESSARY FOR (A) | 01/08/2020 | 01/08/2020 | 01/08/2020 | 01/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMY2A68 | TT_Task | DELTA DESIGN MEDIUM LEAD ITEMS INCL. MTO | 13/11/2020 | 05/03/2021 | 13/11/2020 | 05/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-----2M13 | TT_Task | DELTA DESIGN / VERIFICATION GROUP V | 13/02/2021 | 05/03/2021 | 13/02/2021 | 05/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-----2M12 | TT_Task | DELTA DESIGN / VERIFICATION GROUP IV | 30/01/2021 | 05/03/2021 | 30/01/2021 | 05/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-----2M14 | TT_Mile | CONCEPT / PLANT DESIGN YARD AREA | 13/11/2020 | 13/11/2020 | 13/11/2020 | 13/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI---5P2-10 | TT_Mile | (M2) FOR ORDER ABILITY GROUP V (NO TOTAL M2) | 10/06/2021 | 10/06/2021 | 10/06/2021 | 10/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI---4P2-10 | TT_Mile | (M2) FOR ORDER ABILITY GROUP IV (NO TOTAL M2) | 02/06/2021 | 02/06/2021 | 02/06/2021 | 02/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI---3P2-10 | TT_Mile | (M2) FOR ORDER ABILITY GROUP III (NO TOTAL M2) | 19/05/2021 | 19/05/2021 | 19/05/2021 | 19/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI---2P2-10 | TT_Mile | (M2) FOR ORDER ABILITY GROUP II (NO TOTAL M2) | 06/05/2021 | 06/05/2021 | 06/05/2021 | 06/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI---1P2-10 | TT_Mile | (M2) FOR ORDER ABILITY GROUP I (NO TOTAL M2) | 06/05/2021 | 06/05/2021 | 06/05/2021 | 06/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-----2M35 | TT_Task | DELTA DESIGN / VERIFICATION EKG | 16/01/2021 | 29/01/2021 | 16/01/2021 | 29/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-----2M34 | TT_Task | DELTA DESIGN / VERIFICATION MAA / MAB / MAV | 09/01/2021 | 29/01/2021 | 09/01/2021 | 29/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-----2M33 | TT_Task | DELTA DESIGN / VERIFICATION MAG / MAL / MAM / MAW | 09/01/2021 | 29/01/2021 | 09/01/2021 | 29/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-----2M32 | TT_Task | DELTA DESIGN / VERIFICATION PAB 20 | 09/01/2021 | 29/01/2021 | 09/01/2021 | 29/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-----2M31 | TT_Task | DELTA DESIGN / VERIFICATION LAB HP | 09/01/2021 | 29/01/2021 | 09/01/2021 | 29/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-----2M29 | TT_Task | DELTA DESIGN / VERIFICATION LBx | 09/01/2021 | 29/01/2021 | 09/01/2021 | 29/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-----2M08 | TT_Task | DELTA DESIGN LONG LEAD ITEMS INCL. MTO | 18/11/2020 | 29/01/2021 | 18/11/2020 | 29/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-----2M30 | TT_Mile | 30% DESIGN REVIEW (3DR) BUILDING BLOCKS | 12/03/2021 | 12/03/2021 | 12/03/2021 | 12/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-----2-00 | TT_Mile | (M1) DATA / PID FOR ALL OTHER SYSTEMS | 14/02/2021 | 14/02/2021 | 14/02/2021 | 14/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--EKG2-10 | TT_Mile | (M2) FOR ORDER ABILITY EKG (NO TOTAL M2) | 06/05/2021 | 06/05/2021 | 06/05/2021 | 06/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--MA-2E10 | TT_Mile | (M2) FOR ORDER ABILITY MAA / MAB / MAV (NO TOTAL M2) | 19/05/2021 | 19/05/2021 | 19/05/2021 | 19/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-----2M39 | TT_Mile | PRELIMINARY LBx STRESS REPORT AVAILABLE | 30/01/2021 | 30/01/2021 | 30/01/2021 | 30/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--MA-2-10 | TT_Mile | (M2) FOR ORDER ABILITY MAG / MAL / MAM / MAW (NO TOTAL M2) | 06/05/2021 | 06/05/2021 | 06/05/2021 | 06/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--PAB2-10 | TT_Mile | (M2) FOR ORDER ABILITY PAB 20 (NO TOTAL M2) | 22/04/2021 | 22/04/2021 | 22/04/2021 | 22/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--H--2-10 | TT_Mile | HRSG STARTS LBx / Hxx VERIFICATION | 12/12/2020 | 12/12/2020 | 12/12/2020 | 12/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--LAB2-10 | TT_Mile | (M2) FOR ORDER ABILITY LAB HP (NO TOTAL M2) | 22/04/2021 | 22/04/2021 | 22/04/2021 | 22/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--LB-2-10 | TT_Mile | (M2) FOR ORDER ABILITY LBx (NO TOTAL M2) | 22/04/2021 | 22/04/2021 | 22/04/2021 | 22/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-----2M20 | TT_Mile | INPUT FROM GT / ST / GENO / HRSG / BoP / COMPONENTS | 02/01/2021 | 02/01/2021 | 02/01/2021 | 02/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-----2M96 | TT_Task | ADAPTION OF COLLUMN GRID, FRAME CONCEPT | 15/08/2020 | 09/10/2020 | 15/08/2020 | 09/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-----2M95 | TT_Task | ADAPTION OF TRANSPORT UNIT, ARANGEMENTS, ERECTION | 02/12/2020 | 26/01/2021 | 02/12/2020 | 26/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---3B12 | TT_FinMile | ERECTION MANUALS ON SITE (CLOUD) FOR OFF RACK PIPING LOT 4 | 21/01/2022 | 21/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---3B19 | TT_FinMile | ERECTION MANUALS ON SITE (CLOUD) FOR OFF RACK PIPING LOT 5 | 17/02/2022 | 17/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---3B18 | TT_FinMile | ERECTION MANUALS ON SITE (CLOUD) FOR OFF RACK PIPING LOT 6 | 09/07/2022 | 09/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---3M86 | TT_FinMile | ERECTION MANUALS ON SITE (CLOUD) FOR SHIPMENT LOT 3 | 07/04/2022 | 07/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---3M85 | TT_FinMile | ERECTION MANUALS ON SITE (CLOUD) FOR SHIPMENT LOT 2 | 05/03/2022 | 05/03/2022 |  |  | 8 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---3M84 | TT_FinMile | ERECTION MANUALS ON SITE (CLOUD) FOR SHIPMENT LOT 1 | 18/03/2022 | 18/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---3G80 | TT_FinMile | START OF STEELWORK OF ASSEMBLY LOT 3 | 18/03/2022 | 18/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---3G78 | TT_Task | PROCUREMENT BOLTS / NUTS / WASHERS (100%) | 10/07/2021 | 08/10/2021 | 10/07/2021 | 09/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---3G79 | TT_FinMile | START OF STEELWORK OF ASSEMBLY LOT 2 | 19/02/2022 | 19/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---3G76 | TT_Task | PROCUREMENT STEEL PLATES (50%) | 10/07/2021 | 08/10/2021 | 10/07/2021 | 08/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---3G77 | TT_FinMile | START OF STEELWORK OF ASSEMBLY LOT 1 | 21/01/2022 | 21/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---3G74 | TT_Task | PROCUREMENT STEEL PLATES (50%) | 05/06/2021 | 03/09/2021 | 05/06/2021 | 03/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---3G75 | TT_FinMile | START OF STEELWORK PREFABRICATION SHIPMENT LOT 3 | 09/11/2021 | 09/11/2021 | 09/11/2021 | 09/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---3G72 | TT_Task | PROCUREMENT STEEL PROFILES (25%) | 05/06/2021 | 03/09/2021 | 05/06/2021 | 03/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---3G73 | TT_FinMile | START OF STEELWORK PREFABRICATION SHIPMENT LOT 2 | 07/10/2021 | 07/10/2021 | 07/10/2021 | 07/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-----2F87 | TT_Mile | BoQ QUALITY GATE | 01/05/2021 | 01/05/2021 | 01/05/2021 | 01/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI----P3I32 | TT_Mile | FINAL CONTROL VALVE DRAWINGS AVAILABLE | 27/05/2021 | 27/05/2021 | 27/05/2021 | 27/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI----P3I31 | TT_Mile | PRELIMINARY CONTROL VALVE DRAWINGS AVAILABLE | 29/04/2021 | 29/04/2021 | 29/04/2021 | 29/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI----P3I30 | TT_Mile | FINAL VALVE DRAWINGS AVAILABLE | 19/06/2021 | 19/06/2021 | 19/06/2021 | 19/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI----P3I29 | TT_Mile | PRELIMINARY VALVE DRAWINGS AVAILABLE | 22/05/2021 | 22/05/2021 | 22/05/2021 | 22/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---3M105 | TT_Task | PROCUREMENT LONG LEAD ITEMS PART 3 (100%) | 04/06/2021 | 09/09/2021 | 04/06/2021 | 09/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-----2E88 | TT_Mile | ORDER MTO LONG LEAD ITEMS (100%) | 04/06/2021 | 04/06/2021 | 04/06/2021 | 04/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-----2E87 | TT_Mile | BoQ QUALITY GATE | 12/03/2021 | 12/03/2021 | 12/03/2021 | 12/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-----2H60 | TT_Mile | (MS3) BB STEELWORK LOT 3 | 27/05/2021 | 27/05/2021 | 27/05/2021 | 27/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-----2G60 | TT_Mile | (MS3) BB STEELWORK LOT 2 | 02/06/2021 | 02/06/2021 | 02/06/2021 | 02/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-----2F60 | TT_Mile | (MS3) BB STEELWORK LOT 1 | 11/05/2021 | 11/05/2021 | 11/05/2021 | 11/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-----3M64 | TT_Task | DETAIL DESIGN BB STEELWORK LOT 1 | 11/05/2021 | 16/06/2021 | 11/05/2021 | 16/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---3B11 | TT_FinMile | DELIVERY OF VALVES (FLANGE) FOR SHIPMENT LOT 3 | 01/12/2021 | 01/12/2021 | 01/12/2021 | 01/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---3B09 | TT_FinMile | DELIVERY OF VALVES (WELDING) FOR SHIPMENT LOT 3 | 31/10/2021 | 31/10/2021 | 31/10/2021 | 31/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---2M30 | TT_Mile | SUBMISSION OF 50% OF FABRICATION DOCUMENTS FOR SHIPMENT LOT 3 | 10/11/2021 | 10/11/2021 | 10/11/2021 | 10/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---3B13 | TT_FinMile | DELIVERY OF COMPONENTS FOR SHIPMENT LOT 3 | 08/03/2022 | 08/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---3B10 | TT_FinMile | DELIVERY OF COMPONENTS FOR SHIPMENT LOT 2 | 10/01/2022 | 10/01/2022 |  |  | 128 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---3B07 | TT_FinMile | DELIVERY OF VALVES (FLANGE) FOR SHIPMENT LOT 2 | 01/12/2021 | 01/12/2021 | 01/12/2021 | 01/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---3B06 | TT_FinMile | DELIVERY OF VALVES (WELDING) FOR SHIPMENT LOT 2 | 31/10/2021 | 31/10/2021 | 31/10/2021 | 31/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---2M29 | TT_Mile | SUBMISSION OF 50% OF FABRICATION DOCUMENTS FOR SHIPMENT LOT 2 | 08/10/2021 | 08/10/2021 | 08/10/2021 | 08/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---3B05 | TT_FinMile | DELIVERY OF VALVES (FLANGE) FOR SHIPMENT LOT 1 | 01/12/2021 | 01/12/2021 | 01/12/2021 | 01/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---3B04 | TT_FinMile | DELIVERY OF VALVES (WELDING) FOR SHIPMENT LOT 1 | 31/10/2021 | 31/10/2021 | 31/10/2021 | 31/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---2M28 | TT_Mile | KICK OFF MEETING PREFABRICATION | 08/09/2021 | 08/09/2021 | 08/09/2021 | 08/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---2M27 | TT_Mile | SUBMISSION OF 50% OF FABRICATION DOCUMENTS FOR SHIPMENT LOT 1 | 08/09/2021 | 08/09/2021 | 08/09/2021 | 08/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PCB6M16 | TT_Task | ERECTION MODULE 20PCB10Y | 02/06/2022 | 08/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--CP-4-28 | TT_Task | TRANSPORT CCR FURNITURE AND HMI EQUIPMENT | 03/05/2022 | 27/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--C--4-12 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION CCR FURNITURE AND HMI EQUIPMENT | 05/04/2022 | 02/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--C--3-72 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) CCR FURNITURE AND HMI EQUIPMENT | 04/04/2022 | 04/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--C--3E26 | TT_Task | DETAIL DESIGN / MANUFACTURING/ SHOP TEST CCR FURNITURE AND HMI EQUIPMENT | 04/06/2021 | 04/04/2022 | 04/06/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--C--3E82 | TT_FinMile | (RFS) READY FOR SHIPMENT CCR FURNITURE AND HMI EQUIPMENT | 02/05/2022 | 02/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20CFE4-25 | TT_Task | TRANSPORT TO SITE EMISSION MONITORING SYSTEM 20CFE | 05/05/2022 | 29/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20CFE4-10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION - EMISSION MONITORING SYSTEM 20CFE | 07/04/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20CFE3-70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) EMISSION MONITORING SYSTEM 20CFE | 06/04/2022 | 06/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20CFE3-25 | TT_Task | DETAIL DESIGN, MANUFACTURING, SHOP TEST FOR EMISSION MONITORING SYSTEM 20CFE | 10/06/2021 | 06/04/2022 | 10/06/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20CFE3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT EMISSION MONITORING SYSTEM 20CFE | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--CP-4-29 | TT_Task | TRANSPORT BOP IC CABLES (LOT1) | 26/06/2022 | 20/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--C--4-13 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION BOP IC CABLES (LOT1) | 13/01/2022 | 09/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--C--3-73 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) BOP IC CABLES (LOT1) | 12/01/2022 | 12/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--C--3E28 | TT_Task | DETAIL DESIGN / MANUFACTURING/ SHOP TEST FOR BOP IC CABLES (LOT1) | 16/10/2021 | 12/01/2022 | 16/10/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--C--3E83 | TT_FinMile | (RFS) READY FOR SHIPMENT BOP IC CABLES (LOT1) | 09/02/2022 | 09/02/2022 |  |  | 1088 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--CP-4-26 | TT_Task | TRANSPORT BOP IC FIELD DEVICES | 04/08/2022 | 28/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP--CJP2-41 | TT_FinMile | SIGNAL EXCHANGE WITH LOAD DISPATCHER | 16/01/2022 | 16/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP--CJP2-40 | TT_FinMile | (DF) GT FINAL INPUT FOR IC UNIT COORDINATION | 26/12/2021 | 26/12/2021 | 26/12/2021 | 26/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP--CJJ2-39 | TT_FinMile | (DF) ST FINAL INPUT FOR IC UNIT COORDINATION | 26/12/2021 | 26/12/2021 | 26/12/2021 | 26/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP--CJP2-39 | TT_Mile | PREL. XML - DATA FOR SIMULATOR | 07/02/2022 | 07/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--C--2-43 | TT_Task | IMPLEMENTATION HARDWARE PROXIES FUPs OM COMBINED CYCLE | 31/01/2022 | 27/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--C--2-44 | TT_Task | REVISION IC DOCUMENTS | 07/02/2022 | 27/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--C--2-42 | TT_Task | DESIGN REVIEW IC AUTOMATION HMI | 17/01/2022 | 06/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--C--2-40 | TT_Task | ENGINEERING CLOSED LOOP CONTROLS | 03/09/2021 | 16/01/2022 | 03/09/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--CKA2-19 | TT_Task | SERVER CHECK WITHIN PRECOMMISSIONING (PLANT SHOP TEST) | 21/03/2022 | 27/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--CKA2-18 | TT_Task | PRELIMINARY PRODUCT MANUAL THERMODYN. DIAGN. | 21/10/2021 | 10/11/2021 | 21/10/2021 | 10/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--CKA2-17 | TT_Task | SYSTEM SETUP THERMODYN. DIAGN. AT PLANT SHOP TEST FIELD | 14/10/2021 | 10/11/2021 | 14/10/2021 | 10/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--CKA2-16 | TT_Task | DETAILED PLANNING THERMODYN. DIAGN. | 22/07/2021 | 13/10/2021 | 22/07/2021 | 13/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--G--2-88 | TT_FinMile | (DF) SW ENGINEERING / HANDOVER T3000 | 17/10/2021 | 17/10/2021 | 17/10/2021 | 17/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--G--2-87 | TT_Task | IC SW ENGINEERING FUPS HMI'S G-SYSTEM | 01/09/2021 | 12/01/2022 | 01/09/2021 |  | 200 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--G--2-86 | TT_FinMile | FINAL MSR FOR IC | 04/09/2021 | 04/09/2021 | 04/09/2021 | 04/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--G--2-85 | TT_Task | DATA MANAGEMENT G-SYSTEMS | 04/07/2021 | 04/09/2021 | 04/07/2021 | 04/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--G--2-84 | TT_Task | HARA / SIL-STUDY ASSESSMENT OF NONSTANDARD SYSTEMS | 04/07/2021 | 10/07/2021 | 04/07/2021 | 10/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--G--2-83 | TT_Task | HARA / SIL-STUDY ASSESSMENT OF NONSTANDARD SYSTEMS | 28/02/2021 | 03/07/2021 | 28/02/2021 | 03/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--P--2-80 | TT_Mile | (DF) SW ENGINEERING / HANDOVER T3000 | 18/08/2021 | 18/08/2021 | 18/08/2021 | 18/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--P--2-29 | TT_Task | IC SW ENGINEERING FUPS HMI'S P-SYSTEM | 01/09/2021 | 12/01/2022 | 01/09/2021 |  | 200 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--P--2-79 | TT_Task | HARA / SIL-STUDY ASSESSMENT OF STANDARD SYSTEMS | 05/05/2021 | 11/05/2021 | 05/05/2021 | 11/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--P--2-78 | TT_FinMile | FINAL MSR FOR IC | 06/07/2021 | 06/07/2021 | 06/07/2021 | 06/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--L--2-80 | TT_Task | HARA / SIL-STUDY ASSESSMENT OF STANDARD SYSTEMS | 05/05/2021 | 11/05/2021 | 05/05/2021 | 11/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--P--2-77 | TT_Task | HARA / SIL-STUDY ASSESSMENT OF NONSTANDARD SYSTEMS | 13/01/2021 | 04/05/2021 | 13/01/2021 | 04/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--L--2-79 | TT_Mile | (DF) SW ENGINEERING / HANDOVER T3000 | 21/08/2021 | 21/08/2021 | 21/08/2021 | 21/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--L--2-29 | TT_Task | IC SW ENGINEERING FUPS HMI'S L-SYSTEM | 01/09/2021 | 12/01/2022 | 01/09/2021 |  | 200 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--L--2-78 | TT_FinMile | FINAL MSR FOR IC | 06/07/2021 | 06/07/2021 | 06/07/2021 | 06/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--L--2-77 | TT_Task | HARA / SIL-STUDY ASSESSMENT OF NONSTANDARD SYSTEMS | 11/01/2021 | 04/05/2021 | 11/01/2021 | 04/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--HA-2-00 | TT_Task | IC SW ENGINEERING FUPS HMI'S HRSG-SYSTEM | 01/09/2021 | 12/01/2022 | 01/09/2021 |  | 1816 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--HA-2A87 | TT_Mile | HANDOVER OF PID'S TO HRSG ENGINEERING | 19/03/2021 | 19/03/2021 | 19/03/2021 | 19/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--3332-65 | TT_Mile | (DF) PROCESS FINAL / INPUT FOR M2 BUILDING BLOCKS (TBD by building blocks) | 24/10/2020 | 24/10/2020 | 24/10/2020 | 24/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--3332-63 | TT_Mile | (DF) CONFIRMATION OF M-COMP. HEAT LOADS F. PGB-SYS. | 15/08/2020 | 15/08/2020 | 15/08/2020 | 15/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--3332-62 | TT_Mile | CONFIRMATION OF COOLING TOWER HYDRAULIC HIGHT | 15/08/2020 | 15/08/2020 | 15/08/2020 | 15/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--3332-61 | TT_Task | M2 ORDERABILITY PID FOR COMPLETE SYSTEMS (Building Block Scope only) | 01/08/2020 | 23/10/2020 | 01/08/2020 | 23/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI---5P6A09 | TT_Task | PREFABRICATION ON SITE ALL SYSTEMS LOT 5 | 27/05/2022 | 23/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UCA7-08 | TT_Mile | START ERECTION CONTROL ROOM EQUIPMENT | 28/06/2022 | 28/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20CYA8-30 | TT_Task | COMMISSIONING TELECOMMUNICATION UCA | 13/05/2023 | 02/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBR6-48 | TT_Task | FINISH WORKS / INSULATION/ TOUCH-UP DIFFUSER 20MBR | 22/09/2022 | 05/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBR6-47 | TT_Task | WELDING / INSULATION / TOUCH-UP DIFFUSOR 20MBR (before GT final position) | 03/06/2022 | 30/06/2022 |  |  | 440 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MAX2-85 | TT_Mile | CONTRACT INTO FORCE ST HYDRAULIC SYSTEM MAX | 24/07/2021 | 24/07/2021 | 24/07/2021 | 24/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MAX2-81 | TT_Task | QUOTATION STAGE ST HYDRAULIC SYSTEM MAX | 12/06/2021 | 23/07/2021 | 12/06/2021 | 23/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MAX2-80 | TT_Task | PREPARE TEC RFQ DOC ST HYDRAULIC SYSTEM MAX | 15/05/2021 | 11/06/2021 | 15/05/2021 | 11/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MAW2-85 | TT_Mile | CONTRACT INTO FORCE GLAND STEAM CONDENSER MAW | 16/07/2021 | 16/07/2021 | 16/07/2021 | 16/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MAV2-82 | TT_Task | QUOTATION STAGE GLAND STEAM CONDENSER MAW | 04/06/2021 | 15/07/2021 | 04/06/2021 | 15/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MAW2-80 | TT_Task | PREPARE TEC RFQ DOC GLAND STEAM CONDENSER MAW | 07/05/2021 | 03/06/2021 | 07/05/2021 | 03/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MAV2-85 | TT_Mile | CONTRACT INTO FORCE LUBE OIL MODULE MAV | 29/07/2021 | 29/07/2021 | 29/07/2021 | 29/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MAV2-81 | TT_Task | QUOTATION STAGE LUBE OIL MODULE MAV | 04/06/2021 | 28/07/2021 | 04/06/2021 | 28/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MAV2-80 | TT_Task | PREPARE TEC RFQ DOC LUBE OIL MODULE MAV | 07/05/2021 | 03/06/2021 | 07/05/2021 | 03/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MAN2-85 | TT_Mile | CONTRACT INTO FORCE ST BYPASS VALVES MAN | 03/08/2021 | 03/08/2021 | 03/08/2021 | 03/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MAN2-81 | TT_Task | QUOTATION STAGE ST BYPASS VALVES MAN | 14/06/2021 | 02/08/2021 | 14/06/2021 | 02/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MAN2-80 | TT_Task | PREPARE TEC RFQ DOC ST BYPASS VALVES MAN | 26/03/2021 | 13/06/2021 | 26/03/2021 | 13/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MAJ3-84 | TT_Task | DESIGN / MANUFACTURING AIR REMOVAL SYSTEM 20MAJ | 11/06/2021 | 14/02/2022 | 11/06/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SP20MAJ2-85 | TT_Mile | CONTRACT INTO FORCE AIR REMOVAL SYSTEM MAJ | 11/06/2021 | 11/06/2021 | 11/06/2021 | 11/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MAJ2-81 | TT_Task | QUOTATION STAGE AIR REMOVAL SYSTEM MAJ | 30/04/2021 | 10/06/2021 | 30/04/2021 | 10/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MAJ2-80 | TT_Task | PREPARE TEC RFQ DOC AIR REMOVAL SYSTEM MAJ | 26/03/2021 | 29/04/2021 | 26/03/2021 | 29/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MBK3B80 | TT_FinMile | (RFS) READY FOR SHIPMENT TURNING DEVICE 20MBK | 29/04/2022 | 29/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBK4E25 | TT_Task | TRANSPORT TURNING DEVICE 20MBK | 30/04/2022 | 23/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MBK4-10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION TURNING DEVICE 20MBK | 02/04/2022 | 29/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MBK4H40 | TT_FinMile | (OTD-OS) ON SITE TURNING DEVICE 20MBK | 23/07/2022 | 23/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MBK3-70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) TURNING DEVICE 20MBK | 01/04/2022 | 01/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---3B89 | TT_FinMile | (RFS) READY FOR SHIPMENT GT INTERMEDIATE SHAFT 20MB- | 29/04/2022 | 29/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---4-18 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION GT INTERMEDIATE SHAFT 20MB- | 02/04/2022 | 29/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-6-40 | TT_Task | REMAINING EXTERNAL INSULATION FOR OUTLET DUCT HRSG20 | 01/12/2022 | 11/01/2023 |  |  | 768 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-6D18 | TT_Task | ALIGNMENT HP VESSEL / IP AND LP DRUM | 19/05/2022 | 20/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-6C28 | TT_Task | ERECTION DRUM SUPPORT STEEL / ERECTION TOP PLATFORMS FOR DRUM INSTALL/ROOF PANELS | 29/04/2022 | 16/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-6C24 | TT_Task | PREPARATIONS FOR MODULE LOADING HRSG20 | 23/03/2022 | 29/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-6C25 | TT_FinMile | (RFE) MODULE LIFTING 20 | 29/03/2022 | 29/03/2022 |  |  | 16 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-6C26 | TT_Task | ERECTION TOP PLATFORMSHRSG20 | 21/03/2022 | 03/04/2022 |  |  | 136 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-6C25 | TT_Task | PRE-ASSEMBLY TOP PLATFORMS HRSG20 | 07/03/2022 | 27/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-6C24 | TT_Task | ERECTION STAIRCASE 1 (STACK) HRSG20 | 07/03/2022 | 13/03/2022 |  |  | 56 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-6-19 | TT_Task | MAIN CASING ERECTION WELDING HRSG20 | 20/01/2022 | 02/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-6-18 | TT_Task | STEEL ALIGNMENT AND BOLT TIGHTENING HRSG20 | 15/01/2022 | 13/02/2022 |  |  | 80 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20CJF2-82 | TT_FinMile | (DF) IC DATA HRSG | 01/04/2021 | 01/04/2021 | 01/04/2021 | 01/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20CJF2-15 | TT_Task | BASIC DESIGN /QUOTATION STAGE/ ODERING ELECTRICAL / IC EQUIPMENT HRSG | 22/01/2021 | 01/04/2021 | 22/01/2021 | 01/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--HA-3E25 | TT_Task | BASIC / DETAIL DESIGN / ORDERING / DELIVERY / MANUFACTURING PIPING HRSG20_Last Part (SB &lt;= 3'') | 28/01/2021 | 06/04/2022 | 28/01/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--HA-3E27 | TT_Task | BASIC / DETAIL DESIGN / ORDERING / DELIVERY / MANUFACTURING PIPING HRSG20_2nd part (LB HIGH ALLOY STEEL) | 28/01/2021 | 03/03/2022 | 28/01/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20HB-3E25 | TT_Task | DETAIL DESIGN INLET DUCT HRSG20 | 30/01/2021 | 12/03/2021 | 30/01/2021 | 12/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20HB-3F25 | TT_Task | DETAIL DESIGN OUTLET DUCT HRSG 20 | 28/01/2021 | 27/02/2021 | 28/01/2021 | 27/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20HB-3D25 | TT_Task | DETAIL DESIGN STACK HRSG 20 | 28/01/2021 | 10/04/2021 | 28/01/2021 | 10/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--HB-2D80 | TT_Task | QUOTATION STAGE / ORDERING STACK HRSG incl. OUTLET DUCT | 01/01/2021 | 11/02/2021 | 01/01/2021 | 11/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20HA-4B14 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION PIPING HRSG20_2nd Part (LB HIGH ALLOY STEEL) | 04/03/2022 | 31/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-3B74 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) PIPING HRSG20_2nd Part (LB HIGH ALLOY STEEL) | 03/03/2022 | 03/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-3B81 | TT_FinMile | (RFS) READY FOR SHIPMENT PIPING HRSG20_2nd Part (LB HIGH ALLOY STEEL) | 31/03/2022 | 31/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-4B27 | TT_Task | TRANSPORT PIPING HRSG20_2nd Part (LB HIGH ALLOY STEEL) | 01/04/2022 | 30/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-4B42 | TT_FinMile | (OTD-OS) ON SITE PIPING HRSG20_2nd Part (LB HIGH ALLOY STEEL) | 30/04/2022 | 30/04/2022 |  |  | 200 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-4B13 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION PIPING HRSG20_Last Part (SB &lt;= 3'') | 07/04/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-3B73 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) PIPING HRSG20_Last Part (SB &lt;= 3'') | 06/04/2022 | 06/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-3B82 | TT_FinMile | (RFS) READY FOR SHIPMENT PIPING HRSG20_Last Part (SB &lt;= 3'') | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-4B26 | TT_Task | TRANSPORT PIPING HRSG20_Last Part (SB &lt;= 3'') | 05/05/2022 | 03/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-4B41 | TT_FinMile | (OTD-OS) ON SITE PIPING HRSG20_Last Part (SB &lt;= 3'') | 03/06/2022 | 03/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-3D25 | TT_Task | DETAIL DESIGN DRUMS HRSG20 | 28/01/2021 | 27/02/2021 | 28/01/2021 | 27/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--HB-2D62 | TT_FinMile | (DF) INPUT FOR MS3 STACK HRSG incl. OUTLET DUCT | 11/02/2021 | 11/02/2021 | 11/02/2021 | 11/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--HB-2B05 | TT_FinMile | ERECTION MANUALS ON SITE STEEL STRUCTURE HRSG | 29/12/2021 | 29/12/2021 | 29/12/2021 | 29/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--HB-2B62 | TT_FinMile | FINAL ERECTION CONCEPT HRSG | 26/02/2021 | 26/02/2021 | 26/02/2021 | 26/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--HB-2B61 | TT_FinMile | PRELIMINARY ERECTION CONCEPT HRSG | 27/01/2021 | 27/01/2021 | 27/01/2021 | 27/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHA2B-14 | TT_FinMile | (OTD-OS) ON SITE EMBEDDED PARTS HRSG20 | 28/09/2021 | 28/09/2021 | 28/09/2021 | 28/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHA2B-13 | TT_Task | TRANSPORT EMBEDDED PARTS HRSG20 | 04/08/2021 | 28/09/2021 | 04/08/2021 | 28/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--HA-2-83 | TT_FinMile | PROCESS DOCUMENTS FOR RFQ HRSG | 11/12/2020 | 11/12/2020 | 11/12/2020 | 11/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--HA-2-90 | TT_Task | FINAL NEGOTIATION HRSG | 15/01/2021 | 26/01/2021 | 15/01/2021 | 26/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--HA-2-88 | TT_FinMile | HRSG OFFER AVAILABLE | 05/12/2020 | 05/12/2020 | 05/12/2020 | 05/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--HA-2-87 | TT_FinMile | SPECIFICATION OF VALVES | 28/11/2020 | 28/11/2020 | 28/11/2020 | 28/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--HA-2-84 | TT_FinMile | FIRE EXPLOSION PROTECTION CONCEPT | 28/11/2020 | 28/11/2020 | 28/11/2020 | 28/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--HA-2-99 | TT_FinMile | NOISE PROTECTION CONCEPT HRSG | 11/02/2021 | 11/02/2021 | 11/02/2021 | 11/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--HA-2-98 | TT_FinMile | PID's, DATA SHEETS LIFE TIME DESIGN CRITERIA FOR INQUIRY ORDERING HRSG AVAILABLE | 14/08/2020 | 14/08/2020 | 14/08/2020 | 14/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--HA-2-82 | TT_Task | OFFER PREPARATION BY HRSG SUPPLIER | 03/11/2020 | 04/12/2020 | 03/11/2020 | 04/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--HA-2-97 | TT_FinMile | GENERAL DESIGN CRITERIA FOR STRUCTURAL ENGINEERING FINALISED FOR HRSG ORDER | 14/08/2020 | 14/08/2020 | 14/08/2020 | 14/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--HA-2-96 | TT_FinMile | PROJECT SPEC. GENERAL TCC`S AVAILABLE | 14/08/2020 | 14/08/2020 | 14/08/2020 | 14/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--HA-2-79 | TT_Mile | START OFFER PREPARATION HRSG | 01/08/2020 | 01/08/2020 | 01/08/2020 | 01/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-UZA2-45 | TT_Task | COMPOSITE DRAWING RING ROAD INCL. UNDERGROUND (U/G) DRAINAGE PART 2 | 22/02/2021 | 29/05/2021 | 22/02/2021 | 29/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PCB4-40 | TT_FinMile | (OTD-OS) ON SITE MODULE 20PCB10Y | 21/05/2022 | 21/05/2022 |  |  | 88 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---3B82 | TT_FinMile | (RFS) READY FOR SHIPMENT OFFRACK / YARD LOT 6 | 20/08/2022 | 20/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---4B27 | TT_Task | TRANSPORT OFFRACK PIPING LOT 6 | 21/08/2022 | 24/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---4-12 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION OFFRACK / YARD LOT 6 | 24/07/2022 | 20/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---3-72 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) FOR OFFRACK PIPING LOT 6 | 23/07/2022 | 23/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---3B81 | TT_FinMile | (RFS) READY FOR SHIPMENT OFFRACK / YARD LOT 5 | 31/03/2022 | 31/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---4B26 | TT_Task | TRANSPORT OFFRACK PIPING/ YARD LOT 5 | 01/04/2022 | 05/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---4-11 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION OFFRACK / YARD LOT 5 | 04/03/2022 | 31/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---3-71 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) FOR OFFRACK PIPING LOT 5 | 03/03/2022 | 03/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---3B80 | TT_FinMile | (RFS) READY FOR SHIPMENT OFFRACK / YARD LOT 4 | 02/03/2022 | 02/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---4B25 | TT_Task | TRANSPORT OFFRACK PIPING / YARD LOT 4 | 03/03/2022 | 06/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---4-10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION OFFRACK / YARD LOT 4 | 03/02/2022 | 02/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---3-70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) FOR OFFRACK PIPING LOT 4 | 02/02/2022 | 02/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI----P3A92 | TT_FinMile | (RFS) READY FOR SHIPMENT MEDIUM LEAD SUPPORT ITEMS (100%) | 01/10/2021 | 01/10/2021 | 01/10/2021 | 01/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI----P3A93 | TT_Task | FABRICATION MEDIUM LEAD SUPPORT ITEMS (100%) | 24/07/2021 | 01/10/2021 | 24/07/2021 | 01/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI----P4A27 | TT_Task | TRANSPORT MEDIUM LEAD SUPPORT ITEMS (100%) | 02/10/2021 | 19/11/2021 | 02/10/2021 | 19/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---3B52 | TT_Task | SKID ASSEMBLY FOR SHIPMENT LOT 3 | 19/03/2022 | 13/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---3B51 | TT_Task | PREFABRICATION OF ITEMS FOR SHIPMENT LOT 3 | 10/11/2021 | 15/03/2022 | 10/11/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20---3B45 | TT_Task | SKID ASSEMBLY FOR SHIPMENT LOT 2 | 20/02/2022 | 16/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---3B44 | TT_Task | PREFABRICATION OF ITEMS FOR SHIPMENT LOT 2 | 08/10/2021 | 18/02/2022 | 08/10/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20---3B37 | TT_Task | SKID ASSEMBLY FOR SHIPMENT LOT 1 | 22/01/2022 | 18/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20-1P340 | TT_Task | PREFABRICATION OF ITEMS FOR SHIPMENT LOT 1 | 08/09/2021 | 19/01/2022 | 08/09/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20---3B33 | TT_Task | FABRICATION LONG LEAD SUPPORTS FOR SHIPMENT LOT 3 AND LOT 4 | 24/07/2021 | 25/11/2021 | 24/07/2021 | 26/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---4B31 | TT_Task | TRANSPORT LONG LEAD SUPPORTS FOR SHIPMENT LOT 3 AND LOT 4 | 27/11/2021 | 14/01/2022 | 27/11/2021 |  | 504 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20---3B86 | TT_FinMile | (RFS) READY FOR SHIPMENT LONG LEAD SUPPORTS FOR SHIPMENT LOT 3 AND LOT 4 | 26/11/2021 | 26/11/2021 | 26/11/2021 | 26/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---3B31 | TT_Task | PROCUREMENT MEDIUM LEAD ITEMS 2 (95%) | 12/06/2021 | 15/09/2021 | 12/06/2021 | 15/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---2B85 | TT_Mile | ORDER MTO MEDIUM LEAD ITEMS 2 (95%) | 12/06/2021 | 12/06/2021 | 12/06/2021 | 12/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI----P2J85 | TT_Mile | THERMODYNAMICAL INPUT FROM GT / ST / HRSG / (HFD, WATER BALANCE, WS-DOS, PL PLAN) | 17/01/2021 | 17/01/2021 | 17/01/2021 | 17/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMY2A67 | TT_Task | DELTA DESIGN / VERIFICATION GROUP I | 02/01/2021 | 22/01/2021 | 02/01/2021 | 22/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---2B50 | TT_Task | DETAIL DESIGN BB STEELWORK LOT 3 | 27/05/2021 | 02/08/2021 | 27/05/2021 | 02/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---2B43 | TT_Task | DETAIL DESIGN BB STEELWORK LOT 2 | 02/06/2021 | 04/07/2021 | 02/06/2021 | 04/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---3B26 | TT_FinMile | DELIVERY OF COMPONENTS FOR SHIPMENT LOT 1 | 10/12/2021 | 10/12/2021 | 10/12/2021 | 10/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MBA2D05 | TT_Mile | ERECTION MANUALS ON SITE WASH WATER TANK MBA | 16/10/2022 | 16/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBA2D86 | TT_FinMile | (DF) INPUT FOR MS3 WASH WATER TANK 20MBA (from D1) | 15/09/2021 | 15/09/2021 | 15/09/2021 | 15/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MBA3-25 | TT_Task | DETAIL DESIGN WASH WATER TANK 20MBA | 16/09/2021 | 29/09/2021 | 16/09/2021 | 29/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PGB2C05 | TT_Mile | ERECTION MANUALS TO SKIDDER HEAT EXCHANGER PGB | 02/08/2021 | 02/08/2021 | 02/08/2021 | 02/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PGB3C25 | TT_Task | DETAIL DESIGN HEAT EXCHANGER 20PGB | 12/04/2021 | 25/04/2021 | 12/04/2021 | 25/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PGB2C86 | TT_Task | DESIGN DATA SHEETS HEAT EXCHANGER PGB | 18/01/2021 | 24/01/2021 | 18/01/2021 | 24/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PGB2D05 | TT_Mile | ERECTION MANUALS TO SKIDDER CCW EXPANSION TANK PGB | 11/01/2022 | 11/01/2022 |  |  | 320 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PGB2D86 | TT_Task | DESIGN DATA SHEETS CCW EXPANSION TANK PGB | 25/03/2021 | 31/03/2021 | 25/03/2021 | 31/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PGB3D25 | TT_Task | DETAIL DESIGN CCW EXPANSION TANK 20PGB | 07/08/2021 | 13/08/2021 | 07/08/2021 | 13/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20LBG2C05 | TT_Mile | ERECTION MANUALS ON SITE EL. SUPERHEATER LBG | 08/04/2022 | 08/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LBG3C25 | TT_Task | DETAIL DESIGN EL. SUPERHEATER 20LBG | 07/06/2021 | 27/06/2021 | 07/06/2021 | 27/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20LBG2C86 | TT_Task | DESIGN DATA SHEETS EL. SUPERHEATER LBG | 29/01/2021 | 18/02/2021 | 29/01/2021 | 18/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20SCA2-05 | TT_Mile | ERECTION MANUALS ON SITE AIR COMPRESSOR SYSTEM SCA | 31/05/2022 | 31/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SCA3-25 | TT_Task | DETAIL DESIGN / CLARIFICATION AIR COMPRESSOR SYSTEM 20SCA | 21/09/2021 | 17/12/2021 | 21/09/2021 | 17/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20SCA2-86 | TT_Task | DESIGN DATA SHEETS AIR COMPRESSOR SYSTEM SCA | 05/02/2021 | 18/02/2021 | 05/02/2021 | 18/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--GM-2B66 | TT_FinMile | (DF) INPUT FOR M2 SUMP PUMP GM | 06/08/2021 | 06/08/2021 | 06/08/2021 | 06/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--GM-2B87 | TT_Mile | PROPOSAL PUMP CURVE FOR DESIGN C-V SUMP PUMP GM | 02/10/2021 | 02/10/2021 | 02/10/2021 | 02/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--GM-2B86 | TT_Task | DESIGN DATA SHEETS SUMP PUMP GM | 30/01/2021 | 03/05/2021 | 30/01/2021 | 03/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20LCL2B05 | TT_Mile | ERECTION MANUALS ON SITE BOILER BLOWDOWN PUMP LCL | 25/06/2022 | 25/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LCL2B66 | TT_FinMile | (DF) INPUT FOR M2 BOILER BLOWDOWN PUMP LCL | 21/05/2021 | 21/05/2021 | 21/05/2021 | 21/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20LCL2B87 | TT_Mile | PROPOSAL PUMP CURVE FOR DESIGN C-V BOILER BLOWDOWN PUMP LCL | 29/04/2021 | 29/04/2021 | 29/04/2021 | 29/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PGB2B05 | TT_Mile | ERECTION MANUALS TO SKIDDER CCW PUMP PGB | 31/07/2021 | 31/07/2021 | 31/07/2021 | 31/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PGB2B87 | TT_Mile | PROPOSAL PUMP CURVE FOR DESIGN C-V CCW PUMP PGB | 23/04/2021 | 23/04/2021 | 23/04/2021 | 23/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PGB2B86 | TT_Task | DESIGN DATA SHEETS CCW PUMP PGB | 17/01/2021 | 30/01/2021 | 17/01/2021 | 30/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PCB2B05 | TT_Mile | ERECTION MANUALS TO SKIDDER COOLING WATER BOOSTER PUMP PCB | 06/10/2021 | 06/10/2021 | 06/10/2021 | 06/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BFA3-70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) LV- / DC-SWITCHGEAR BFA/BFB/BMA/BUA/BUB/BUC | 16/01/2022 | 16/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PCB2B67 | TT_FinMile | (DF) INPUT FOR MS3 SERVICE COOLING WATER BOOSTER PUMP PCB | 30/04/2021 | 30/04/2021 | 30/04/2021 | 30/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PCB2B66 | TT_FinMile | (DF) INPUT FOR M2 SERVICE COOLING WATER BOOSTER PUMP PCB | 30/04/2021 | 30/04/2021 | 30/04/2021 | 30/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PCB2B65 | TT_Mile | PROPOSAL PUMP CURVE FOR DESIGN C-V SERVICE COOLING WATER BOOSTER PUMP PCB | 23/04/2021 | 23/04/2021 | 23/04/2021 | 23/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PCB2B64 | TT_Task | DESIGN DATA SHEETS SERVICE COOLING WATER BOOSTER PUMP PCB | 07/01/2021 | 14/01/2021 | 07/01/2021 | 14/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20LDK2B90 | TT_Mile | PROPOSAL PUMP CURVE FOR DESIGN C-V CONDENSATE POLISHING PUMP 20LDK | 05/03/2021 | 05/03/2021 | 05/03/2021 | 05/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20LDK2B05 | TT_Mile | ERECTION MANUALS AT SKIDDER CONDENSATE POLISHING PUMP 20LDK | 09/12/2021 | 09/12/2021 | 09/12/2021 | 09/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20LDK2B86 | TT_Task | DESIGN DATA SHEETS CONDENSATE POLISHING PUMP 20LDK | 29/01/2021 | 11/02/2021 | 29/01/2021 | 11/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--LD-2A63 | TT_FinMile | (DF) INPUT FOR MS3 CONDENSATE POLISHING PLANT 20LD | 01/06/2021 | 01/06/2021 | 01/06/2021 | 01/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--LD-2-65 | TT_FinMile | (DF) INPUT FOR M2 CONDENSATE POLISHING PLANT 20LD | 06/07/2021 | 06/07/2021 | 06/07/2021 | 06/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20QU-2-06 | TT_Mile | ERECTION MANUALS ON SITE SAMPLING CONTAINER 20QU | 21/10/2022 | 21/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20QU-3-25 | TT_Task | DETAIL DESIGN SAMPLING CONTAINER 20QU | 25/07/2021 | 11/09/2021 | 25/07/2021 | 11/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20LCL3B25 | TT_Task | DETAIL DESIGN / CLARIFICATION BOILER BLOWDOWN PUMP 20LCL | 03/05/2021 | 30/05/2021 | 03/05/2021 | 30/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20LCL2B86 | TT_Task | DESIGN DATA SHEETS BOILER BLOWDOWN PUMP LCL | 02/02/2021 | 15/02/2021 | 02/02/2021 | 15/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20LCA2B05 | TT_Mile | ERECTION MANUALS AT SKIDDER CONDENSATE RECIRC.PUMP LCA51 | 06/10/2021 | 06/10/2021 | 06/10/2021 | 06/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20LCA2B87 | TT_Task | DESIGN DATA SHEETS CONDENSATE RECIRC.PUMP LCA51 | 30/01/2021 | 12/02/2021 | 30/01/2021 | 12/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--PAC2B05 | TT_Mile | ERECTION MANUALS ON SITE CIRC. CW PUMP PAC | 17/05/2022 | 17/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--PAC2B86 | TT_Task | DESIGN DATA SHEETS CIRC. CW PUMP PAC | 16/01/2021 | 29/01/2021 | 16/01/2021 | 29/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20LAC2B05 | TT_Mile | ERECTION MANUALS ON SITE FEEDWATER PUMP 20LAC | 26/05/2022 | 26/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LAC2B86 | TT_Task | DESIGN DATA SHEETS FEEDWATER PUMP 20LAC | 20/01/2021 | 02/02/2021 | 20/01/2021 | 02/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20LCB2B05 | TT_Mile | ERECTION MANUALS ON SITE CONDENSATE EXTRACTION PUMP LCB | 05/05/2022 | 05/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LCB2B92 | TT_Task | DESIGN DATA SHEETS CONDENSATE EXTRACTION PUMPS LCB | 01/01/2021 | 14/01/2021 | 01/01/2021 | 14/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--HA-2A86 | TT_Mile | (DF) HEAT FLOW DIAGRAM | 05/12/2020 | 05/12/2020 | 05/12/2020 | 05/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2J81 | TT_Mile | E-AND IC- MANUALS FOR COMP.INSTALL.AVAILABLE ELECTRICAL MODULES 20UBA7610/20 | 27/12/2021 | 27/12/2021 | 27/12/2021 | 27/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UBA2K05 | TT_Mile | ERECTION MANUALS ON SITE ELECTRICAL MODULES UBA | 06/07/2022 | 06/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--UBA3K50 | TT_FinMile | ELECTRICAL MODULES READY FOR INSTALLATION OF COMP. ELECTRICAL MODULES UBA | 16/02/2022 | 16/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--CYA2-05 | TT_Mile | ERECTION MANUALS ON SITE TELECOMMUNICATION CYA | 29/12/2022 | 29/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BZL2-05 | TT_Mile | ERECTION MANUALS ON SITE LIGHTING SMALL POWER BZL ALL STRUCTURE | 06/05/2022 | 06/05/2022 |  |  | 728 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BZP2-05 | TT_Mile | ERECTION MANUALS ON SITE CABLE SUPPORT SYSTEM BZP | 17/03/2022 | 17/03/2022 |  |  | 184 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BZP2-92 | TT_FinMile | FIRST BOQ CABLE SUPPORT SYSTEM BZP | 18/12/2021 | 18/12/2021 | 18/12/2021 | 18/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--BZP2-91 | TT_Task | ADJUSTMENT OF CABLE SUPPORT ACC. TO MANUFACTURER STANDARD | 30/09/2021 | 24/11/2021 | 30/09/2021 | 24/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--BZK2-06 | TT_Mile | ERECTION MANUALS ON SITE IC CABLES BZK | 22/06/2022 | 22/06/2022 |  |  | 256 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BZK2-05 | TT_Mile | ERECTION MANUALS ON SITE MV/LV CABLES | 24/07/2022 | 24/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--B--2-65 | TT_Mile | TENDER BOQ MV/LV CABLES BZK | 24/08/2021 | 24/08/2021 | 24/08/2021 | 24/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--BFT2-05 | TT_Mile | ERECTION MANUALS ON SITE LV-TRANSFORMERS BFT | 01/06/2022 | 01/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAT2-05 | TT_Mile | ERECTION MANUALS ON SITE MAIN TRANSFORMER BAT | 16/07/2022 | 16/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20XKA2-05 | TT_Mile | ERECTION MANUALS ON SITE EMERGENCY DIESEL GEN.SET XKA | 16/06/2022 | 16/06/2022 |  |  | 520 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BTL3-25 | TT_Task | DETAIL DESIGN / MANUFACTURING / SHOP TEST BATTERY CHARGER BTL | 30/09/2021 | 04/01/2022 | 30/09/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20BTL4-10 | TT_Task | TRANSPORT TO WORKSHOP BATTERY CHARGER BTL (TO ST. INGBERT-INSTALL INTO ELECTRICAL MODULES) | 05/01/2022 | 06/01/2022 |  |  | 376 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BRU3-25 | TT_Task | DETAIL DESIGN / MANUFACTURING / SHOP TEST INVERTER BRU | 30/09/2021 | 04/01/2022 | 30/09/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20BRU4-10 | TT_Task | TRANSPORT TO WORKSHOP INVERTER BRU (TO ST. INGBERT-INSTALL INTO ELECTRICAL MODULES) | 05/01/2022 | 06/01/2022 |  |  | 376 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BFF2-88 | TT_Mile | (DF) MANUFACTURING LV/DV-SWITCHGEAR FOR HRSG 20BFF/BMF | 08/09/2021 | 08/09/2021 | 08/09/2021 | 08/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--5552-10 | TT_Mile | BOQ - REVIEW MAIN CIVIL WORKS | 13/12/2020 | 13/12/2020 | 13/12/2020 | 13/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BTA4B10 | TT_Task | TRANSPORT TO WORKSHOP BATTERY RACKS BTA (TO ST. INGBERT-INSTALL INTO ELECTRICAL MODULES) | 21/02/2022 | 22/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BFC2Z77 | TT_Mile | (DF) MANUFACTURING LV/DV-SWITCHGEAR 20BFC/BFD | 08/12/2021 | 08/12/2021 | 08/12/2021 | 08/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BFC3-24 | TT_Task | DETAIL DESIGN / CLARIFICATION TYPICAL OF LV- / DC-SWITCHGEAR 20BFC/BFD | 30/07/2021 | 07/12/2021 | 30/07/2021 | 07/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BFC2Z85 | TT_Mile | CONTRACT INTO FORCE LV- / DC-SWITCHGEAR 20BFC/BFD | 30/07/2021 | 30/07/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--BFF3-25 | TT_Task | DETAIL DESIGN / CLARIFICATION TYPICAL OF LV SWITCHGEAR FOR HRSG 20BFF/BMF | 30/07/2021 | 07/09/2021 | 30/07/2021 | 07/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BFA2-86 | TT_Mile | (DF) MANUFACTURING LV- / DC-SWITCHGEAR BFA/BFB/BMA/BUA/BUB/BUC | 08/09/2021 | 08/09/2021 | 08/09/2021 | 08/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BFA2-25 | TT_Task | DETAIL DESIGN / CLARIFICATION TYPICAL OF LV- / DC-SWITCHGEAR BFA/BFB/BMA/BUA/BUB/BUC | 30/07/2021 | 07/09/2021 | 30/07/2021 | 07/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--BAW2-05 | TT_Mile | ERECTION MANUALS ON SITE IN- / OUTDOOR GROUNDING BAW | 27/03/2022 | 27/03/2022 |  |  | 672 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BAC2-05 | TT_Mile | ERECTION MANUALS ON SITE GEN. CIRCUIT BREAKER BAC | 01/08/2022 | 01/08/2022 |  |  | 224 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BAA2-05 | TT_Mile | ERECTION MANUALS ON SITE IPB BAA | 19/07/2022 | 19/07/2022 |  |  | 336 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--3332-24 | TT_Task | INTERCONNECTION ENGINEERING, CMI, FUP | 30/04/2021 | 12/07/2021 | 30/04/2021 | 12/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--B--2-67 | TT_Mile | BINDING ELECTRICAL AND IC CABLE LIST AVAILABLE | 20/12/2021 | 20/12/2021 | 20/12/2021 | 20/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--B--2A56 | TT_Mile | LV- SWITCHGEAR DATA FINAL | 31/07/2021 | 31/07/2021 | 31/07/2021 | 31/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--BAW2-06 | TT_Task | PREPARATION VEL (after ELV3) | 01/07/2021 | 30/07/2021 | 01/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--BAW2-04 | TT_Task | PREPARATION VEL (before ELV3) | 16/03/2021 | 14/06/2021 | 16/03/2021 | 14/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--BAW2-03 | TT_Task | PREPARATION VEL (before ELV2) | 05/02/2021 | 15/03/2021 | 05/02/2021 | 15/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--3332-26 | TT_Mile | APPROVED SINGLE LINE DIAGRAM RELEASED | 20/02/2021 | 20/02/2021 | 20/02/2021 | 20/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--3332-25 | TT_Task | APPROVAL SINGLE LINE DIAGRAM | 15/01/2021 | 19/02/2021 | 15/01/2021 | 19/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAA2-05 | TT_Mile | ERECTION MANUALS ON SITE COOLING TOWER COARSE SCREEN 20PAA | 10/08/2022 | 10/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAH2-05 | TT_Mile | ERECTION MANUALS AT SKIDDER CONDENSER TUBE CLEANING SYSTEM 20PAH | 15/11/2021 | 15/11/2021 | 15/11/2021 | 15/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAH3-25 | TT_Task | DETAIL DESIGN CONDENSER TUBE CLEANING SYSTEM 20PAH | 15/05/2021 | 28/06/2021 | 15/05/2021 | 28/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20SMM3-25 | TT_Task | DETAIL AND FABRICATION DESIGN CRANE 20SMM01/02 FOR 20UMC | 08/08/2021 | 02/10/2021 | 08/08/2021 | 02/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PDB2-05 | TT_Mile | ERECTION MANUALS TO SKIDDER DEBRIS FILTER 20PDB | 21/12/2021 | 21/12/2021 | 21/12/2021 | 21/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PDB3-25 | TT_Task | DETAIL DESIGN DEBRIS FILTER 20PDB | 04/05/2021 | 15/06/2021 | 04/05/2021 | 15/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--LD-2A05 | TT_Mile | ERECTION MANUALS ON SITE CONDENSATE POLISHING PLANT 20LD | 08/07/2022 | 08/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LD-3-25 | TT_Task | DETAIL DESIGN CONDENSATE POLISHING PLANT 20LD | 19/05/2021 | 27/07/2021 | 19/05/2021 | 27/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--LD-2-87 | TT_Task | PREPARATION RFQ CONDENSATE POLISHING PLANT 20LD | 03/03/2021 | 18/03/2021 | 03/03/2021 | 18/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--LD-2-86 | TT_FinMile | (DF) PID's CONDENSATE POLISHING PLANT 20LD | 02/03/2021 | 02/03/2021 | 02/03/2021 | 02/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20QC-2-65 | TT_FinMile | (DF) INPUT FOR M2 DOSING CONTAINER QC | 13/08/2021 | 13/08/2021 | 13/08/2021 | 13/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20QC-2-89 | TT_FinMile | (DF) INPUT FOR MS3 DOSING CONTAINER QC | 31/08/2021 | 31/08/2021 | 31/08/2021 | 31/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20QC-2-06 | TT_Mile | ERECTION MANUALS ON SITE DOSING CONTAINER 20QC | 28/08/2022 | 28/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20S--2J31 | TT_Mile | ERECTION MANUAL ON SITE HVAC SYSTEM SA/SB FOR UMC | 13/10/2022 | 13/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SAM4B11 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION EQUIPMENT FOR HVAC SYSTEM UMC 20SA | 06/03/2022 | 02/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SAM3B71 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) EQUIPMENT FOR HVAC SYSTEM UMC 20SA | 05/03/2022 | 05/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20S--4-41 | TT_FinMile | (OTD-OS) ON SITE EQUIPMENT FOR HVAC SYSTEM UMC 20SA | 13/10/2022 | 13/10/2022 |  |  | 168 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SAM3E31 | TT_Task | MANUFACTURING SHOP TEST EQUIPMENT FOR HVAC SYSTEM UMC 20SA | 07/11/2021 | 05/03/2022 | 07/11/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20S--3-81 | TT_FinMile | (RFS) READY FOR SHIPMENT EQUIPMENT FOR HVAC SYSTEM UMC 20SA | 02/04/2022 | 02/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SAM4-26 | TT_Task | TRANSPORT EQUIPMENT FOR HVAC SYSTEM UMC 20SA | 03/04/2022 | 24/06/2022 |  |  | 880 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20S--2J35 | TT_FinMile | (DF) DETAIL DESIGN DWGS HVAC SYSTEM SA/SB FOR UMC WITH CONTRACTOR | 26/09/2021 | 26/09/2021 | 26/09/2021 | 26/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20S--2J29 | TT_FinMile | (DF) INPUT FOR MS3 HVAC SYSTEM SA/SB UMC SA | 05/09/2021 | 05/09/2021 | 05/09/2021 | 05/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--SA-2-31 | TT_FinMile | KICK OFF FINISHED HVAC SYSTEM SA | 22/04/2021 | 22/04/2021 | 22/04/2021 | 22/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--SG-2-30 | TT_Task | INTERMEDIATE FIRE- EXPLOSION PROTECTION CONCEPT | 29/09/2020 | 19/10/2020 | 29/09/2020 | 19/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--SGA2-05 | TT_Mile | ERECTION MANUALS ON SITE FOR FIRE FIGHTING PUMP CONTAINER 20SGA | 31/10/2022 | 31/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--SGA2-31 | TT_FinMile | (DF) INPUT FOR MS3 FIRE FIGHTING PUMP CONTAINER 20SGA | 27/09/2021 | 27/09/2021 | 27/09/2021 | 27/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20SGA3-81 | TT_FinMile | (RFS) READY FOR SHIPMENT FIRE FIGHTING PUMP CONTAINER 20SGA | 14/02/2022 | 14/02/2022 |  |  | 1896 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGA4-44 | TT_FinMile | ON SITE FIRE FIGHTING PUMP CONTAINER 20SGA | 27/11/2022 | 27/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGA3-26 | TT_Task | DETAIL DESIGN / MANUFACTURING / SHOP TEST FIRE FIGHTING PUMP CONTAINER 20SGA | 10/09/2021 | 17/01/2022 | 10/09/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20SGA4-26 | TT_Task | TRANSPORT FIRE FIGHTING PUMP CONTAINER 20SGA | 10/10/2022 | 27/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGA4-11 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION FIRE FIGHTING PUMP CONTAINER 20SGA | 18/01/2022 | 14/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGA3-71 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) FIRE FIGHTING PUMP CONTAINER 20SGA | 17/01/2022 | 17/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--SG-2-06 | TT_Mile | ERECTION MANUALS ON SITE FOR FIRE FIGHTING RING MAIN SGA | 03/06/2022 | 03/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--SGY2-05 | TT_Mile | ERECTION MANUALS ON SITE FOR FIRE FIGHTING SYSTEMS SGY | 04/03/2022 | 04/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--SG-2-05 | TT_Mile | ERECTION MANUALS ON SITE FOR FIRE FIGHTING SYSTEMS 20SGC/SGE/SGF/SGJ | 25/08/2022 | 25/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--SG-2-46 | TT_FinMile | (DF) INPUT FOR MS3 FIRE FIGHTING SYSTEMS SGC/SGE/SGF/SGJ | 07/10/2021 | 07/10/2021 | 07/10/2021 | 07/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--SG-2-18 | TT_Mile | BASIC DESIGN DWGS FIRE FIGHTING SYSTEMS SG- AVAILABLE | 24/07/2021 | 24/07/2021 | 24/07/2021 | 24/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--SG-2-43 | TT_Task | PREP. RFQ FIRE FIGHTING SYSTEMS SG- | 02/07/2021 | 15/07/2021 | 02/07/2021 | 15/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--SG-2-17 | TT_Task | BASIC DESIGN FIRE FIGHTING RING MAIN SGA (prel. LH020) | 31/05/2021 | 11/07/2021 | 31/05/2021 | 11/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--PAD2-05 | TT_Mile | ERECTION MANUALS ON SITE MECHANICAL EQUIPMENT PAD | 30/06/2022 | 30/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD3-24 | TT_Task | DETAIL DESIGN COOLING TOWER EQUIPMENT 20PAD | 19/02/2021 | 05/07/2021 | 19/02/2021 | 05/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--EK-2-07 | TT_Mile | ERECTION MANUALS ON SITE FUEL GAS RECEIVING AND MIXING SYSTEM EK | 27/06/2022 | 27/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--EK-2-81 | TT_Task | QUOTATION STAGE FUEL GAS RECEIVING AND MIXING SYSTEM EK | 31/03/2021 | 27/06/2021 | 31/03/2021 | 27/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--EK-2-77 | TT_Task | BASIC DESIGN / PREP. RFQ FUEL GAS RECEIVING AND MIXING SYSTEM EK | 26/01/2021 | 30/03/2021 | 26/01/2021 | 30/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MA-2-81 | TT_Mile | ORDER ENTRY STEAM TURBINE | 15/01/2021 | 15/01/2021 | 15/01/2021 | 15/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--EK-2-05 | TT_Mile | ERECTION MANUALS ON SITE GAS FINAL FILTER/ PREHEATER EKG02Y | 04/12/2022 | 04/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20EK-3-27 | TT_Task | DETAIL DESIGN FUEL GAS RECEIVING AND MIXING SYSTEM 01EK | 28/06/2021 | 12/08/2021 | 28/06/2021 | 12/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20SMM2-83 | TT_Mile | ERECTION MANUAL ON SITE CRANE SMM01/02/3 FOR 20UMC | 13/01/2022 | 13/01/2022 |  |  | 656 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAB3-30 | TT_Task | MANUFACTURING PIPING SYSTEM (OUTSIDE) 20PAB | 28/03/2021 | 26/06/2021 | 28/03/2021 | 26/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC2B35 | TT_Task | CLIENT - REVIEW - BUILDING DETAIL DESIGN CONCRETE 20UMC | 16/07/2021 | 09/08/2021 | 16/07/2021 | 09/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC2B25 | TT_Task | PREPARATION FOUNDATION GROUNDING DWGS 20UMC | 02/07/2021 | 15/07/2021 | 02/07/2021 | 15/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC2B15 | TT_Task | BASIC DESIGN / BASIC BUILDING DESIGN INCL. 3D MODEL BUILDING FOUNDATION 20UMC | 15/05/2021 | 28/05/2021 | 15/05/2021 | 28/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2Y81 | TT_Task | PREPARATION FOUNDATION GROUNDING DWGS CEP/LDK PIT 20UMC | 02/03/2021 | 15/03/2021 | 02/03/2021 | 15/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2Y79 | TT_Task | BASIC DESIGN CEP/LDK PIT 20UMC | 01/01/2021 | 22/02/2021 | 01/01/2021 | 22/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2E78 | TT_Task | HANDRAILS AND GRATING DWGS CONNECTION FORCE REPORT LOT1 20UMC | 27/05/2021 | 16/06/2021 | 27/05/2021 | 16/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UBA2D78 | TT_Task | HANDRAILS AND GRATING DWGS CONNECTION FORCE REPORT 20UBA8110/20 | 16/11/2021 | 06/12/2021 | 16/11/2021 | 06/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2B-15 | TT_Task | HANDRAILS AND GRATING DWGS CONNECTION FORCE REPORT 20UBA1110/20 | 24/12/2021 | 13/01/2022 | 24/12/2021 |  | 360 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--UBF2B78 | TT_Task | HANDRAILS AND GRATING DWGS CONNECTION FORCE REPORT 20UBE/UBF | 20/07/2021 | 09/08/2021 | 20/07/2021 | 09/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBD2-84 | TT_Task | FOUNDATION GROUNDING DWGS 20UBD01/02 | 13/09/2021 | 06/12/2021 | 13/09/2021 | 06/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UEY2-77 | TT_Task | BASIC DESIGN / BASIC BUILDING DESIGN INCL. 3D MODEL 20UEY03-05 | 11/06/2021 | 01/07/2021 | 11/06/2021 | 01/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UEN2-12 | TT_Task | BASIC DESIGN / BASIC BUILDING DESIGN INCL. 3D MODEL 01UEN | 02/08/2021 | 21/08/2021 | 02/08/2021 | 21/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--URD2-71 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN CONCRETE 20URD xx | 14/07/2021 | 07/08/2021 | 14/07/2021 | 07/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--URD2-74 | TT_Mile | BASIC DESIGN FREEZE / REVIEW / APPROVAL 20URD xx | 30/05/2021 | 30/05/2021 | 30/05/2021 | 30/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--URD2-77 | TT_Task | BASIC BUILDING DESIGN INCL. 3D MODEL 20URD xx | 02/05/2021 | 29/05/2021 | 02/05/2021 | 29/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2C77 | TT_Task | BASIC BUILDING DESIGN INCL. 3D MODEL 20UBA8110/20 | 20/05/2021 | 16/06/2021 | 20/05/2021 | 16/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHX2-20 | TT_Task | PREPARATION FOUNDATION GROUNDING 20UHX | 15/09/2021 | 28/09/2021 | 15/09/2021 | 28/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHX2-5 | TT_Task | BASIC BUILDING DESIGN INCL. 3D MODEL 20UHX (if required) | 30/01/2022 | 19/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--UMY2-78 | TT_Task | PREPARATION FOUNDATION GROUNDING DWGS 20ULY/UMY | 30/06/2021 | 13/07/2021 | 30/06/2021 | 13/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMY2-77 | TT_Task | BASIC BUILDING DESIGN INCL. 3D MODEL 20ULY/UMY | 09/05/2021 | 29/05/2021 | 09/05/2021 | 29/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--ULA2-71 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN CONCRETE 20ULA | 03/07/2021 | 27/07/2021 | 03/07/2021 | 27/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--ULA2-77 | TT_Task | BASIC DESIGN / BASIC BUILDING DESIGN INCL. 3D MODEL 20ULA | 05/05/2021 | 18/05/2021 | 05/05/2021 | 18/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2-10 | TT_Task | BASIC BUILDING DESIGN INCL. 3D MODEL 20UBA1110/20 | 20/05/2021 | 07/07/2021 | 20/05/2021 | 07/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20USX2-20 | TT_Task | PREPARATION FOUNDATION GROUNDING DWGS 20USX | 22/11/2021 | 27/02/2022 | 22/11/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20USX2-10 | TT_Task | BASIC BUILDING DESIGN INCL. 3D MODEL 20USX | 01/09/2021 | 21/09/2021 | 01/09/2021 | 21/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBX2-25 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN CONCRETE - 20UBX/20UBG03 | 07/12/2021 | 31/12/2021 | 07/12/2021 |  | 992 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--UBA2-65 | TT_Task | BASIC BUILDING DESIGN INCL. 3D MODEL UBA7xxx | 16/04/2021 | 28/05/2021 | 16/04/2021 | 28/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-10 | TT_Task | BASIC BUILDING DESIGN INCL. 3D MODEL 20UTG01 | 16/08/2021 | 24/12/2021 | 16/08/2021 | 24/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMX2-77 | TT_Task | BASIC BUILDING DESIGN INCL. 3D MODEL UMX-Deleted | 30/06/2021 | 26/07/2021 | 30/06/2021 | 26/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBN2-10 | TT_Task | BASIC BUILDING DESIGN INCL. 3D MODEL 20UBN | 17/12/2021 | 06/01/2022 | 17/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UBX2-15 | TT_Task | BASIC BUILDING DESIGN INCL. 3D MODEL 20UBX/20UBG03 | 30/08/2021 | 19/09/2021 | 30/08/2021 | 19/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UEN2-71 | TT_Task | BASIC BUILDING DESIGN INCL. 3D MODEL 20UEN | 12/07/2021 | 01/08/2021 | 12/07/2021 | 01/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UBA2-81 | TT_Task | BASIC BUILDING DESIGN INCL. 3D MODEL UBA7910/7920 | 20/05/2021 | 23/06/2021 | 20/05/2021 | 23/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UBA2B97 | TT_Task | HANDRAILS AND GRATING DWGS CONNECTION FORCE REPORT UBA7xxx | 11/01/2022 | 31/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBX2-60 | TT_Task | HANDRAILS AND GRATING DWGS CONNECTION FORCE REPORT 20UBX | 13/01/2022 | 02/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2B78 | TT_Task | HANDRAILS AND GRATING DWGS CONNECTION FORCE REPORT 20UMC | 26/04/2021 | 16/05/2021 | 26/04/2021 | 16/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2B71 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN - STEEL STRUCTURE 20UMC | 17/05/2021 | 10/06/2021 | 17/05/2021 | 10/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UBF2-71 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN CONCRETE - 20UBE/UBF | 10/08/2021 | 03/09/2021 | 10/08/2021 | 03/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UBF2-79 | TT_FinMile | (DF) TRANSFORMER YARD DWGS AVAILABLE BAT/BBT | 25/03/2021 | 25/03/2021 | 25/03/2021 | 25/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UBF2-78 | TT_Task | PREPARATION TRANSFORMER YARD DWGS BAT/BBT | 26/02/2021 | 25/03/2021 | 26/02/2021 | 25/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UBF2-77 | TT_Task | BASIC DESIGN / BASIC BUILDING DESIGN INCL. 3D MODEL 20UBE/UBF | 06/06/2021 | 21/06/2021 | 06/06/2021 | 21/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UHA2-78 | TT_Task | BASIC DESIGN / BASIC BUILDING DESIGN INCL. 3D MODEL UHA | 10/05/2021 | 30/05/2021 | 10/05/2021 | 30/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2A75 | TT_FinMile | (F) CONCRETE STRUC. DWGS ON SITE, RELEASED FOR EXECUTION TS FOUND 20UMC | 08/07/2021 | 08/07/2021 | 08/07/2021 | 08/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2A71 | TT_Task | CLIENT - REVIEW - TURBOSET DETAIL DESIGN CONCRETE 20UMC | 22/04/2021 | 16/05/2021 | 22/04/2021 | 16/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--5552-25 | TT_Mile | KICK OFF MEETING MAIN CIVIL WORKS | 28/05/2021 | 28/05/2021 | 28/05/2021 | 28/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--5552-24 | TT_Task | PREPARATION KICK OFF MAIN CIVIL WORKS | 14/05/2021 | 27/05/2021 | 14/05/2021 | 27/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--5552-13 | TT_Task | EVALUATION/NEGOTIATION MAIN CIVIL WORKS | 09/04/2021 | 13/05/2021 | 09/04/2021 | 13/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UHA2-40 | TT_Mile | (MS2) DESIGN LOAD DATA, DIMENSIONS AVAILABLE (UHA,UVM01,UEY01,UMX,UMY,UHW,UHX,UBA11,ULA) | 15/01/2021 | 15/01/2021 | 15/01/2021 | 15/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UM-2-35 | TT_FinMile | (C) BASIC DESIGN PLANT LAYOUT DWGS AVAILABLE (UMC,UPY,UTG01/05,UHA,UVM01,UEY01,UMX,UMY,UHW,UHX,UBA11,ULA,ULY01) | 07/04/2021 | 07/04/2021 | 07/04/2021 | 07/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--U--2-16 | TT_Task | BASIC DESIGN PLANT LAYOUT POWER BLOCK AREA (UMC,UPY,UTG01/05,UHA,UVM01,UEY01,UMX,UMY,UHW,UHX,UBA11,ULA,ULY01) | 29/01/2021 | 07/04/2021 | 29/01/2021 | 07/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UM-2-40 | TT_Mile | (MS2) DESIGN LOAD DATA, DIMENSIONS AVAILABLE (UMC,UPY,UTG01,/05) | 15/01/2021 | 15/01/2021 | 15/01/2021 | 15/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--GHC6-10 | TT_Mile | DEMINERALIZED WATER REQUIRED | 18/03/2023 | 18/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-116 | TT_Mile | TP-M5A - TOWNSWATER DOMESTIC SYSTEM (POTABLE WATER) | 26/08/2022 | 26/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-----5-20 | TT_Mile | SITE HANDOVER FOR CONSTRUCTION - EARLY WORKS COMPLETED INCL. WORK PREPARATION IN UHA, URD URA AREA | 01/07/2021 | 01/07/2021 | 01/07/2021 | 01/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-----5-10 | TT_Mile | WATER AND POWER SUPPLY FOR SITE REQUIRED FROM CLIENT | 01/07/2021 | 01/07/2021 | 01/07/2021 | 01/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-----2M10 | TT_Mile | CONTACT PERSON FROM CUSTOMER, HRSG, GT, ST ANNOUNCED AND READY ALONG WITH TEAM SETUP | 02/01/2021 | 02/01/2021 | 02/01/2021 | 02/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-----2M15 | TT_Task | PLANT DESIGN YARD AREA | 30/08/2020 | 19/12/2020 | 30/08/2020 | 19/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-----2M00 | TT_Task | 3D MODEL SETUP CLEANING | 01/08/2020 | 14/08/2020 | 01/08/2020 | 14/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-----2M38 | TT_Task | TERMINAL POINT LOCATION / VERIFICATION | 17/01/2021 | 30/01/2021 | 17/01/2021 | 30/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---2M10 | TT_Mile | (A) PROJECT START = FULL ENGINEERING = FULL TEAM SETUP | 01/08/2020 | 01/08/2020 | 01/08/2020 | 01/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMY4M25 | TT_Task | TRANSPORT MODULE 20UMY00Y | 19/03/2022 | 11/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-----2M09 | TT_Task | DELTA DESIGN / VERIFICATION GROUP III | 30/01/2021 | 19/02/2021 | 30/01/2021 | 19/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--L--2-00 | TT_Mile | (M1) DATA / PID FOR L-SYSTEMS | 15/02/2021 | 15/02/2021 | 15/02/2021 | 15/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--P--2-00 | TT_Mile | (M1) DATA / PID FOR P-SYSTEMS | 15/02/2021 | 15/02/2021 | 15/02/2021 | 15/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---2M51 | TT_Task | PIPING ENGINEERING TEAM PROJECT SETUP | 29/08/2020 | 25/09/2020 | 29/08/2020 | 25/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---2M53 | TT_Mile | CONTRACT DOCUMENTS AVAILABLE; PROPOSAL MODELS/DATA/DOCUMENTS AVAILABLE INLC. OFFER MTO / REFERENCE MTO | 01/08/2020 | 01/08/2020 | 01/08/2020 | 01/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---2M54 | TT_Mile | START OF RFQ (WITH MPA) | 24/10/2020 | 24/10/2020 | 24/10/2020 | 24/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---2M60 | TT_Task | PREL. PIPING DESIGN BASIC REPORT (PDBR) | 26/09/2020 | 23/10/2020 | 26/09/2020 | 23/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---2M56 | TT_Task | PLANT DESIGN POWER CORE | 15/08/2020 | 18/09/2020 | 15/08/2020 | 18/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---2M55 | TT_Task | CREATION OF PROJECT EXECUTION PLANS | 22/08/2020 | 18/09/2020 | 22/08/2020 | 18/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-----2M18 | TT_Mile | 30% DESIGN REVIEW (3DR) BUILDING BLOCKS | 24/03/2021 | 24/03/2021 | 24/03/2021 | 24/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-----2M16 | TT_Mile | INPUT FROM GT / ST / GENO / HRSG / BoP / COMPONENTS | 02/01/2021 | 02/01/2021 | 02/01/2021 | 02/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-----2M17 | TT_Task | DELTA DESIGN / VERIFICATION GROUP II | 16/01/2021 | 12/02/2021 | 16/01/2021 | 12/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-----2M11 | TT_Task | MEDIUM LEAD ROUTING ADAPTION | 13/11/2020 | 10/12/2020 | 13/11/2020 | 10/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-----2E66 | TT_Task | PREPARATION OF MTO FOR LONG LEAD PIPING | 15/01/2021 | 11/03/2021 | 15/01/2021 | 11/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---3M30 | TT_Task | PROCUREMENT LONG LEAD ITEMS PART 1 (80%) | 19/03/2021 | 07/09/2021 | 19/03/2021 | 07/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-----2E85 | TT_Mile | CONTRACT INTO FORCE PIPING BUILDING BLOCK / ORDER MTO LONG LEAD ITEMS (80%) VALVES (INCL. CONTRACTUAL MTO) | 01/05/2021 | 01/05/2021 | 01/05/2021 | 01/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---3M31 | TT_Task | PROCUREMENT LONG LEAD ITEMS PART 2 (95%) | 23/04/2021 | 07/09/2021 | 23/04/2021 | 07/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-----2E86 | TT_Mile | ORDER MTO LONG LEAD ITEMS (95%) | 23/04/2021 | 23/04/2021 | 23/04/2021 | 23/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7-15 | TT_Task | ERECTION CABLE TRAYS FOR 20ULY00Y INCL. SCAFOLDING | 14/04/2022 | 11/05/2022 |  |  | 56 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PGB3M81 | TT_FinMile | (RFS) READY FOR SHIPMENT MODULE 20PGB20Y | 16/04/2022 | 16/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PGB3M80 | TT_FinMile | (RFS) READY FOR SHIPMENT MODULE 20PGB10Y | 16/04/2022 | 16/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MB-3B80 | TT_FinMile | (RFS) READY FOR SHIPMENT GT ACCESSORY EQUIPMENT / CCR / IN-LINE COMPONENTS GT-PIPING MB | 29/04/2022 | 29/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MB-3B80 | TT_FinMile | (RFS) READY FOR SHIPMENT GT SUPPORTS 20MB- | 29/04/2022 | 29/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP--MB-3B80 | TT_FinMile | (RFS) READY FOR SHIPMENTGT INSULATION MB- | 23/04/2022 | 23/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAC3B80 | TT_FinMile | (RFS) READY FOR SHIPMENT GEN. CIRCUIT BREAKER 20BAC | 19/06/2022 | 19/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BBT3B80 | TT_FinMile | (RFS) READY FOR SHIPMENT AUX. TRANSFORMER 20BBT | 13/07/2022 | 13/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAA3B80 | TT_FinMile | (RFS) READY FOR SHIPMENT IPB 20BAA | 04/07/2022 | 04/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MBL3B80 | TT_FinMile | (RFS) READY FOR SHIPMENT AIR INTAKE SYSTEM 20MBL | 18/05/2022 | 18/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---2M26 | TT_FinMile | FINAL SHOP DRAWINGS FOR MODULES LOT 3 | 07/12/2021 | 07/12/2021 | 07/12/2021 | 07/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---2M24 | TT_Mile | FINAL SHOP DRAWINGS FOR MODULES LOT 2 | 05/11/2021 | 05/11/2021 | 05/11/2021 | 05/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---2M22 | TT_Mile | SUBMISSION OF OTHER 50% OF FABRICATION DOCUMENTS FOR SHIPMENT LOT 1 | 06/10/2021 | 06/10/2021 | 06/10/2021 | 06/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PGB6M15 | TT_Task | ERECTION MODULE 20PGB10Y (PGB10YE / PGB10YD) | 31/05/2022 | 06/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PGB4M40 | TT_FinMile | (OTD-OS) ON SITE MODULE 20PGB10Y | 14/05/2022 | 14/05/2022 |  |  | 128 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PGB4M22 | TT_FinMile | DELIVERY OF COMPONENTS MODULE_CCW PUMP / EXPANSION TANK | 10/01/2022 | 10/01/2022 |  |  | 456 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PGB4M25 | TT_Task | TRANSPORT MODULE 20PGB10Y | 17/04/2022 | 10/05/2022 |  |  | 32 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-----3M63 | TT_Task | BASIC DESIGN BB STEELWORK LOT 3 | 21/04/2021 | 26/05/2021 | 21/04/2021 | 26/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-----2M44 | TT_Mile | INPUTS FOR DETAIL DESIGN REQUIRED LOT3 | 21/04/2021 | 21/04/2021 | 21/04/2021 | 21/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-----3M62 | TT_Task | BASIC DESIGN BB STEELWORK LOT 2 | 24/03/2021 | 01/06/2021 | 24/03/2021 | 01/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-----2M40 | TT_Mile | INPUTS FOR DETAIL DESIGN REQUIRED LOT 2 | 24/03/2021 | 24/03/2021 | 24/03/2021 | 24/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---3B88 | TT_FinMile | (RFS) READY FOR SHIPMENT GT SPECIAL TOOLS 20MB- | 29/04/2022 | 29/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---3M82 | TT_FinMile | (RFS) READY FOR SHIPMENT FOR SHIPMENT LOT 3 | 19/05/2022 | 19/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---3M81 | TT_FinMile | (RFS) READY FOR SHIPMENT FOR SHIPMENT LOT 2 | 16/04/2022 | 16/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---3M80 | TT_FinMile | (RFS) READY FOR SHIPMENT FOR SHIPMENT LOT 1 | 18/03/2022 | 18/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--ZTB3B80 | TT_FinMile | (RFS) READY FOR SHIPMENT - PIPING / VALVES FOR STEAM BLOWING SYSTEM ZTB | 06/01/2023 | 06/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--ZTA3B80 | TT_FinMile | (RFS) READY FOR SHIPMENT - TEMP. PIPING / VALVES FOR CHEMICAL CLEANING SYSTEM ZTA | 09/01/2023 | 09/01/2023 |  |  | 88 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PDB7B16 | TT_Task | E- AND IC-ERECTION CONDENSATE POLISHING PUMP | 01/10/2022 | 07/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI----P3I21 | TT_Task | PROCUREMENT VALVES | 01/05/2021 | 01/12/2021 | 01/05/2021 | 02/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---4M27 | TT_Task | TRANSPORT FOR SHIPMENT LOT 3 | 20/05/2022 | 12/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---3M14 | TT_Task | 1st SHOP DRAWINGS FOR MODULES LOT 3 | 06/10/2021 | 09/11/2021 | 06/10/2021 | 09/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---2M25 | TT_Mile | FABRICATION DRAWINGS BB STEELWORK FINISHED LOT 3 PART 1 | 06/10/2021 | 06/10/2021 | 06/10/2021 | 06/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---3M15 | TT_Task | REMAINING SHOP DRAWINGS FOR MODULES LOT 3 | 10/11/2021 | 07/12/2021 | 10/11/2021 | 07/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---3M27 | TT_Task | FABRICATION DESIGN BB STEELWORK LOT 3 | 05/08/2021 | 05/10/2021 | 05/08/2021 | 05/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---4M26 | TT_Task | TRANSPORT FOR SHIPMENT LOT 2 | 17/04/2022 | 10/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---3M10 | TT_Task | 1st SHOP DRAWINGS FOR MODULES LOT 2 | 03/09/2021 | 07/10/2021 | 03/09/2021 | 08/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---2M23 | TT_Mile | FABRICATION DRAWINGS BB STEELWORK FINISHED LOT 2 | 03/09/2021 | 03/09/2021 | 03/09/2021 | 03/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---3M11 | TT_Task | REMAINING SHOP DRAWINGS FOR MODULES LOT 2 | 08/10/2021 | 04/11/2021 | 08/10/2021 | 04/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---3M26 | TT_Task | FABRICATION DESIGN BB STEELWORK LOT 2 | 17/06/2021 | 31/08/2021 | 17/06/2021 | 01/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---4M25 | TT_Task | TRANSPORT FOR SHIPMENT LOT 1 | 19/03/2022 | 11/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---3M06 | TT_Task | 1st SHOP DRAWINGS FOR MODULES LOT 1 | 16/08/2021 | 07/09/2021 | 16/08/2021 | 07/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---2M21 | TT_Mile | FABRICATION DRAWINGS BB STEELWORK FINISHED LOT 1 | 01/08/2021 | 01/08/2021 | 01/08/2021 | 01/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---3M07 | TT_Task | REMAINING SHOP DRAWINGS FOR MODULES LOT 1 | 08/09/2021 | 05/10/2021 | 08/09/2021 | 05/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---3M25 | TT_Task | FABRICATION DESIGN BB STEELWORK LOT 1 | 30/05/2021 | 31/07/2021 | 30/05/2021 | 31/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-----3M61 | TT_Task | BASIC DESIGN BB STEELWORK LOT 1 | 27/01/2021 | 10/05/2021 | 27/01/2021 | 10/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-----2M36 | TT_Mile | INPUTS FOR DETAIL DESIGN REQUIRED LOT1 | 27/01/2021 | 27/01/2021 | 27/01/2021 | 27/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMY4M40 | TT_FinMile | (OTD-OS) ON SITE MODULE 20UMY00Y | 11/04/2022 | 11/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--LDK2B75 | TT_Task | TECHNICAL CLARFICIATION / PREP. RFQ CONDENSATE POLISHING PUMP 20LDK | 22/01/2021 | 04/03/2021 | 22/01/2021 | 04/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20LDK3B81 | TT_FinMile | (RFS) READY FOR SHIPMENT CONDENSATE POLISHING PUMP 20LDK | 10/10/2021 | 10/10/2021 | 10/10/2021 | 10/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--PDB2B75 | TT_Task | PREPARATION RFQ DEBRIS FILTER 20PDB | 15/01/2021 | 10/02/2021 | 15/01/2021 | 10/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PDB3B80 | TT_FinMile | (RFS) READY FOR SHIPMENT DEBRIS FILTER 20PDB | 16/12/2021 | 16/12/2021 | 16/12/2021 | 16/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--PDB2B60 | TT_FinMile | (DF) INPUT FOR MS3 DEBRIS FILTER 20PDB | 11/06/2021 | 11/06/2021 | 11/06/2021 | 11/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--PDB2B65 | TT_FinMile | (DF) INPUT FOR M2 DEBRIS FILTER 20PDB | 07/06/2021 | 07/06/2021 | 07/06/2021 | 07/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--LDK2B61 | TT_FinMile | (DF) INPUT FOR MS3 CONDENSATE POLISHING PUMP LDK | 10/05/2021 | 10/05/2021 | 10/05/2021 | 10/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--LDK2B86 | TT_Mile | CONTRACT INTO FORCE CONDENSATE POLISHING PUMP 20LDK | 09/04/2021 | 09/04/2021 | 09/04/2021 | 09/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--LDK2B81 | TT_Task | QUOTATION STAGE CONDENSATE POLISHING PUMP 20LDK | 05/03/2021 | 08/04/2021 | 05/03/2021 | 08/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PDB4B14 | TT_FinMile | (OTD-OS) ARRIVAL AT SKIDDER DEBRIS FILTER 20PDB | 10/01/2022 | 10/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PDB4B25 | TT_Task | TRANSPORT TO SKIDDER DEBRIS FILTER 20PDB | 01/01/2022 | 10/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PDB3B25 | TT_Task | MANUFACTURING / SHOP TEST DEBRIS FILTER 20PDB | 16/06/2021 | 16/12/2021 | 16/06/2021 | 16/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--PDB2B85 | TT_Mile | CONTRACT INTO FORCE DEBRIS FILTER 20PDB | 04/05/2021 | 04/05/2021 | 04/05/2021 | 04/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B48 | TT_Task | ERECTION CRANE WALKWAY 20SMM01/02 20UMC | 19/03/2022 | 16/04/2022 |  |  | 24 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LDK3B31 | TT_Task | MANUFACTURING / SHOP TEST CONDENSATE POLISHING PUMP 20LDK | 09/04/2021 | 12/09/2021 | 09/04/2021 | 12/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--LDK2B66 | TT_FinMile | (DF) INPUT FOR M2 CONDENSATE POLISHING PUMP LDK | 01/06/2021 | 01/06/2021 | 01/06/2021 | 01/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20LDK4B41 | TT_FinMile | (OTD) CONDENSATE POLISHING PUMP AT SKIDDER 20LDK | 10/12/2021 | 10/12/2021 | 10/12/2021 | 10/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20LDK4B26 | TT_Task | TRANSPORT TO SKIDDER CONDENSATE POLISHING PUMP 20LDK | 16/10/2021 | 10/12/2021 | 16/10/2021 | 10/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--LCA2B60 | TT_FinMile | (DF) INPUT FOR MS3 CONDENSATE RECIRC.PUMP LCA51 | 06/05/2021 | 06/05/2021 | 06/05/2021 | 06/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20LCA3B39 | TT_Task | MANUFACTURING / SHOP TEST CONDENSATE RECIRC.PUMP 20LCA51 | 09/04/2021 | 19/10/2021 | 09/04/2021 | 19/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--PDB2B80 | TT_Task | QUOTATION STAGE DEBRIS FILTER 20PDB | 11/02/2021 | 03/05/2021 | 11/02/2021 | 03/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UPY4M40 | TT_FinMile | (OTD-OS) ON SITE MODULE 20UPY00Y | 10/08/2022 | 10/08/2022 |  |  | 24 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UPY4M25 | TT_Task | TRANSPORT MODULE 20UPY00Y | 18/07/2022 | 10/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC6M41 | TT_FinMile | (RFP) READY FOR PIPE CONNECTION PXB PIPERACK 20UMCL1Y | 24/05/2022 | 24/05/2022 |  |  | 904 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--LCA2B65 | TT_FinMile | (DF) INPUT FOR M2 CONDENSATE RECIRC.PUMP LCA51 | 22/05/2021 | 22/05/2021 | 22/05/2021 | 22/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20LCA3B80 | TT_FinMile | (RFS) READY FOR SHIPMENT CONDENSATE RECIRC.PUMP 20LCA51 | 16/11/2021 | 16/11/2021 | 16/11/2021 | 16/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC4M41 | TT_FinMile | (OTD-OS) ON SITE MODULE PxB 20UMCL1Y | 10/05/2022 | 10/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC4M26 | TT_Task | TRANSPORT MODULE PxB 20UMCL1Y | 17/04/2022 | 10/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC6M16 | TT_Task | MECHANICAL ERECTION MODULE PxB 20UMCL1Y | 11/05/2022 | 24/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PGB6M16 | TT_Task | ERECTION MODULE 20PGB20Y | 04/06/2022 | 10/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LCA3M81 | TT_FinMile | (RFS) READY FOR SHIPMENT FOR MODULE 20LCA50Y | 16/04/2022 | 16/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--LCA2B20 | TT_Mile | PROPOSAL PUMP CURVES FOR DESIGN C-V CONDENSATE RECIRC.PUMP LCA51 | 30/04/2021 | 30/04/2021 | 30/04/2021 | 30/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20LCA4B42 | TT_FinMile | (OTD) CONDENSATE RECIRC.PUMP AT SKIDDER 20LCA51 | 10/01/2022 | 10/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--LCA2B75 | TT_Task | CONTRACT REVIEW / PREP. RFQ CONDENSATE RECIRC.PUMP LCA51 | 05/02/2021 | 04/03/2021 | 05/02/2021 | 04/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20LCA4B25 | TT_Task | TRANSPORT TO SKIDDER CONDENSATE RECIRC.PUMP 20LCA51 | 17/11/2021 | 10/01/2022 | 17/11/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--LCA2B85 | TT_Mile | CONTRACT INTO FORCE CONDENSATE RECIRC.PUMP LCA51 | 09/04/2021 | 09/04/2021 | 09/04/2021 | 09/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--LCA2B80 | TT_Task | QUOTATION STAGE CONDENSATE RECIRC.PUMP LCA51 | 05/03/2021 | 08/04/2021 | 05/03/2021 | 08/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PGB4M41 | TT_FinMile | (OTD-OS) ON SITE MODULE 20PGB20Y | 10/05/2022 | 10/05/2022 |  |  | 192 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PGB4M24 | TT_FinMile | DELIVERY OF COMPONENTS MODULE_PGB HEAT EXCHANGER | 07/11/2021 | 07/11/2021 | 07/11/2021 | 07/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PGB4M26 | TT_Task | TRANSPORT MODULE 20PGB20Y | 17/04/2022 | 10/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC6M15 | TT_Task | MECHANICAL ERECTION MODULE 20UMCM1Y | 11/05/2022 | 24/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC6M40 | TT_FinMile | (RFP) READY FOR PIPE CONNECTION MODULE 20UMCM1Y | 24/05/2022 | 24/05/2022 |  |  | 1256 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC4M40 | TT_FinMile | (OTD-OS) ON SITE MODULE 20UMCM1Y | 10/05/2022 | 10/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC4M25 | TT_Task | TRANSPORT MODULE 20UMCM1Y | 17/04/2022 | 10/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LDK4M25 | TT_Task | TRANSPORT MODULE 20LDK00Y | 19/03/2022 | 11/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LDK6M15 | TT_Task | MECHANICAL ERECTION MODULE 20LDK00Y | 30/04/2022 | 02/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LDK3M80 | TT_FinMile | (RFS) READY FOR SHIPMENT MODULE 20LDK00Y | 18/03/2022 | 18/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LCA6M16 | TT_Task | MECHANICAL ERECTION MODULE 20LCA50Y | 19/05/2022 | 25/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LCA4M23 | TT_FinMile | DELIVERY OF COMPONENTS MODULE_CONDENSATE RECIR. PUMP | 10/01/2022 | 10/01/2022 |  |  | 456 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LCA4M41 | TT_FinMile | (OTD-OS) ON SITE MODULE 20LCA50Y | 10/05/2022 | 10/05/2022 |  |  | 64 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LCA4M26 | TT_Task | TRANSPORT MODULE 20LCA50Y | 17/04/2022 | 10/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--PGB2B85 | TT_Mile | CONTRACT INTO FORCE CCW PUMP PGB | 31/03/2021 | 31/03/2021 | 31/03/2021 | 31/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--PGB2B80 | TT_Task | QUOTATION STAGE CCW PUMP PGB | 07/02/2021 | 30/03/2021 | 07/02/2021 | 30/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--PGB2B75 | TT_Task | CONTRACT REVIEW / PREP. RFQ CCW PUMP PGB | 10/01/2021 | 06/02/2021 | 10/01/2021 | 06/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--PGB2B60 | TT_FinMile | (DF) INPUT FOR MS3 CCW PUMP PGB | 30/04/2021 | 30/04/2021 | 30/04/2021 | 30/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PGB4B41 | TT_FinMile | (OTD) CCW PUMP PGB AT SKIDDER 20PGB | 10/01/2022 | 10/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PGB4B25 | TT_Task | TRANSPORT TO SKIDDER CCW PUMP 20PGB (arrival at Skidder no later than 10.01.22) | 17/11/2021 | 10/01/2022 | 17/11/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20PGB3B32 | TT_Task | MANUFACTURING / SHOP TEST CCW PUMP 20PGB | 31/03/2021 | 19/10/2021 | 31/03/2021 | 19/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PGB3B80 | TT_FinMile | (RFS) READY FOR SHIPMENT CCW PUMP 20PGB | 16/11/2021 | 16/11/2021 | 16/11/2021 | 16/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--PGB2B65 | TT_FinMile | (DF) INPUT FOR M2 CCW PUMP PGB | 30/04/2021 | 30/04/2021 | 30/04/2021 | 30/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20LDK4M40 | TT_FinMile | (OTD-OS) ON SITE MODULE 20LDK00Y | 11/04/2022 | 11/04/2022 |  |  | 16 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAW4M26 | TT_Task | TRANSPORT MODULE 20MAW50Y | 19/03/2022 | 11/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAW6M11 | TT_Task | MECHANICAL ERECTION MODULE 20MAW50Y | 07/05/2022 | 09/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAW3M81 | TT_FinMile | (RFS) READY FOR SHIPMENT MODULE 20MAW50Y | 18/03/2022 | 18/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAW4M41 | TT_FinMile | (OTD-OS) ON SITE MODULE 20MAW50Y | 11/04/2022 | 11/04/2022 |  |  | 200 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--LAC2B80 | TT_Task | QUOTATION STAGE FEEDWATER PUMP 20LAC | 10/02/2021 | 08/04/2021 | 10/02/2021 | 08/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20LAC3B30 | TT_Task | DETAIL DESIGN / MANUFACTURING / SHOP TEST FEEDWATER PUMP 20LAC | 09/04/2021 | 18/03/2022 | 09/04/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--LAC2B20 | TT_Mile | CONFIRMED PUMP CURVES FEEDWATER PUMP 20LAC | 14/05/2021 | 14/05/2021 | 14/05/2021 | 14/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--LAC2B60 | TT_FinMile | (DF) INPUT FOR MS3 FEEDWATER PUMP 20LAC | 04/05/2021 | 04/05/2021 | 04/05/2021 | 04/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--LAC2B85 | TT_Mile | CONTRACT INTO FORCE FEEDWATER PUMP 20LAC | 09/04/2021 | 09/04/2021 | 09/04/2021 | 09/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20LAC4B40 | TT_FinMile | (OTD-OS) ON SITE FEEDWATER PUMP SKID 20LAC | 10/06/2022 | 10/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--LAC2B75 | TT_Task | CONTRACT REVIEW / PREP. RFQ FEEDWATER PUMP 20LAC | 23/12/2020 | 09/02/2021 | 23/12/2020 | 09/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20LAC4B26 | TT_Task | TRANSPORT FEEDWATER PUMP SKID 20LAC | 16/04/2022 | 10/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--LAC2B65 | TT_FinMile | (DF) INPUT FOR M2 FEEDWATER PUMP 20LAC | 11/05/2021 | 11/05/2021 | 11/05/2021 | 11/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20LAC3B80 | TT_FinMile | (RFS) READY FOR SHIPMENT FEEDWATER PUMP SKID 20LAC | 15/04/2022 | 15/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAW6M10 | TT_Task | MECHANICAL ERECTION MODULE 20MAW10Y | 23/04/2022 | 25/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAW3M80 | TT_FinMile | (RFS) READY FOR SHIPMENT MODULE 20MAW10Y | 18/03/2022 | 18/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAW4M40 | TT_FinMile | (OTD-OS) ON SITE MODULE 20MAW10Y | 11/04/2022 | 11/04/2022 |  |  | 88 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAW4M25 | TT_Task | TRANSPORT MODULE 20MAW10Y | 19/03/2022 | 11/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--PGB2D85 | TT_Mile | CONTRACT INTO FORCE CCW EXPANSION TANK PGB | 07/08/2021 | 07/08/2021 | 07/08/2021 | 07/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--PGB2D61 | TT_FinMile | (DF) INPUT FOR MS3 CCW EXPANSION TANK PGB | 07/08/2021 | 07/08/2021 | 07/08/2021 | 07/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--PGB2D80 | TT_Task | QUOTATION STAGE CCW EXPANSION TANK PGB | 22/04/2021 | 06/08/2021 | 22/04/2021 | 06/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--PGB2D75 | TT_Task | CONTRACT REVIEW / PREP. RFQ CCW EXPANSION TANK PGB | 18/03/2021 | 21/04/2021 | 18/03/2021 | 21/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PGB3D80 | TT_FinMile | (RFS) READY FOR SHIPMENT CCW EXPANSION TANK 20PGB | 15/11/2021 | 15/11/2021 | 15/11/2021 | 15/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--PGB2D65 | TT_FinMile | (DF) INPUT FOR M2 CCW EXPANSION TANK PGB | 08/06/2021 | 08/06/2021 | 08/06/2021 | 08/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PGB4D42 | TT_FinMile | (OTD) CCW EXPANSION TANK PGB AT SKIDDER 20PGB | 10/01/2022 | 10/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PGB4D25 | TT_Task | TRANSPORT TO SKIDDER CCW EXPANSION TANK 20PGB | 16/11/2021 | 10/01/2022 | 16/11/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20PGB3D33 | TT_Task | PROCURMENT / PRE-FABRICATION CCW EXPANSION TANK 20PGB | 14/08/2021 | 16/10/2021 | 14/08/2021 | 16/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MAG4M40 | TT_FinMile | (OTD-OS) ON SITE MODULE 20MAG50Y | 11/04/2022 | 11/04/2022 |  |  | 112 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAG4M25 | TT_Task | TRANSPORT MODULE 20MAG50Y | 19/03/2022 | 11/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAG6M10 | TT_Task | MECHANICAL ERECTION MODULE 20MAG50Y | 26/04/2022 | 28/04/2022 |  |  | 168 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PGB3C80 | TT_FinMile | (RFS) READY FOR SHIPMENT HEAT EXCHANGER 20PGB | 12/09/2021 | 12/09/2021 | 12/09/2021 | 12/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--PGB2C65 | TT_FinMile | (DF) INPUT FOR M2 HEAT EXCHANGER PGB | 08/06/2021 | 08/06/2021 | 08/06/2021 | 08/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--PGB2C62 | TT_FinMile | (DF) INPUT FOR MS3 HEAT EXCHANGER PGB | 26/05/2021 | 26/05/2021 | 26/05/2021 | 26/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--PGB2C85 | TT_Mile | CONTRACT INTO FORCE HEAT EXCHANGER PGB | 12/04/2021 | 12/04/2021 | 12/04/2021 | 12/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--PGB2C80 | TT_Task | QUOTATION STAGE HEAT EXCHANGER PGB | 15/02/2021 | 11/04/2021 | 15/02/2021 | 11/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--PGB2C75 | TT_Task | CONTRACT REVIEW / PREP. HEAT EXCHANGER PGB | 18/01/2021 | 14/02/2021 | 18/01/2021 | 14/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PGB4C44 | TT_FinMile | (OTD) HEAT EXCHANGER PGB AT SKIDDER | 07/11/2021 | 07/11/2021 | 07/11/2021 | 07/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PGB4C25 | TT_Task | TRANSPORT TO SKIDDER HEAT EXCHANGER 20PGB | 13/09/2021 | 07/11/2021 | 13/09/2021 | 07/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PGB3C41 | TT_Task | PROCURMENT / PRE-FABRICATION HEAT EXCHANGER 20PGB | 26/04/2021 | 15/08/2021 | 26/04/2021 | 15/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MAL6M10 | TT_Task | MECHANICAL ERECTION MODULE 20MAL00YC | 20/04/2022 | 22/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAL3M80 | TT_FinMile | (RFS) READY FOR SHIPMENT MODULE 20MAL00YC | 18/03/2022 | 18/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAL4M40 | TT_FinMile | (OTD-OS) ON SITE MODULE 20MAL00YC | 11/04/2022 | 11/04/2022 |  |  | 64 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAL4M25 | TT_Task | TRANSPORT MODULE 20MAL00YC | 19/03/2022 | 11/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UPY6M10 | TT_Task | MECHANICAL ERECTION MODULE 20UPY00Y | 14/08/2022 | 20/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMY6M16 | TT_Task | ERECTION RACK TOWER UMY00YG12/13 (2 Towers) | 18/04/2022 | 23/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMY6M18 | TT_Task | ERECTION RACK TOWER UMY00YE (2 Towers) E-12,43 | 12/04/2022 | 17/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMY6M06 | TT_Task | PRE-ASSEMBLY RACK TOWER ULY (2 Towers) | 27/04/2022 | 01/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMY6M07 | TT_Task | PRE-ASSEMBLY RACK TOWER UMY00YK (2 Towers) | 12/04/2022 | 16/04/2022 |  |  | 56 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMY6M05 | TT_Task | PRE-ASSEMBLY RACK TOWER UMY00YG (2 Towers) | 07/04/2022 | 11/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMY6M70 | TT_Task | PRESSURE TEST OF PIPING SYSTEMS AND HRSG (ON CONNECTED MODULES) | 18/03/2023 | 14/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LAC4M40 | TT_FinMile | (OTD-OS) ON SITE MODULE 20LAC10Y (w/o Pump) | 10/05/2022 | 10/05/2022 |  |  | 64 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LAC4M25 | TT_Task | TRANSPORT MODULE 20LAC10Y (w/o Pump) | 17/04/2022 | 10/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LAC6M15 | TT_Task | MECHANICAL ERECTION MODULE 20LAC10Y | 19/05/2022 | 15/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMY6M10 | TT_Task | PLACING AND ALIGNMENT OF MODULE - TRANU U1 ULY | 19/05/2022 | 19/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMY6M12 | TT_Task | PLACING AND ALIGNMENT OF MODULE - UMY00E12/43 | 08/05/2022 | 09/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMY6M11 | TT_Task | PLACING AND ALIGNMENT OF MODULE - UMY00G12/43 | 10/05/2022 | 11/05/2022 |  |  | 56 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMY6M08 | TT_Task | PRE-ASSEMBLY RACK TOWER UMY00YE (2 Towers) | 01/04/2022 | 05/04/2022 |  |  | 8 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMY6M15 | TT_Task | ERECTION RACK TOWER ULY (2 Towers) | 02/05/2022 | 07/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMY6M17 | TT_Task | ERECTION RACK TOWER UMY00YK12 (2 Towers) A,D,K | 24/04/2022 | 29/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20ULY4M40 | TT_FinMile | (OTD-OS) ON SITE MODULE 20ULY00Y | 11/04/2022 | 11/04/2022 |  |  | 16 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20ULY4M25 | TT_Task | TRANSPORT MODULE 20ULY00Y | 19/03/2022 | 11/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20ULY7M16 | TT_Task | ELECTRICAL AND IC ERECTION MODULE 20ULY00Y | 29/05/2022 | 04/06/2022 |  |  | 2512 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---3M28 | TT_Task | PROCUREMENT INSULATION AND TRACE HEATING | 24/07/2021 | 17/12/2021 | 24/07/2021 | 18/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---3M20 | TT_Task | PROCUREMENT CABLE TRAYS, IC | 24/07/2021 | 22/10/2021 | 24/07/2021 | 22/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-----2H85 | TT_Mile | ORDER MTO MEDIUM LEAD ITEMS 3 (100%) | 24/07/2021 | 24/07/2021 | 24/07/2021 | 24/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-----3H34 | TT_Task | PROCUREMENT MEDIUM LEAD ITEMS PART 3 (100%) | 24/07/2021 | 30/09/2021 | 24/07/2021 | 01/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---3A27 | TT_Task | FABRICATION LONG LEAD SUPPORTS FOR SHIPMENT LOT 1 AND LOT 2 | 01/05/2021 | 03/09/2021 | 01/05/2021 | 03/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---4A25 | TT_Task | TRANSPORT LONG LEAD SUPPORTS FOR SHIPMENT LOT 1 AND LOT 2 | 04/09/2021 | 22/10/2021 | 04/09/2021 | 22/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---3A80 | TT_FinMile | (RFS) READY FOR SHIPMENT LONG LEAD SUPPORTS FOR SHIPMENT LOT 1 AND LOT 2 | 03/09/2021 | 03/09/2021 | 03/09/2021 | 03/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-----2F71 | TT_Task | PREPARATION ORDER MTO MEDIUM LEAD ITEMS (80%) | 15/01/2021 | 30/04/2021 | 15/01/2021 | 30/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---3G26 | TT_Task | PROCUREMENT MEDIUM LEAD ITEMS 1 (80%) | 01/05/2021 | 07/09/2021 | 01/05/2021 | 07/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-----2F85 | TT_Mile | ORDER MTO MEDIUM LEAD ITEMS 1 (80%) | 01/05/2021 | 01/05/2021 | 01/05/2021 | 01/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---3G25 | TT_Task | PROCUREMENT STEEL PROFILES (75%) | 01/05/2021 | 30/07/2021 | 01/05/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI----P3I33 | TT_Task | PROCUREMENT CONTROL VALVES | 08/04/2021 | 07/10/2021 | 08/04/2021 | 08/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7-145 | TT_Task | ERECTION CABLE TRAYS FOR 20URA AREA PART 1 | 23/02/2023 | 22/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-3E84 | TT_Task | MANUFACTURING VALVES &gt; 2 HRSG20 | 28/01/2021 | 19/01/2022 | 28/01/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--PAB2-24 | TT_Mile | RELEASE BASIC DESIGN TO DETAIL DESIGN CONCRETE DESIGNER / SUPPLIER PAB | 15/03/2021 | 15/03/2021 | 15/03/2021 | 15/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--PAB2-23 | TT_Task | FINALIZE BASIC DESIGN PAB | 15/02/2021 | 14/03/2021 | 15/02/2021 | 14/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--PAB2-22 | TT_Task | 3D MODEL PAB | 02/02/2021 | 15/02/2021 | 02/02/2021 | 15/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--PAB2-16 | TT_Mile | BASIC DESIGN RELEASE PAB | 09/02/2021 | 09/02/2021 | 09/02/2021 | 09/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--PAB2-15 | TT_Task | BASIC DESIGN OF PIPING / ROUTING PAB | 15/01/2021 | 08/02/2021 | 15/01/2021 | 08/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--SG-2-27 | TT_Mile | RELEASE FIRE FIGHTING RING MAIN - BASIC DESIGN | 12/05/2021 | 12/05/2021 | 12/05/2021 | 12/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--SG-2-26 | TT_Task | FINALIZE RING MAIN BASIC DESIGN | 14/04/2021 | 11/05/2021 | 14/04/2021 | 11/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--SG-2-25 | TT_Task | UPDATE RING MAIN DESIGN | 31/03/2021 | 13/04/2021 | 31/03/2021 | 13/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--SG-2-23 | TT_Mile | MODELLING COMPLETE | 19/02/2021 | 19/02/2021 | 19/02/2021 | 19/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--SG-2-22 | TT_Task | PLANNING 3D MODELLING OF F/F RING MAIN OUTSIDE BUILDING | 29/01/2021 | 18/02/2021 | 29/01/2021 | 18/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--SG-2-21 | TT_Task | PID, FINALIZE RING MAIN CONCEPT | 15/01/2021 | 04/02/2021 | 15/01/2021 | 04/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20HB-3C91 | TT_Task | MANUFACTURING SECONDARY STEEL STRUCTURE HRSG20_Last Part | 16/07/2021 | 31/01/2022 | 16/07/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI-UZA2-10 | TT_Task | ROAD DESIGN STRUCTURAL FINAL HYDRAULIC CALCULATIONS | 25/01/2021 | 21/02/2021 | 25/01/2021 | 21/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMY4M10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION MODULE 20UMY00Y | 19/02/2022 | 18/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMY3M70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) MODULE 20UMY00Y | 19/02/2022 | 19/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMY3M80 | TT_FinMile | (RFS) READY FOR SHIPMENT MODULE 20UMY00Y | 18/03/2022 | 18/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LCA4M11 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION MODULE 20LCA50Y | 20/03/2022 | 16/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LCA3M71 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) MODULE 20LCA50Y | 20/03/2022 | 20/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LAC4B10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION FEEDWATER PUMP SKID 20LAC | 19/03/2022 | 15/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LAC3B70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) FEEDWATER PUMP SKID 20LAC | 18/03/2022 | 18/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LAC4M10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION MODULE 20LAC10Y (w/o Pump) | 20/03/2022 | 16/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LAC3M70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) MODULE 20LAC10Y (w/o Pump) | 20/03/2022 | 20/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LAC3M80 | TT_FinMile | (RFS) READY FOR SHIPMENT FOR MODULE 20LAC10Y (w/o Pump) | 16/04/2022 | 16/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-4B15 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION VALVES &gt; 2 HRSG20 | 20/01/2022 | 16/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-3B75 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) VALVES &gt; 2 HRSG20 | 19/01/2022 | 19/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-4B12 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION PIPING HRSG20_1st Part (LB CARBON STEEL) | 10/02/2022 | 09/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-3B72 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) PIPING HRSG20_1st Part (LB CARBON STEEL) | 10/02/2022 | 10/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA4B11 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION ELECTRICAL MODULES 20UBA7110/20/30 (TO SITE) | 31/03/2022 | 27/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA3B71 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) ELECTRICAL MODULES 20UBA7110/20/30 | 31/03/2022 | 31/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC4M11 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION MODULE PxB 20UMCL1Y | 20/03/2022 | 16/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC3M71 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) MODULE PxB 20UMCL1Y | 20/03/2022 | 20/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC3M81 | TT_FinMile | (RFS) READY FOR SHIPMENT MODULE PxB 20UMCL1Y | 16/04/2022 | 16/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC4M10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION MODULE 20UMCM1Y | 20/03/2022 | 16/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC3M70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) MODULE 20UMCM1Y | 20/03/2022 | 20/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAW4M11 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION MODULE 20MAW50Y | 19/02/2022 | 18/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAW3M71 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) MODULE 20MAW50Y | 19/02/2022 | 19/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC3M80 | TT_FinMile | (RFS) READY FOR SHIPMENT MODULE 20UMCM1Y | 16/04/2022 | 16/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBL4-25 | TT_Task | TRANSPORT AIR INTAKE SYSTEM AIR INTAKE SYSTEM 20MBL- Lower Cone | 19/05/2022 | 15/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBL6-06 | TT_Task | PRE-ASSEMBLY GT AIR INTAKE MBL LOWER PART INNER CONE BEFORE GT 20 | 16/06/2022 | 03/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MAG3D70 | TT_Mile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) CONDENSER FOUNDATION PARTS | 10/06/2021 | 10/06/2021 | 10/06/2021 | 10/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20LAC6B18 | TT_Task | LIGHTING AND SMALL POWER INSIDE NOISE ENCLOSURE FEEDWATER PUMPS 20LAC | 01/09/2022 | 21/09/2022 |  |  | 1640 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7-60 | TT_Task | ERECTION CABLE TRAYS BELOW ELECTRICAL MODULES 20UBA1110/20 | 11/10/2022 | 24/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LDK6B17 | TT_Task | ELECTRICAL ERECTION CONDENSATE POLISHING PLANT 20LD | 20/10/2022 | 02/11/2022 |  |  | 784 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZL8B26 | TT_Task | COMMISSIONING HIGH BAY LIGHTING INSIDE 20UMC | 11/04/2023 | 17/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-6E29 | TT_Task | ERECTION INLET DUCT HRSG20 | 21/05/2022 | 10/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-UZA2-5 | TT_Task | CONCEPT COMPOSITE DRAWING RING ROAD INCL. UNDERGROUND (U/G) DRAINAGE | 15/01/2021 | 28/01/2021 | 15/01/2021 | 28/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20CJF4B10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION ELECTRICAL / IC EQUIPMENT HRSG20 | 22/03/2022 | 18/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20CJF3B70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) ELECTRICAL / IC EQUIPMENT HRSG20 | 21/03/2022 | 21/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-4B11 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION DRUMS HRSG20 | 11/01/2022 | 07/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-3B71 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) DRUMS HRSG20 | 10/01/2022 | 10/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-4B10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION HEATING SURFACES HRSG20 MODULE 2-6 | 18/02/2022 | 12/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-3B70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) HEATING SURFACES HRSG20 MODULE 2-6 | 18/02/2022 | 18/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-4B13 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION OUTLET DUCT HRSG 20 | 11/01/2022 | 07/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-3B73 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) OUTLET DUCT HRSG 20 | 10/01/2022 | 10/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-4B14 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION STACK HRSG 20 | 11/01/2022 | 07/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-3B74 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) STACK HRSG 20 | 10/01/2022 | 10/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-4B15 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION INLET DUCT HRSG20 | 06/12/2021 | 02/01/2022 | 06/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20HB-3B75 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) INLET DUCT HRSG20 | 05/12/2021 | 05/12/2021 | 05/12/2021 | 05/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20HB-4B12 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION SECONDARY STEEL STRUCTURE HRSG20_Last Part | 01/02/2022 | 28/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-3B72 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) SECONDARY STEEL STRUCTURE HRSG20_Last Part | 31/01/2022 | 31/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-4B11 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION SECONDARY STEEL STRUCTURE HRSG20_1st Part incl. Drum Supports | 31/12/2021 | 27/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-3B71 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) SECONDARY STEEL STRUCTURE HRSG20_1st Part incl. Drum Supports | 30/12/2021 | 30/12/2021 | 30/12/2021 | 30/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20HB-4B10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION MAIN STEEL STRUCTURE HRSG20 | 11/11/2021 | 29/12/2021 | 11/11/2021 | 29/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20HB-3B70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) MAIN STEEL STRUCTURE HRSG20 | 10/11/2021 | 10/11/2021 | 10/11/2021 | 10/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20HSJ4B10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION - SCR SKID HSJ/HSK | 10/05/2022 | 06/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HSJ3B70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) - SCR SKID HSJ/HSK | 09/05/2022 | 09/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20QC-4B10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION DOSING CONTAINER 20QC | 22/05/2022 | 18/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20QC-3B70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) DOSING CONTAINER 20QC | 21/05/2022 | 21/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAT4B10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION MAIN TRANSFORMERS 20BAT | 16/06/2022 | 13/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAT3B70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) MAIN TRANSFORMERS 20BAT | 15/06/2022 | 15/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA4B10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION ELECTRICAL MODULES 20UBA7610/20 (TO SITE) | 04/04/2022 | 01/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA3B70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) ELECTRICAL MODULES 20UBA7610/20 | 04/04/2022 | 04/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PGB4M11 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION MODULE 20PGB20Y | 20/03/2022 | 16/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PGB3M71 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) MODULE 20PGB20Y | 20/03/2022 | 20/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PGB4B10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION CCW PUMP 20PGB | 20/10/2021 | 16/11/2021 | 20/10/2021 | 16/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PGB3B70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) CCW PUMP 20PGB | 19/10/2021 | 19/10/2021 | 19/10/2021 | 19/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PGB4D10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION CCW EXPANSION TANK 20PGB | 17/10/2021 | 14/11/2021 | 17/10/2021 | 14/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PGB3D70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) CCW EXPANSION TANK 20PGB | 16/10/2021 | 16/10/2021 | 16/10/2021 | 16/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20LDK4B10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION CONDENSATE POLISHING PLANT 20LD | 29/04/2022 | 26/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LDK3B70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) CONDENSATE POLISHING PLANT 20LD | 28/04/2022 | 28/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SAM4B10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION DUCT FOR HVAC SYSTEM UMC 20SA | 24/06/2022 | 21/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SAM3B70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) DUCT FOR HVAC SYSTEM UMC 20SA | 23/06/2022 | 23/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MB-4-10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION GAS TURBINE 20MB- | 02/04/2022 | 29/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MB-3-70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) GAS TURBINE 20MB- | 01/04/2022 | 01/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MB-4-11 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION - GT INTERCONNECTING PIPING 20MB- | 14/05/2022 | 10/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MB-3-71 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) GT INTERCONNECTING PIPING 20MB- | 13/05/2022 | 13/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--EK-4-10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION GAS FINAL FILTER/ PREHEATER 20EKG | 20/07/2022 | 16/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--EK-3-70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) GAS FINAL FILTER/ PREHEATER 20EKG | 19/07/2022 | 19/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--C--4-10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION BOP IC FIELD DEVICES | 16/03/2022 | 12/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--C--3-70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) BOP IC FIELD DEVICES | 15/03/2022 | 15/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--CP-4-10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION BOP IC FIELD CABINETS | 21/05/2022 | 17/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--CP-3-70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) BOP IC FIELD CABINETS | 20/05/2022 | 20/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--UB-2-21 | TT_Task | BASIC DESIGN PLANT LAYOUT TRANSFORMER AREA | 26/02/2021 | 07/04/2021 | 26/02/2021 | 07/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UB-2-35 | TT_FinMile | (C) BASIC DESIGN PLANT LAYOUT DWGS (UE) TRANSFORMER AREA AVAILABLE | 07/04/2021 | 07/04/2021 | 07/04/2021 | 07/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UB-2E40 | TT_FinMile | (MS2) DESIGN LOAD DATA, DIMENSIONS TRANSFORMER AREA AVAILABLE | 26/02/2021 | 26/02/2021 | 26/02/2021 | 26/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UEN2-40 | TT_FinMile | (MS2) DESIGN LOAD DATA, DIMENSIONS FUEL GAS AREA AVAILABLE | 20/03/2021 | 20/03/2021 | 20/03/2021 | 20/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PGB4C10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION HEAT EXCHANGER 20PGB | 16/08/2021 | 12/09/2021 | 16/08/2021 | 12/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PGB3C70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) HEAT EXCHANGER 20PGB | 15/08/2021 | 15/08/2021 | 15/08/2021 | 15/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PCB4B10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION SERVICE COOLING WATER BOOSTER PUMP 20PCB | 20/10/2021 | 16/11/2021 | 20/10/2021 | 16/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PCB3B70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) SERVICE COOLING WATER BOOSTER PUMP 20PCB | 19/10/2021 | 19/10/2021 | 19/10/2021 | 19/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20LDK4B11 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION CONDENSATE POLISHING PUMP 20LDK | 13/09/2021 | 10/10/2021 | 13/09/2021 | 10/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20LDK3B71 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) CONDENSATE POLISHING PUMP 20LDK | 12/09/2021 | 12/09/2021 | 12/09/2021 | 12/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20SMM4-10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION CRANE 20SMM01/02/03 FOR 20UMC | 13/01/2022 | 02/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SMM3-70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) CRANE 20SMM01/02/03 FOR 20UMC | 12/01/2022 | 12/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBP4A40 | TT_FinMile | (OTD-OS) ON SITE GT FUEL GAS STRAINER SKID MBP | 23/07/2022 | 23/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBX4-25 | TT_Task | TRANSPORT MBX INSTRUMENT AIR SKID TANK | 30/04/2022 | 23/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBX4-12 | TT_Task | ERECTION MBX INSTRUMENT AIR SKID TANK | 25/08/2022 | 14/09/2022 |  |  | 1792 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBP4-27 | TT_Task | TRANSPORT GT FUEL GAS STRAINER SKID MBP | 30/04/2022 | 23/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBP6-11 | TT_Task | ERECTION FUEL GAS STRAINER SKID MBP | 25/08/2022 | 14/09/2022 |  |  | 864 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MPB6E82 | TT_Task | ERECTION OF ENCLOSURE 20MPB | 06/10/2022 | 23/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MPB4-26 | TT_Task | TRANSPORT ENCLOSURE 20MPB | 13/07/2022 | 05/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URD5-46 | TT_Task | BACKFILLING 20URD | 29/03/2022 | 04/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-06 | TT_Task | WORK PREPARATION, EXCAVATION 20URD | 03/09/2021 | 10/10/2021 | 03/09/2021 | 10/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-51 | TT_Task | CONSTRUCTION ROOF CHANNEL/WALLS PART 2 20URA | 11/07/2022 | 18/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-75 | TT_Task | PAB BACKFILLING (APPROX. UP TO PIPE AXISOR PIPE CROWN LEVEL) | 05/09/2021 | 30/10/2021 | 05/09/2021 | 30/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-80 | TT_Mile | READY FOR FIRST BACK FILLING PAB-PIPES OUTSIDE UMC - URD | 05/09/2021 | 05/09/2021 | 05/09/2021 | 05/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MKA9-41 | TT_Task | SYSTEM CHECKS 20MBA | 29/06/2023 | 30/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-6-20 | TT_Task | PREPARATION PRESSURE TEST HRSG20 | 25/02/2023 | 17/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LCL8B10 | TT_FinMile | (TOP-20LCL) BOILER BLOWDOWN SYSTEM | 14/04/2023 | 14/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LCA7A15 | TT_Task | ELECTRICAL ERECTION / VALVES CONDENSATE SYSTEM 20LCA | 15/02/2023 | 21/02/2023 |  |  | 56 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA8-60 | TT_FinMile | (TOP-20UBA1) POWER CONTROL CENTER (ELECTRICAL MODULES) 20UBA1110/20 | 10/04/2023 | 10/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA7L15 | TT_Task | INSTALLATION ELECTRICAL MODULES 20UBA1110/20 | 21/11/2022 | 30/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK7L25 | TT_Task | CABLING GT LATS GT20 | 18/12/2022 | 25/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--UBF2B60 | TT_FinMile | (MS3) STEEL STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UBE/UBF | 05/06/2021 | 05/06/2021 | 05/06/2021 | 05/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--HA-2-76 | TT_FinMile | PROCESS DOCUMENTS FOR RFQ HRSG (App.20.2 - 20.6) | 04/09/2020 | 04/09/2020 | 04/09/2020 | 04/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MB-9-02 | TT_Mile | START HOT COMMISSIONING GT20 | 01/07/2023 | 01/07/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20EKG6H15 | TT_Task | ERECTION, NDT, PT (PT PIGGING) PIPES / VALVES 20EKG70 (20UEN - GT FUEL GAS PURGE SKID) | 08/01/2023 | 11/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--5552-62 | TT_Mile | LIST OF ALL ROOM NUMBERS AVAILABLE | 02/05/2021 | 02/05/2021 | 02/05/2021 | 02/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BTA2-80 | TT_Task | QUOTATION STAGE BATTERIES RACKS BTA | 12/08/2021 | 17/11/2021 | 12/08/2021 | 17/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BTA2-85 | TT_Mile | CONTRACT INTO FORCE BATTERIES RACKS BTA | 18/11/2021 | 18/11/2021 | 18/11/2021 | 18/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BTA2-75 | TT_Mile | RFQ BATTERIES RACKS BTA | 12/08/2021 | 12/08/2021 | 12/08/2021 | 12/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BUK2-75 | TT_Mile | RFQ INVERTER, CONVERTER, BATTERY CHARGER BRU/BTL | 19/08/2021 | 19/08/2021 | 19/08/2021 | 19/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MKA6-63 | TT_Mile | GENERATOR READY FOR PRE-ASSEMBLING BAA BUSDUCT | 09/09/2022 | 09/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAG6-50 | TT_Task | FITTING OF CONDENSER TO LP TURBINE MAG20 | 25/08/2022 | 07/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAG6-59 | TT_Task | INSULATION CONDENSER MAG20 | 02/10/2022 | 12/11/2022 |  |  | 1248 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20ULA5-45 | TT_Mile | (RFE) FOUNDATION 20ULA | 15/01/2022 | 15/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAW5A15 | TT_Task | ERECTION LIGHTNING PROTECTION 20UHA | 30/09/2022 | 27/10/2022 |  |  | 784 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAW5-15 | TT_Task | ERECTION LIGHTNING PROTECTION 20UBE / UBF | 24/09/2022 | 04/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAB8-05 | TT_FinMile | (TOP-20PAB) CIRCULATING COOLING WATER SYSTEM | 14/04/2023 | 14/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20CFE8-13 | TT_FinMile | (TOP-20CFE) CONTINUOUS EMISSION MONITORING SYSTEM | 15/06/2023 | 15/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PCB6M40 | TT_FinMile | (RFP) READY FOR PIPE CONNECTION SERVICE COOLING WATER EXTRACTION PUMP PCB | 17/06/2022 | 17/06/2022 |  |  | 456 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK7A26 | TT_Task | CABLING LV /MV CABLES GT INTERNAL / TO AUXILIARIES 20UMC | 13/10/2022 | 06/12/2022 |  |  | 56 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--2222-26 | TT_FinMile | REVISED OPERATING MANUAL (BHB) WITH REDMARKS | 31/12/2023 | 31/12/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--UMX2-70 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE UMX-To be deleted | 27/07/2021 | 09/09/2021 | 27/07/2021 | 09/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMX2-60 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE UMX-Deleted | 30/06/2021 | 30/06/2021 | 30/06/2021 | 30/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMX2-50 | TT_Task | PREPARATION FOUNDATION GROUNDING DWGS UMX-To be deleted | 27/08/2021 | 09/09/2021 | 27/08/2021 | 09/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--BBA2-75 | TT_Mile | RFQ MV SWITCHGEAR 20/90BBA/BBB | 01/05/2021 | 01/05/2021 | 01/05/2021 | 01/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--BBA2-85 | TT_Mile | CONTRACT INTO FORCE MV SWITCHGEAR 20/90BBA/BBB | 14/08/2021 | 14/08/2021 | 14/08/2021 | 14/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAC4B25 | TT_Task | TRANSPORT CIRC. CW PUMP 20PAC | 01/05/2022 | 30/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--GM-2B85 | TT_Mile | CONTRACT INTO FORCE SUMP PUMP GM | 14/10/2021 | 14/10/2021 | 14/10/2021 | 14/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MB-6-40 | TT_FinMile | (RFP) READY FOR PIPE CONNECTION GT AUXILIARIES 20MB- | 31/08/2022 | 31/08/2022 |  |  | 360 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5A10 | TT_Mile | (H) START PLACING FORMWORK TURBOSET FOUNDATION 20UMC | 26/08/2021 | 26/08/2021 | 26/08/2021 | 26/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7-125 | TT_Task | ERECTION CABLE TRAYS HRSG20 | 19/05/2022 | 15/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZL8B25 | TT_Task | COMMISSIONING LIGHTING/SMALL POWER INSIDE 20UMC | 18/04/2023 | 24/04/2023 |  |  | 408 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZL8-10 | TT_FinMile | (TOP-20BZL-01) LIGHTING / SMALL POWER 20UMC | 10/04/2023 | 10/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-100 | TT_Task | PRESSURE TEST 20PAB20-PIPES OUTSIDE | 19/12/2021 | 07/01/2022 | 19/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--SGA3A80 | TT_FinMile | (RFS) READY FOR SHIPMENT FIRE FIGHTING RING MAIN SGA | 05/05/2022 | 05/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--GM-2B80 | TT_Task | QUOTATION STAGE SUMP PUMP GM | 15/05/2021 | 13/10/2021 | 15/05/2021 | 13/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MB-7A15 | TT_Task | ELECTRICAL ERECTION FOR PIPE CLEANING SYSTEM (GT20) | 20/10/2022 | 02/11/2022 |  |  | 1032 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMY5-10 | TT_Mile | (H) START PLACING FORMWORK PIPE BRIDGE 20ULY/UMY | 30/11/2021 | 30/11/2021 | 30/11/2021 | 30/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20SGY7-15 | TT_Task | ERECTION FIRE DETECTION IN 20UMC | 27/05/2022 | 07/07/2022 |  |  | 824 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMY5-45 | TT_FinMile | (RFE) FOUNDATION PIPE BRIDGE 20ULY/UMY | 08/02/2022 | 08/02/2022 |  |  | 40 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBA8-10 | TT_FinMile | (TOP-20MBA) GAS TURBINE SYSTEM | 26/04/2023 | 26/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEN2-90 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE 01UEN | 22/08/2021 | 12/12/2021 | 22/08/2021 | 12/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--1102-20 | TT_Mile | PRELIMINARY OM DOCUMENTATION 20BAA | 30/08/2022 | 30/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MB-6-10 | TT_Mile | PLACING GT20 | 04/08/2022 | 04/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20XKA2-75 | TT_Mile | RFQ EMERGENCY DIESEL GEN.SET XKA | 01/09/2021 | 01/09/2021 | 01/09/2021 | 01/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20XKA2-80 | TT_Task | QUOTATION STAGE EMERGENCY DIESEL GEN.SET XKA | 01/09/2021 | 16/12/2021 | 01/09/2021 | 16/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--BAC2-15 | TT_Task | BASIC DESIGN / SPECIFICATION GEN. CIRCUIT BREAKER BAC | 29/01/2021 | 06/05/2021 | 29/01/2021 | 06/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UBA2-50 | TT_Task | PREPARATION FOUNDATION GROUNDING DWGS UBA7910/7920 | 09/08/2021 | 22/08/2021 | 09/08/2021 | 22/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20GHD8A50 | TT_Mile | SERVICE WATER AVAILABLE (ES AND SC) GHD | 05/05/2023 | 05/05/2023 |  |  | 64 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20GKB8H25 | TT_Task | COLD COMMISSIONING DRINKING WATER DISTRIBUTION SYSTEM GKB | 29/04/2023 | 05/05/2023 |  |  | 456 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--C--2-55 | TT_Mile | (ICSY3) FINAL LOGICS AND HMI GRAPHICS | 07/02/2022 | 07/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20GKB6H15 | TT_Task | ERECTION / PT IN UMC 20GKB-PIPES | 17/01/2023 | 20/02/2023 |  |  | 16 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PCB8M26 | TT_Task | FINAL COLD COMMISSIONING 20PCB | 26/05/2023 | 15/06/2023 |  |  | 32 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PCB8M25 | TT_Task | COLD COMMISSIONING 20PCB | 12/05/2023 | 25/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PCB8M10 | TT_FinMile | (TOP-20PCB) SERVICE COOLING WATER SYSTEM | 14/04/2023 | 14/04/2023 |  |  | 216 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PCB6M10 | TT_Task | PIPING WORKS FOR PCB SYSTEM - INTERNAL PIPIES | 11/06/2022 | 08/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAH6-40 | TT_FinMile | (RFP) READY FOR PIPE CONNECTION CONDENSER TUBE CLEANING SYSTEM 20PAH | 21/08/2022 | 21/08/2022 |  |  | 808 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGY4A40 | TT_FinMile | (OTD-OS) ON SITE FIRE FIGHTING DETECTION SYSTEM SGY | 26/05/2022 | 26/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA3G55 | TT_Task | INSTALL. COMP., INT. CABLING, FIRE PROT., SHOP TEST ELECTRICAL MODULES 20UBA1110/20 | 16/06/2022 | 01/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA3L25 | TT_Task | MANUFACTURING ELECTRICAL MODULES 20UBA1110/20 | 27/01/2022 | 15/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20CPC8-25 | TT_Task | COMMISSIONING ET200 STATIONS HRSG20 CPC | 11/04/2023 | 17/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20CPB8A30 | TT_Task | IC FIELD COMMISSIONING ST | 18/04/2023 | 19/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAN8-10 | TT_FinMile | (TOP-20MAN) ST BYPASS SYSTEM | 17/04/2023 | 17/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--B--7-55 | TT_Task | PULLING DATA PREPARATION ON SITE (BOP SYSTEMS) | 20/04/2022 | 03/05/2022 |  |  | 256 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA3J80 | TT_FinMile | (RFS) READY FOR SHIPMENT ELECTRICAL MODULES 20UBA7610/20 | 01/05/2022 | 01/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA4J50 | TT_Mile | (ET4b) ELECTRICAL MODULES AT WORKSHOP READY FOR COMPONENT INSTALLATION ELECTRICAL MODULES 20UBA7610/20 | 24/01/2022 | 24/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP--SGJ2-10 | TT_Mile | SYSTEM DESCRIPTION FIRE FIGHTING / GAS DETECTION SGJ / CYQ / CYE | 19/02/2021 | 19/02/2021 | 19/02/2021 | 19/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP--SGJ2-87 | TT_Mile | INSPECTION PLAN FIRE FIGHTING / GAS DETECTION SGJ / CYQ / CYE | 16/07/2021 | 16/07/2021 | 16/07/2021 | 16/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--BAW8B10 | TT_FinMile | (TOP-20BAW-03) LIGHTNING PROTECTION | 02/02/2023 | 02/02/2023 |  |  | 480 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BAW8-10 | TT_FinMile | (TOP-20BAW-02) PLANT EARTHING GRID COMPLETE | 02/07/2023 | 02/07/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UHX2-10 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UHX | 24/07/2021 | 24/07/2021 | 24/07/2021 | 24/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BFA8-35 | TT_Task | FEEDER COMMISSIONING LV SWITCHGEAR 20BFA / BMA / BFB | 11/04/2023 | 29/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BFA8-25 | TT_Task | COMMISSIONING LV SWITCHGEAR 20BFA / BMA / BFB | 07/02/2023 | 13/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--C--3E27 | TT_Task | DETAIL DESIGN / MANUFACTURING/ SHOP TEST FOR BOP IC FIELD DEVICES | 15/05/2021 | 15/03/2022 | 15/05/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20HB-3D26 | TT_Task | MANUFACTURING STACK HRSG 20 | 11/04/2021 | 10/01/2022 | 11/04/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UBA8G26 | TT_Task | ELECTRICAL COMMISSIONING 20UBA8110/20 | 11/04/2023 | 17/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP--CJJ2-38 | TT_FinMile | ST PREL. INPUT FOR IC UNIT COORDINATION (incl. Final SREL) | 16/09/2021 | 16/09/2021 | 16/09/2021 | 16/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--C--2A40 | TT_Task | HW ENGINEERING BOP IC | 09/04/2021 | 17/12/2021 | 09/04/2021 | 17/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--C--2B35 | TT_Task | SW ENGINEERING BOP IC, T3000 DB MERGING Fail Safe | 19/09/2021 | 16/01/2022 | 19/09/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2A60 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE TS FOUND. 20UMC | 05/02/2021 | 05/02/2021 | 05/02/2021 | 05/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20M--9-70 | TT_Task | COMBINED CYCLE POWER PLANT LOAD TESTS - MAIN GAS | 01/08/2023 | 29/09/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBV6-55 | TT_Mile | START LUBE OIL FLUSHING GT20 | 12/03/2023 | 12/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZL7-38 | TT_Task | LIGHTING AND SMALL POWER INSTALLATION UBF/UBN | 14/12/2022 | 10/01/2023 |  |  | 720 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6-30 | TT_Task | ALIGNMENT FRONT REAR HP-BEARING PEDESTALS TO DRAWING AND DEFLECTION CURVE MA | 17/06/2022 | 25/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBN5-20 | TT_FinMile | (RFE) FOUNDATION 20UBN | 28/07/2022 | 28/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--C--2-41 | TT_Task | ENGINEERING FUP'S UNIT COORDINATION | 07/02/2022 | 01/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BAA2-75 | TT_Mile | RFQ IPB BAA | 19/03/2021 | 19/03/2021 | 19/03/2021 | 19/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--CP-3-25 | TT_Task | DETAIL DESIGN / MANUFACTURING/ SHOP TEST FOR BOP IC FIELD CABINETS | 30/07/2021 | 20/05/2022 | 30/07/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SP20MB-2-85 | TT_Mile | CONTRACT INTO FORCE GT ACCESSORY EQUIPMENT / CCR / IN-LINE COMPONENTS GT-PIPING MB | 27/11/2021 | 27/11/2021 | 27/11/2021 | 27/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MB-2-81 | TT_Task | QUOTATION STAGE GT ACCESSORY EQUIPMENT / CCR / IN-LINE COMPONENTS GT-PIPING MB | 16/10/2021 | 26/11/2021 | 16/10/2021 | 26/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--LCB2B20 | TT_Mile | CONFIRMED PUMP CURVES CONDENSATE EXTRACTION LCB-PUMP | 14/05/2021 | 14/05/2021 | 14/05/2021 | 14/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--LCB2B85 | TT_Mile | CONTRACT INTO FORCE CONDENSATE EXTRACTION PUMP LCB | 09/04/2021 | 09/04/2021 | 09/04/2021 | 09/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MB-9A15 | TT_Mile | 1ST. IGNITION GT | 01/07/2023 | 01/07/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-8-60 | TT_Mile | INITIAL STEAM ADMISSION FOR ST20 | 01/08/2023 | 01/08/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MB-8E25 | TT_Task | COLD COMMISSIONING GT20 SYSTEMS MBA 20MBP | 18/05/2023 | 24/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--UBA2D75 | TT_Mile | (F) DETAIL DESIGN STEEL STRUCTURE WITH CONTRACTOR UBA7xxx | 01/02/2022 | 01/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--UBA2B70 | TT_Task | DETAIL DESIGN STEEL STRUCTURE UBA7xxx | 24/06/2021 | 01/08/2021 | 24/06/2021 | 01/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2C31 | TT_FinMile | DESIGN INPUT (FINAL LOAD DATA) FROM VENDOR FOR 20UBA8110/20 AVAILABLE | 23/06/2021 | 23/06/2021 | 23/06/2021 | 23/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--PAD4-25 | TT_Task | TRANSPORT PARTS EMB. INTO RISERES 20PAD | 13/08/2021 | 05/11/2021 | 13/08/2021 | 05/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20LCL4B40 | TT_FinMile | (OTD-OS) ON SITE BOILER BLOWDOWN PUMP 20LCL | 21/07/2022 | 21/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI---2P2A10 | TT_FinMile | LAST SUPPLIER INPUT GROUP II (EKT,EKG,LCA10,LCA30,LCL,LDK10,MAG,MAG50,MAW,MAM,MAL) LOT4 | 18/07/2021 | 18/07/2021 | 18/07/2021 | 18/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBH5E48 | TT_FinMile | (RFE) FOUNDATION 20UBH01 | 24/04/2022 | 24/04/2022 |  |  | 696 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBH5-10 | TT_Mile | (H) START PLACING FORMWORK 20UBH01 | 05/03/2022 | 05/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--B--2-14 | TT_Mile | 1ST. ROOM TO ROOM MATRIX | 02/05/2021 | 02/05/2021 | 02/05/2021 | 02/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--BAA2-60 | TT_FinMile | (DF) INPUT FOR MS3 IPB BAA | 26/06/2021 | 26/06/2021 | 26/06/2021 | 26/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--LBH2D60 | TT_FinMile | (DF) INPUT FOR MS3 BLOW DOWN TANK LBH | 29/03/2021 | 29/03/2021 | 29/03/2021 | 29/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--LBH2D65 | TT_FinMile | (DF) INPUT FOR M2 BLOW DOWN TANK LBH | 18/06/2021 | 18/06/2021 | 18/06/2021 | 18/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MAN7H15 | TT_Task | ELECTRICAL ERECTION PIPES / VALVES MAN | 24/02/2023 | 16/03/2023 |  |  | 256 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MAN3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT ST BYPASS VALVES 20MAN | 26/05/2022 | 26/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAT2-80 | TT_Task | QUOTATION STAGE MAIN TRANSFORMERS BAT/BBT | 26/02/2021 | 10/05/2021 | 26/02/2021 | 10/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20S--4-40 | TT_FinMile | (OTD-OS) ON SITE DUCT FOR HVAC SYSTEM UMC 20SA | 12/10/2022 | 12/10/2022 |  |  | 168 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BAW2-85 | TT_Mile | CONTRACT INTO FORCE IN- / OUTDOOR GROUNDING BAW | 30/01/2022 | 30/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BAW2-80 | TT_Task | QUOTATION STAGE IN- / OUTDOOR GROUNDING BAW | 19/12/2021 | 29/01/2022 | 19/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--BAW2-75 | TT_Mile | RFQ BOQ IN- / OUTDOOR GROUNDING | 19/12/2021 | 19/12/2021 | 19/12/2021 | 19/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MBR6-35 | TT_Task | INTERMEDIATE ALIGNMENT / PLACING AND WELDING EXPANSION JOINT TO DIFFUSER 20MBR | 08/09/2022 | 21/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBR6-15 | TT_Task | ASSEMBLY MAIN PIECES PF DIFFUSER / WELDING SHELLS | 22/04/2022 | 02/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBJ7-10 | TT_Task | PLACING 20MKC01/20MBJ01-TRANSFORMER (on UBG01/02) | 09/07/2022 | 10/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAH6-15 | TT_Task | ERECTION CONDENSER TUBE CLEANING SYSTEM 20PAH | 21/08/2022 | 17/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7-20 | TT_Task | ERECTION CABLE TRAYS 20UMY | 14/04/2022 | 04/05/2022 |  |  | 24 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAS4B40 | TT_FinMile | (OTD-OS) ON SITE CT MAKE-UP WATER PUMP PAS | 31/03/2022 | 31/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAW5B16 | TT_Task | ERECTION LIGHTNING PROTECTION 20UMC | 25/08/2022 | 19/10/2022 |  |  | 2048 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5B10 | TT_Mile | (HS) START ERECTION STEEL STRUCTURE 20UBA7910/20 | 07/08/2022 | 07/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEN5D15 | TT_Task | CONSTRUCTION FENCING FINISHING WORKS 20UEN | 26/02/2023 | 18/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZL7F17 | TT_Task | LIGHTING AND SMALL POWER INSTALLATION 20UMC - REMAINING | 20/08/2022 | 17/02/2023 |  |  | 360 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKQ8-25 | TT_FinMile | (TOP-20MKQ) GENERATOR WASTE GAS SYSTEM | 24/04/2023 | 24/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKQ6A15 | TT_Task | PIPING ERECTION EXHAUST GAS SYSTEM FOR GENERATOR 20MKQ | 11/09/2022 | 26/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZL7G15 | TT_Task | LIGHTING AND SMALL POWER INSTALLATION HRSG20 | 24/08/2022 | 22/11/2022 |  |  | 1168 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZL8-25 | TT_Task | COMMISSIONING LIGHTING/SMALL POWER 20UHA AREA | 18/04/2023 | 24/04/2023 |  |  | 200 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZL8A10 | TT_FinMile | (TOP-20BZL-02) LIGHTING / SMALL POWER INCL. BMZ FOR UHA AREA | 17/04/2023 | 17/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZL7F15 | TT_Task | LIGHTING AND SMALL POWER INSTALLATION 20UMC - HIGH BAY | 20/05/2022 | 09/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20S--3J25 | TT_Task | DETAIL DESIGN DUCTS HVAC SYSTEM UMC SA | 02/08/2021 | 26/09/2021 | 02/08/2021 | 26/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20SAM3E25 | TT_Task | MANUFACTURING DUCT FOR HVAC SYSTEM UMC 20SA | 11/03/2022 | 23/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKA6-32 | TT_Task | ALIGNMENT OF GENERATOR AND SLIPRING SHAFT TO STEAM TURBINE MKA | 01/09/2022 | 06/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZL8E25 | TT_Task | COMMISSIONING LIGHTING/SMALL POWER IN 20URD/URA/UGJ | 03/05/2023 | 09/05/2023 |  |  | 296 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP--B--2-50 | TT_Mile | PREL. ELECTRICAL LOAD DATA (VEL) FOR LV | 08/05/2021 | 08/05/2021 | 08/05/2021 | 08/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BAT2-75 | TT_Mile | RFQ MAIN TRANSFORMERS BAT/BBT | 26/02/2021 | 26/02/2021 | 26/02/2021 | 26/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP--CJT2-80 | TT_Task | ORDERING / NEGOTIATIONS SFC CUBICLES CJT | 02/04/2021 | 27/05/2021 | 02/04/2021 | 27/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP--CJT2-77 | TT_Task | PREPARATION OF SPEC. / ORDER DOCU. SFC CUBICLES CJT | 19/02/2021 | 01/04/2021 | 19/02/2021 | 01/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--3331-35 | TT_FinMile | PROJECT SPECIFIC TCC`s AVAILABLE | 15/01/2021 | 15/01/2021 | 15/01/2021 | 15/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBN2-20 | TT_Task | PREPARATION FOUNDATION GROUNDING DWGS 20UBN | 17/01/2022 | 30/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-6E33 | TT_Task | WELDING INLET DUCT | 25/05/2022 | 03/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SAM8-29 | TT_FinMile | (TOP-20SAM30) HVAC SYSTEM FOR GT NOISE ENCLOSURE MPB | 24/05/2023 | 24/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBX8E25 | TT_Task | COLD COMMISSIONING GT HYDRAULIC OIL SYSTEM 20MBX | 09/05/2023 | 15/05/2023 |  |  | 16 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBX8-25 | TT_Task | COLD COMMISSIONING GT20 PNEUMATIC SYSTEM MBX21 | 22/06/2023 | 28/06/2023 |  |  | 16 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LBA6H45 | TT_Task | INSULATION PIPES / VALVES FOR STEAM SYSTEM 20LBA10 | 03/02/2023 | 16/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LBA6J45 | TT_Task | INSULATION PIPES / VALVES FOR STEAM SYSTEM 20LBA80 (BOP) | 03/02/2023 | 09/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK3-25 | TT_Task | MANUFACTURING / SHOP TEST MV/LV CABLES20/00BZK (LOT 1) | 30/01/2022 | 23/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT MV/LV CABLES20/00BZK (LOT 1) | 21/05/2022 | 21/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--2222-37 | TT_Mile | COMMISSIONING MANUAL - WATER STEAM CYCLE | 18/03/2023 | 18/03/2023 |  |  | 224 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5B46 | TT_FinMile | (RFE) STEEL STRUCTURE 20UBA8110/20 | 07/12/2022 | 07/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---9-85 | TT_Mile | START RELIABILITY RUN COMBINED CYCLE POWER PLANT | 17/12/2023 | 17/12/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--SG-2-15 | TT_Task | BASIC DESIGN FIRE FIGHTING SYSTEMS SG- | 16/03/2021 | 19/04/2021 | 16/03/2021 | 19/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BFT4-25 | TT_Task | TRANSPORT LV-TRANSFORMERS 20BFT01/02 | 29/04/2022 | 23/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BFT3-25 | TT_Task | DETAIL DESIGN / MANUFACTURING / SHOP TEST LV-TRANSFORMERS BFT | 22/09/2021 | 31/03/2022 | 22/09/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20GM-7E15 | TT_Task | ELECTRICAL ERECTION SUMP PUMPS GM FOR UBF | 22/07/2022 | 28/07/2022 |  |  | 280 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20GM-7-15 | TT_Task | ELECTRICAL ERECTION SUMP PUMPS/OIL SEPARATOR GM FOR 20UBH01 | 04/08/2022 | 10/08/2022 |  |  | 176 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAW5B15 | TT_Task | ERECTION OUTDOOR EARTHING 20UMC AREA | 16/01/2023 | 12/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2B70 | TT_Task | DETAIL DESIGN STEEL STRUCTURE / CRANE 20UMC | 03/03/2021 | 16/05/2021 | 03/03/2021 | 16/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20CPC8A25 | TT_Task | IC FIELD COMMISSIONING HRSG20 CPC | 18/04/2023 | 15/05/2023 |  |  | 32 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--CKA4-25 | TT_Task | TRANSPORT THERMODYN. DIAGNOSIS SERVER | 05/02/2023 | 01/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BFF3-25 | TT_Task | MANUFACTURING / SHOP TEST LV SWITCHGEAR FOR HRSG 20BFF/BMF | 15/01/2022 | 13/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--ZTA4A40 | TT_FinMile | (OTD-OS) ON SITE EQUIPMENT/ MOBILIZATION CHEMICAL CLEANING SYSTEM ZTA | 17/03/2023 | 17/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-5-25 | TT_Task | GROUTING MAIN STEEL incl. CURING HRSG20 | 24/02/2022 | 02/03/2022 |  |  | 216 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-6D17 | TT_Task | ERECTION HP VESSEL / IP AND LP DRUM | 17/05/2022 | 18/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-6A48 | TT_FinMile | (RFP) READY FOR PIPING HRSG20 | 20/05/2022 | 20/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAA6-15 | TT_Task | ERECTION COOLING TOWER COARSE SCREEN 20PAA | 07/09/2022 | 11/10/2022 |  |  | 1480 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--UBA2F60 | TT_FinMile | (MS3) STEEL STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE UBA7xxx | 23/06/2021 | 23/06/2021 | 23/06/2021 | 23/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MBA8-23 | TT_Mile | START COLD COMMISSIONING GT/GEN 20 | 09/04/2023 | 09/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20QC-2-85 | TT_Mile | CONTRACT INTO FORCE DOSING CONTAINER QC | 12/08/2021 | 12/08/2021 | 12/08/2021 | 12/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--URA2-55 | TT_Mile | FOUNDATION GROUNDING DWGS RELEASED FOR EXEC. 20URA/URD | 25/06/2021 | 25/06/2021 | 25/06/2021 | 25/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--URA2-60 | TT_FinMile | COOLING TOWER COMPONENTS (SPIG) SUBSTRUCTURE-20URA/URD | 27/07/2021 | 27/07/2021 | 27/07/2021 | 27/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--HB-2A40 | TT_FinMile | (MS2) DESIGN LOAD DATA, DIMENSIONS HRSG AND STACK | 15/01/2021 | 15/01/2021 | 15/01/2021 | 15/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--PAC2B45 | TT_Mile | DESIGN DATA SHEETS FOR CW PUMP PAC | 30/01/2021 | 30/01/2021 | 30/01/2021 | 30/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20HB-6A17 | TT_Task | ERECTION MAIN STEEL COLUMNS INCL. BOTTOM PANELS TOP CROSS GIRDER HRSG20 | 15/01/2022 | 13/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-8-12 | TT_FinMile | (TOP-20HBK) HRSG EXHAUST GAS SYSTEM HRSG20 | 17/04/2023 | 17/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKA6E16 | TT_Task | PLACING OF GENERATOR SKIDS MKA | 07/08/2022 | 27/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKA6-50 | TT_Mile | GENERATOR READY FOR PREPARATION LUBE OIL FLUSHING MKA | 22/09/2022 | 22/09/2022 |  |  | 1368 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKA6-80 | TT_Task | GENERATOR COMPLETE ERECTION (SLIPRING, BEARINGS, SHAFT SEALING; BEARING BRACKET OIL SEALS; GROUNDING BRUSHES) MKA | 10/02/2023 | 25/03/2023 |  |  | 240 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6C55 | TT_Task | PERFORM AXIAL AND RADIAL CLEARANCE CHECK OF K-TURBINE MA | 15/08/2022 | 16/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6C20 | TT_Task | SET DOWN K-SHAFT IN BEARINGS AND ALIGNMENT OF SHAFT MA | 08/08/2022 | 14/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY2-60 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UEY03-05 | 02/06/2021 | 02/06/2021 | 02/06/2021 | 02/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--3332-01 | TT_Mile | PROJECT SETUP PID | 01/08/2020 | 01/08/2020 | 01/08/2020 | 01/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--LCB2B75 | TT_Task | TECHNICAL CLARIFCATION / PREP. RFQ CONDENSATE EXTRACTION PUMPS LCB | 15/01/2021 | 04/02/2021 | 15/01/2021 | 04/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BTA2-15 | TT_Task | BASIC DESIGN / SPECIFICATION BATTERIES RACKS BTA | 30/06/2021 | 11/08/2021 | 30/06/2021 | 11/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--2226-58 | TT_FinMile | KKS PLANT LABELLING COMPLETE | 08/09/2023 | 08/09/2023 |  |  | 168 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--2226-55 | TT_Task | ERECTION KKS PLANT LABELLING (REQUIRED FOR BACK ENERGISING) | 30/01/2023 | 26/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGA8-10 | TT_FinMile | (TOP-20SGA-03) FF INDOOR HYDRANTS FOR UHA, ULA AND UMC BUILDINGS | 03/04/2023 | 03/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20CPC8-10 | TT_FinMile | (TOP-20CP-WS) INTERFACE PANELS IN FUNCTION AREA WATER / STEAM CYCLE | 27/02/2023 | 27/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MA-3D80 | TT_Mile | STEAM TURBINE FOUNDATION PARTS EX WORKS (DG01060000) | 16/06/2021 | 16/06/2021 | 16/06/2021 | 16/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-10 | TT_Mile | (H) START PLACING FORMWORK 20URA | 30/09/2021 | 30/09/2021 | 30/09/2021 | 30/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PCB7M15 | TT_Task | ELECTRICAL ERECTION SERVICE COOLING WATER EXTRACTION PUMP PCB | 08/10/2022 | 21/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BFA4-10 | TT_Task | TRANSPORT TO WORKSHOP LV- / DC-SWITCHGEAR BFA/BFB/BMA/BUA/BUB/BUC (TO ST. INGBERT-INSTALL INTO ELECTRICAL MODULES) | 17/01/2022 | 18/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BFA3-25 | TT_Task | MANUFACTURING / SHOP TEST LV- / DC-SWITCHGEAR BFA/BFB/BMA/BUA/BUB/BUC | 08/09/2021 | 16/01/2022 | 08/09/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20SG-3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT FIRE FIGHTING SYSTEMS 20SGC/SGE/SGF/SGJ | 24/03/2022 | 24/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20CPB8-25 | TT_Task | COMMISSIONING ET200 STATIONS ST CJJ | 11/04/2023 | 17/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5-75 | TT_FinMile | (RFE) FINISHING WORKS 20UBA7910/20 | 16/06/2022 | 16/06/2022 |  |  | 1880 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK4-25 | TT_Task | TRANSPORT MV/LV CABLES20/00BZK (LOT 1) | 22/05/2022 | 16/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SG-4-41 | TT_FinMile | ON SITE FIRE FIGHTING SYSTEMS 20SGC/SGE/SGF/SGJ | 19/05/2022 | 19/05/2022 |  |  | 480 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MBL2-05 | TT_Mile | PI DIAGRAMS AIR INTAKE MBL | 26/04/2021 | 26/04/2021 | 26/04/2021 | 26/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MBL2-95 | TT_Mile | LAYOUT COMPONENT DRAWING AIR INTAKE MBL | 07/06/2021 | 07/06/2021 | 07/06/2021 | 07/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MBL2-87 | TT_Mile | INSPECTION PLAN AIR INTAKE MBL | 02/09/2021 | 02/09/2021 | 02/09/2021 | 02/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MBL2-60 | TT_Mile | FOUNDATION LOADS AIR INTAKE MBL | 03/05/2021 | 03/05/2021 | 03/05/2021 | 03/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20GHC8H25 | TT_FinMile | (TOP-20GHC) DEMIN WATER SYSTEM | 30/03/2023 | 30/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20EK-7H15 | TT_Task | ELECTRICAL ERECTION / VALVES 20EKG | 17/03/2023 | 30/03/2023 |  |  | 352 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--UMY2-60 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20ULY/UMY | 08/05/2021 | 08/05/2021 | 08/05/2021 | 08/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MB-7-15 | TT_Task | INSTALLATION EMERGENCY PUSH BUTTON GT20 | 12/02/2023 | 18/02/2023 |  |  | 536 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAW2-28 | TT_Task | QUOTATION PHASE FOR LIGHTNING PROTECTION | 11/12/2021 | 24/12/2021 | 11/12/2021 | 24/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMX5-10 | TT_Mile | (H) START PLACING FORMWORK 20UMX-deleted | 01/11/2021 | 01/11/2021 | 01/11/2021 | 01/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMX5-05 | TT_Task | WORK PREPARATION, EXCAVATION 20UMX- deleted | 01/11/2021 | 01/11/2021 | 01/11/2021 | 01/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20--P6A00 | TT_Mile | START PIPE ERECTION WSC | 28/06/2022 | 28/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MB-6-15 | TT_Mile | START COMPONENT ERECTION IN 20UMC | 04/07/2022 | 04/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5A45 | TT_FinMile | TURBOSET FOUNDATION READY FOR ERECTION 20UMC | 29/01/2022 | 29/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LCL7B15 | TT_Task | ELECTRICAL ERECTION BOILER BLOWDOWN PUMP 20LCL | 20/08/2022 | 08/09/2022 |  |  | 1744 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MAD3-25 | TT_Task | MANUFACTURING ST BEARINGS 20MAD | 10/09/2021 | 10/03/2022 | 10/09/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20MKA4-40 | TT_FinMile | (OTD-OS) ON SITE GENERATOR 20MKA | 23/07/2022 | 23/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAW5C15 | TT_Task | ERECTION OUTDOOR EARTHING/LIGHTNING 00UEN03/04 AREA | 19/06/2022 | 30/07/2022 |  |  | 1856 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--LCB2B60 | TT_FinMile | (DF) INPUT FOR MS3 CONDENSATE EXTRACTION PUMPS LCB | 13/05/2021 | 13/05/2021 | 13/05/2021 | 13/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20HB-6-46 | TT_Task | REMAINING EXTERNAL INSULATION FOR STACK HRSG20 COMPLETION PLATFORMS | 30/08/2022 | 26/09/2022 |  |  | 1624 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAH2-60 | TT_FinMile | (DF) INPUT FOR MS3 CONDENSER TUBE CLEANING SYSTEM 20PAH | 19/05/2021 | 19/05/2021 | 19/05/2021 | 19/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20LCL8B35 | TT_Task | FINAL COLD COMMISSIONING BOILER BLOWDOWN DRAIN PUMP 20LCL | 25/04/2023 | 01/05/2023 |  |  | 88 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LCL8B25 | TT_Task | COLD COMMISSIONING BOILER BLOWDOWN SYSTEM (FOR CHEM. CLEANING) 20LCL | 18/04/2023 | 24/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UHA2B-8 | TT_Mile | DESIGN INPUT FOR EMBEDDED PARTS FOR 20UHA AVAILABLE | 04/05/2021 | 04/05/2021 | 04/05/2021 | 04/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC2B-20 | TT_Mile | DESIGN INPUT FOR EMBEDDED PARTS TS FDN 20 UMC AVAILABLE | 31/03/2021 | 31/03/2021 | 31/03/2021 | 31/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--G--2-75 | TT_Task | DESIGN REVIEW INCL. SIL-STUDY G-SYSTEMS | 30/05/2021 | 03/07/2021 | 30/05/2021 | 03/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--G--2B45 | TT_Mile | DESIGN DATA SHEETS FOR ALL G- COMPONENTS AVAILABLE | 30/05/2021 | 30/05/2021 | 30/05/2021 | 30/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--G--2-35 | TT_Task | DESIGN DATA SHEETS G-COMPONENTS | 17/10/2020 | 29/01/2021 | 17/10/2020 | 29/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI---1P2A10 | TT_FinMile | LAST SUPPLIER INPUT GROUP I (LAB, LBA, LBB, LBC, PAB) LOT4 | 29/06/2021 | 29/06/2021 | 29/06/2021 | 29/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MAX7H15 | TT_Task | ELECTRICAL ERECTION PIPES / VALVES MAX | 03/03/2023 | 09/03/2023 |  |  | 712 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBQ7H15 | TT_Task | ELECTRICAL ERECTION / VALVES IGN. GAS PIPES 20MBQ | 19/03/2023 | 25/03/2023 |  |  | 256 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MB-7J15 | TT_Task | ELECTRICAL ERECTION / VALVES 20MB | 05/02/2023 | 18/02/2023 |  |  | 536 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SCA8-17 | TT_Task | COLD COMMISSIONING FOR COMPRESSED AIR/INSTRUMENT AIR SYSTEM SCA/QFA | 23/05/2023 | 12/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SCA8-16 | TT_FinMile | (TOP-20SCB) COMPRESSED AIR SUPPLY SYSTEM | 22/05/2023 | 22/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LDK6B40 | TT_FinMile | (RFP) READY FOR PIPE CONNECTION CONDENSATE POLISHING PUMP 20LDK | 02/05/2022 | 02/05/2022 |  |  | 752 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LDK8B10 | TT_FinMile | (TOP-20LDK) CONDENSATE POLISHING SYSTEM | 28/02/2023 | 28/02/2023 |  |  | 112 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA3J55 | TT_Task | INSTALL. COMP., INT. CABLING, FIRE PROT., SHOP TEST ELECTRICAL MODULES 20UBA7610/20 | 24/01/2022 | 10/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--PAD2-75 | TT_Task | BASIC DESIGN / PREP. RFQ COOLING TOWER EQUIPMENT PAD (GFK) | 01/11/2020 | 19/12/2020 | 01/11/2020 | 19/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2Y70 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE CEP/LDK PIT 20UMC | 29/01/2021 | 15/03/2021 | 29/01/2021 | 15/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--ZTA2-85 | TT_Mile | CONTRACT INTO FORCE CHEMICAL CLEANING | 13/08/2022 | 13/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI---3P2A10 | TT_FinMile | LAST SUPPLIER INPUT GROUP III (MAJ,MAN,MAV,LCW,MAX,LCE,GHC,HSJ) LOT4 | 18/06/2021 | 18/06/2021 | 18/06/2021 | 18/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BAT2-15 | TT_Task | BASIC DESIGN / SPECIFICATION MAIN TRANSFORMERS BAT/BBT | 15/01/2021 | 25/02/2021 | 15/01/2021 | 25/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6B45 | TT_Task | PROVISIONALLY MOUNT OF EXPANSION JOINT FOR LP1-SUPPORTING ARM AND CENTERING GUIDE MA | 28/08/2022 | 03/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6B06 | TT_Task | WELDING ENTIRE LP1-OUTER CASING MA | 11/08/2022 | 27/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6D50 | TT_Mile | STEAM TURBINE READY FOR PREPARATION LUBE OIL FLUSHING MA | 09/02/2023 | 09/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--B--2A50 | TT_Mile | (ELV2) PREL. EL. LOAD DATA FOR LV | 16/03/2021 | 16/03/2021 | 16/03/2021 | 16/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20QU-6-15 | TT_Task | ERECTION SAMPLING CONTAINER 20QU | 18/11/2022 | 01/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20QU-6-40 | TT_FinMile | (RFP) READY FOR PIPE CONNECTION SAMPLING CONTAINER 20QU | 21/11/2022 | 21/11/2022 |  |  | 456 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20GM-8B10 | TT_FinMile | (TOP-20GM-01) PLANT DRAINAGE SYSTEM FOR UBE/UBF AREA | 13/02/2023 | 13/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMY5-05 | TT_Task | WORK PREPARATION, EXCAVATION PIPE BRIDGE 20ULY/UMY | 20/11/2021 | 29/11/2021 | 20/11/2021 | 29/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BZL7A15 | TT_Task | LIGHTING AND SMALL POWER INSTALLATION 20UBA76xx/77xx/7410/73xx/7210/7110/7920/10 | 21/08/2022 | 10/09/2022 |  |  | 1696 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MB-9-15 | TT_Mile | 1ST. IGNITION GT20 | 01/07/2023 | 01/07/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--HB-2A65 | TT_FinMile | (DF) INPUT FOR M2 MAIN COLUMNS HRSG/STACK | 15/01/2021 | 15/01/2021 | 15/01/2021 | 15/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--2222-38 | TT_Mile | STEAM BLOWING INSTRUCTION | 15/04/2023 | 15/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--2222-35 | TT_Mile | COMMISSIONING MANUAL - ELECTRICAL AND IC-PART | 30/01/2023 | 30/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6-50 | TT_Mile | STEAM TURBINE READY FOR Cable Trays / E and IC / Fire Fighting | 17/09/2022 | 17/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20QFB7H15 | TT_Task | ELECTRICAL ERECTION / VALVES ST CONTROL AIR 20QFB | 15/11/2022 | 21/11/2022 |  |  | 1528 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--UR-2-44 | TT_Task | BASIC DESIGN PLANT LAYOUT COOLING TOWER | 20/12/2020 | 16/04/2021 | 20/12/2020 | 16/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MAG3-81 | TT_FinMile | (RFS) READY FOR SHIPMENT ST CONDENSER 20MAG | 21/03/2022 | 21/03/2022 |  |  | 8 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MKC3-25 | TT_Task | MANUFACTURING SEE/SFC TRANSFORMER 20MKC / 20MBJ | 29/07/2021 | 01/04/2022 | 29/07/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--URD2-75 | TT_FinMile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION 20URD xx | 10/10/2021 | 10/10/2021 | 10/10/2021 | 10/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--URD2-55 | TT_Task | FOUNDATION GROUNDING DWGS RELEASED FOR EXEC. 20URD xx | 30/06/2021 | 13/07/2021 | 30/06/2021 | 13/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PGB8B25 | TT_Task | COLD COMMISSIONING CLOSED COOLING WATER SYSTEM FOR COMBINED CYCLE OPERATION PGB | 18/04/2023 | 08/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5B47 | TT_FinMile | (RFE) STEEL STRUCTURE FOR ELECTRICAL MODULES 20UBA7xxx | 01/09/2022 | 01/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5-47 | TT_FinMile | (RFE) FOUNDATION 20UBA7xxx | 13/04/2022 | 13/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BAW2-13 | TT_Task | SPECIFICATION GROUNDING LIGHTNING PROTECTION | 18/05/2021 | 28/06/2021 | 18/05/2021 | 28/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--BAW2-02 | TT_Mile | KICK OFF LIGHTNING PROTECTION | 23/04/2021 | 23/04/2021 | 23/04/2021 | 23/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--2222-31 | TT_FinMile | PROJECT SPECIFIC QUALITY PLAN | 13/07/2021 | 13/07/2021 | 13/07/2021 | 13/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--2222-30 | TT_FinMile | PROJECT QUALITY MANUAL | 07/07/2021 | 07/07/2021 | 07/07/2021 | 07/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA4-52 | TT_Mile | (ET4b) ELECTRICAL MODULES AT WORKSHOP READY FOR COMPONENT INSTALLATION 20UBA7110/20/30 | 19/01/2022 | 19/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-4A26 | TT_Task | TRANSPORT MAIN STEEL STRUCTURE HRSG20 (MAIN FRAME / CASING) | 30/12/2021 | 03/01/2022 | 30/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20HB-3A25 | TT_Task | MANUFACTURING MAIN STEEL STRUCTURE HRSG20 | 14/04/2021 | 10/11/2021 | 14/04/2021 | 10/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20HB-8-25 | TT_Task | COLD COMMISSIONING BOILER INLET, OUTLET DUCT, STACK HBK/HNE 20 | 18/04/2023 | 24/04/2023 |  |  | 144 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MBR3A25 | TT_Task | DETAIL DESIGN / MANUFACTURING DIFFUSER 20MBR | 29/07/2021 | 22/02/2022 | 29/07/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20HAA8E17 | TT_FinMile | (TOP-20HAA) HRSG CONDENSATE PREHEATING SYSTEM | 21/04/2023 | 21/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBF5-10 | TT_Mile | (H) START PLACING FORMWORK 20UBE/UBF | 18/01/2022 | 18/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBA8B10 | TT_FinMile | (TOP-20MBA5) GT HYDRAULIC CLEARANCE OPTIMIZATION SYSTEM | 26/04/2023 | 26/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBA8D10 | TT_FinMile | (TOP-20MBA3) GT ADVANCED COMPRESSOR CLEANING SYSTEM | 26/04/2023 | 26/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LBB7J15 | TT_Task | ELECTRICAL ERECTION / VALVES 20LBB-LBC80 | 17/03/2023 | 23/03/2023 |  |  | 200 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LBB6J47 | TT_Task | INSULATION PIPES / VALVES FOR STEAM SYSTEM 20LBB-LBC80 | 17/02/2023 | 23/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LBB6J15 | TT_Task | ERECTION, NDT PIPE / VALVES 20LBB-LBC80 | 31/08/2022 | 15/11/2022 |  |  | 640 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UVM5-05 | TT_Task | WORK PREPARATION, EXCAVATION 20UVM01 | 19/05/2022 | 24/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--2222-86 | TT_Mile | CONTRACT INTO FORCE ERECTION CONTRACTOR (MECHANICAL) | 23/10/2021 | 23/10/2021 | 23/10/2021 | 23/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--2222-81 | TT_Task | QUOTATION STAGE ERECTION CONTRACTOR (MECHANICAL) | 19/03/2021 | 09/07/2021 | 19/03/2021 | 09/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--2222-60 | TT_Task | PREPARATION RFQ DOCUMENTS FOR ERECTION CONTRACTOR (MECHANICAL) | 15/01/2021 | 18/03/2021 | 15/01/2021 | 18/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--2226-66 | TT_Task | MOBILISATION ERECTION CONTRACTOR (MECHANICAL) | 07/11/2021 | 15/01/2022 | 07/11/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--2227-67 | TT_Mile | KICK OFF MEETING ERECTION CONTRACTOR (E AND IC) | 26/01/2022 | 26/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5-12 | TT_Mile | (H) START PLACING FORMWORK 20UBA7xxx | 08/02/2022 | 08/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAD8-10 | TT_FinMile | (TOP-20MAD) ST BEARING SYSTEM | 06/06/2023 | 06/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20USX2-5 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20USX | 31/08/2021 | 31/08/2021 | 31/08/2021 | 31/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MBA6D15 | TT_Task | ERECTION WASH WATER TANK 20MBA | 16/10/2022 | 29/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGC8-10 | TT_FinMile | (TOP-20SGC-01) FF SPRAY DELUGE SYSTEMS FOR UBE/UBF and UBA CABLE AREA | 19/02/2023 | 19/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20QC-6-15 | TT_Task | ERECTION DOSING CONTAINER QC | 28/08/2022 | 10/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--SMM2-85 | TT_Mile | CONTRACT INTO FORCE CRANES 20SMM01/02 FOR 20UMC | 30/03/2021 | 30/03/2021 | 30/03/2021 | 30/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20HB-3F80 | TT_FinMile | (RFS) READY FOR SHIPMENT OUTLET DUCT HRSG 20 | 07/02/2022 | 07/02/2022 |  |  | 408 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-3F26 | TT_Task | MANUFACTURING OUTLET DUCT HRSG 20 | 28/02/2021 | 10/01/2022 | 28/02/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--C--2D56 | TT_Mile | DESIGN REVIEW BOP AUTOMATION | 18/06/2022 | 18/06/2022 |  |  | 136 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZL7E15 | TT_Task | LIGHTING AND SMALL POWER INSTALLATION 20UBA8110/20 | 01/12/2022 | 14/12/2022 |  |  | 936 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MBR2-10 | TT_Mile | SYSTEM DESCRIPTION DIFFUSER 20MBR | 12/03/2021 | 12/03/2021 | 12/03/2021 | 12/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP--CYE2-70 | TT_Mile | IC INPUT (PID, DESCR., SIGNAL EXCHANGE DWGS) FIRE FIGHTING / GAS DETECTION SGJ / CYQ / CYE | 16/04/2021 | 16/04/2021 | 16/04/2021 | 16/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BFG8-50 | TT_Mile | LV AVAILABLE FOR 20UBA (ENERGISING TEMPORARY POWER) | 14/02/2023 | 14/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20GM-8B27 | TT_Task | COLD COMMISSIONING PLANT DRAINAGE SYSTEM FOR 20ULA GM | 29/03/2023 | 04/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--ZTB2A85 | TT_Mile | CONTRACT INTO FORCE STEAM BLOWING PIPING | 27/05/2021 | 27/05/2021 | 27/05/2021 | 27/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--ZTB2A75 | TT_Task | INTEGRATION OF ACID CLEANING SYSTEM ZTB | 15/04/2021 | 26/05/2021 | 15/04/2021 | 26/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20LBA6J15 | TT_Task | ERECTION, NDT PIPE / VALVES 20LBA80 (BOP) | 27/08/2022 | 30/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAV7-15 | TT_Task | ELECTRICAL ERECTION FOR MAV MODUL | 26/09/2022 | 09/10/2022 |  |  | 320 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20GHC7H15 | TT_Task | ELECTRICAL ERECTION / VALVES DEMIN WATER 20GHC | 15/11/2022 | 05/12/2022 |  |  | 920 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--ZTB4A40 | TT_FinMile | (OTD-OS) ON SITE PIPING FOR STEAM BLOWING SYSTEM ZTB | 03/03/2023 | 03/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP--MB-2A55 | TT_FinMile | FINAL ELECTRICAL LOAD DATA (VEL) FOR GTGT-AUX. (EIF) | 01/07/2021 | 01/07/2021 | 01/07/2021 | 01/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP--MB-2G40 | TT_FinMile | WIRING DIAGRAMS GT (EIF) | 15/04/2021 | 15/04/2021 | 15/04/2021 | 15/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP--MB-2E40 | TT_FinMile | LIST OF MEASURING DEVICES GTGT-AUX. (MPL) (EIF) | 01/04/2021 | 01/04/2021 | 01/04/2021 | 01/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP--MB-2-50 | TT_FinMile | PREL. ELECTRICAL LOAD DATA (VEL) FOR GTGT-AUX. | 01/04/2021 | 01/04/2021 | 01/04/2021 | 01/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20B--8-50 | TT_FinMile | MV AVAILABLE (BACK ENERGISING) VIA 20BAT | 10/04/2023 | 10/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKA6F08 | TT_Task | FINAL COUPLING OF SLIPRING SHAFT MKA | 07/02/2023 | 11/02/2023 |  |  | 576 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKA6F15 | TT_Task | FINAL ASSEMBLING OF SLIPRING SET MKA | 28/01/2023 | 09/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKA5F25 | TT_Task | GROUTING OF SLIPRING BASEPLATES MKA | 02/02/2023 | 06/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SAM8-26 | TT_Task | COLD COMMISSIONING HVAC FOR MPB NOISE ENCLOSURE | 25/05/2023 | 07/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20QJ-6B42 | TT_Task | ERECTION GAS SUPPLY BOTTLES FOR CO2 | 22/10/2022 | 28/10/2022 |  |  | 1424 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--3332-27 | TT_Mile | SINGLE LINE DIAGRAM READY | 15/01/2021 | 15/01/2021 | 15/01/2021 | 15/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20HA-3B80 | TT_FinMile | (RFS) READY FOR SHIPMENT PIPING HRSG20_1st Part (LB CARBON STEEL) incl. Primary Piping Supports | 09/03/2022 | 09/03/2022 |  |  | 8 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-4B25 | TT_Task | TRANSPORT PIPING HRSG20_1st Part (LB CARBON STEEL) | 11/03/2022 | 09/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LCB3B80 | TT_FinMile | (RFS) READY FOR SHIPMENT CONDENSATE EXTRACTION PUMP 20LCB | 01/06/2022 | 01/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--CKA2-08 | TT_Mile | REMOTE ACCESS TO ERLANGEN | 11/04/2023 | 11/04/2023 |  |  | 408 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK7B32 | TT_Task | CABLING FROM 20UBA (10x) TO 20UBN | 07/12/2022 | 31/01/2023 |  |  | 48 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY5-45 | TT_FinMile | (RFE) FOUNDATION 20UEY03-05 | 17/05/2022 | 17/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY5-15 | TT_Task | CONSTRUCTION FOUNDATION 20UEY03-05 | 13/04/2022 | 17/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY5-10 | TT_Mile | (H) START PLACING FORMWORK 20UEY03-05 | 13/04/2022 | 13/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY5-06 | TT_Task | WORK PREPARATION, EXCAVATION 20UEY03-05 | 14/02/2022 | 27/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BZL3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT LIGHTING SMALL POWER BZL HIGHBAY,20UMC | 05/05/2022 | 05/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BZL2-15 | TT_Task | BASIC DESIGN / SPECIFICATION / PLANTLAYOUT DWG / BOQ LIGHTING SMALL POWER BZL | 04/02/2021 | 28/04/2021 | 04/02/2021 | 28/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--BZL2-75 | TT_Mile | RFQ LIGHTING SMALL POWER BZL | 13/05/2021 | 13/05/2021 | 13/05/2021 | 13/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--BZL2-85 | TT_Mile | CONTRACT INTO FORCE LIGHTING SMALL POWER BZL ALL STRUCTURE | 16/12/2021 | 16/12/2021 | 16/12/2021 | 16/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAC6B15 | TT_Task | ERECTION CIRC. CW PUMP 20PAC | 14/06/2022 | 08/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAC6B40 | TT_FinMile | (RFP) READY FOR PIPE CONNECTION CIRC. CW PUMP 20PAC | 27/06/2022 | 27/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP--CJT2-85 | TT_Mile | CONTRACT INTO FORCE SFC CUBICLES CJT | 28/05/2021 | 28/05/2021 | 28/05/2021 | 28/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20GM-6H15 | TT_Task | ERECTION PIPES DRAINAGE SYSTEM 20GM BOILER/STEAM TURBINE | 04/08/2022 | 14/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MB-6-20 | TT_Task | FURTHER ASSEMBLY / PIPING / INSULATION GT20 | 04/08/2022 | 28/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBA6-35 | TT_Task | PRELIMINARY ALIGNMENT / COUPLING OF SHAFT GT20 | 25/08/2022 | 07/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBA6-16 | TT_Task | LOWER, ALIGN FIX GT20 / INST. INTERMEDIATE SHAFT | 04/08/2022 | 24/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MB-6-22 | TT_FinMile | (RFE) STEEL STRUCTURE GT FOR CABLE TRAYS GT20 | 28/09/2022 | 28/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK7F26 | TT_Task | CABLING (E AND IC CABLES) GT20 | 08/01/2023 | 18/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BFF2-85 | TT_Mile | CONTRACT INTO FORCE LV SWITCHGEAR FOR HRSG BFF/BMF | 30/07/2021 | 30/07/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--C--2C50 | TT_Mile | (ICBB2) PRELIMINARY MEASUREMENT LIST, SIGNAL LIST AND BB INTERFACE SHEETS | 30/07/2021 | 30/07/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20LCL7A15 | TT_Task | ELECTRICAL ERECTION / VALVES STEAM GENERATOR DRAINS 20LCL | 16/02/2023 | 01/03/2023 |  |  | 352 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5D50 | TT_Task | FIRE BARRIER FOR WALL PENETRATIONS IN 20UMC | 26/02/2023 | 08/04/2023 |  |  | 664 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGJ6-5 | TT_Task | ERECTION FF CO2 SYSTEM IN GT ENCLOSURE 20MPB SGJ | 24/11/2022 | 21/12/2022 |  |  | 40 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--ULA2-50 | TT_Task | PREPARATION FOUNDATION GROUNDING DWGS 20ULA | 19/06/2021 | 02/07/2021 | 19/06/2021 | 02/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UBA2G15 | TT_Task | BASIC DESIGN / CONCEPTUAL DESIGN SPECIFICATION ELECTRICAL MODULES UBA | 13/11/2020 | 28/02/2021 | 13/11/2020 | 28/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20M--8-65 | TT_Task | UV TEST (BLACK OUT) GT20 | 08/06/2023 | 14/06/2023 |  |  | 8 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKA6-20 | TT_Mile | GENERATOR READY FOR PRE-ASSEMBLING PGB-PIPING | 10/09/2022 | 10/09/2022 |  |  | 1152 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6B16 | TT_Task | PLACING LP1-TURBINE SHAFT IN BEARINGS MA | 08/09/2022 | 09/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6B00 | TT_Task | CLEANING LP1-END WALLS AND PREPARATION OF ASSEMBLY STEAM TURBINE MA | 06/05/2022 | 07/05/2022 |  |  | 512 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2E60 | TT_FinMile | (MS3) STEEL PLATFORMS COND. PIT. FINAL DIMENSIONS, LOADS AVAILABLE LOT1 20UMC | 29/03/2021 | 29/03/2021 | 29/03/2021 | 29/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA4-50 | TT_Mile | (ET4b) ELECTRICAL MODULES AT WORKSHOP READY FOR COMPONENT INSTALLATION ELECTRICAL MODULES 20UBA7910/20 | 17/02/2022 | 17/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA4B40 | TT_FinMile | (OTD-OS) ON SITE (ET4d) ELECTRICAL MODULES 20UBA7910/20 | 27/07/2022 | 27/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BFT4-40 | TT_FinMile | (OTD-OS) ON SITE (ET7) LV-TRANSFORMERS 20BFT01/02 | 23/06/2022 | 23/06/2022 |  |  | 32 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--P--2-50 | TT_FinMile | (DF) MECH. ENGINEERING / PLANT LAYOUT P SYSTEMS | 11/02/2021 | 11/02/2021 | 11/02/2021 | 11/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20CYQ8-25 | TT_Task | COLD COMMISSIONING GAS DETECTION SYSTEM 20CYQ | 23/05/2023 | 29/05/2023 |  |  | 256 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGY3A25 | TT_Task | DETAIL DESIGN / MANUFACTURING FIRE FIGHTING DETECTION SYSTEM SGY | 10/09/2021 | 03/03/2022 | 10/09/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20PAH3-26 | TT_Task | MANUFACTURING SHOP TEST CONDENSER TUBE CLEANING SYSTEM 20PAH | 29/06/2021 | 26/12/2021 | 29/06/2021 | 26/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAH4-40 | TT_FinMile | (OTD-OS) ARRIVAL AT SKIDDER CONDENSER TUBE CLEANING SYSTEM 20PAH (BALL STRAINER) | 08/03/2022 | 08/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PGB7H15 | TT_Task | ELECTRICAL ERECTION PIPES / VALVES 20PGB | 08/02/2023 | 21/02/2023 |  |  | 416 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PCB7H15 | TT_Task | ELECTRICAL ERECTION / VALVES SERVICE COOL.WATER 20PCB | 25/12/2022 | 31/12/2022 |  |  | 776 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAB7A15 | TT_Task | ELECTRICAL ERECTION / VALVES 20PAB | 15/11/2022 | 12/12/2022 |  |  | 984 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAL7A15 | TT_Task | ELECTRICAL ERECTION PIPES / VALVES MAL | 03/12/2022 | 16/12/2022 |  |  | 976 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LDK6B55 | TT_Task | LEAK TEST CONDENSATE POLISHING PLANT 20LD | 09/02/2023 | 15/02/2023 |  |  | 104 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LDK6B16 | TT_Task | ERECTION CONDENSATE POLISHING PLANT 20LD | 05/08/2022 | 02/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--L--2I45 | TT_Mile | DESIGN DATA SHEETS SAFETY / CONTROL VALVES L SYSTEMS (on rack) | 14/05/2021 | 14/05/2021 | 14/05/2021 | 14/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--L--2-75 | TT_Task | DESIGN REVIEW INCL. SIL-STUDY L-SYSTEMS | 31/03/2021 | 04/05/2021 | 31/03/2021 | 04/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-----1-04 | TT_Mile | START PRODUCTS (FULL ENGINEERING START) (no Hardware Order before NTP) | 15/01/2021 | 15/01/2021 | 15/01/2021 | 15/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-70 | TT_FinMile | (OTD-OS) FIRST PIPES ON SITE PIPING SYSTEM (OUTSIDE) 20PAB (FIRST DELIVERY) | 07/07/2021 | 07/07/2021 | 07/07/2021 | 07/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB3-20 | TT_Task | FABRICATION / DETAIL DESIGN PIPING SYSTEM (OUTSIDE) 20PAB | 15/03/2021 | 11/04/2021 | 15/03/2021 | 11/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MAW7H15 | TT_Task | ELECTRICAL ERECTION PIPES / VALVES MAW | 12/03/2023 | 18/03/2023 |  |  | 280 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAV7H15 | TT_Task | ELECTRICAL ERECTION / VALVES MAV | 17/12/2022 | 23/12/2022 |  |  | 1256 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-6-55 | TT_FinMile | PRESSURE TEST HRSG20 COMPLETED | 14/04/2023 | 14/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-6A45 | TT_Task | INSULATION HRSG / PIPES HRSG20 FOR CHEMICAL CLEANING | 15/04/2023 | 12/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKC7-16 | TT_Task | ERECTION MKC05 SLIP RING STRUCTURE MKC20 | 08/09/2022 | 21/09/2022 |  |  | 72 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGC8-65 | TT_Task | SIGNAL AND INTERFACE TESTS FF SPRAY DELUGE SYSTEM FOR 20BAT/ BBT SGC | 20/02/2023 | 26/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAH2-75 | TT_Task | PREPARATION RFQ CONDENSER TUBE CLEANING SYSTEM 20PAH | 15/01/2021 | 10/02/2021 | 15/01/2021 | 10/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA3J25 | TT_Task | MANUFACTURING ELECTRICAL MODULES 20UBA7610/20 | 12/08/2021 | 12/01/2022 | 12/08/2021 |  | 32 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SP20MAV3-25 | TT_Task | DESIGN / MANUFACTURING LUBE OIL MODULE 20MAV | 29/07/2021 | 01/04/2022 | 29/07/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20LD8B110 | TT_FinMile | (TOP-20LD) CONDENSATE POLISHING PLANT | 28/02/2023 | 28/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2A70 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE TS FOUND. 20UMC | 06/02/2021 | 21/04/2021 | 06/02/2021 | 21/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC2B40 | TT_Task | BD - SUBMISSION APPROVAL - AMENDMENT BUILDING (incl. CEP MS3 Input) 20UMC | 23/07/2021 | 11/08/2021 | 23/07/2021 | 12/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--C--2-77 | TT_FinMile | IC CONFIGURATION AND CONCEPTS READY | 25/03/2021 | 25/03/2021 | 25/03/2021 | 25/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--M--2C20 | TT_Mile | LAYOUT DOCUMENTS [external interfaces final] | 20/03/2021 | 20/03/2021 | 20/03/2021 | 20/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UZA5-22 | TT_FinMile | (RFE) FOUNDATION FOR LIGHTING POLES UZA | 04/10/2022 | 04/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UZA5-23 | TT_Task | FINISHING WORKS UZA | 06/03/2023 | 04/05/2023 |  |  | 1928 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--UBA2J60 | TT_FinMile | (MS3) STEEL STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UBA8110/20 | 11/05/2021 | 11/05/2021 | 11/05/2021 | 11/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20LDK4B40 | TT_FinMile | (OTD-OS) ON SITE CONDENSATE POLISHING PLANT 20LD | 21/07/2022 | 21/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LDK3B80 | TT_FinMile | (RFS) READY FOR SHIPMENT CONDENSATE POLISHING PLANT 20LD | 26/05/2022 | 26/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LDK4B25 | TT_Task | TRANSPORT CONDENSATE POLISHING PLANT 20LD | 27/05/2022 | 21/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LDK3B32 | TT_Task | MANUFACTURING/SHOP TEST CONDENSATE POLISHING PLANT 20LD | 28/07/2021 | 28/04/2022 | 28/07/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--2222-80 | TT_Task | QUOTATION STAGE KKS PLANT LABELLING | 12/01/2022 | 22/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-4F25 | TT_Task | TRANSPORT OUTLET DUCT HRSG 20 | 31/03/2022 | 19/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAH6-10 | TT_Task | FEASIBLE PLACING CONDENSER CLEANING SCREEN | 18/09/2022 | 19/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HAA8F26 | TT_Task | COLD COMMISSIONING HRSG CONDENSATE RH SYS (FOR CHEM. CLEANING) 20HAA | 29/04/2023 | 12/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAX4-25 | TT_Task | TRANSPORT ST HYDRAULIC SYSTEM 20MAX | 30/04/2022 | 23/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBL8-25 | TT_Task | COLD COMMISSIONING AIR INTAKE SYSTEM UNIT 20MBL | 08/06/2023 | 14/06/2023 |  |  | 8 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BBA8-35 | TT_Task | FEEDER COMMISSIONING MV SWITCHGEAR 20BBB | 12/04/2023 | 30/05/2023 |  |  | 24 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BBA8-25 | TT_Task | COMMISSIONING MV SWITCHGEAR 20BBB | 29/03/2023 | 11/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-9-05 | TT_Mile | 1ST. TURNING GEAR ST | 20/06/2023 | 20/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20M--8-67 | TT_Task | UNDER VOLTAGE (UV) TEST (BLACK OUT) ST | 20/06/2023 | 26/06/2023 |  |  | 32 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--UBA2H75 | TT_FinMile | (F) DETAIL DESIGN STEEL STRUCTURE WITH CONTRACTOR 20UBA8110/20 | 14/03/2022 | 14/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--UBA2D70 | TT_Task | DETAIL DESIGN STEEL STRUCTURE 20UBA8110/20 | 21/09/2021 | 06/12/2021 | 21/09/2021 | 06/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2I60 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UBA8110/20 | 11/05/2021 | 11/05/2021 | 11/05/2021 | 11/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2C50 | TT_Task | PREPARATION FOUNDATION GROUNDING DWGS 20UBA8110/20 | 21/08/2021 | 06/12/2021 | 21/08/2021 | 06/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2C61 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE 20UBA8110/20 | 24/06/2021 | 06/12/2021 | 24/06/2021 | 06/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20--P6-75 | TT_Task | CHEMICAL CLEANING HRSG20 STEAM LINES TO ST | 13/05/2023 | 02/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-9A45 | TT_Task | STEAM BLOW (ABO) HRSG / WD 20 | 03/07/2023 | 09/07/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAB7-15 | TT_Task | ERECTION CT / GROUNDING CUBICLE 20BAB | 21/08/2022 | 03/09/2022 |  |  | 1864 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBX5C10 | TT_Mile | (HC) START ERECTION ROOF DECKING 20UBX | 02/09/2022 | 02/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGA8B27 | TT_Task | COLD COMMISSIONING FIRE FIGHTING MAIN RING AND OUTDOOR HYDRANTS SGA | 14/02/2023 | 19/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--UR-2-35 | TT_FinMile | (C) BASIC DESIGN PLANT LAYOUT DWGS (UE) COOLING TOWER AVAILABLE | 16/04/2021 | 16/04/2021 | 16/04/2021 | 16/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MB-6-00 | TT_Task | PREPARATION FOUNDATION / INSTALL SUPPORT BEAM GT20 | 16/07/2022 | 29/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MB-6-38 | TT_Task | INSULATION / COMPLETE ERECTION GT20 - BEFORE BURNERS INSTALLATION | 29/09/2022 | 02/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBV6-55 | TT_Task | OIL FLUSHING GT20 | 12/03/2023 | 01/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MB-6-25 | TT_Task | PRE-ALIGN AND FIX GT20 | 04/08/2022 | 17/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UHX2-40 | TT_FinMile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION 20UHX | 05/04/2022 | 05/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBA8-25 | TT_Task | COLD COMMISSIONING GT20 INCLUDING COMBUSTION CHAMBER | 27/04/2023 | 21/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--PAD2-86 | TT_Mile | PRELIMINARY INPUT FOR MS2 COOLING TOWER PAD | 20/12/2020 | 20/12/2020 | 20/12/2020 | 20/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20SGC6-15 | TT_Task | ERECTION SPRAY DELUGE SYSTEM SGC FOR 20BAT 20SGC | 21/11/2022 | 25/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGJ8-20 | TT_FinMile | (TOP-20SGJ) FF CO2 SYSTEM IN GT ENCLOSURE 20MPB SGJ | 24/05/2023 | 24/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--SG-2-16 | TT_Task | BASIC DESIGN DWGS FIRE FIGHTING SYSTEMS SG- (incl. Design Review) | 20/04/2021 | 23/07/2021 | 20/04/2021 | 23/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--HA-2-70 | TT_FinMile | (DF) IC HRSG | 22/04/2021 | 22/04/2021 | 22/04/2021 | 22/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--HA-2-11 | TT_Mile | PID'S, DATA SHEETS / LIFE TIME DESIGN CRITERIA FOR INQUIRY / ORDERING HRSG AVAILABLE | 23/08/2020 | 23/08/2020 | 23/08/2020 | 23/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--P--2-30 | TT_Task | REVISION PID'S AFTER 3D DRV P SYSTEMS | 15/01/2021 | 11/02/2021 | 15/01/2021 | 11/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20LCW6H15 | TT_Task | ERECTION, NDT, PT PIPES / VALVES 20LCW | 09/11/2022 | 17/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20CPB8-10 | TT_FinMile | (TOP-20CP-ST) INTERFACE PANELS IN FUNCTION AREA ST | 10/04/2023 | 10/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGC8-37 | TT_Task | COLD COMMISSIONING FF SPRAY DELUGE SYSTEMS FOR TS AUXILIARY OIL SYSTEMS / H2 SYSTEMS SGC | 18/04/2023 | 01/05/2023 |  |  | 56 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MKC3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT SEE/SFC TRANSFORMER GT 20MKC / 20MBJ | 29/04/2022 | 29/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--ZTB3A25 | TT_Task | DESIGN, PROC. PIPING / VALVES FOR STEAM BLOWING SYSTEM ZTB | 27/05/2021 | 09/02/2022 | 27/05/2021 |  | 2424 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--ZTB2A20 | TT_FinMile | (DF) MATERIAL TAKE OFF FOR TEMPORARY PIPING AND VALVES | 30/09/2021 | 30/09/2021 | 30/09/2021 | 30/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20M--9-60 | TT_Mile | INITIAL STEAM ADMISSION TO ST 20 | 01/08/2023 | 01/08/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20M--9-10 | TT_Task | OPTIMIZING COMBINED CYCLE POWER PLANT | 21/10/2023 | 04/12/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20M--9-50 | TT_Mile | FIRST BYPASS OPERATION FOR ST 20 | 25/07/2023 | 25/07/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LBB8H25 | TT_Task | COLD COMMISSIONING REHEAT SYSTEM (FOR CHEM. CLEANING) 20LBB | 18/04/2023 | 01/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BAC2-75 | TT_Mile | RFQ GEN. CIRCUIT BREAKER BAC | 07/05/2021 | 07/05/2021 | 07/05/2021 | 07/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--BAC2-80 | TT_Task | QUOTATION STAGE GEN. CIRCUIT BREAKER BAC | 07/05/2021 | 15/07/2021 | 07/05/2021 | 15/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP--CJP2-38 | TT_FinMile | GT PREL. INPUT FOR IC UNIT COORDINATION (incl. Final SREL) | 23/11/2021 | 23/11/2021 | 23/11/2021 | 23/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MB-9-05 | TT_Mile | 1ST. TURNING GEAR GT20 | 16/06/2023 | 16/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20QU-4-25 | TT_Task | TRANSPORT SAMPLING CONTAINER 20QU | 09/09/2022 | 03/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20CJ-8-25 | TT_Task | COMMISSIONING AUTOMATION SYSTEM 20UBA | 21/02/2023 | 06/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--SGM6-15 | TT_Task | ERECTION FIRE FIGHTING EXTINGUISHERS SGM | 09/09/2022 | 06/10/2022 |  |  | 360 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--ZTB4A25 | TT_Task | TRANSPORT PIPING FOR STEAM BLOWING SYSTEM ZTB | 07/01/2023 | 03/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--C--2C55 | TT_FinMile | (ICBB3) FINAL MEASUREMENT LIST, SIGNAL LIST AND BB INTERFACE SHEETS | 20/08/2021 | 20/08/2021 | 20/08/2021 | 20/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20SCA2-75 | TT_Task | CONTRACT REVIEW / PREP. RFQ AIR COMPRESSOR SYSTEM SCA | 19/02/2021 | 30/04/2021 | 19/02/2021 | 30/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMX5-45 | TT_FinMile | (RFE) FOUNDATION 20UMX-deleted | 01/11/2021 | 01/11/2021 | 01/11/2021 | 01/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMX5-15 | TT_Task | CONSTRUCTION FOUNDATION 20UMX-deleted | 01/11/2021 | 21/11/2021 | 01/11/2021 | 01/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20SAM8-10 | TT_FinMile | (TOP-20SAM70) HVAC SYSTEM FOR GENERATOR FOUNDATION | 24/05/2023 | 24/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP--MKC2-80 | TT_Task | ORDERING / NEGOTIATIONS SEE/SFC TRANSFORMER MKC / MBJ | 08/06/2021 | 28/07/2021 | 08/06/2021 | 28/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP--MKC2-75 | TT_Task | PREPARATION OF SPEC. / ORDER DOCU. SEE/SFC TRANSFORMER MKC / MBJ | 13/04/2021 | 07/06/2021 | 13/04/2021 | 07/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP--MKC2-85 | TT_Mile | CONTRACT INTO FORCE SEE/SFC TRANSFORMER MKC / MBJ | 29/07/2021 | 29/07/2021 | 29/07/2021 | 29/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BAW5A18 | TT_Task | ERECTION OUTDOOR EARTHING/LIGHTNING BOP AREA | 16/07/2022 | 23/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20GM-8B25 | TT_Task | COLD COMMISSIONING PLANT DRAINAGE SYSTEM GM FOR UBF | 14/02/2023 | 20/02/2023 |  |  | 72 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAJ6-40 | TT_FinMile | (RFP) READY FOR PIPE CONNECTION VACUUM PUMP UNIT MAJ | 07/07/2022 | 07/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAJ8-10 | TT_FinMile | (TOP-20MAJ) EVACUATION SYSTEM | 17/04/2023 | 17/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-76 | TT_FinMile | (RFE) FOUNDATION 20UTG07 | 15/06/2022 | 15/06/2022 |  |  | 112 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-6E27 | TT_Task | REMAINING INTERNAL INSULATION FOR INLET DUCT HRSG20 | 04/07/2022 | 24/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--2222-82 | TT_Task | QUOTATION STAGE ERECTION CONTRACTOR (E and IC) | 19/03/2021 | 09/07/2021 | 19/03/2021 | 09/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--2222-63 | TT_Task | PREPARATION RFQ DOCUMENTS FOR ERECTION CONTRACTOR (E and IC) | 15/01/2021 | 18/03/2021 | 15/01/2021 | 18/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--2222-87 | TT_Mile | CONTRACT INTO FORCE ERECTION CONTRACTOR (E and IC) | 03/12/2021 | 03/12/2021 | 03/12/2021 | 03/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--BZP4-25 | TT_Task | TRANSPORT CABLE SUPPORT SYSTEM BZP (LOT 1) | 26/03/2022 | 08/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP--MB-2A85 | TT_Mile | CONTRACT INTO FORCE INTERCONNECTING PIPING MB- | 30/10/2021 | 30/10/2021 | 30/10/2021 | 30/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20M--9-85 | TT_Task | RELIABILITY RUN COMBINED CYCLE POWER PLANT | 17/12/2023 | 31/12/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20M--9-90 | TT_Task | PERFORMANCE TEST COMBINED CYCLE POWER PLANT | 05/12/2023 | 16/12/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20XKA2-85 | TT_Mile | CONTRACT INTO FORCE EMERGENCY DIESEL GEN.SET XKA FUEL OIL TANK EG | 17/12/2021 | 17/12/2021 | 17/12/2021 | 17/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP--MB-2-12 | TT_FinMile | LIST OF CONTROL SETTINGS GT.-AUX. (SREL) (EIF) | 02/04/2021 | 02/04/2021 | 02/04/2021 | 02/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBX2C-50 | TT_Task | BASIC DESIGN CLADDING INCL. ARCHITECTUAL LAYOUT DWGS 10 - 20 UBX | 22/04/2022 | 12/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBV6-70 | TT_Task | PREPARATION FOR PIPE CLEANING SYSTEM (GT20) | 20/11/2022 | 10/12/2022 |  |  | 728 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEN2-70 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE 20UEN | 02/08/2021 | 15/09/2021 | 02/08/2021 | 15/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UEN2-50 | TT_Task | PREPARATION FOUNDATION GROUNDING DWGS 20UEN | 02/09/2021 | 15/09/2021 | 02/09/2021 | 15/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--HA-3E26 | TT_Task | BASIC / DETAIL DESIGN / ORDERING / DELIVERY / MANUFACTURING PIPING HRSG20_1st part (LB CARBON STEEL) | 28/01/2021 | 24/02/2022 | 28/01/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--PAC2B85 | TT_Mile | CONTRACT INTO FORCE CIRC. CW PUMP PAC | 09/04/2021 | 09/04/2021 | 09/04/2021 | 09/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20EK-8-25 | TT_Task | COLD COMMISSIONING FUEL GAS COMPONENTS FOR GT20 | 23/05/2023 | 19/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAT5B15 | TT_Task | INSTALLATION GRATING 20UBE/UBF | 20/08/2022 | 22/08/2022 |  |  | 1400 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAT7-15 | TT_Task | ERECTION GENERATOR TRANSFORMER 20BAT | 20/08/2022 | 23/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20L--6A80 | TT_Task | REMOVE PIPES (CHEMICAL CLEANING) 20 | 03/06/2023 | 30/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAV7-30 | TT_Task | CONSTR. POWER SUPPLY AVAIL. FOR LIFTING OIL SYSTEM 20MAV | 12/02/2023 | 25/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAV6-70 | TT_Task | PREPARATION FOR PIPE CLEANING SYSTEM (ST) | 19/11/2022 | 09/12/2022 |  |  | 48 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAV6-55 | TT_Task | LUBE OIL FLUSHING (INCL. PRESSURE TESTS) ST | 12/03/2023 | 01/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LAC8B10 | TT_FinMile | (TOP-20LAB) FEEDWATER SUPPLY SYSTEM | 14/04/2023 | 14/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PCB6H15 | TT_Task | ERECTION, NDT, PT / VALVES SERVICE COOL.WATER 20PCB | 14/08/2022 | 26/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SCA2-70 | TT_FinMile | (DF) IC INPUT (MEL) AIR COMPRESSOR SYSTEM SCA | 21/09/2021 | 21/09/2021 | 21/09/2021 | 21/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP--MKA2B41 | TT_Mile | METHOD OF MOUNTING GENERATOR ON FOUNDATION | 23/04/2021 | 23/04/2021 | 23/04/2021 | 23/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UEN2A75 | TT_FinMile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION 20UEN | 11/01/2022 | 11/01/2022 |  |  | 176 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MAW3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT (NORTH SEA PORT) GLAND STEAM CONDENSER 20MAW | 29/04/2022 | 29/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MAW3-25 | TT_Task | DESIGN / MANUFACTURING GLAND STEAM CONDENSER 20MAW | 31/07/2021 | 01/04/2022 | 31/07/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20BAA4-25 | TT_Task | TRANSPORT IPB IPB 20BAA | 05/07/2022 | 29/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-4B40 | TT_FinMile | (OTD-OS) ON SITE PIPING HRSG20_1st Part (LB CARBON STEEL) | 09/04/2022 | 09/04/2022 |  |  | 48 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--2222-51 | TT_Task | REVIEW CLIENT KKS PLANT LABELLING | 18/12/2021 | 11/01/2022 | 18/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--2222-50 | TT_Mile | KKS LISTING COMPLETE | 18/12/2021 | 18/12/2021 | 18/12/2021 | 18/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--2222-85 | TT_Mile | CONTRACT INTO FORCE KKS PLANT LABELLING | 23/02/2022 | 23/02/2022 |  |  | 1608 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--HA-2-75 | TT_Task | PREPARATION PROCESS DOCUMENTS FOR RFQ HRSG | 01/08/2020 | 04/09/2020 | 01/08/2020 | 04/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20SGE6E15 | TT_Task | ERECTION FIRE FIGHTING FOR TS AUXILIARY OIL SYSTEMS / H2 SYSTEMS SGC | 25/08/2022 | 19/10/2022 |  |  | 256 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGM6-15 | TT_Task | ERECTION FF INERTGAS SYSTEM IN UBA7110/7120/7410 SGM | 16/09/2022 | 29/09/2022 |  |  | 416 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LBG8A10 | TT_FinMile | (TOP-20LBG) AUXILIARY STEAM SYSTEM | 01/05/2023 | 01/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LCL6B40 | TT_FinMile | (RFP) READY FOR PIPE CONNECTION BOILER BLOWDOWN PUMP 20LCL | 29/07/2022 | 29/07/2022 |  |  | 656 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LCL6B15 | TT_Task | ERECTION STEAM BOILER BLOWDOWN PUMP 20LCL | 23/07/2022 | 19/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MB-6A15 | TT_Task | ERECTION, NDT, PT / VALVES 20MB (BOP) | 23/10/2022 | 31/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--HA-2-85 | TT_Mile | CONTRACT INTO FORCE HRSG | 27/01/2021 | 27/01/2021 | 27/01/2021 | 27/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BU-8-25 | TT_Task | COMMISSIONING DC SYSTEM 20BU/BRU | 14/02/2023 | 20/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAG6A15 | TT_Task | ERECTION, NDT, PT PIPES / VALVES MAG | 11/06/2022 | 25/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAG6-39 | TT_Task | CONNECTION AND WELDING OF REAR COVER MAG20 | 31/07/2022 | 06/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20GM-8F10 | TT_FinMile | (TOP-20GM-03) OIL WATER SEPARATOR AND DISCHARGE SYSTEM | 14/04/2023 | 14/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--CYA4-25 | TT_Task | TRANSPORT TELECOMMUNICATION CYA | 01/11/2022 | 30/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--CYA3-25 | TT_Task | MANUFACTURING / SHOP TEST TELECOMMUNICATION CYA | 30/04/2022 | 01/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BF-8-25 | TT_Task | FEEDER COMMISSIONING LV SWITCHGEAR BFF/BMF | 18/04/2023 | 05/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MBR3A80 | TT_FinMile | (RFS) READY FOR SHIPMENT DIFFUSER 20MBR | 22/03/2022 | 22/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--HA-2-14 | TT_FinMile | PROJECT SPECIFICATION HRSG (BLACK BOXES, MOTORS) SPEC. | 07/10/2020 | 07/10/2020 | 07/10/2020 | 07/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UVM2-75 | TT_FinMile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION 20UVM01 | 31/03/2022 | 31/03/2022 |  |  | 384 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2-5 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UBA1110/20 | 23/06/2021 | 23/06/2021 | 23/06/2021 | 23/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20LCL2B85 | TT_Mile | CONTRACT INTO FORCE BOILER BLOWDOWN PUMP LCL | 03/05/2021 | 03/05/2021 | 03/05/2021 | 03/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MKC8-75 | TT_Mile | ENERGISATION SEE TRANSFORMER 20MKC01 | 09/06/2023 | 09/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20M--8-25 | TT_Task | COLD COMMISSIONING SEE TRANSFORMER 20MKC01 | 14/03/2023 | 20/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKA3-85 | TT_Mile | RECEIPT OF GENERATOR CASING IN FACTORY FOR 20MKA | 26/10/2021 | 26/10/2021 | 26/10/2021 | 26/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBX5B15 | TT_Task | ERECTION STEEL STRUCTURE 20UBX/20UBG | 22/07/2022 | 04/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC2B-50 | TT_FinMile | (OTD-OS) ON SITE TURBOSET EMBEDDED PARTS MA- (UMC) | 15/09/2021 | 15/09/2021 | 15/09/2021 | 15/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC2B-45 | TT_Task | TRANSPORT TURBOSET EMBEDDED PARTS MA- POE TO SITE (UMC) | 14/07/2021 | 07/09/2021 | 14/07/2021 | 07/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MKA4-25 | TT_Task | TRANSPORT GEN. 20MKA | 30/04/2022 | 23/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20CJT4-25 | TT_Task | TRANSPORT SFC CUBICLES 20CJT TO WORKSHOP | 22/02/2022 | 23/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY2-50 | TT_Task | PREPARATION FOUNDATION GROUNDING DWGS 20UEY03-05 | 27/08/2021 | 05/12/2021 | 27/08/2021 | 05/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20GHD6I15 | TT_Task | ERECTION / PT PIPES GHD FOR UGD IN UMC | 11/08/2022 | 12/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20GHD6H15 | TT_Task | PRE-ERECTION / PT PIPES GHD FOR UGD TO UMC | 21/07/2022 | 10/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAT3-25 | TT_Task | DETAIL DESIGN / MANUFACTURING / SHOP TEST MAIN TRANSFORMERS 20BAT | 05/05/2021 | 15/06/2022 | 05/05/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20BAT8-25 | TT_Task | COMMISSIONING MAIN TRANSFORMER 20BAT | 21/02/2023 | 06/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--M--2A20 | TT_FinMile | PLANT LAYOUT DRAWING (FINAL) | 28/01/2021 | 28/01/2021 | 28/01/2021 | 28/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20LCA8M10 | TT_FinMile | (TOP-20LCA) MAIN CONDENSATE SUPPLY AND PREHEATING SYSTEM | 28/04/2023 | 28/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LCA6M40 | TT_FinMile | (RFP) READY FOR PIPE CONNECTION CONDENS. RECIRCULATING PUMP LCA51 | 01/06/2022 | 01/06/2022 |  |  | 672 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAN6H15 | TT_Task | ERECTION, NDT, PT PIPES / VALVES MAN | 25/11/2022 | 02/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BZK2-82 | TT_Task | PREPARATION OF FINAL LENGTH MATRIX | 16/05/2021 | 14/07/2021 | 16/05/2021 | 14/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--BZK2-81 | TT_Mile | FINAL LENGTH MATRIX AVAILABLE | 15/07/2021 | 15/07/2021 | 15/07/2021 | 15/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBD5-11 | TT_Mile | (H) START PLACING FORMWORK 20UBD03/04 | 13/05/2022 | 13/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBD5-58 | TT_FinMile | (RFE) FOUNDATION 20UBD03/04 | 09/06/2022 | 09/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PGB8-10 | TT_FinMile | (TOP-20PGB) CLOSED COOLING WATER SYSTEM | 17/04/2023 | 17/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBD5-55 | TT_Task | WORK PREPARATION / EXCAVATION FOUNDATION 20UBD03/04 | 06/05/2022 | 12/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5A10 | TT_Mile | (H) START PLACING FORMWORK TS FOUND. 20UMC | 12/08/2021 | 12/08/2021 | 12/08/2021 | 12/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5A45 | TT_FinMile | (RFE) TURBOSET FOUNDATION READY 20UMC | 29/01/2022 | 29/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-8-05 | TT_Mile | 1ST. TURNING GEAR ST | 20/06/2023 | 20/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20QC-2-40 | TT_FinMile | (DF) PID's DOSING CONTAINER AVAILABLE QC | 22/04/2021 | 22/04/2021 | 22/04/2021 | 22/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MBL2-80 | TT_Task | PREPARE TEC RFQ DOC AIR INTAKE SYSTEM MBL | 01/03/2021 | 21/03/2021 | 01/03/2021 | 21/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20M--6-04 | TT_Mile | REFERENCE POINTS ON FOUNDATION CENTRE LINE AVAILABLE (BY OFFICIAL GEOMETER) | 30/01/2022 | 30/01/2022 |  |  | 816 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--SA-2-10 | TT_FinMile | (DF) HEAT LOADS AVAILABLE FOR HVAC-SYSTEM SA | 12/02/2021 | 12/02/2021 | 12/02/2021 | 12/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--HA-2-65 | TT_FinMile | (DF) PROCESS FINAL HRSG SYSTEMS | 22/04/2021 | 22/04/2021 | 22/04/2021 | 22/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--3332-02 | TT_Task | KICK OFF PROCESS ENGINEERING | 01/08/2020 | 28/08/2020 | 01/08/2020 | 28/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MA-8-10 | TT_FinMile | (TOP-20MA) STEAM TURBINE | 17/04/2023 | 17/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MB-4-40 | TT_FinMile | (OTD-OS) ON SITE GAS TURBINE 20MB- | 23/07/2022 | 23/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LDK8B25 | TT_Task | COLD COMMISSIONING CONDENSATE POLISHING PLANT (FOR BENSON BOILER) | 29/03/2023 | 02/05/2023 |  |  | 80 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MBL2-81 | TT_Task | QUOTATION STAGE AIR INTAKE SYSTEM MBL | 22/03/2021 | 02/05/2021 | 22/03/2021 | 02/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2-50 | TT_Task | PREPARATION FOUNDATION GROUNDING DWGS UBA7xxx | 14/07/2021 | 27/07/2021 | 14/07/2021 | 27/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP--MB-2B40 | TT_FinMile | WIRING DIAGRAMS GT-AUX. (EIF) | 01/04/2021 | 01/04/2021 | 01/04/2021 | 01/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP--MB-2D40 | TT_FinMile | WIRING DIAGRAMS GTGT-AUX. (STANDARD VALUES, SYSTEM SPECIFIC) | 01/04/2021 | 01/04/2021 | 01/04/2021 | 01/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--2222-24 | TT_Task | REVISION OF OPERATING MANUAL (BHB) ON SITE | 09/10/2023 | 07/12/2023 |  |  | 192 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--HB-2A60 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE HRSG | 11/02/2021 | 11/02/2021 | 11/02/2021 | 11/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--M--2C00 | TT_Mile | LAYOUT DOCUMENTS [initial] | 02/04/2021 | 02/04/2021 | 02/04/2021 | 02/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MPB7E81 | TT_Task | ELECTRICAL ERECTION WORK FOR GT ENCLOSURE 20MPB / SAM | 08/12/2022 | 21/12/2022 |  |  | 1232 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-6-41 | TT_Task | PRE-ASSEMBLY STACK INCL. INSULATION / SEC. STEEL HRSG20_1st/2nd part | 30/04/2022 | 03/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--CYA3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT TELECOMMUNICATION CYA | 31/10/2022 | 31/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--CYA8-25 | TT_Task | COMMISSIONING TELECOMMUNICATION ENTIRE PLANT | 27/05/2023 | 16/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAH4-25 | TT_Task | TRANSPORT TO SKIDDER CONDENSER TUBE CLEANING SYSTEM (BALL STRAINER) 20PAH | 12/01/2022 | 08/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LCA6A15 | TT_Task | ERECTION, NDT, PT PIPES / VALVES 20LCA | 25/08/2022 | 17/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y15 | TT_Task | WORK PREPARATION CEP/LDK PIT 20UMC | 23/07/2021 | 15/08/2021 | 23/07/2021 | 15/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MAX6H15 | TT_Task | ERECTION, NDT, PT PIPES / VALVES MAX | 06/01/2023 | 09/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGJ6A15 | TT_Task | ERECTION ECONOPAC FIRE PROTECTION / GAS DETECTION SYSTEM 20CYE/CYQ/SGJ | 22/01/2023 | 18/02/2023 |  |  | 536 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LBA6J70 | TT_Task | PT, RE-INSTALLATION PIPES / VALVES 11LBA80 (TURBOSET) | 03/02/2023 | 16/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MKA3B25 | TT_Task | MANUFACTURING GENERATOR SKIDS 20MKA | 20/08/2021 | 01/04/2022 | 20/08/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--UHA2-70 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE UHA | 31/05/2021 | 29/07/2021 | 31/05/2021 | 29/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MKA6-12 | TT_Mile | PLACING GENERATOR ON FOUNDATION 20MKA | 26/07/2022 | 26/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAA3-25 | TT_Task | DETAIL DESIGN / MANUFACTURING COOLING TOWER COARSE SCREEN 20PAA (MPA) | 29/09/2021 | 31/05/2022 | 29/09/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20PAA3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT READY FOR SHIPMENT COOLING TOWER COARSE SCREEN 20PAA | 28/06/2022 | 28/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAH2-65 | TT_FinMile | (DF) INPUT FOR M2 CONDENSER TUBE CLEANING SYSTEM 20PAH | 19/05/2021 | 19/05/2021 | 19/05/2021 | 19/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20XKA3-25 | TT_Task | DETAIL DESIGN / MANUFACTURING / SHOP TEST EMERGENCY DIESEL GEN.SET XKA | 17/12/2021 | 15/06/2022 | 17/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20XKA2-60 | TT_FinMile | (DF) INPUT FOR MS3 EMERGENCY DIESEL GEN.SET XKA | 17/12/2021 | 17/12/2021 | 17/12/2021 | 17/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20QJ-4B40 | TT_FinMile | (OTD-OS) ON SITE CENTRAL GAS SUPPLY (H2,CO2) QJ_ | 24/08/2022 | 24/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--GM-3B80 | TT_FinMile | (RFS) READY FOR SHIPMENT SUMP PUMP GM | 12/05/2022 | 12/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6C11 | TT_Task | SET DOWN K-TURBINE ON BEARINGS AND PROVISIONALLY ALIGNMENT MA | 04/08/2022 | 05/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BZP3-25 | TT_Task | MANUFACTURING / SHOP TEST CABLE SUPPORT SYSTEM BZP (LOT 1) | 15/01/2022 | 11/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAJ6-15 | TT_Task | ERECTION VACUUM PUMP UNIT MAJ | 01/07/2022 | 14/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBX5E45 | TT_FinMile | (RFE) ROOF DECKING 20UBX | 08/09/2022 | 08/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBD5-45 | TT_FinMile | (RFE) FOUNDATION 20UBD01/02 | 27/05/2022 | 27/05/2022 |  |  | 120 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20GM-6H19 | TT_Task | ERECTION PIPES STORM SYSTEM 00GM | 28/07/2022 | 07/09/2022 |  |  | 1752 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK7F25 | TT_Task | CABLING 20UBA (10x) to 20UEN AND DOSING | 05/02/2023 | 25/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAA7A15 | TT_Task | ELECTRICAL ERECTION PIPES / VALVES MAA-C | 24/11/2022 | 14/12/2022 |  |  | 32 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--2222-34 | TT_Mile | COMMISSIONING MANUAL - AUXILIARY SYSTEMS CYCLE | 22/04/2023 | 22/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAH2E60 | TT_FinMile | (DF) INPUT FOR MS3 STEEL PLATFORMS CONDENSER TUBE CLEANING SYSTEM PAH | 28/06/2021 | 28/06/2021 | 28/06/2021 | 28/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20CPA8A25 | TT_Task | IC FIELD COMMISSIONING GT20 | 28/02/2023 | 01/05/2023 |  |  | 296 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--3331-36 | TT_FinMile | TRANSPORT STUDY FOR HEAVY COMPONENTS | 15/04/2021 | 15/04/2021 | 15/04/2021 | 15/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--3331-34 | TT_Mile | TCC PACKING AND DISPATCH GUIDELINE FOR HRSG PHASE 1 AVAILABLE | 05/12/2020 | 05/12/2020 | 05/12/2020 | 05/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--3331-32 | TT_Mile | PROJECT SPECIFIC GENERAL TCCs AVAILABLE | 10/01/2021 | 10/01/2021 | 10/01/2021 | 10/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7-50 | TT_Task | ERECTION CABLE TRAYS BELOW ELECTRICAL MODULES 20UBA7920/7910 | 17/06/2022 | 23/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7-100 | TT_Task | ERECTION CABLE TRAYS 20UMC GT AREA | 29/09/2022 | 12/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI---5P2A10 | TT_FinMile | LAST SUPPLIER INPUT GROUPV (ZTB,ZTM-MAV,ZTM-MAW,ZTE/ZTP) | 31/08/2021 | 31/08/2021 | 31/08/2021 | 31/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20LBG6A17 | TT_Task | ERECTION, NDT, PT PIPES / VALVES 20LBG | 20/05/2022 | 28/07/2022 |  |  | 968 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LBG6A47 | TT_Task | INSULATION PIPES / VALVES FOR STEAM SYSTEM 20LBG | 27/11/2022 | 24/12/2022 |  |  | 912 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5C55 | TT_FinMile | (RFE) BUILDING CLOSED 20UMC | 20/07/2022 | 20/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5C15 | TT_Task | WALL AND ROOF CLADDING FINISHING WORKS 20UMC | 21/07/2022 | 24/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MB-2-80 | TT_Task | PREPARE TEC RFQ DOC GT ACCESSORY EQUIPMENT / CCR / IN-LINE COMPONENTS GT-PIPING MB | 31/07/2021 | 15/10/2021 | 31/07/2021 | 15/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MBV4A25 | TT_Mile | SUPPLY LUBE OIL FOR OIL FLUSHING 20MBV | 20/11/2022 | 20/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--UBH2-61 | TT_FinMile | PLANT DESIGN INPUT FOR 20UBH01/02 | 29/01/2021 | 29/01/2021 | 29/01/2021 | 29/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UBA2-60 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE UBA7910/7920 | 23/06/2021 | 23/06/2021 | 23/06/2021 | 23/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UBA2G80 | TT_Task | QUOTATION STAGE ELECTRICAL MODULES UBA | 01/03/2021 | 18/05/2021 | 01/03/2021 | 18/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--CHY2-85 | TT_Mile | CONTRACT INTO FORCE PROT./SYNCHR./METERING CHA/CHY | 09/09/2021 | 09/09/2021 | 09/09/2021 | 09/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP--B--2-52 | TT_FinMile | FINAL ELECTRICAL LOAD DATA (VEL) FOR LV (ECONOPAC) | 01/07/2021 | 01/07/2021 | 01/07/2021 | 01/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP--B--2-18 | TT_Mile | PROKABEL PLANT REPORT TO IC | 06/07/2021 | 06/07/2021 | 06/07/2021 | 06/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP--B--2-12 | TT_Task | PREPARATION OF CMI`s INTERLOCKING DIAGRAMS | 04/05/2021 | 05/07/2021 | 04/05/2021 | 05/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URD5-45 | TT_Mile | (RFE) FOR MECHANICAL AND ELECTRICAL ERECTION 20URD | 05/04/2022 | 05/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20XKA4-40 | TT_FinMile | (OTD-OS) ON SITE EMERGENCY DIESEL GEN.SET XKA | 07/09/2022 | 07/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5B12 | TT_Mile | (HS) START ERECTION STEEL STRUCTURE 20UBA8110/20 | 11/11/2022 | 11/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA3B27 | TT_Task | FABRICATION DESIGN FABRICATION TRANSPORT STEEL STRUCTURE 20UBA8110/20 | 15/03/2022 | 20/06/2022 |  |  | 1144 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MB-9-15 | TT_Mile | 1ST. IGNITION GT20 | 01/07/2023 | 01/07/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--HA-2-92 | TT_FinMile | (DF) THERMODYNAMIC FOR HRSG / FINALIZATION HBDs FOR ALL CASES | 11/12/2020 | 11/12/2020 | 11/12/2020 | 11/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20HB-4C40 | TT_FinMile | (OTD-OS) ON SITE SECONDARY STEEL STRUCTURE HRSG20_Last Part | 29/04/2022 | 29/04/2022 |  |  | 784 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-3C80 | TT_FinMile | (RFS) READY FOR SHIPMENT HRSG20 SECONDARY STEEL STRUCTURE HRSG20_Last Part | 28/02/2022 | 28/02/2022 |  |  | 240 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-6-42 | TT_Task | ERECTION STACK DAMPER HRSG20 | 25/06/2022 | 03/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAW5C21 | TT_Task | ERECTION LIGHTNING PROTECTION BOP | 26/09/2022 | 23/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAW5C22 | TT_Task | ERECTION LIGHTNING PROTECTION COOLING TOWER AREA (20URA/URD/UBA8110/20/UBD03/04) | 23/03/2023 | 23/05/2023 |  |  | 320 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20CPD8-36 | TT_Task | COMMISSIONING ET200 STATIONS AUXILIARY/ANCILLIARY CPD (BAT) | 28/02/2023 | 13/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20CPD8-37 | TT_Task | IC FIELD COMMISSIONING AUX. POWER (BAT) | 14/03/2023 | 27/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--EK-2-80 | TT_Task | QUOTATION STAGE GAS FINAL FILTER/ PREHEATER 20EKG | 26/03/2021 | 27/06/2021 | 26/03/2021 | 27/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--BFT2-85 | TT_Mile | CONTRACT INTO FORCE LV-TRANSFORMERS BFT | 22/09/2021 | 22/09/2021 | 22/09/2021 | 22/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MBL7-25 | TT_Task | E- AND IC- ERECTION AIR INTAKE SYSTEM 20MBL | 11/12/2022 | 07/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBL6-05 | TT_Task | PLACING GT AIR INTAKE LOWER PART 20MBL | 04/07/2022 | 06/07/2022 |  |  | 224 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAJ4-40 | TT_FinMile | (OTD-OS) ON SITE AIR REMOVAL SYSTEM 20MAJ | 09/05/2022 | 09/05/2022 |  |  | 168 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--L--2-28 | TT_Task | DATA MANAGEMENT L- SYSTEMS | 05/05/2021 | 06/07/2021 | 05/05/2021 | 06/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAH2-85 | TT_Mile | CONTRACT INTO FORCE CONDENSER TUBE CLEANING SYSTEM 20PAH | 15/05/2021 | 15/05/2021 | 15/05/2021 | 15/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20SGJ4-25 | TT_Task | TRANSPORT FF SYSTEM CO2 / GAS DETECTION 20SGJ/CYQ | 26/02/2022 | 22/04/2022 |  |  | 1168 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--2222-71 | TT_Mile | HRSG NOISE PROTECTION DATA AVAILABLE | 19/02/2021 | 19/02/2021 | 19/02/2021 | 19/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--CP-4-25 | TT_Task | TRANSPORT BOP IC FIELD CABINETS | 04/08/2022 | 28/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20GHD8A35 | TT_Task | FINAL COLD COMMISSIONING SERVICE WATER DISTRIBUTION SYSTEM GHD | 30/04/2023 | 04/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKA8-10 | TT_FinMile | (TOP-20MKA) GENERATOR SYSTEM | 24/04/2023 | 24/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20ULA5-10 | TT_Mile | (H) START PLACING FORMWORK 20ULA | 12/10/2021 | 12/10/2021 | 12/10/2021 | 12/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHX5-45 | TT_FinMile | (RFE) FOUNDATION 20UHX | 02/05/2022 | 02/05/2022 |  |  | 1592 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UHX5-10 | TT_Mile | (H) START PLACING FORMWORK 20UHX | 13/04/2022 | 13/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UHX5-05 | TT_Task | WORK PREPARATION, EXCAVATION 20UHX | 06/04/2022 | 12/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20QC-6H17 | TT_Task | ERECTION, NDT, PT / VALVES DOSING 20QC | 20/01/2023 | 16/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6A12 | TT_Task | ASSEMBLY OF TEMPORARY/FINAL HP/IP-VALVE SUPPORTS (OPTIONAL) | 05/08/2022 | 11/08/2022 |  |  | 40 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6A35 | TT_Mile | HP-VALVE READY FOR PRE-ASSEMBLING LBA10- PIPING | 24/08/2022 | 24/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6A11 | TT_Mile | BYPASS VALVES READY FOR PRE-ASSEMBLING LBA80/LBB-PIPING | 05/08/2022 | 05/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK7A27 | TT_Task | CABLING (E AND IC CABLES) GENERATOR 20 | 01/10/2022 | 28/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKA6-37 | TT_Mile | FINAL ALIGNMENT ROTOR ST20/GEN20 COMPLETE 20MKA | 16/01/2023 | 16/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBQ6H15 | TT_Task | ERECTION, NDT, PT / VALVES IGN. GAS PIPES 20MBQ | 01/01/2023 | 04/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--CYA2-15 | TT_Task | BASIC DESIGN / SPECIFICATION / PLANTLAYOUT DWGS BOQ TELECOMMUNICATION CYA | 12/09/2021 | 04/12/2021 | 12/09/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--CYA8-70 | TT_FinMile | (CCC) TELECOMMUNICATION ENTIRE PLANT | 16/06/2023 | 16/06/2023 |  |  | 112 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--CYA7A15 | TT_Task | ERECTION TELECOMMUNICATION OTHER BUILDINGS (EXCEPT UMC) | 23/02/2023 | 19/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGC8E10 | TT_FinMile | (TOP-20SGC-02) FF SPRAY DELUGE SYSTEMS FOR TS AUXILIARY OIL SYSTEMS / H2 SYSTEMS SGC | 17/04/2023 | 17/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20S--8-25 | TT_Task | COLD COMMISSIONING HVAC SYSTEM FOR 20UMC SAM | 11/04/2023 | 01/05/2023 |  |  | 256 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SAM8-11 | TT_FinMile | (TOP-20SAM10) HVAC SYSTEM FOR UMC BUILDING | 10/04/2023 | 10/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC3B25 | TT_Task | FABRICATION DESIGN/FABRICATION/TRANSPORT STEEL STRUCTURE 20UMC | 12/08/2021 | 28/01/2022 | 12/08/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UBF5E45 | TT_FinMile | (RFE) WALLS READY 20UBE/UBF | 11/05/2022 | 11/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKA8-70 | TT_Task | PREPARATION FOR VENTILATION TEST (COMM. DEPT.) MKA | 30/06/2023 | 02/07/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKA8-74 | TT_Task | INSPECTION AFTER VENTILATION TEST (COMM. DEPT.) MKA | 10/07/2023 | 13/07/2023 |  |  | 144 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKA8-72 | TT_Task | VENTILATION TEST AT 3000 rpm (COMM. DEPT.) -after first ignition- MKA | 03/07/2023 | 04/07/2023 |  |  | 40 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20--P6-73 | TT_Task | PREPARATION CHEMICAL CLEANING HRSG20 | 15/04/2023 | 12/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20CFE4-40 | TT_FinMile | (OTD-OS) ON SITE EMISSION MONITORING SYSTEM 20CFE | 29/06/2022 | 29/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20CFE8-35 | TT_Task | COMMISSIONING CONTINIOUS EMISSION MONITORING SYSTEM (2) (CALIBRATION) HRSG20 | 11/07/2023 | 17/07/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP--SGJ2-55 | TT_Mile | FINAL ELECTRICAL LOAD DATA (VEL) FIRE FIGHTING / GAS DETECTION SGJ / CYQ / CYE | 18/06/2021 | 18/06/2021 | 18/06/2021 | 18/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP--SGJ2-03 | TT_Mile | PI DIAGRAM FIRE FIGHTING / GAS DETECTION SGJ / CYQ / CYE | 18/06/2021 | 18/06/2021 | 18/06/2021 | 18/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MB-4G40 | TT_FinMile | (OTD-OS) ON SITE GT INSULATION MB- | 23/07/2022 | 23/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBA4G25 | TT_Task | TRANSPORT GT INSULATION MB- | 23/04/2022 | 17/06/2022 |  |  | 288 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--EK-2-89 | TT_FinMile | (DF) INPUT FOR MS3 FUEL GAS RECEIVING AND MIXING SYSTEM EK | 01/08/2021 | 01/08/2021 | 01/08/2021 | 01/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAA2-85 | TT_Mile | CONTRACT INTO FORCE COOLING TOWER COARSE SCREEN 20PAA (MPA) | 29/09/2021 | 29/09/2021 | 29/09/2021 | 29/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--LBF2B85 | TT_Mile | CONTRACT INTO FORCE BYPASS STATION 20LBF | 27/01/2021 | 27/01/2021 | 27/01/2021 | 27/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--LBF2B80 | TT_Task | QUOTATION STAGE BYPASS STATION 20LBF | 30/12/2020 | 26/01/2021 | 30/12/2020 | 26/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--LBF2B75 | TT_Task | CONTRACT REVIEW, PREPARATION RFQ BYPASS STATION 20LBF | 02/12/2020 | 29/12/2020 | 02/12/2020 | 29/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5-60 | TT_FinMile | (RFE) FOUNDATION 20UBA1110/20 | 15/05/2022 | 15/05/2022 |  |  | 1432 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SMM4-25 | TT_Task | TRANSPORT CRANE SMM01/02/03 FOR 20UMC | 03/02/2022 | 30/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SMM3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT CRANE SMM01/02/03 FOR 20UMC | 02/02/2022 | 02/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SMM6-70 | TT_Mile | (CCC) CRANE 20SMM01/02 IN SERVICE 20UMC | 07/05/2022 | 07/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B85 | TT_Mile | (H) START PLACING FORMWORK BUILD.FOUNDATION 20UMC | 18/11/2021 | 18/11/2021 | 18/11/2021 | 18/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-105 | TT_Task | BACKFILLING OF SHEET PILE PIPING SYSTEM (OUTSIDE) PAB UMC - URD | 08/01/2022 | 08/02/2022 |  |  | 248 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAW5C17 | TT_Task | ERECTION OUTDOOR EARTHING/LIGHTNING 20URA/URD AREA | 19/06/2022 | 26/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BAW8A10 | TT_FinMile | (TOP-20BAW-01) PLANT EARTHING GRID FOR BACK-ENERGISING | 19/03/2023 | 19/03/2023 |  |  | 120 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--L--2-45 | TT_Mile | DESIGN DATA SHEETS FOR ALL L-COMPONENTS AVAILABLE | 07/02/2021 | 07/02/2021 | 07/02/2021 | 07/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--L--2-35 | TT_Task | DESIGN DATA SHEETS L-COMPONENTS | 29/11/2020 | 06/02/2021 | 29/11/2020 | 06/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UVM5-45 | TT_FinMile | (RFE) FOUNDATION 20UVM01 | 16/06/2022 | 16/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20QU-2-40 | TT_FinMile | (DF) PID'S SAMPLING CONTAINER 20QU | 22/04/2021 | 22/04/2021 | 22/04/2021 | 22/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BBA4-10 | TT_Task | TRANSPORT TO WORKSHOP MV SWITCHGEAR 20/01BBA/BBB (TO ST. INGBERT-INSTALL INTO ELECTRICAL MODULES) | 22/01/2022 | 23/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MB-6-15 | TT_Task | ERECTION GT AUXILIARIES 20MB- | 25/08/2022 | 19/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBV8-10 | TT_FinMile | (TOP-20MBV) GT LUBE OIL / LIFTING OIL SYSTEM | 26/04/2023 | 26/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LBB6J17 | TT_Task | ERECTION, NDT PIPE / VALVES 20LBB-LBC80 | 09/12/2022 | 19/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LBB8J11 | TT_FinMile | (TOP-20LBB) REHEATING STEAM SYSTEM | 17/04/2023 | 17/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBA2D65 | TT_FinMile | (DF) INPUT FOR M2 WASH WATER TANK 20MBA | 18/06/2021 | 18/06/2021 | 18/06/2021 | 18/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20LCL2B80 | TT_Task | QUOTATION STAGE BOILER BLOWDOWN PUMP LCL | 23/02/2021 | 02/05/2021 | 23/02/2021 | 02/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PGB6M40 | TT_FinMile | (RFP) READY FOR PIPE CONNECTION CLOSED COOLING WATER PUMP PGB | 10/06/2022 | 10/06/2022 |  |  | 400 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKW6-57 | TT_Task | FINAL ERECTION MKW PIPING AFTER OIL FLUSHING MKW | 02/04/2023 | 08/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKW6H15 | TT_Task | PIPING ERECTION SEAL OIL SYSTEM FOR GENERATOR 20MKW | 28/08/2022 | 22/10/2022 |  |  | 1344 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKW8-10 | TT_FinMile | (TOP-20MKW) GT GENERATOR SEAL OIL SUPPLY SYSTEM | 08/04/2023 | 08/04/2023 |  |  | 480 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKW6-15 | TT_Task | ERECTION SEAL OIL SYSTEM 20MKW | 07/08/2022 | 27/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LBB7J17 | TT_Task | ELECTRICAL ERECTION / VALVES 20LBB-LBC80 | 17/03/2023 | 23/03/2023 |  |  | 200 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--CHY2-80 | TT_Task | QUOTATION STAGE PPROT./SYNCHR./METERING CHA/CHY | 23/06/2021 | 08/09/2021 | 23/06/2021 | 08/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UCA7-15 | TT_Task | ERECTION CONTROL ROOM CCR FURNITURE AND HMI EQUIPMENT UCA | 28/06/2022 | 11/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20CR-8-25 | TT_Task | COMMISSIONING CONTROL ROOM EQUIPMENT | 21/02/2023 | 06/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--C--2-85 | TT_Mile | CONTRACT INTO FORCE BOP IC | 09/04/2021 | 09/04/2021 | 09/04/2021 | 09/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--2222-33 | TT_Mile | COMMISSIONING MANUAL - ST / GENERATOR / COND. | 06/01/2023 | 06/01/2023 |  |  | 816 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20EK-6-40 | TT_FinMile | (RFP) READY FOR PIPE CONNECTION GAS SYSTEM 20EKG | 28/01/2023 | 28/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BAW4-40 | TT_FinMile | (OTD-OS) ON SITE MATERIAL IN- / OUTDOOR GROUNDING BAW | 18/06/2022 | 18/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HAD8F25 | TT_Task | COLD COMMISSIONING HRSG IP STEAM (FOR CHEM. CLEANING) 20HAD50 | 29/04/2023 | 12/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-230 | TT_Mile | TP-I12 - EXISTING STATION DCIS PANEL (00UCA) | 30/06/2022 | 30/06/2022 |  |  | 2056 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAD6-70 | TT_FinMile | BEARING CASINGS READY FOR OPERATION | 01/04/2023 | 01/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20CJ-8-10 | TT_FinMile | (TOP-20CJ) AUTOMATION SYSTEM 20CJ | 21/02/2023 | 21/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAA7-56 | TT_Task | CLOSING BUSDUCT AND LEAKAGE TEST 20BAA | 06/01/2023 | 12/01/2023 |  |  | 368 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD8-10 | TT_FinMile | (TOP-20PAD) WET CELL HYBRID COOLING TOWER | 17/05/2023 | 17/05/2023 |  |  | 16 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LCB6B41 | TT_FinMile | (RFP) READY FOR PIPE CONNECTION CONDENSATE EXTRACTION PUMP 20LCB | 05/08/2022 | 05/08/2022 |  |  | 152 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LCB6B10 | TT_Task | PLACING CONDENSATE EXTRACTION PUMP 20LCB | 28/07/2022 | 29/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAN6-15 | TT_Task | INSTALLATION BYPASS-STATION MAN (incl. VALVES AND PIPES) Umleitdampfeinf�hrung | 22/07/2022 | 04/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6A55 | TT_Task | INSTALLATION ALL VALVE ACTUATORS FOR MAIN STEAM, REHEAT STOP AND CONTROL VALVES | 31/08/2022 | 27/09/2022 |  |  | 304 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6A25 | TT_Mile | IP-VALVE READY FOR PRE-ASSEMBLING LBB-PIPING | 31/08/2022 | 31/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6A60 | TT_Mile | LBC-FLAP READY FOR PRE-ASSEMBLING LBC-PIPING | 24/08/2022 | 24/08/2022 |  |  | 56 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAX6A65 | TT_Mile | ALL VALVES READY FOR PRE-ASSEMBLING MAX-PIPING | 05/11/2022 | 05/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--ULA2-70 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE 20ULA | 19/05/2021 | 02/07/2021 | 19/05/2021 | 02/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--ULA2-75 | TT_FinMile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION 20ULA | 07/09/2021 | 07/09/2021 | 07/09/2021 | 07/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--B--2-04 | TT_FinMile | PROJECT SPECIFIC BASIC ELECTRICAL REQUIREMENTS (LIGHTING/ GROUNDING/ CABLING) FOR HRSG | 28/01/2021 | 28/01/2021 | 28/01/2021 | 28/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MKA3-80 | TT_Mile | (RFS-FAS) READY FOR SHIPMENT GEN. 20MKA | 30/04/2022 | 30/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SG-3-25 | TT_Task | DETAIL DESIGN / MANUFACTURING FIRE FIGHTING SYSTEMS 20SGC/SGE/SGF/SGJ | 10/09/2021 | 24/02/2022 | 10/09/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SP20CJP3A25 | TT_Task | MANUFACTURING GT IC CABINETS | 21/08/2021 | 28/12/2021 | 21/08/2021 | 28/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20CJP3A10 | TT_Task | TRANSPORT GT IC CABINETS CJ-/CPA TO ELECTRICAL MODULES MANUFACTURER | 29/12/2021 | 03/01/2022 | 29/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SP20MAD3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT (NORTH SEA PORT) ST BEARINGS 20MAD | 07/04/2022 | 07/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--2222-21 | TT_Mile | INPUTS FOR OPERATING MANUAL (BHB) | 11/02/2023 | 11/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--1102-10 | TT_Mile | PRELIMINARY OM DOCUMENTATION | 18/03/2023 | 18/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--2222-70 | TT_Task | NOISE PROTECTION CONCEPT | 17/01/2021 | 27/02/2021 | 17/01/2021 | 27/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--3331-61 | TT_Mile | SITE REGULATIONS (FINAL) AVAILABLE | 15/08/2020 | 15/08/2020 | 15/08/2020 | 15/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20SMG3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT OTHER CRANES AND HOIST | 04/08/2022 | 04/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SMG2-85 | TT_Mile | CONTRACT INTO FORCE OTHER CRANES AND HOIST | 18/02/2022 | 18/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SMG4-40 | TT_FinMile | (OTD-OS) ON SITE OTHER CRANES AND HOIST | 29/09/2022 | 29/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAB6A15 | TT_Task | ERECTION, NDT, PT / VALVES (MECHANICAL) 20PAB UMC | 14/08/2022 | 10/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--3332-17 | TT_FinMile | INPUT FOR EL.SPECS. (BLACK BOXES, MOTORS) AVAILABLE | 21/01/2021 | 21/01/2021 | 21/01/2021 | 21/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--P--2-35 | TT_Task | DESIGN DATA SHEETS P-COMPONENTS | 03/11/2020 | 02/03/2021 | 03/11/2020 | 02/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--P--2-45 | TT_FinMile | DESIGN DATA SHEETS FOR ALL P-COMPONENTS AVAILABLE | 03/03/2021 | 03/03/2021 | 03/03/2021 | 03/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--G--2I45 | TT_Mile | DESIGN DATA SHEETS SAFETY VALVES GHC SYSTEM | 14/05/2021 | 14/05/2021 | 14/05/2021 | 14/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20ZTB6A00 | TT_Task | TEMPORARY PIPE INSTALLATION FOR STEAM BLOWING ZTB | 22/04/2023 | 12/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20ZTA6A00 | TT_Task | TEMPORARY PIPE INSTALLATION FOR CHEMICAL CLEANING ZTA | 01/04/2023 | 12/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAW6H45 | TT_Task | INSULATION PIPES / VALVES FOR STEAM SYSTEM MAW | 12/02/2023 | 18/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAW6H15 | TT_Task | ERECTION, NDT, PT PIPES / VALVES MAW | 17/09/2022 | 09/12/2022 |  |  | 512 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP--MB-3G75 | TT_Task | PROCUREMENT/ MANUFACTURING GT INSULATION MB- | 30/10/2021 | 01/04/2022 | 30/10/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20LBG2C60 | TT_FinMile | (DF) INPUT FOR MS3 EL. SUPERHEATER LBG | 28/05/2021 | 28/05/2021 | 28/05/2021 | 28/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--2223-54 | TT_Task | DESIGN,PREFABRICATION, TRANSPORT KKS PLANT LABELLING | 12/09/2022 | 29/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MKA3B80 | TT_FinMile | (RFS) READY FOR SHIPMENT GENERATOR SKIDS 20MKA | 29/04/2022 | 29/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKW8H25 | TT_Task | COLD COMMISSIONING GEN SEAL OIL SYSTEM (COMM OIL FLUSHING) | 08/06/2023 | 14/06/2023 |  |  | 8 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BZL4-25 | TT_Task | TRANSPORT LIGHTING SMALL POWER BZL HIGHBAY, 20UMC | 06/05/2022 | 19/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BZL3-25 | TT_Task | MANUFACTURING /SHOP TEST LIGHTING SMALL POWER BZL HIGHBAY, 20UMC | 19/03/2022 | 07/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBL6-20 | TT_Task | ERECTION FILTERHOUSE 20MBL | 25/09/2022 | 26/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBL6-25 | TT_Task | ERECTION AIR INTAKE SILENCER BAFFELS 20MBL | 27/11/2022 | 10/12/2022 |  |  | 40 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B10 | TT_Mile | (HS) START ERECTION STEEL STRUCTURE/ CRANE RAILS 20UMC | 25/01/2022 | 25/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B15 | TT_Task | ERECTION STEEL STRUCTURE MAIN BUILDING / CRANE RAILS 20UMC | 25/01/2022 | 25/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LBH3D80 | TT_FinMile | (RFS) READY FOR SHIPMENT BLOW DOWN TANK 20LBH | 09/03/2022 | 09/03/2022 |  |  | 8 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20USX2-40 | TT_FinMile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION 20USX | 26/05/2022 | 26/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20USX5-25 | TT_FinMile | (RFE) FOUNDATION 20USX | 22/06/2022 | 22/06/2022 |  |  | 448 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--PAC2B75 | TT_Task | CONTRACT REVIEW / PREP. CIRC. CW PUMP PAC | 19/12/2020 | 29/01/2021 | 19/12/2020 | 29/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--HA-2A40 | TT_Mile | AGREED PIPING DESIGN BASIC REPORT (PDBR) | 12/12/2020 | 12/12/2020 | 12/12/2020 | 12/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MBA6A15 | TT_Task | ERECTION, NDT, PT / VALVES 20MBA | 23/10/2022 | 31/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20CPA8-10 | TT_FinMile | (TOP-20CP-GT) INTERFACE PANELS IN FUNCTION AREA GAS TURBINE | 27/02/2023 | 27/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SCA6-15 | TT_Task | ERECTION COMPRESSED AIR/INSTRUMENT AIR SYSTEM SCA/QFA AND INTERCONNECTING PIPIES | 06/09/2022 | 07/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAG5-25 | TT_Task | GROUTING OF CONDENSER SHELL SUPPORT STRUCTURE SEISMIC TIE DOWNS MAG20 | 24/09/2022 | 28/09/2022 |  |  | 360 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEN5-45 | TT_FinMile | (RFE) FOUNDATION 20UEN | 01/04/2022 | 01/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEN5-10 | TT_Mile | (H) START PLACING FORMWORK 20UEN | 18/02/2022 | 18/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-20 | TT_Task | PREPARATION FOUNDATION GROUNDING DWGS UTG 20UTG01 | 11/01/2022 | 24/01/2022 |  |  | 48 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-15 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE 20UTG01 | 30/10/2021 | 24/01/2022 | 30/10/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-40 | TT_FinMile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION 20UTG01 | 02/05/2022 | 02/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MAV3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT (NORTH SEA PORT) LUBE OIL MODULE 20MAV | 29/04/2022 | 29/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BFF2-80 | TT_Task | QUOTATION STAGE LV SWITCHGEAR FOR HRSG BFF/BMF | 28/05/2021 | 08/07/2021 | 28/05/2021 | 08/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--BFF2-15 | TT_Task | BASIC DESIGN / SPECIFICATION LV SWITCHGEAR FOR HRSG BFF/BMF | 02/04/2021 | 27/05/2021 | 02/04/2021 | 27/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--BFF2-75 | TT_Mile | RFQ LV SWITCHGEAR FOR HRSG BFF/BMF | 28/05/2021 | 28/05/2021 | 28/05/2021 | 28/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5-50 | TT_Mile | (H) START PLACING FORMWORK 20UBA1110/20 | 08/04/2022 | 08/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20CYE8-10 | TT_FinMile | (TOP-20CYE) FIRE DETECTION SYSTEM FOR GT NOISE ENLOSURE MPB | 22/05/2023 | 22/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK7-25 | TT_Mile | PRECONDITION FOR CABLING ACTIVITIES AVAILABLE (95% cable pulling cards released, cards, cables + manuals on site) | 24/07/2022 | 24/07/2022 |  |  | 16 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--LBH2D15 | TT_Task | BASIC DESIGN / QUOTATION STAGE / ORDERING BLOW DOWN TANK LBH | 18/11/2020 | 26/01/2021 | 18/11/2020 | 26/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP--MB-2-40 | TT_FinMile | LIST OF MEASURING DEVICES GTGT-AUX. (MPL) (PROJECT SPECIFIC KKS-MASTER ACC. TO STANDARD VARIATION) | 01/04/2021 | 01/04/2021 | 01/04/2021 | 01/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP--CJP2-17 | TT_FinMile | FUNCTIONAL SPECIFICATION FOR IC GT (FSD) | 20/03/2021 | 20/03/2021 | 20/03/2021 | 20/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP--MB-2A10 | TT_FinMile | SYSTEM REQUIREMENTS FOR FOR GT AUX. SYSTEMS | 05/03/2021 | 05/03/2021 | 05/03/2021 | 05/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6-03 | TT_Task | CHECK AND PREPARATION OF FOUNDATION STEAM TURBINE MA | 03/06/2022 | 09/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBX2-75 | TT_Mile | (F) DETAIL DESIGN STEEL STRUCTURE WITH CONTRACTOR 20UBX/20UBG | 29/04/2022 | 29/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBX2-55 | TT_Task | DETAIL DESIGN STEEL STRUCTURE 20UBX | 07/10/2021 | 02/02/2022 | 07/10/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6-00 | TT_Task | SET UP EQUIPMENT ON SITE, SET UP SITE STORES STEAM TURBINE MA | 27/05/2022 | 02/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-5-25 | TT_Task | GROUTING OF REAR LP1-BEARING PEDESTAL MA | 01/07/2022 | 08/07/2022 |  |  | 16 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK7A25 | TT_Task | CABLING GENERATOR INTERNAL / GEN. AUXILIARIES | 01/10/2022 | 21/10/2022 |  |  | 864 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA3H25 | TT_Task | MANUFACTURING ELECTRICAL MODULES 20UBA7310/30 | 01/07/2021 | 17/11/2021 | 01/07/2021 | 17/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--BZK2-13 | TT_Task | PREPARATION OF 1ST LENGTH MATRIX | 02/05/2021 | 15/05/2021 | 02/05/2021 | 15/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--BZK2-19 | TT_Mile | 1ST. LENGTH MATRIX AVAILABLE | 16/05/2021 | 16/05/2021 | 16/05/2021 | 16/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BZK7-130 | TT_Task | ELECTRICAL ERECTION STACK HRSG20_3rd part INCL. CABLES / HEATED PROBE FOR EMISSION MONITORING | 20/08/2022 | 29/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK7C25 | TT_Task | CABLING (LATS) GENERATOR 20 | 26/02/2023 | 11/03/2023 |  |  | 224 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK7-28 | TT_Task | CABLING (LATS) ST 20 | 03/11/2022 | 14/12/2022 |  |  | 368 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAB6A16 | TT_Task | ERECTION, NDT, PT / VALVES (MECHANICAL) 20PAB URD | 28/06/2022 | 08/08/2022 |  |  | 1008 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LAB6H45 | TT_Task | INSULATION PIPES / VALVES FEEDWATER SYSTEM 20LAB | 10/11/2022 | 21/12/2022 |  |  | 552 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5C45 | TT_Mile | (RFE) ROOF CLOSED (MAIN BUILDLING) 20UMC (single layer) | 06/05/2022 | 06/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA8G27 | TT_Task | ELECTRICAL COMMISSIONING 20UBA7xxx | 27/02/2023 | 12/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAX4-40 | TT_FinMile | (OTD-OS) ON SITE ST HYDRAULIC SYSTEM 20MAX | 23/07/2022 | 23/07/2022 |  |  | 256 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAW4-40 | TT_FinMile | (OTD-OS) ON SITE GLAND STEAM CONDENSER 20MAW | 24/06/2022 | 24/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAW8-25 | TT_Task | COLD COMMISSIONING ST GLAND/ LEAKAGE STEAM SYSTEM BEFORE TURNING GEAR MAW | 25/04/2023 | 12/05/2023 |  |  | 304 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAJ8-25 | TT_Task | COLD COMMISSIONING ST EVACUATION SYSTEM BEFORE TURNING GEAR MAJ | 07/06/2023 | 11/06/2023 |  |  | 64 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-8B25 | TT_Task | COLD COMMISSIONING HP- / LP- VALVES -MAA/B | 10/07/2023 | 14/07/2023 |  |  | 80 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP--MB-2-07 | TT_FinMile | 3D-MODEL OF GAS TURBINE (ELECTRONIC FORMAT) | 26/02/2021 | 26/02/2021 | 26/02/2021 | 26/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBX2-50 | TT_FinMile | (MS3) STEEL STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UBX | 26/08/2021 | 26/08/2021 | 26/08/2021 | 26/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UBX2A75 | TT_FinMile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION 20UBX/20UBG03 | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBD5-10 | TT_Mile | (H) START PLACING FORMWORK 20UBD01/02 | 21/04/2022 | 21/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBD5-05 | TT_Task | WORK PREPARATION, EXCAVATION 20UBD01/02 | 14/04/2022 | 20/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKA6-09 | TT_Task | CHECK AND PREPARATION OF FOUNDATION MKA | 26/06/2022 | 09/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKA6-55 | TT_Task | SET UP EQUIPMENT ON SITE, SET UP SITE STORES GENERATOR MKA | 10/06/2022 | 16/06/2022 |  |  | 72 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGY7-17 | TT_Task | ERECTION FIRE DETECTION SYSTEM IN 01UEN SGY | 26/09/2022 | 30/10/2022 |  |  | 1576 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UHA5-45 | TT_FinMile | (RFE) FOUNDATION 20UHA | 20/12/2021 | 20/12/2021 | 20/12/2021 | 20/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAH8-25 | TT_FinMile | (TOP-20PAH) CONDENSER TUBE CLEANING SYSTEM | 11/05/2023 | 11/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20L--9I80 | TT_Task | REMOVAL INSERTS OF EMERGENCY STOP VALVES | 10/07/2023 | 14/07/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--5552-60 | TT_Mile | ROOM NUMBERS ASSIGNED TO EQUIPMENT | 18/04/2021 | 18/04/2021 | 18/04/2021 | 18/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MAV8-25 | TT_Task | COLD COMMISSIONING LUBE AND LIFTING OIL SYSTEM INCL. GEN AND GT | 30/05/2023 | 19/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAV4-25 | TT_Task | TRANSPORT LUBE OIL MODULE 20MAV | 30/04/2022 | 23/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UVM2-60 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UVM01 | 20/05/2021 | 20/05/2021 | 20/05/2021 | 20/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UVM2-50 | TT_Task | PREPARATION FOUNDATION GROUNDING DWGS 20UVM01 | 19/07/2021 | 01/08/2021 | 19/07/2021 | 01/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UVM2-70 | TT_Task | DETAIL DESIGN, CHECKER CONCRETE STRUCTURE 20UVM01 | 18/06/2021 | 01/08/2021 | 18/06/2021 | 01/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--SG-2-80 | TT_Task | QUOTATION STAGE FIRE FIGHTING SYSTEMS SG- | 16/07/2021 | 09/09/2021 | 16/07/2021 | 09/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP--MPB2-10 | TT_Mile | SYSTEM DESCRIPTION GT ENCLOSURE MPB / SAM | 07/05/2021 | 07/05/2021 | 07/05/2021 | 07/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP--MPB2-05 | TT_Mile | PI DIAGRAM GT ENCLOSURE MPB / SAM | 07/05/2021 | 07/05/2021 | 07/05/2021 | 07/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20EK-6-21 | TT_FinMile | (RFP) READY FOR PIPE CONNECTION GAS SYSTEM 01EK | 07/08/2022 | 07/08/2022 |  |  | 560 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20EK-6-19 | TT_Task | MECHANICAL ERECTION FUEL GAS RECEIVING AND MIXING SYSTEM 01EK | 25/07/2022 | 25/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URD5-10 | TT_Mile | (H) START PLACING FORMWORK 20URD | 11/10/2021 | 11/10/2021 | 11/10/2021 | 11/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-45 | TT_FinMile | (RFE) READY FOR MECHANICAL ERECTION 20URA PART 1 | 24/08/2022 | 24/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5E45 | TT_FinMile | (RFE) READY FOR MECHANICAL ERECTION 20URA PART 2 | 18/09/2022 | 18/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LAB7H15 | TT_Task | ELECTRICAL ERECTION PIPES / VALVES 20LAB | 15/11/2022 | 21/11/2022 |  |  | 792 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2B60 | TT_FinMile | (MS3) STEEL STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UMC | 16/05/2021 | 16/05/2021 | 16/05/2021 | 16/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BFF4-25 | TT_Task | TRANSPORT LV SWITCHGEAR FOR HRSG 20BFF/BMFF TO WORKSHOP OF ELECTRICAL MODULES MANUFACTURER xxx | 14/05/2022 | 15/05/2022 |  |  | 24 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MB-3A80 | TT_FinMile | (RFS) READY FOR SHIPMENT GT INTERCONNECTING PIPING 20MB- PORT OF EXPORT | 10/06/2022 | 10/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BZP2-14 | TT_Task | PREPARATION TENDER BOQ CABLE SUPPORT SYSTEM BZP | 14/07/2021 | 10/08/2021 | 14/07/2021 | 10/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BZL7-15 | TT_Task | LIGHTING AND SMALL POWER INSTALLATION STREET LIGHTING 20UZA | 05/10/2022 | 01/02/2023 |  |  | 2664 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20XKA7-15 | TT_Task | ERECTION EMERGENCY DIESEL GEN.SET XKA | 17/09/2022 | 21/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20XKA8-10 | TT_FinMile | (TOP-20XKA) EMERGENCY DIESEL GENERATOR SET XKA | 26/05/2023 | 26/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LCB6B15 | TT_Task | ERECTION CONDENSATE EXTRACTION PUMP 20LCB | 30/07/2022 | 26/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5B45 | TT_FinMile | (RFE) STEEL STRUCTURE 20UBA7910/20 | 20/08/2022 | 20/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5B15 | TT_Task | ERECTION STEEL PLATFORMS 20UBA7910/20 | 07/08/2022 | 20/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--GM-2B70 | TT_FinMile | (DF) IC INPUT (MEL) SUMP PUMP GM | 22/12/2021 | 22/12/2021 | 22/12/2021 | 22/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6B35 | TT_Task | COMMON FINAL ALIGNMENT K-,LP-TURBINE AND GENERATOR | 06/01/2023 | 15/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKA6F03 | TT_Task | PREASSEMBLING OF SLIPRING BASEPLATE MKA | 17/08/2022 | 22/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKA6F00 | TT_Task | PREPARATION OF FOUNDATION FOR SLIPRING MKA | 13/07/2022 | 17/07/2022 |  |  | 184 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKA6F05 | TT_Task | PREASSEMBLING OF SLIPRING SET MKA | 23/08/2022 | 27/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--PAC2B14 | TT_Mile | CONFIRMED PUMP CURVES CIRC. CW PUMP PAC | 23/04/2021 | 23/04/2021 | 23/04/2021 | 23/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20QC-4-25 | TT_Task | TRANSPORT DOSING CONTAINER 20QC | 19/06/2022 | 13/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-----8-07 | TT_Mile | HV GRID REQUIRED FROM CLIENT (FOR BACK ENERGISING) | 02/03/2023 | 02/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-----1-03 | TT_Mile | (A) FULL ENGINEERING START = FULL TEAM SETUP (no Hardware Order before NTP) | 01/08/2020 | 01/08/2020 | 01/08/2020 | 01/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--5552-61 | TT_Task | PREPARATION ROOM MODEL | 18/04/2021 | 01/05/2021 | 18/04/2021 | 01/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--PAC2B65 | TT_FinMile | (DF) INPUT FOR M2 CIRC. CW PUMP PAC (required for Piping M2) | 30/04/2021 | 30/04/2021 | 30/04/2021 | 30/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MAG6-33 | TT_Task | INSTALLING AND WELDING OF SEISMIC TIE-DOWNS MAG20 | 21/06/2022 | 24/06/2022 |  |  | 72 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAG6-22 | TT_Task | FITTING/WELDING OF GUIDE BOLTS AND STIFFENING PLATES AND NOZZLES IN THE BOTTOM PLATE MAG20 | 11/06/2022 | 20/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAG6-18 | TT_Task | ALIGNMENT OF CONDENSER STEAM SHELL MAG20 | 10/06/2022 | 10/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAG6-16 | TT_Task | PLACING STEAM SHELL (UPPER PART) AND CONNECTION/WELDING TO LOWER PART MAG20 | 03/06/2022 | 16/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAG6-10 | TT_Task | INSTALLING PROTECTIVE COVER FOR COOLING TUBES IN THE STEAM SHELL (LOWER) MAG20 | 24/05/2022 | 26/05/2022 |  |  | 56 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAG6-06 | TT_Mile | PLACING HOTWELL MAG20 | 20/05/2022 | 20/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAN6E40 | TT_FinMile | (RFP) READY FOR PIPE CONNECTION BYPASS STATION - LBA/LBB | 24/08/2022 | 24/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAN6-36 | TT_Task | FLOATING OF BYPASS STATION MAN Einschwimmen, etc. MAG20 | 05/08/2022 | 14/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-12 | TT_Mile | (H) START PLACING FORMWORK 20UTG01 | 11/05/2022 | 11/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP--C--2-40 | TT_Mile | CONNECTION DIAGRAM OF E-COMPONENTS FOR ELECTRICAL MODULES ASSEMBLY | 20/01/2022 | 20/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP--B--2-14 | TT_Mile | CMI's INTERLOCKING DIAGRAMS SIGNAL LIST AVAILABLE FOR IC | 21/10/2021 | 21/10/2021 | 21/10/2021 | 21/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP--B--2-16 | TT_Mile | TYPICALS FOR GT PLANT TO IC | 08/05/2021 | 08/05/2021 | 08/05/2021 | 08/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP--C--2-15 | TT_Mile | CONNECTION DIAGRAM (IC INTERFACE) OF E-COMPONENTS FOR GT AUTOM. | 21/10/2021 | 21/10/2021 | 21/10/2021 | 21/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BUK2-85 | TT_Mile | CONTRACT INTO FORCE INVERTER, CONVERTER, BATTERY CHARGER BRU/BTL | 21/09/2021 | 21/09/2021 | 21/09/2021 | 21/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BUK2-80 | TT_Task | QUOTATION STAGE INVERTER, CONVERTER, BATTERY CHARGER BRU/BTL | 19/08/2021 | 20/09/2021 | 19/08/2021 | 21/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6A20 | TT_Task | INSTALLATION AND ALIGNMENT REHEAT STOP AND CONTROL IP-VALVE MAB | 24/08/2022 | 30/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6A30 | TT_Task | INSTALLATION LP-FLAP (ERECTION ON PLATFORM) | 05/11/2022 | 18/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK4-40 | TT_FinMile | (OTD-OS) ON SITE MV/LV CABLES20/00BZK (LOT 1) | 16/07/2022 | 16/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20CHA8-10 | TT_FinMile | (TOP-20CHA) GENERATOR TRANSFORMER PROTECTION 20CHA/CHY | 13/03/2023 | 13/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6B04 | TT_Task | ALIGNMENT LP1-OUTER CASING TO LONGITUDINAL AND TRAVERSE AXES AND VERTICALY WITH DEFELCTION CURVE MA | 01/08/2022 | 10/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKA6-30 | TT_Task | PREPARATION AND PLACING GENERATOR ON FOUNDATION MKA | 10/07/2022 | 12/07/2022 |  |  | 104 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKA6E17 | TT_Task | GENERATOR TO FIXATORS MKA | 07/09/2022 | 09/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LBG8A25 | TT_Task | COLD COMMISSIONING AUXILIARY STEAM SYSTEM LBG | 02/05/2023 | 05/05/2023 |  |  | 56 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--ULA2-60 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20ULA | 04/05/2021 | 04/05/2021 | 04/05/2021 | 04/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--LBF2B65 | TT_FinMile | (DF) INPUT FOR M2 BYPASS STATION 20LBF | 29/06/2021 | 29/06/2021 | 29/06/2021 | 29/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20GM-6H16 | TT_Task | ERECTION PIPES DRAINAGE SYSTEM 00GM FROM WATER TRETAMENT TO UBH02 | 28/07/2022 | 07/09/2022 |  |  | 1752 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBH2-80 | TT_Task | DETAIL DESIGN, CHECKER CONCRETE STRUCTURE 20UBH01 | 18/06/2021 | 22/07/2021 | 18/06/2021 | 22/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BBA8-10 | TT_FinMile | (TOP-20BBA) MV SWITCHGEAR 20BBA INCL. HSBTS | 13/02/2023 | 13/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBH5-20 | TT_Task | WORK PREPARATION, EXCAVATION 20UBH01 | 25/02/2022 | 04/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBH2-75 | TT_FinMile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION 20UBH01 | 24/02/2022 | 24/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBH2-60 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UBH01 | 28/05/2021 | 28/05/2021 | 28/05/2021 | 28/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBH2-79 | TT_Task | PREPARATION FOUNDATION GROUNDING DWGS 20UBH01 | 09/07/2021 | 22/07/2021 | 09/07/2021 | 22/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20CPC8A30 | TT_Task | IC FIELD COMMISSIONING WSC (2) CPC | 03/06/2023 | 23/06/2023 |  |  | 56 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20EK-3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT GAS FINAL FILTER/ PREHEATER 20EKG | 16/08/2022 | 16/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20EK-4-40 | TT_FinMile | (OTD-OS) ON SITE GAS FINAL FILTER/ PREHEATER 20EKG | 31/12/2022 | 31/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20EK-4-25 | TT_Task | TRANSPORT GAS FINAL FILTER/ PREHEATER 20EKG | 06/11/2022 | 31/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--SMM2-75 | TT_Task | CONTRACT REVIEW / PREP. RFQ CRANE 20SMM01/02 FOR 20UMC | 15/01/2021 | 01/02/2021 | 15/01/2021 | 01/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--SMM2-20 | TT_FinMile | (DF) BASIC DESIGN INPUT FOR CRANES 20SMM01/02 FOR 20UMC | 01/02/2021 | 01/02/2021 | 01/02/2021 | 01/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--G--2A05 | TT_Task | PREPARATION PID'S G-SYSTEMS (INPUT FOR M1) | 04/01/2021 | 14/02/2021 | 04/01/2021 | 14/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--G--2-30 | TT_Task | REVISION PID'S AFTER 3D DRV G-SYSTEMS | 11/07/2021 | 07/09/2021 | 11/07/2021 | 07/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20SGY7A15 | TT_Task | ERECTION FIRE DETECTION SYSTEM IN 20UBA76xx/77xx/7410/73xx/7210/7110 SGY | 16/09/2022 | 29/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA7-15 | TT_Task | INSTALLATION ELECTRICAL MODULES 20UBA7910/20 | 31/07/2022 | 09/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA7-17 | TT_Task | INSTALLATION ELECTRICAL MODULES 20UBA7710/20 | 24/06/2022 | 14/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA8-12 | TT_FinMile | (TOP-20UBA7) POWER CONTROL CENTER (ELECTRICAL MODULES) 20UBA7xxx | 06/02/2023 | 06/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LBG6A15 | TT_Task | ERECTION, NDT, PT PIPES / VALVES 20LBG | 05/07/2022 | 12/09/2022 |  |  | 488 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LBG6A45 | TT_Task | INSULATION PIPES / VALVES FOR STEAM SYSTEM 20LBG | 13/11/2022 | 24/12/2022 |  |  | 912 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20CYQ8-10 | TT_FinMile | (TOP-20CYQ) GAS DETECTION SYSTEM FOR GT NOISE ENCLOSURE MPB | 26/04/2023 | 26/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZL7C15 | TT_Task | LIGHTING AND SMALL POWER INSTALLATION 20ULA AREA | 20/08/2022 | 18/10/2022 |  |  | 1016 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--CP-3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT BOP IC FIELD CABINETS | 17/06/2022 | 17/06/2022 |  |  | 376 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--G--2-10 | TT_Task | ENGINEERING PID'S G-SYSTEMS | 29/01/2021 | 29/05/2021 | 29/01/2021 | 29/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BAB4-25 | TT_Task | TRANSPORT CT / GROUNDING CUBICLE 20BAB | 28/05/2022 | 20/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAW5D17 | TT_Task | ERECTION LIGHTNING PROTECTION 00UEN | 26/09/2022 | 23/10/2022 |  |  | 1632 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAA7-15 | TT_Task | ERECTION IPB PART 1 - 20BAT TO 20BAC | 30/08/2022 | 17/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK7B26 | TT_Task | LV/CONTROL CABLE WORKS IN 00UCA | 16/09/2022 | 13/10/2022 |  |  | 984 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BRU8-22 | TT_FinMile | (TOP-20BT) DC-SYSTEMS | 13/02/2023 | 13/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LCL3B26 | TT_Task | MANUFACTURING / SHOP TEST BOILER BLOWDOWN PUMP 20LCL | 31/05/2021 | 28/04/2022 | 31/05/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--9998-20 | TT_Mile | START COLD COMMISSIONING E- / IC SYSTEM A / B / C / MKC / XKA | 07/02/2023 | 07/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--9998-21 | TT_Mile | START COLD COMMISSIONING WSC / HRSG SYSTEM L / P / H | 15/04/2023 | 15/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--9998-22 | TT_Mile | START COLD COMMISSIONING AUX. SYSTEM E / G / S / Q | 14/02/2023 | 14/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HAD8E25 | TT_Task | COLD COMMISSIONING HRSG HP SYSTEM (FOR CHEMICAL CLEANING) 20HAD10 | 29/04/2023 | 12/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP--B--2-08 | TT_Mile | INPUT DATA FOR ELECTRICAL MODULES INTERNAL CABLES | 06/07/2021 | 06/07/2021 | 06/07/2021 | 06/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP--B--2-13 | TT_Task | PREPARATION OF CABLE PULLING CARDS ELECTRICAL MODULES INTERNAL | 04/11/2021 | 11/11/2021 | 04/11/2021 | 11/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20SGA8B26 | TT_FinMile | (TOP-20SGA-01) FIRE FIGHTING SEA WATER RING MAIN AND OUTDOOR HYDRANTS | 13/02/2023 | 13/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--SGA4A40 | TT_FinMile | (OTD-OS) ON SITE FIRE FIGHTING RING MAIN SGA | 30/06/2022 | 30/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGA6A26 | TT_Task | ERECTION FIRE FIGHTING RING MAIN CONNECTIONS / HYDRANTS SGA | 01/07/2022 | 27/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGA6A27 | TT_Task | ERECTION FIRE FIGHTING CONN.PIPE SGA | 28/11/2022 | 25/12/2022 |  |  | 8 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAA4-40 | TT_FinMile | (OTD-OS) ON SITE COOLING TOWER COARSE SCREEN 20PAA | 30/08/2022 | 30/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAA4-25 | TT_Task | TRANSPORT COOLING TOWER COARSE SCREEN 20PAA | 06/07/2022 | 30/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SG-4-25 | TT_Task | TRANSPORT FIRE FIGHTING SYSTEMS 20SGC/SGE/SGF/SGJ | 25/03/2022 | 19/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20EKT6I15 | TT_Task | ERECTION, NDT, PT PIPES - CONDENSER PREHEATING PIPE 20EKT | 10/01/2023 | 13/02/2023 |  |  | 40 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-4D25 | TT_Task | TRANSPORT STACK HRSG 20 | 31/03/2022 | 19/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAX8-25 | TT_Task | COLD COMMISSIONING ST HYDRAULIC SYSTEM MAX | 07/06/2023 | 16/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-4D40 | TT_FinMile | (OTD-OS) ON SITE DRUMS HRSG20 | 24/04/2022 | 24/04/2022 |  |  | 176 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-3D80 | TT_FinMile | (RFS) READY FOR SHIPMENT DRUMS HRSG20 | 07/02/2022 | 07/02/2022 |  |  | 528 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAV6-55 | TT_Mile | START LUBE OIL FLUSHING ST20 | 12/03/2023 | 12/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6A15 | TT_Task | INSTALLATION HP-VALVE MAA | 17/08/2022 | 23/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAX6-40 | TT_FinMile | (RFP) READY FOR PIPE CONNECTION HYDRAULIC SYSTEM MAX | 14/09/2022 | 14/09/2022 |  |  | 904 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAW8-10 | TT_FinMile | (TOP-20MAW) ST SEAL STEAM SYSTEM | 22/04/2023 | 22/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBN2-40 | TT_FinMile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION 20UBN | 16/06/2022 | 16/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--UBA2-75 | TT_FinMile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION UBA7xxx | 30/11/2021 | 30/11/2021 | 30/11/2021 | 30/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MB-3C70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) GT INTERMEDIATE SHAFT 20MB- | 01/04/2022 | 01/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MB-3F25 | TT_Task | PROCUREMENT / MANUFACTURING GT INTERMEDIATE SHAFT 20MB- | 02/05/2021 | 01/04/2022 | 02/05/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2G60 | TT_FinMile | (DF) INPUT FOR MS3 ELECTRICAL MODULES 20UBA7110/20/30 | 23/06/2021 | 23/06/2021 | 23/06/2021 | 23/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--B--2-03 | TT_Mile | KICK OFF ELECTRICAL PLANNING | 26/02/2021 | 26/02/2021 | 26/02/2021 | 26/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--B--2-44 | TT_Mile | CABLE MANAGEMENT MEETING | 11/03/2021 | 11/03/2021 | 11/03/2021 | 11/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA3K50 | TT_Mile | ELECTRICAL MODULES READY FOR INSTALLATION OF COMP. ELECTRICAL MODULES 20UBA8110/20 | 17/06/2022 | 17/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2K02 | TT_Mile | E-AND IC- MANUALS FOR COMP. INSTALL. AVAILABLE ELECTRICAL MODULES 20UBA8110/20 | 20/05/2022 | 20/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA3K80 | TT_FinMile | (RFS) READY FOR SHIPMENT TO SITE FOR ELECTRICAL MODULES 20UBA8110/20 | 22/09/2022 | 22/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA3K55 | TT_Task | INSTALL.COMP., INT.CABLING,FIRE PROT.,SHOP TEST ELECTRICAL MODULES 20UBA8110/20 | 17/06/2022 | 01/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA3K25 | TT_Task | MANUFACTURING ELECTRICAL MODULES 20UBA8110/20 | 28/01/2022 | 16/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBL6-15 | TT_Task | ERECTION AIR INTAKE DUCT INCL: SUPPORT STRUCTURE 20MBL | 30/08/2022 | 24/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBL8-10 | TT_FinMile | (TOP-20MBL) GT AIR INTAKE SYSTEM | 26/04/2023 | 26/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGA8-26 | TT_Task | COLD COMMISSIONING INDOOR FIRE FIGHTING HYDRANTS 20SGA INSIDE 20UMC | 11/04/2023 | 24/04/2023 |  |  | 536 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20QC-4-40 | TT_FinMile | (OTD-OS) ON SITE DOSING CONTAINER 20QC | 13/08/2022 | 13/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20QU-2-85 | TT_Mile | CONTRACT INTO FORCE SAMPLING CONTAINER 20QU | 19/07/2021 | 19/07/2021 | 19/07/2021 | 19/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20QU-2-60 | TT_FinMile | (DF) INPUT FOR MS3 SAMPLING CONTAINER 20QU | 24/07/2021 | 24/07/2021 | 24/07/2021 | 24/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20SCA3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT AIR COMPRESSOR SYSTEM 20SCA | 11/07/2022 | 11/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY2-70 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE 20UEY03-05 | 02/07/2021 | 05/12/2021 | 02/07/2021 | 05/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UEY2-75 | TT_Mile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION 20UEY03-05 | 11/02/2022 | 11/02/2022 |  |  | 24 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20GKB6H16 | TT_Task | ERECTION / PT PIPES 00GKB FOR UGD TO UMC | 20/11/2022 | 21/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MB-9-20 | TT_Task | FULL SPEED NO LOAD GT20 | 01/07/2023 | 01/07/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBR4-25 | TT_Task | TRANSPORT DIFFUSOR 20MBR | 23/03/2022 | 21/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGC8-75 | TT_Task | LIVE SPRAY DELUGE TEST AND EVALUATION OF TEST FOR BAT/ BBT 20SGC | 27/02/2023 | 01/03/2023 |  |  | 208 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20CHY4-10 | TT_Task | TRANSPORT TO WORKSHOP PROT./ SYNCHR./METERING 20CHA/CHY (TO ST. INGBERT-INSTALL INTO ELECTRICAL MODULES) | 15/02/2022 | 16/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKQ6-15 | TT_Task | ERECTION EXHAUST GAS SYSTEM FOR GENERATOR 20MKQ | 28/08/2022 | 10/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--HB-2-15 | TT_Task | BASIC DESIGN MAIN STEEL STRUCTURE HRSG (Main Frame) | 05/11/2020 | 30/12/2020 | 05/11/2020 | 30/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20XKA2-15 | TT_Task | BASIC DESIGN / SPECIFICATION EMERGENCY DIESEL GEN.SET XKA | 22/08/2021 | 30/08/2021 | 22/08/2021 | 31/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--PAD4-40 | TT_FinMile | (OTD-OS) ON SITE: PARTS EMB. INTO RISERES 20PAD | 05/11/2021 | 05/11/2021 | 05/11/2021 | 05/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20HB-3D80 | TT_FinMile | (RFS) READY FOR SHIPMENT STACK / SILENCER DAMPER HRSG 20 (incl. Platforms) | 07/02/2022 | 07/02/2022 |  |  | 408 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-8-25 | TT_Task | COLD COMMISSIONING LP-TURBINE 20MAB | 18/04/2023 | 19/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-4-40 | TT_FinMile | (OTD-OS) ON SITE STEAM TURBINE (HI-L) | 30/07/2022 | 30/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBA9-25 | TT_Task | AIR DISTRIBUTION TEST 20MKA | 02/07/2023 | 02/07/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA4-51 | TT_Mile | (ET4b) ELECTRICAL MODULES AT WORKSHOP READY FOR COMPONENT INSTALLATION ELECTRICAL MODULES 20UBA7310/30 | 18/11/2021 | 18/11/2021 | 18/11/2021 | 18/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20QC-2-80 | TT_Task | QUOTATION STAGE DOSING CONTAINER QC | 30/04/2021 | 30/07/2021 | 30/04/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP--CJJ2-37 | TT_FinMile | ST IC TEST DOCUMENTS AT TEST FIELD | 28/12/2021 | 28/12/2021 | 28/12/2021 | 28/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MBA8E25 | TT_Task | COLD COMMISSIONING GT20 BLOW OFF SYSTEM MBA4x | 22/06/2023 | 28/06/2023 |  |  | 16 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--CKA7-15 | TT_Task | ERECTION THERMODYNAMIC SERVER | 02/04/2023 | 08/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAA8-20 | TT_Task | COLD COMMISSIONING COOLING TOWER COARSE SCREEN AND STOPLOGS 20PAA | 15/04/2023 | 28/04/2023 |  |  | 128 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MB-6-04 | TT_Mile | TEMP. LIFTING OIL SYSTEM AVAILABLE FOR ALIGNMENT GT20/GEN20 | 04/08/2022 | 04/08/2022 |  |  | 144 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20QFB6H15 | TT_Task | ERECTION, NDT, PT / VALVES ST CONTROL AIR 20QFB | 20/09/2022 | 14/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAL6A45 | TT_Task | INSULATION PIPES / VALVES FOR STEAM SYSTEM MAL | 12/11/2022 | 16/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAL6A15 | TT_Task | ERECTION, NDT, PT PIPES / VALVES MAL | 01/10/2022 | 11/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-16 | TT_FinMile | (RFE) FOUNDATION 20UTG01 | 18/05/2022 | 18/05/2022 |  |  | 272 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP--MB-2A81 | TT_Task | QUOTATION STAGE INTERCONNECTING PIPING MB- | 25/09/2021 | 29/10/2021 | 25/09/2021 | 29/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP--MB-2A80 | TT_Task | PREPARE TEC RFQ DOC INTERCONNECTING PIPING | 28/08/2021 | 24/09/2021 | 28/08/2021 | 24/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP--MBK2-85 | TT_Mile | CONTRACT INTO FORCE TURNING DEVICE MBK | 23/10/2021 | 23/10/2021 | 23/10/2021 | 23/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP--MBK2-81 | TT_Task | QUOTATION STAGE TURNING DEVICE MBK | 11/09/2021 | 22/10/2021 | 11/09/2021 | 22/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MA-5-27 | TT_Task | GROUTING OF STEEL BARS FOR LP1 CENTERING GUIDE MA | 09/07/2022 | 16/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6-12 | TT_Task | INSTALL. AND PREALIGNMENT OF STEEL BARS FOR LP1 CENTERING GUIDE MA | 01/07/2022 | 10/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20EK-7-25 | TT_Task | E- AND IC-ERECTION 20UEN | 12/02/2023 | 25/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20GHC6H17 | TT_Task | ERECTION, NDT, PT / VALVES DEMIN WATER GHC COMMON HEADER | 20/07/2022 | 16/08/2022 |  |  | 384 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-3C25 | TT_Task | MANUFACTURING SECONDARY STEEL STRUCTURE HRSG20_1st Part | 06/06/2021 | 30/12/2021 | 06/06/2021 | 30/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MAJ3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT AIR REMOVAL SYSTEM 20MAJ | 14/03/2022 | 14/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC2B-15 | TT_FinMile | CONTRACT INTO FORCE FOR EMBEDDED PARTS UMC | 30/03/2021 | 30/03/2021 | 30/03/2021 | 30/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC2B-10 | TT_Task | QUOTATION FOR EMBEDDED PARTS UMC | 24/02/2021 | 30/03/2021 | 24/02/2021 | 30/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC2B-5 | TT_Task | RFQ FOR EMBEDDED PARTS UMC | 27/01/2021 | 23/02/2021 | 27/01/2021 | 23/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA3B-25 | TT_Task | FABRICATION DESIGN FABRICATION TRANSPORT STEEL STRUCTURE 20UBA1110/20 | 19/08/2022 | 10/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SMG4-25 | TT_Task | TRANSPORT OTHER CRANES AND HOIST | 05/08/2022 | 29/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SMG3-25 | TT_Task | FABRICATION DESIGN/ MANUFACTURING / SHOP TEST OTHER CRANES AND HOIST | 18/02/2022 | 07/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SMG6-19 | TT_Task | ERECTION ACCEPTANCE TEST CRANE FOR HOIST | 14/10/2022 | 08/12/2022 |  |  | 1632 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SMG2-75 | TT_Task | CONTRACT REVIEW / PREP. RFQ OTHER CRANES AND HOIST | 01/09/2021 | 29/09/2021 | 01/09/2021 | 29/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20HA-6C26 | TT_FinMile | FINALISATION OF ERECTION HRSG MODULES20 | 28/04/2022 | 28/04/2022 |  |  | 2584 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7-110 | TT_Task | ERECTION CABLE TRAYS 20UMC ST AREA | 19/09/2022 | 28/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7-95 | TT_Task | ERECTION CABLE TRAYS FOR 20 URD AREA | 09/08/2022 | 13/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20C--7B15 | TT_Task | INSTALLATION OF IC EQUIPMENT ET200 FOR LATS GT | 20/10/2022 | 16/11/2022 |  |  | 472 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UPY5P10 | TT_Mile | (H) START PLACING FORMWORK 20UPY | 01/02/2022 | 01/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC2D5 | TT_Task | DETAIL DESIGN FINISHING WORKS 20UMC | 26/02/2022 | 22/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC2D25 | TT_FinMile | (F) FINISHING WORKS DWGS ON SITE RELEASED FOR EXEC. FINISHING WORKS 20UMC | 22/04/2022 | 22/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SCA7-15 | TT_Task | ELECTRICAL ERECTION COMPRESSED AIR/INSTRUMENT AIR SYSTEM SCA/QFA | 25/12/2022 | 14/01/2023 |  |  | 1024 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BAA2-15 | TT_Task | BASIC DESIGN / SPECIFICATION IPB BAA | 15/01/2021 | 18/03/2021 | 15/01/2021 | 18/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--BAW7-55 | TT_Task | EARTHING MEASUREMENT | 10/05/2021 | 18/06/2021 | 10/05/2021 | 18/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20LCL2B60 | TT_FinMile | (DF) INPUT FOR MS3 BOILER BLOWDOWN PUMP LCL | 09/05/2021 | 09/05/2021 | 09/05/2021 | 09/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20LCL2B75 | TT_Task | CONTRACT REVIEW / PREP. RFQ BOILER BLOWDOWN PUMP LCL | 15/01/2021 | 22/02/2021 | 15/01/2021 | 22/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAS3B25 | TT_Task | DETAIL DESIGN, MANUFACTURING, SHOP TEST CT MAKE-UP WATER PUMP PAS | 15/06/2021 | 06/01/2022 | 15/06/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--BFT2-60 | TT_FinMile | (DF) INPUT FOR MS3 LV-TRANSFORMERS BFT | 29/07/2021 | 29/07/2021 | 29/07/2021 | 29/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MA-3-80 | TT_Mile | (RFS-FAS) READY FOR SHIPMENT STEAM TURBINE (HI-L) | 07/05/2022 | 07/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20CPC8A10 | TT_FinMile | (TOP-20CP-HR) INTERFACE PANELS IN FUNCTION AREA 20 HRSG | 10/04/2023 | 10/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5C10 | TT_Mile | (HC) START ERECTION CLADDING 20UMC | 08/04/2022 | 08/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--LDK2B85 | TT_Mile | CONTRACT INTO FORCE CONDENSATE POLISHING PLANT 20LD | 19/05/2021 | 19/05/2021 | 19/05/2021 | 19/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--LDK2B80 | TT_Task | QUOTATION STAGE CONDENSATE POLISHING PLANT 20LD | 19/03/2021 | 18/05/2021 | 19/03/2021 | 18/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UEN5D45 | TT_FinMile | (RFE) FENCING, FINISHING WORKS 20UEN | 18/03/2023 | 18/03/2023 |  |  | 480 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEN3D25 | TT_Task | PURCHASING, TRANSPORT FENCING, FINISHING WORKS MATERIAL 20UEN | 18/12/2022 | 11/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20QC-6H15 | TT_Task | ERECTION, NDT, PT / VALVES DOSING SYSTEM 20QC | 04/09/2022 | 01/10/2022 |  |  | 1528 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBA6F15 | TT_Task | ERECTION, NDT, PT / VALVES HCO 20MBA51/54/MBV (BOP FOR LUBE OIL FLUSHING) | 16/10/2022 | 26/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20CJF4-25 | TT_Task | TRANSPORT ELECTRICAL / IC EQUIPMENT HRSG20 | 19/04/2022 | 18/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20CJF3-25 | TT_Task | DETAIL DESIGN / MANUFACTURING ELECTRICAL / IC EQUIPMENT HRSG20 | 02/04/2021 | 21/03/2022 | 02/04/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UBA4-42 | TT_FinMile | (OTD-OS) ON SITE (ET4d) ELECTRICAL MODULES 20UBA7710/20 AND 7410 | 22/06/2022 | 22/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKA6E40 | TT_FinMile | (RFP) READY FOR PIPE CONNECTION GENERATOR - MKA/PGB | 24/01/2023 | 24/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAD8-25 | TT_Task | COLD COMMISSIONING ST BEARING SYSTEM MAD | 07/06/2023 | 13/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MBK3-25 | TT_Task | DESIGN / MANUFACTURING TURNING DEVICE 20MBK | 23/10/2021 | 01/04/2022 | 23/10/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UMC2B10 | TT_Mile | (MS3) BUILDING FOUNDATION FINAL DIMENSIONS, LOADS AVAILABLE 20UMC | 15/05/2021 | 15/05/2021 | 15/05/2021 | 15/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBX2C-55 | TT_Mile | (F) DETAIL DESIGN CLADDING WITH CONTRACTOR UBX | 08/07/2022 | 08/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MAN4-25 | TT_Task | TRANSPORT ST BYPASS VALVES 20MAN | 27/05/2022 | 21/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--3332-76 | TT_Mile | ELECTRICAL SPECIFICATION BLACK BOXES LV MOTORS AVAILABLE | 29/01/2021 | 29/01/2021 | 29/01/2021 | 29/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--3332-75 | TT_Task | PREPARATION OF SPECIFICATION BLACK BOXES (LET) LV-MOTORS | 22/01/2021 | 28/01/2021 | 22/01/2021 | 28/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP--B--2-58 | TT_Mile | E-CONSUMER LIST - DETAIL MOUNTING LOCATION TO GT IC | 30/06/2021 | 30/06/2021 | 30/06/2021 | 30/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BAT2-85 | TT_Mile | CONTRACT INTO FORCE MAIN TRANSFORMERS BAT/BBT | 11/05/2021 | 11/05/2021 | 11/05/2021 | 11/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BZL8A27 | TT_Task | COMMISSIONING LIGHTING/SMALL POWER IN UBA/UBF/UBE | 11/04/2023 | 17/04/2023 |  |  | 1320 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20QC-7-15 | TT_Task | ELECTRICAL ERECTION DOSING CONTAINER QC | 11/09/2022 | 17/09/2022 |  |  | 1640 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAV6-15 | TT_Task | ERECTION LUBE OIL MODULE UMC 20MAV | 04/08/2022 | 24/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBF5B15 | TT_Task | ERECTION STEEL STRUCTURE 20UBE/UBF | 24/05/2022 | 13/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--GM-2B60 | TT_FinMile | (DF) INPUT FOR MS3 SUMP PUMP GM | 28/05/2021 | 28/05/2021 | 28/05/2021 | 28/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--GM-2B75 | TT_Task | CONTRACT REVIEW / PREP. RFQ SUMP PUMP GM | 04/05/2021 | 14/05/2021 | 04/05/2021 | 14/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--CHY2-75 | TT_Mile | RFQ PROT./SYNCHR./METERING CHA/CHY | 23/06/2021 | 23/06/2021 | 23/06/2021 | 23/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--CHY2-15 | TT_Task | BASIC DESIGN / SPECIFICATION PROT./SYNCHR./METERING CHA/CHY | 01/05/2021 | 22/06/2021 | 01/05/2021 | 22/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMX2-75 | TT_FinMile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION UMX-deleted | 01/11/2021 | 01/11/2021 | 01/11/2021 | 01/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--CYA2-85 | TT_Mile | CONTRACT INTO FORCE TELECOMMUNICATION CYA | 30/04/2022 | 30/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--CYA2-75 | TT_Mile | RFQ TELECOMMUNICATION CYA | 31/01/2022 | 31/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA7-16 | TT_Task | INSTALLATION ELECTRICAL MODULES 20UBA8110/20 | 21/11/2022 | 30/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA8-11 | TT_FinMile | (TOP-20UBA8) POWER CONTROL CENTER (ELECTRICAL MODULES) 20UBA8110/20 | 10/04/2023 | 10/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--2222-22 | TT_Task | PREPARATION PREL. OPERATING MANUAL (BHB) | 11/02/2023 | 10/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--2222-23 | TT_Mile | PREL. OPERATING MANUAL (BHB) | 11/06/2023 | 11/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGA3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT FIRE FIGHTING INDOOR HYDRANTS SGA 20UMC | 14/04/2022 | 14/04/2022 |  |  | 296 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BFT3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT LV-TRANSFORMERS | 28/04/2022 | 28/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAT8-10 | TT_FinMile | (TOP-20BAT) TRANSFORMER BAT01 AND BBT01 | 13/02/2023 | 13/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK7D25 | TT_Task | CABLING FROM 20UBA (10x) TO 01UBA9010/20 | 30/11/2022 | 24/01/2023 |  |  | 40 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK7B24 | TT_Task | CABLING FROM 20UBA (10x) TO 20UBA8110/20 AND URD | 22/12/2022 | 08/02/2023 |  |  | 72 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKA7-15 | TT_Task | E- AND IC- INSTALLATION (INCL.EARTHING / STARPOINT TRANSFORMER) GEN 20 | 29/10/2022 | 18/11/2022 |  |  | 1256 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAB8-25 | TT_Task | COLD COMMISSIONING COOLING WATER SYSTEMS PAB | 15/04/2023 | 19/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-4B40 | TT_FinMile | (OTD-OS) ON SITE SECONDARY STEEL STRUCTURE HRSG20_1st Part incl. Drum Supports | 06/03/2022 | 06/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20USX5-20 | TT_Mile | (H) START PLACING FORMWORK 20USX | 01/06/2022 | 01/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-6C22 | TT_Mile | START ERECTION PRESSURE PARTS HRSG20 | 01/04/2022 | 01/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6-55 | TT_Mile | START LUBE OIL FLUSHING COMPLETE TURBOSET ST20 | 12/03/2023 | 12/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BHT4-25 | TT_Task | TRANSPORT LV TRANSFORMER 20BFT03/04 | 12/09/2022 | 06/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZL8E10 | TT_FinMile | (TOP-20BZL-04) LIGHTING/SMALL POWER IN 20URD/URA/UGJ | 02/05/2023 | 02/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI---4P2A10 | TT_FinMile | LAST SUPPLIER INPUT GROUP4 (GHD,GKB,GMx,QFB,SCB,SGA,MAA/B/C) | 19/07/2021 | 19/07/2021 | 19/07/2021 | 19/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBN2-5 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UBN | 17/12/2021 | 17/12/2021 | 17/12/2021 | 17/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5B61 | TT_Mile | (HS) START ERECTION STEEL STRUCTURE 20UBA7xxx | 03/06/2022 | 03/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LCW7H15 | TT_Task | ELECTRICAL ERECTION PIPES / VALVES 20LCW | 15/02/2023 | 28/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAG7A15 | TT_Task | ELECTRICAL ERECTION / VALVES MAG | 24/12/2022 | 30/12/2022 |  |  | 864 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6-07 | TT_Task | PLACING BEARING CASINGS INCL. ANCHOR BOLTS MA | 10/06/2022 | 16/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MBL2-70 | TT_Mile | IC INPUT (PID, DESCR., SIGNAL EXCHANGE DWGS) AIR INTAKE SYSTEM MBL | 10/05/2021 | 10/05/2021 | 10/05/2021 | 10/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MBA6D40 | TT_FinMile | (RFP) READY FOR PIPE CONNECTION WASH WATER TANK 20MBA | 22/10/2022 | 22/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-6-20 | TT_Task | INSTALL PIPING HRSG20_Small Bore | 25/07/2022 | 09/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-6-15 | TT_Task | PRE-ASSEMBLY PIPING HRSG20_Small Bore | 04/06/2022 | 26/08/2022 |  |  | 72 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-6-14 | TT_Task | INSTALL PIPING HRSG20_External Large Bore - HRSG TP FOR PIPING AVAILABLE | 26/05/2022 | 23/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BFC8-10 | TT_FinMile | (TOP-20BFC) LV SWITCHGEAR 20BFC/BFD | 17/04/2023 | 17/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20CPD8-11 | TT_FinMile | (TOP-20CP-AA) INTERFACE PANELS IN FUNCTION AREA 00 AUXILIARY AND ANCILIARY | 27/02/2023 | 27/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-6-13 | TT_Task | INSTALL PIPING HRSG20_Internal Large Bore | 16/04/2022 | 08/07/2022 |  |  | 128 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MB-7-05 | TT_Task | ELECTRICAL TEMPORARIES FOR OIL FLUSHING GT20 | 08/02/2023 | 14/02/2023 |  |  | 200 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MB-7-20 | TT_Task | INSTALLATION OF HEAT TRACING GT20 | 29/09/2022 | 12/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-3E26 | TT_Task | MANUFACTURING INLET DUCT HRSG20 | 12/05/2021 | 05/12/2021 | 12/05/2021 | 05/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BUK2-15 | TT_Task | BASIC DESIGN / SPECIFICATION INVERTER,CONVERTER,BATTERY CHARGER BRU/BTL | 30/07/2021 | 18/08/2021 | 30/07/2021 | 18/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20HB-6-44 | TT_Task | PRE-ASSEMBLY STACK INCL. INSULATION / SEC. STEEL HRSG 3rd/4th part | 30/05/2022 | 03/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAT4-10 | TT_Task | PLACEMENT ON FOUNDATION TRANSFORMER 20BAT | 13/08/2022 | 19/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-----1-01 | TT_Mile | (LNTP) START PRE-ENGINEERING | 01/08/2020 | 01/08/2020 | 01/08/2020 | 01/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--GM-4B40 | TT_FinMile | (OTD-OS) ON SITE SUMP PUMP GM | 07/07/2022 | 07/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--GM-4B25 | TT_Task | TRANSPORT SUMP PUMP GM | 13/05/2022 | 07/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--GM-3B26 | TT_Task | MANUFACTURING / SHOP TEST SUMP PUMP GM | 14/10/2021 | 14/04/2022 | 14/10/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20EK-7-15 | TT_Task | ELECTRICAL ERECTION FUEL GAS COMPONENTS 20EK- | 19/09/2022 | 23/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEN5D50 | TT_Task | CONSTRUCTION FENCING FINISHING WORKS 01UEN | 30/04/2022 | 27/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEN5D49 | TT_FinMile | (RFE) FENCING, FINISHING WORKS 01UEN | 27/05/2022 | 27/05/2022 |  |  | 968 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEN3D30 | TT_Task | PURCHASING, TRANSPORT FENCING, FINISHING WORKS MATERIAL 01UEN | 02/04/2022 | 29/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEN2D75 | TT_FinMile | (F) FINISHING WORKS DWGS ON SITE RELEASED FOR EXEC. 01UEN | 16/01/2022 | 16/01/2022 |  |  | 600 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEN2D80 | TT_Task | DETAIL DESIGN FENCING, FINISHING WORKS 01UEN | 13/12/2021 | 16/01/2022 | 13/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UEN2-75 | TT_FinMile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION 01UEN | 19/01/2022 | 19/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20EK-8-99 | TT_Task | COLD COMMISSIONING FUEL GAS METERING SYSTEM FOR GT20 | 23/05/2023 | 19/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--C--2B80 | TT_Task | SW ENGINEERING BOP IC, T3000 DB MERGING, PROXIE GENERATION | 02/08/2022 | 26/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--P--2-10 | TT_Task | ENGINEERING PID'S P-SYSTEMS | 01/01/2021 | 18/02/2021 | 01/01/2021 | 18/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--C--2-80 | TT_Task | BOP IC SCOPE CALCULATION | 26/02/2021 | 08/04/2021 | 26/02/2021 | 08/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--C--2-10 | TT_Task | TECHNICAL CLARIFICATION BOP IC | 15/01/2021 | 25/03/2021 | 15/01/2021 | 25/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--C--2B70 | TT_FinMile | (DF) HANDOVER T3000 DB FOR Precomm./ Fail Safe TEST | 07/02/2022 | 07/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SAM7-25 | TT_Task | E- AND IC- ERECTION HVAC SYSTEM 20SA | 01/12/2022 | 11/01/2023 |  |  | 712 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGC6J15 | TT_Task | ERECTION SPRAY DELUGE SYSTEM UNDER ELECTRICAL MODULES 20UBA76xx/77xx/7410/73xx/7210/7110 20SGC | 25/09/2022 | 08/10/2022 |  |  | 624 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20QU-2-80 | TT_Task | QUOTATION STAGE SAMPLING CONTAINER 20QU | 30/04/2021 | 24/07/2021 | 30/04/2021 | 24/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20QU-2-75 | TT_Task | PREPARATION RFQ SAMPLING CONTAINER 20QU | 23/04/2021 | 29/04/2021 | 23/04/2021 | 29/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20QU-2-05 | TT_Task | BASIC DESIGN / PREPARATION PID'S DOSING CONTAINER 20QU | 26/03/2021 | 22/04/2021 | 26/03/2021 | 22/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20LCA6A45 | TT_Task | INSULATION PIPES / VALVES CONDENSATE SYSTEM 20LCA | 18/01/2023 | 21/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--UR-2-40 | TT_FinMile | (MS2) DESIGN LOAD DATA, DIMENSIONS COOLING TOWER AVAILABLE | 20/12/2020 | 20/12/2020 | 20/12/2020 | 20/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BAA4-40 | TT_FinMile | (OTD-OS) ON SITE (ET8) IPB 20BAA | 29/08/2022 | 29/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--HA-2-86 | TT_Task | TECHNIAL CLARIFICATION WITH HRSG SUPPLIERS | 18/12/2020 | 14/01/2021 | 18/12/2020 | 14/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--BZP2-15 | TT_Task | BASIC DESIGN / SPECIFICATION CABLE SUPPORT SYSTEM BZP | 16/06/2021 | 13/07/2021 | 16/06/2021 | 13/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BAC4-25 | TT_Task | TRANSPORT GEN. CIRCUIT BREAKER 20BAC | 20/06/2022 | 14/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAC3-25 | TT_Task | DETAIL DESIGN / MANUFACTURING / SHOP TEST GEN. CIRCUIT BREAKER 20BAC | 16/07/2021 | 28/04/2022 | 16/07/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20MAJ4-25 | TT_Task | TRANSPORT AIR REMOVAL SYSTEM 20MAJ | 15/03/2022 | 09/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAG4-25 | TT_Task | TRANSPORT ST CONDENSER 20MAG | 23/03/2022 | 21/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGM8-25 | TT_Task | COLD COMMISSIONING FF INERTGAS SYSTEM IN UBA7110/7120/7410 SGM INSIDE CONTAINERS | 27/02/2023 | 05/03/2023 |  |  | 288 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--3331-33 | TT_Mile | TCC INSURANCE FOR HRSG PHASE 1 AVAILABLE | 05/12/2020 | 05/12/2020 | 05/12/2020 | 05/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20HB-4E40 | TT_FinMile | (OTD-OS) ON SITE INLET DUCT HRSG20 | 06/03/2022 | 06/03/2022 |  |  | 600 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-3E80 | TT_FinMile | (RFS) READY FOR SHIPMENT INLET DUCT HRSG20 | 02/01/2022 | 02/01/2022 |  |  | 104 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-4E25 | TT_Task | TRANSPORT INLET DUCT HRSG20 | 15/02/2022 | 06/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20EK-7-95 | TT_FinMile | ATEX - GAS SYSTEM 20EKG | 20/05/2023 | 20/05/2023 |  |  | 16 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BZL4-40 | TT_Mile | (OTD-OS) ON SITE LIGHTING SMALL POWER BZL HIGHBAY | 20/05/2022 | 20/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC3D30 | TT_Task | PURCHASING, TRANSPORT FINISHING WORKS MATERIAL 20UMC | 23/04/2022 | 01/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LBH4D40 | TT_FinMile | (OTD-OS) ON SITE BLOW DOWN TANK 20LBH | 08/04/2022 | 08/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--HA-2E65 | TT_FinMile | (DF) INPUT FOR M2 HRSG | 12/02/2021 | 12/02/2021 | 12/02/2021 | 12/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--SG-2-50 | TT_Mile | FINAL FIRE PROTECTION CONCEPT ESCAPE ROUTE AND FIRE PROTECTION DWGS AVAILABLE | 04/07/2021 | 04/07/2021 | 04/07/2021 | 04/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--L--2-50 | TT_FinMile | (DF) MECH. ENGINEERING / PLANT LAYOUT L SYSTEMS | 20/06/2021 | 20/06/2021 | 20/06/2021 | 20/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--L--2-30 | TT_Task | REVISION PID'S AFTER 3D DRV L SYSTEMS | 12/05/2021 | 20/06/2021 | 12/05/2021 | 20/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--P--2-28 | TT_Task | DATA MANAGEMENT P SYSTEMS | 05/05/2021 | 06/07/2021 | 05/05/2021 | 06/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--P--2-75 | TT_Task | DESIGN REVIEW INCL. SIL-STUDY P-SYSTEMS | 31/03/2021 | 04/05/2021 | 31/03/2021 | 04/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20SMM3-26 | TT_Task | FABRICATION DESIGN/ MANUFACTURING / SHOP TEST / TRANSPORT CRANE 20SMM01/02 FOR 20UMC | 03/10/2021 | 12/01/2022 | 03/10/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20USC2-12 | TT_Mile | PLANT DESIGN INPUT SCA | 04/02/2021 | 04/02/2021 | 04/02/2021 | 04/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20GM-6H18 | TT_Task | ERECTION PIPES DRAINAGE SYSTEM 00GM FROM STEAM TURBINE / HRSG TO UBH02 | 14/08/2022 | 24/09/2022 |  |  | 1616 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LBB6J49 | TT_Task | INSULATION PIPES / VALVES FOR REHEAT SYSTEM 20LBB-LBC80 | 17/02/2023 | 23/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BRU8-21 | TT_Task | COMMISSIONING 20BTA/BTL | 14/02/2023 | 20/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBX3C25 | TT_Task | DETAIL DESIGN FABRICATION DESIGN/FABRICATION/TRANSPORT CLADDING 20UBX | 08/07/2022 | 01/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKA9-40 | TT_FinMile | 1ST. SYNCHRONIZATION GT GENERATOR 20MKA | 03/07/2023 | 03/07/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20QC-2-05 | TT_Task | BASIC DESIGN / PREPARATION PID'S DOSING CONTAINER QC | 26/03/2021 | 22/04/2021 | 26/03/2021 | 22/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20SGA4-25 | TT_Task | TRANSPORT FIRE FIGHTING INDOOR HYDRANTS SGA 20UMC | 22/05/2022 | 16/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGA3-25 | TT_Task | DETAIL DESIGN / MANUFACTURING FIRE FIGHTING INDOOR HYRDANTS SGA 20UMC | 10/09/2021 | 17/03/2022 | 10/09/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--HA-2E20 | TT_FinMile | (DF) BASIC DESIGN PIPE ROUTING FOR HRSG SYSTEMS LAB/LBA10/LBB/C | 12/02/2021 | 12/02/2021 | 12/02/2021 | 12/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAH2-80 | TT_Task | QUOTATION STAGE CONDENSER TUBE CLEANING SYSTEM 20PAH | 11/02/2021 | 14/05/2021 | 11/02/2021 | 14/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--BAA2-80 | TT_Task | QUOTATION STAGE IPB BAA | 19/03/2021 | 01/05/2021 | 19/03/2021 | 01/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--BAA2-21 | TT_Mile | DWGS AVAILABLE IPB BAA | 02/05/2021 | 02/05/2021 | 02/05/2021 | 02/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP--CJJ3-10 | TT_Mile | ARRIVAL ST IC CABINETS AT ELECTRICAL MODULES MANUFACTURER-20CJ11222+20CJJ21+20CJJ23 | 04/01/2022 | 04/01/2022 |  |  | 8 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP--CJJ3-25 | TT_Task | ST IC DESIGN/PROCUREMENT/MANUFACTURING CABINETS | 20/09/2021 | 28/12/2021 | 20/09/2021 | 28/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6D80 | TT_Task | REASSEMBLY PIPING / TANK AFTER LUBE OIL FLUSHING MA | 02/04/2023 | 08/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6D70 | TT_Task | CLOSING BEARING PEDESTALS (READY FOR OPERATION) MA | 09/04/2023 | 22/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6D45 | TT_Task | INSTALLATION ST INSULATION MA | 12/03/2023 | 22/04/2023 |  |  | 408 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP--MPB2E55 | TT_Mile | FINAL ELECTRICAL LOAD DATA (VEL) GT ENCLOSURE MPB / SAM | 18/06/2021 | 18/06/2021 | 18/06/2021 | 18/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP--MPB2E70 | TT_Mile | IC INPUT (PID, DESCR.) GT ENCLOSURE MPB / SAM | 07/05/2021 | 07/05/2021 | 07/05/2021 | 07/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MBR2-05 | TT_Mile | PI DIAGRAMS DIFFUSER 20MBR | 20/02/2021 | 20/02/2021 | 20/02/2021 | 20/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MBR2-95 | TT_Mile | LAYOUT DRAWING DIFFUSER 20MBR | 07/07/2021 | 07/07/2021 | 07/07/2021 | 07/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MBR2A70 | TT_Mile | IC INPUT (PID, DESCR.) DIFFUSER 20MBR | 01/06/2021 | 01/06/2021 | 01/06/2021 | 01/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MBL2-85 | TT_Mile | CONTRACT INTO FORCE AIR INTAKE SYSTEM MBL | 03/05/2021 | 03/05/2021 | 03/05/2021 | 03/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MBL2-10 | TT_Mile | SYSTEM DESCRIPTION AIR INTAKE MBL | 26/04/2021 | 26/04/2021 | 26/04/2021 | 26/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA3B25 | TT_Task | FABRICATION DESIGN/FABRICATION/TRANSPORT STEEL STRUC.20UBA7xxx | 01/02/2022 | 09/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LAC6B40 | TT_FinMile | (RFP) READY FOR PIPE CONNECTION FEEDWATER PUMPS 20LAC | 04/07/2022 | 04/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--5552-64 | TT_FinMile | FINAL AND COMPLETE ROOM NUMBERS ASSIGNED TO EQUIPMENT | 19/06/2021 | 19/06/2021 | 19/06/2021 | 19/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--2222-32 | TT_Mile | HEALTH / SAFETY PLAN | 14/05/2021 | 14/05/2021 | 14/05/2021 | 14/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--2222-36 | TT_Mile | CLEANING INST. TURBOSET LUBE / LIFTING OIL SYSTEM | 12/02/2023 | 12/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAT7B72 | TT_Task | ELECTRICAL ERECTION SURGE ARRESTORS (BUILT IN GIL) | 14/11/2022 | 20/11/2022 |  |  | 680 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LAB6H15 | TT_Task | ERECTION, NDT, PT PIPES / VALVES 20LAB | 28/07/2022 | 09/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-110 | TT_Mile | READY FOR COMPLETION OF BACKFILLING PIPING SYSTEM (OUTSIDE) PAB UMC - URD | 08/01/2022 | 08/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LAC6B15 | TT_Task | ERECTION FEEDWATER PUMP MOTOR SKID 20LAC | 23/06/2022 | 17/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20EK-6-15 | TT_Task | ERECTION GAS FINAL FILTER/ PREHEATER 20EKG | 01/01/2023 | 11/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAV6H15 | TT_Task | ERECTION, NDT PIPES / VALVES MAV | 17/09/2022 | 18/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20GHC6H15 | TT_Task | ERECTION, NDT, PT / VALVES / PT DEMIN WATER 20GHC | 04/10/2022 | 05/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20C--7B17 | TT_Task | INSTALLATION OF IC EQUIPMENT ET200 FOR LATS ST20 | 29/09/2022 | 02/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BBT7-15 | TT_Task | PLACEMENT AUX. TRANSFORMER 20BBT | 20/08/2022 | 24/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SMM6-05 | TT_Task | PRE-ERECTION CRANE 20SMM01/02 FOR 20UMC / PREPARATION FOR LIFTING | 05/04/2022 | 18/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SMM6-15 | TT_Task | ERECTION / ACCEPTANCE TEST CRANE 20SMM01/02 FOR 20UMC | 16/04/2022 | 06/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LDK6A15 | TT_Task | ERECTION, NDT, PT PIPES / VALVES 20LDK | 05/08/2022 | 28/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAV8-10 | TT_FinMile | (TOP-20MAV) ST LUBE AND LIFTING OIL SYSTEM | 29/05/2023 | 29/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20QU-8-10 | TT_FinMile | (TOP-20QU) SAMPLING SYSTEM | 13/05/2023 | 13/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MB-6-00 | TT_Mile | START PREPARATION FOUNDATION, ERECTION GT20 | 16/07/2022 | 16/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--UBA2K60 | TT_FinMile | (DF) INPUT FOR MS3 ELECTRICAL MODULES UBA (all) | 23/06/2021 | 23/06/2021 | 23/06/2021 | 23/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--EK-2-86 | TT_Mile | CONTRACT INTO FORCE FUEL GAS RECEIVING AND MIXING SYSTEM EK | 28/06/2021 | 28/06/2021 | 28/06/2021 | 28/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20HA-6-70 | TT_FinMile | HRSG20 READY FOR CHEMICAL CLEANING | 12/05/2023 | 12/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LAC8B26 | TT_Task | FIRST FEEDWATER SYSTEM MINIMUM FLOW OPERATION LAB/C | 12/06/2023 | 18/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20EK-8-46 | TT_Task | FORWARDING NATURAL GAS TO GT20 | 20/06/2023 | 24/06/2023 |  |  | 8 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--B--2A55 | TT_Mile | (ELV3) FINAL EL.LOAD DATA FOR LV | 30/07/2021 | 30/07/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--B--2-55 | TT_Mile | (EMV3) FINAL EL. LOAD DATA FOR MV | 29/05/2021 | 29/05/2021 | 29/05/2021 | 29/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--B--2-50 | TT_Mile | (EMV2) PREL. EL. LOAD DATA FOR MV | 15/01/2021 | 15/01/2021 | 15/01/2021 | 15/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BAC4-40 | TT_FinMile | (OTD-OS) ON SITE (ET9) GEN. CIRCUIT BREAKER 20BAC | 14/08/2022 | 14/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BBT4-40 | TT_FinMile | (OTD-OS) ON SITE (ET6) AUX. TRANSFORMER 20BBT | 12/08/2022 | 12/08/2022 |  |  | 56 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--2222-10 | TT_Mile | ORDER PLACED OPERATING MANUAL (BHB) | 31/12/2022 | 31/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--ZTA2A80 | TT_Task | QUOTATION STAGE CHEMICAL CLEANING SYSTEM ZTA | 18/06/2022 | 12/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BAC2-85 | TT_Mile | CONTRACT INTO FORCE GEN. CIRCUIT BREAKER BAC | 16/07/2021 | 16/07/2021 | 16/07/2021 | 16/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20QC-3-26 | TT_Task | MANUFACTURING DOSING CONTAINER 20QC | 25/10/2021 | 21/05/2022 | 25/10/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20QC-3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT DOSING CONTAINER 20QC | 18/06/2022 | 18/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKA8-25 | TT_Task | COLD COMMISSIONING GENERATOR INCL. BEARING SYSTEM 20MKA/MKD | 02/05/2023 | 05/06/2023 |  |  | 80 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BFT8-10 | TT_FinMile | (TOP-20BFT03) TRANSFORMER 20BFT03 | 16/05/2023 | 16/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BHT4-40 | TT_FinMile | (OTD-OS) ON SITE LV TRANSFORMER 20BFT03/04 | 06/11/2022 | 06/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BFT8-25 | TT_Task | COMMISSIONING LV TRANSFORMER 20BFT03 | 17/05/2023 | 23/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20CJP3A11 | TT_Mile | DELIVERY GT IC CABINETS CJ- / CPA TO ELECTRICAL MODULES MANUFACTURER-20CJP01+20CJP41+20CPA01+20CPA02+20CPA03 | 04/01/2022 | 04/01/2022 |  |  | 8 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAG6-02 | TT_Task | PLACING AND ALIGNMENT OF SUPPORT PLATES AND SLIDING SUPPORTS MAG20 | 15/05/2022 | 17/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAG6-00 | TT_Task | SETTING UP OF ASSEMBLY AND CHECK FOUNDATION CONDENSER MAG20 | 12/05/2022 | 14/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-3B80 | TT_FinMile | (RFS) READY FOR SHIPMENT SECONDARY STEEL STRUCTURE HRSG20_1st Part incl. Drum Supports | 27/01/2022 | 27/01/2022 |  |  | 56 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20QFB8-10 | TT_FinMile | (TOP-20QFB) INSTRUMENTATION AIR DISTRIBUTION SYSTEM | 07/06/2023 | 07/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAL8-10 | TT_FinMile | (TOP-20MAL) ST VACUUM DRAIN SYSTEM | 17/04/2023 | 17/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAX6-15 | TT_Task | ERECTION HYDRAULIC SYSTEM MAX | 08/09/2022 | 21/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAX6-75 | TT_Task | PIPE CLEANING CONTROL OIL SYSTEM MAX | 10/02/2023 | 16/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--G--2-50 | TT_FinMile | (DF) MECH. ENGINEERING / PLANT LAYOUT G SYSTEMS | 07/09/2021 | 07/09/2021 | 07/09/2021 | 07/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--G--2-65 | TT_FinMile | (DF) PROCESS FINAL / INPUT FOR M2 G-SYSTEMS | 03/07/2021 | 03/07/2021 | 03/07/2021 | 03/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--C--3E80 | TT_FinMile | (RFS) READY FOR SHIPMENT BOP IC FIELD DEVICES | 12/04/2022 | 12/04/2022 |  |  | 904 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAG6-26 | TT_Task | ASSEMBLING AND WELDING OF CONDENSER NECK WALLS AND NECK BRACING MAG20 | 11/06/2022 | 03/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--PAD3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT PARTS EMBEDDED INTO CONCRETE RISERS | 09/08/2021 | 09/08/2021 | 09/08/2021 | 09/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20QCB8-25 | TT_Task | COLD COMMISSIONING DOSING SYSTEMS REQUIRED FOR PGB-OPERATION QCB | 11/04/2023 | 17/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBX3B26 | TT_Task | FABRICATION DESIGN FABRICATION TRANSPORT STEEL STRUCTURE 20UBX/20UBG | 29/04/2022 | 21/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD4-40 | TT_FinMile | (OTD-OS) ON SITE 20PAD FILL BATCH 1 | 10/08/2022 | 10/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B49 | TT_FinMile | (RFE) STEEL STRUCTURE CRANE WALKWAY RAILS 20SMM01/02 20UMC | 25/04/2022 | 25/04/2022 |  |  | 120 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MKA3-25 | TT_Task | DESIGN / PROCUREMENT / MANUFACTURING GEN. 20MKA | 19/03/2021 | 01/04/2022 | 19/03/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SP20MKA3-81 | TT_Mile | DELIVERY ST GEN. 20MKA | 02/04/2022 | 02/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-6-56 | TT_Task | PRESSURE TEST HRSG20 | 18/03/2023 | 14/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK7C33 | TT_Task | CABLING ST/ST AUXILIARIES | 29/09/2022 | 14/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK7E25 | TT_Task | CABLING 20UMC ST TO LDK | 01/10/2022 | 24/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7-80 | TT_Task | ERECTION CABLE TRAYS FOR 20UBA to UBX/UBE/UBF | 05/08/2022 | 01/09/2022 |  |  | 128 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7-140 | TT_Task | ERECTION CABLE TRAY FOR LATs GT 20UMC | 13/10/2022 | 26/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--UMY2-75 | TT_FinMile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION 20ULY/UMY | 30/11/2021 | 30/11/2021 | 30/11/2021 | 30/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UHA2-75 | TT_FinMile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION UHA | 03/09/2021 | 03/09/2021 | 03/09/2021 | 03/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20LBF3B25 | TT_Task | DETAIL DESIGN, MANUFACTURING, SHOP TEST BYPASS STATION 20LBF | 17/03/2021 | 06/03/2022 | 17/03/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20LBF3B80 | TT_FinMile | (RFS) READY FOR SHIPMENT BYPASS STATION 20LBF | 03/04/2022 | 03/04/2022 |  |  | 752 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LBF4B40 | TT_FinMile | (OTD-OS) ON SITE BYPASS STATION 20LBF | 05/08/2022 | 05/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LBF4B25 | TT_Task | TRANSPORT BYPASS STATION 20LBF | 07/07/2022 | 05/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--EK-2C60 | TT_FinMile | (DF) INPUT FOR MS3 GAS FINAL FILTER/ PREHEATER 20EKG | 11/07/2021 | 11/07/2021 | 11/07/2021 | 11/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20CFE7A25 | TT_Task | CABLING CONTINIOUS EMISSION MONITORING/ STACK HRSG20 | 23/02/2023 | 15/03/2023 |  |  | 736 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-6-38 | TT_Task | ERECTION OUTLET DUCT HRSG20 | 04/07/2022 | 17/07/2022 |  |  | 1088 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-6-85 | TT_Task | INSTALLATION COMPENSATORS | 01/12/2022 | 21/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-6-45 | TT_Task | ERECTION STACK HRSG20_3rd part | 04/07/2022 | 10/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BZK2-87 | TT_Task | QUOTATION MV/LV CABLES BZK | 24/08/2021 | 29/01/2022 | 24/08/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--BZK2-86 | TT_Mile | RFQ MV/LV CABLES BZK | 24/08/2021 | 24/08/2021 | 24/08/2021 | 24/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--BZK2-85 | TT_Mile | CONTRACT INTO FORCE MV/LV CABLES BZK (LOT 1) | 30/01/2022 | 30/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--UBA2E60 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE UBA7xxx + UBD | 23/06/2021 | 23/06/2021 | 23/06/2021 | 23/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAS3B80 | TT_FinMile | (RFS) READY FOR SHIPMENT CT MAKE-UP WATER PUMP PAS | 03/02/2022 | 03/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEN2B75 | TT_FinMile | (F) FINISHING WORKS DWGS ON SITE RELEASED FOR EXEC 20UEN | 17/12/2022 | 17/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEN2D70 | TT_Task | DETAIL DESIGN FENCING, FINISHING WORKS 20UEN | 23/10/2022 | 17/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20C--7L15 | TT_Task | ERECTION IC-EQUIPMENT 20UMC | 17/10/2022 | 27/11/2022 |  |  | 136 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAW5C16 | TT_Task | ERECTION INDOOR EARTHING 20UMC | 28/08/2022 | 22/10/2022 |  |  | 1184 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAN8-25 | TT_Task | COLD COMMISSIONING ST BYPASS SYSTEM MAN | 17/06/2023 | 26/06/2023 |  |  | 224 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD8-45 | TT_Task | FILLING OF COOLING WATER BASIN | 04/06/2023 | 10/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP--SGJ2-85 | TT_Mile | CONTRACT INTO FORCE FIRE FIGHTING / GAS DETECTION SGJ / CYQ / CYE | 16/08/2021 | 16/08/2021 | 16/08/2021 | 16/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP--SGJ2-80 | TT_Task | QUOTATION STAGE FIRE FIGHTING / GAS DETECTION SGJ / CYQ / CYE | 16/04/2021 | 20/05/2021 | 16/04/2021 | 20/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP--SGJ2-11 | TT_Task | ENGINEERING / PREPARATION RFQ FIRE FIGHTING / GAS DETECTION SGJ / CYQ / CYE | 26/02/2021 | 15/04/2021 | 26/02/2021 | 15/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP--SG-2-100 | TT_Mile | SUBMISSION OF OVERALL FIRE EXPLOSION CONCEPT FOR CHECK OF COMPATIBITILITY | 26/02/2021 | 26/02/2021 | 26/02/2021 | 26/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MBR2A80 | TT_Task | ENGINEERING / PREPARE TEC RFQ DOC DIFFUSER 20MBR | 15/01/2021 | 11/03/2021 | 15/01/2021 | 11/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MAX3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT (NORTH SEA PORT) ST HYDRAULIC SYSTEM 20MAX | 29/04/2022 | 29/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MAX3-25 | TT_Task | DESIGN / MANUFACTURING ST HYDRAULIC SYSTEM 20MAX | 24/07/2021 | 01/04/2022 | 24/07/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20SGA4-40 | TT_FinMile | (OTD-OS) ON SITE FIRE FIGHTING INDOOR HYDRANTS SGA 20UMC | 16/07/2022 | 16/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5B-40 | TT_Mile | (HS) START ERECTION STEEL STRUCTURE 20UBA1110/20 | 11/11/2022 | 11/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MAG3-25 | TT_Task | DESIGN / MANUFACTURING ST CONDENSER 20MAG | 26/03/2021 | 20/03/2022 | 26/03/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2A50 | TT_Task | PREPARATION FOUNDATION GROUNDING DWGS TS FOUND. 20UMC | 08/04/2021 | 21/04/2021 | 08/04/2021 | 21/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MA-8-25 | TT_Mile | START COLD COMMISSIONING ST20 | 18/04/2023 | 18/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBA9-55 | TT_Mile | INSPECTION GT SYSTEMS WITH NOTIFIED BODY | 22/06/2023 | 22/06/2023 |  |  | 16 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGY3A80 | TT_FinMile | (RFS) READY FOR SHIPMENT FIRE FIGHTING DETECTION SYSTEM SGY | 31/03/2022 | 31/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BBT3-25 | TT_Task | DETAIL DESIGN / MANUFACTURING / SHOP TEST AUX. TRANSFORMER 20BBT | 05/05/2021 | 22/04/2022 | 05/05/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20SGY4A25 | TT_Task | TRANSPORT MAIN FIRE FIGHTING DETECTION SYSTEM SGY | 01/04/2022 | 26/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UHA2B-9 | TT_Task | MANUFACTURING FOR EMBEDDED PARTS 20UHA | 04/05/2021 | 06/07/2021 | 04/05/2021 | 06/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC2B-25 | TT_Task | MANUFACTURING FOR EMBEDDED PARTS 20UMC | 31/03/2021 | 15/06/2021 | 31/03/2021 | 15/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20SA-2-80 | TT_Task | QUOTATION STAGE HVAC SYSTEM SA | 09/04/2021 | 01/08/2021 | 09/04/2021 | 01/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20SA-2-75 | TT_Task | PREPARATION RFQ HVAC SYSTEM SA | 05/03/2021 | 08/04/2021 | 05/03/2021 | 08/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20SA-2-85 | TT_Mile | CONTRACT INTO FORCE HVAC SYSTEM SA | 02/08/2021 | 02/08/2021 | 02/08/2021 | 02/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20UBA3H55 | TT_Task | INSTALL. COMP., INT. CABLING, FIRE PROT., SHOP TEST ELECTRICAL MODULES 20UBA7910/20 | 24/02/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20M--9-55 | TT_Task | BYPASS OPERATION FOR ST 20 | 25/07/2023 | 31/07/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20QU-4-40 | TT_FinMile | (OTD-OS) ON SITE SAMPLING CONTAINER 20QU | 03/11/2022 | 03/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBX5C15 | TT_Task | ERECTION ROOF DECKING 20UBX | 02/09/2022 | 08/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UHA5-10 | TT_Mile | (H) START PLACING FORMWORK 20UHA | 24/09/2021 | 24/09/2021 | 24/09/2021 | 24/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BFC8-25 | TT_Task | COMMISSIONING LV SWITCHGEAR 20BFC/BFD | 18/04/2023 | 01/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BFC4-10 | TT_Task | TRANSPORT TO WORKSHOP LV- / DC-SWITCHGEAR 20BFC/BFD (only as ELECTRICAL MODULES) | 15/06/2022 | 16/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BFC3-25 | TT_Task | MANUFACTURING / SHOP TEST LV- / DC-SWITCHGEAR 20BFC/BFD | 16/02/2022 | 14/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--SGA4A25 | TT_Task | TRANSPORT FIRE FIGHTING RING MAIN SGA | 06/05/2022 | 30/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA4K25 | TT_Task | TRANSPORT ELECTRICAL MODULES 20UBA8110/20 | 23/09/2022 | 17/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20EK-8H14 | TT_FinMile | (TOP-20EKT20) FUEL GAS PREHEATING SYSTEM - WATER SIDE | 20/05/2023 | 20/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BHT7-20 | TT_Task | ERECTION LV TRANSFORMER 20BFT03/04 | 22/11/2022 | 18/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5-10 | TT_Mile | (H) START PLACING FORMWORK 20UBA7910/20 | 17/05/2022 | 17/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBF5-17 | TT_Task | OIL RESISTANT PAINT 20UBE/UBF | 28/04/2022 | 11/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Z15 | TT_Task | WORK PREPARATION / PILE TRIMMING / PLATE WELDING CEP/LDK - PIT 20UMC | 02/07/2021 | 22/07/2021 | 02/07/2021 | 22/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MB-6-10 | TT_Mile | PLACING GT20 | 04/08/2022 | 04/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MB-8-25 | TT_Mile | START COLD COMMISSIONING GT/GEN 20 | 09/04/2023 | 09/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6-16 | TT_FinMile | CHEMICAL CLEANING COMPLETED | 02/06/2023 | 02/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAG6-04 | TT_Task | FITTING AND WELDING OF FIXING AND GUIDE POINTS MAG20 | 17/05/2022 | 19/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UPY5P45 | TT_FinMile | (RFE) CONCRETE STRUCTURE READY 20UPY | 26/02/2022 | 26/02/2022 |  |  | 1344 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LCL4B25 | TT_Task | TRANSPORT BOILER BLOWDOWN PUMP 20LCL | 27/05/2022 | 21/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LCL3B80 | TT_FinMile | (RFS) READY FOR SHIPMENT BOILER BLOWDOWN PUMP 20LCL | 26/05/2022 | 26/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LBA8J25 | TT_Task | COLD COMMISSIONING LP MAIN STEAM SYSTEM (FOR CHEM. CLEANING) LBA80 | 18/04/2023 | 01/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20QU-3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT SAMPLING CONTAINER 20QU | 14/02/2022 | 14/02/2022 |  |  | 1648 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20QU-3-26 | TT_Task | MANUFACTURING SAMPLING CONTAINER 20QU | 12/09/2021 | 17/01/2022 | 12/09/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20QC-8-25 | TT_Task | COLD COMMISSIONING DOSING / SAMPLING SYSTEMS QCD/QCL | 14/05/2023 | 27/05/2023 |  |  | 64 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20CPC8-27 | TT_Task | COMMISSIONING ET200 STATIONS CPC | 28/02/2023 | 13/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20CPD8-35 | TT_Task | IC FIELD COMMISSIONING AUX. POWER (90BBA) | 14/03/2023 | 27/03/2023 |  |  | 8 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--2227-68 | TT_Task | MOBILISATION ERECTION CONTRACTOR (E AND IC) | 02/02/2022 | 02/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BBA3-25 | TT_Task | DETAIL DESIGN / MANUFACTURING / SHOP TEST MV SWITCHGEAR 20/01BBA/BBB | 14/08/2021 | 21/01/2022 | 14/08/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2F75 | TT_FinMile | (F) DETAIL DESIGN STEEL PLATFORMS WITH CONTRACTOR COND. PIT DWGS LOT1 20UMC | 06/11/2021 | 06/11/2021 | 06/11/2021 | 06/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2E70 | TT_Task | DETAIL DESIGN STEEL PLATFORMS LOT1 20UMC | 03/05/2021 | 16/06/2021 | 03/05/2021 | 16/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5B-50 | TT_FinMile | (RFE) STEEL STRUCTURE 20UBA1110/20 | 07/12/2022 | 07/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--UBA2-69 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE UBA7xxx | 29/05/2021 | 27/07/2021 | 29/05/2021 | 27/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20CHA8-25 | TT_Task | COMMISSIONING UNIT PROTECTION FOR BAT/BBT 20CHA/CHY | 14/03/2023 | 27/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAT2-60 | TT_FinMile | (DF) INPUT FOR MS3 MAIN TRANSFORMERS BAT/BBT | 05/06/2021 | 05/06/2021 | 05/06/2021 | 05/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAH7H15 | TT_Task | ELECTRICAL ERECTION / VALVES 20PAH | 08/02/2023 | 14/02/2023 |  |  | 472 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKA6-35 | TT_Mile | FINAL ALIGNMENT ROTOR GT20/GEN20 COMPLETE 20MKA | 28/08/2022 | 28/08/2022 |  |  | 88 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20CPA8-25 | TT_Task | COMMISSIONING ET200 STATIONS GT/WSC 20CP/CJ | 28/02/2023 | 13/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20SGJ3-55 | TT_Task | TRANSPORT TO ELECTRICAL MODULES ASSEMBLY (UBA02) MB LOCAL FIRE ALARM PANEL 20SGJ / 20CYQ / 20CYE | 21/02/2022 | 23/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--UMY2-30 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE 20ULY/UMY | 30/05/2021 | 13/07/2021 | 30/05/2021 | 13/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BFA2-75 | TT_Mile | RFQ LV- / DC-SWITCHGEAR BFA/BFB/BMA/BUA/BUB/BUC | 14/05/2021 | 14/05/2021 | 14/05/2021 | 14/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BFA2-80 | TT_Task | QUOTATION STAGE LV- / DC-SWITCHGEAR BFA/BFB/BMA/BUA/BUB/BUC | 14/05/2021 | 29/06/2021 | 14/05/2021 | 29/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BFA2-15 | TT_Task | BASIC DESIGN / SPECIFICATION LV- / DC-SWITCHGEAR BFA/BFB/BMA/BUA/BUB/BUC | 12/02/2021 | 13/05/2021 | 12/02/2021 | 13/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BFA2-85 | TT_Mile | CONTRACT INTO FORCE LV- / DC-SWITCHGEAR BFA/BFB/BMA/BUA/BUB/BUC | 30/07/2021 | 30/07/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2Y60 | TT_FinMile | (MS3*) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE CEP/LDK PIT 20UMC | 15/02/2021 | 15/02/2021 | 15/02/2021 | 15/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2Y75 | TT_FinMile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION CEP/LDK PIT 20UMC (ATKINS) | 01/07/2021 | 01/07/2021 | 01/07/2021 | 01/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20CH-8-25 | TT_Task | COMMISSIONING UNIT PROTECTION 20CHA (GENERATOR) | 09/06/2023 | 22/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBA2D85 | TT_Mile | CONTRACT INTO FORCE WASH WATER TANK 20MBA | 16/09/2021 | 16/09/2021 | 16/09/2021 | 16/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20HA-6-26 | TT_Task | ERECTION INTERNAL BAFFLE HRSG20 | 02/05/2022 | 03/07/2022 |  |  | 2056 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SCA3-26 | TT_Task | MANUFACTURING / SHOP TEST AIR COMPRESSOR SYSTEM 20SCA | 18/12/2021 | 13/06/2022 | 18/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SP20MBR2-60 | TT_Mile | (DF) INPUT FOR MS3 DIFFUSER 20MBR | 30/06/2021 | 30/06/2021 | 30/06/2021 | 30/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MA-3-81 | TT_Mile | DELIVERY STEAM TURBINE MA- EX WORKS (MUELHEIM) | 16/04/2022 | 16/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--EK-2-06 | TT_Mile | PID INPUT AGREED WITH BOP-PIPING FUEL GAS RECEIVING AND MIXING SYSTEM EK | 31/03/2021 | 31/03/2021 | 31/03/2021 | 31/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--EK-2-67 | TT_FinMile | (DF) INPUT FOR M2 FUEL GAS RECEIVING AND MIXING SYSTEM EK | 18/07/2021 | 18/07/2021 | 18/07/2021 | 18/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20SGJ3-25 | TT_Task | DETAIL DESIGN / MANUFACTURING FIRE FIGHTING / GAS DETECTION 20SGJ / 20CYQ / 20CYE | 04/07/2021 | 28/01/2022 | 04/07/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SP20MBL3-25 | TT_Task | MANUFACTURING AIR INTAKE SYSTEM 20MBL | 01/10/2021 | 04/05/2022 | 01/10/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SP20MB-3A25 | TT_Task | DESIGN / MANUFACTURING GT INTERCONNECTING PIPING 20MB- | 30/10/2021 | 13/05/2022 | 30/10/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20HA-8-65 | TT_Task | HRSG PROTECTION TESTS 20HA | 22/06/2023 | 23/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7-135 | TT_Task | ERECTION CABLE TRAYS FOR 20ULA | 30/07/2022 | 19/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y10 | TT_Mile | (H) START PLACING FORMWORK CEP/LDK PIT 20UMC | 23/07/2021 | 23/07/2021 | 23/07/2021 | 23/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y45 | TT_FinMile | (RFE) CONCRETE WORKS CEP PIT 20UMC | 21/01/2022 | 21/01/2022 |  |  | 24 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--EK-2-04 | TT_Mile | PID INPUT AGREED WITH BOP-PIPING GAS FINAL FILTER/ PREHEATER 20EKG | 19/07/2021 | 19/07/2021 | 19/07/2021 | 19/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--EK-2-65 | TT_FinMile | (DF) INPUT FOR M2 GAS FINAL FILTER/ PREHEATER 20EKG | 11/07/2021 | 11/07/2021 | 11/07/2021 | 11/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--EK-2-75 | TT_Task | BASIC DESIGN / PREP. RFQ GAS FINAL FILTER/ PREHEATER 20EKG | 02/02/2021 | 25/03/2021 | 02/02/2021 | 25/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--EK-2-85 | TT_Mile | CONTRACT INTO FORCE GAS FINAL FILTER/ PREHEATER 20EKG | 28/06/2021 | 28/06/2021 | 28/06/2021 | 28/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--C--8-58 | TT_Task | OPTIMIZATION AUTOMATIC SEQUENCE CONTROL 20 | 19/06/2023 | 21/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--HB-3-25 | TT_Task | DETAIL DESIGN MAIN STEEL STRUCTURE HRSG | 27/01/2021 | 12/03/2021 | 27/01/2021 | 12/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MA-3-25 | TT_Task | MANUFACTURING STEAM TURBINE (HI-L) | 13/08/2021 | 15/04/2022 | 13/08/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--HB-2D15 | TT_Task | BASIC DESIGN STACK HRSG incl. OUTLET DUCT | 04/12/2020 | 14/01/2021 | 04/12/2020 | 14/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MBR2A81 | TT_Task | QUOTATION STAGE DIFFUSER 20MBR | 12/03/2021 | 10/06/2021 | 12/03/2021 | 10/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MBR2A85 | TT_Mile | CONTRACT INTO FORCE DIFFUSER 20MBR | 11/06/2021 | 11/06/2021 | 11/06/2021 | 11/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MBR2-87 | TT_Mile | INSPECTION PLAN DIFFUSER 20MBR | 07/08/2021 | 07/08/2021 | 07/08/2021 | 07/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20GHD8A25 | TT_Task | COLD COMMISSIONING SERVICE WATER DISTRIBUTION SYSTEM GHD | 25/04/2023 | 29/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BAC2-60 | TT_FinMile | (DF) INPUT FOR MS3 GEN. CIRCUIT BREAKER BAC | 13/08/2021 | 13/08/2021 | 13/08/2021 | 13/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAS4B25 | TT_Task | TRANSPORT CT MAKE-UP WATER PUMP PAS | 04/02/2022 | 31/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAG6A45 | TT_Task | INSULATION PIPES / VALVES FOR CONDENSATION SYSTEM MAG | 26/11/2022 | 30/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--SGA3A25 | TT_Task | DETAIL DESIGN / MANUFACTURING / SHOP TEST FIRE FIGHTING RING MAIN SGA | 23/11/2021 | 10/03/2022 | 23/11/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--BZP4B40 | TT_FinMile | (OTD-OS) ON SITE CABLE SUPPORT SYSTEM BZP (LOT 1) | 08/04/2022 | 08/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAW6-40 | TT_FinMile | (RFP) READY FOR PIPE CONNECTION SEAL/LEAK STEAM SYSTEM MAW | 08/07/2022 | 08/07/2022 |  |  | 560 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BAA2-85 | TT_Mile | CONTRACT INTO FORCE IPB BAA | 30/05/2021 | 30/05/2021 | 30/05/2021 | 30/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--PAC2B60 | TT_FinMile | (DF) INPUT FOR MS3 CIRC. CW PUMP PAC | 06/05/2021 | 06/05/2021 | 06/05/2021 | 06/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--HA-2A01 | TT_Mile | FINAL ERECTION CONCEPT HRSG | 02/05/2021 | 02/05/2021 | 02/05/2021 | 02/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--HA-2-80 | TT_FinMile | COATING INSTRUCTION | 28/11/2020 | 28/11/2020 | 28/11/2020 | 28/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MKA6-26 | TT_Task | FINAL ALIGNMENT OF SLIPRING SET MKA | 23/01/2023 | 27/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKA6-53 | TT_Mile | STATOR INSULATION RESISTANCE TEST | 22/09/2022 | 22/09/2022 |  |  | 128 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKA6-14 | TT_Mile | (RFC) READY FOR FINAL CONNECTION GENERATOR - BUSDUCT BAA | 08/10/2022 | 08/10/2022 |  |  | 80 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAA3-25 | TT_Task | DETAIL DESIGN / MANUFACTURING / SHOP TEST IPB 20BAA | 30/05/2021 | 06/06/2022 | 30/05/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20LBA8H25 | TT_Task | COLD COMMISSIONING HP MAIN STEAM SYSTEM (FOR CHEM. CLEANING) LBA10 | 18/04/2023 | 01/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAH3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT CONDENSER TUBE CLEANING SYSTEM 20PAH (BALL STRAINER) | 26/12/2021 | 26/12/2021 | 26/12/2021 | 26/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6-65 | TT_Mile | STEAM TURBINE READY FOR PRE-ASSEMBLING MAW/MAL/MAM-PIPING K- LP-Turbine | 17/09/2022 | 17/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6B40 | TT_FinMile | (RFP) READY FOR PIPE CONNECTION STEAM TURBINE - MAV-PIPING (ABSAUGUNG NACH ABSPRACHE) | 10/07/2022 | 10/07/2022 |  |  | 544 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6E40 | TT_FinMile | (RFP) READY FOR PIPE CONNECTION STEAM TURBINE - MAW/MAL/MAM | 11/02/2023 | 11/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6A52 | TT_Mile | DE-COUPLING OF LP- AND GENERATOR-SHAFTS | 23/01/2023 | 23/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6D57 | TT_Task | HONE COUPLING HOLES AND COUPLING OF K- AND LP-SHAFTS; CHECKING OF RADIAL RUN-OUT MA | 23/01/2023 | 29/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6D55 | TT_Task | HONE COUPLING HOLES AND COUPLING LP- AND GENERATOR-SHAFTS; CHECKING OF RADIAL RUN-OUT MA | 16/01/2023 | 22/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6D35 | TT_Task | ALIGNMENT AT CASING AND TURBINE BRACKETS MA | 30/01/2023 | 11/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6D20 | TT_Task | COMPLETION OF BEARING PEDESTALS AND PREPARATION FOR FLUSHING MA | 30/01/2023 | 08/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LBA8H10 | TT_FinMile | (TOP-20LBA10) HP MAIN STEAM SYSTEM | 17/04/2023 | 17/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LBA6H70 | TT_Task | PT, RE-INSTALLATION PIPES / VALVES LBA10 | 04/02/2023 | 16/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LBG3C80 | TT_FinMile | (RFS) READY FOR SHIPMENT EL.SUPERHEATER 20LBG | 10/03/2022 | 10/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBX2-10 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UBX/20UBG03 | 13/08/2021 | 13/08/2021 | 13/08/2021 | 13/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UEN2-85 | TT_FinMile | PLANT DESIGN INPUT FOR 01UEN AVAILABLE | 21/08/2021 | 21/08/2021 | 21/08/2021 | 21/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20EK-3-81 | TT_FinMile | (RFS) READY FOR SHIPMENT FUEL GAS RECEIVING AND MIXING SYSTEM 01EK | 18/05/2022 | 18/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20EK-4-41 | TT_FinMile | (OTD-OS) ON SITE FUEL GAS RECEIVING AND MIXING SYSTEM 01EK | 20/07/2022 | 20/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20EK-4-26 | TT_Task | TRANSPORT (FROM GERMANY) FUEL GAS RECEIVING AND MIXING SYSTEM 01EK | 19/05/2022 | 20/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20EK-3-82 | TT_Task | MANUFACTURING / SHOP TEST FUEL GAS RECEIVING AND MIXING SYSTEM 01EK | 13/08/2021 | 20/04/2022 | 13/08/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20BAC7-15 | TT_Task | PLACING GEN. CIRCUIT BREAKER 20BAC | 29/08/2022 | 29/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBX5-45 | TT_FinMile | (RFE) FOUNDATION 20UBX/20UBG03 | 13/06/2022 | 13/06/2022 |  |  | 304 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA4G50 | TT_Mile | (ET4a) IC ELECTRICAL MODULES AT WORKSHOP READY FOR COMPONENT INSTALLATION 20UBA7110/20/30 | 19/01/2022 | 19/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2B-5 | TT_FinMile | (MS3) STEEL STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UBA1110/20 | 23/06/2021 | 23/06/2021 | 23/06/2021 | 23/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2-15 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE 20UBA1110/20 | 08/07/2021 | 22/10/2021 | 08/07/2021 | 22/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2-40 | TT_FinMile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION 20UBA1110/20 | 31/03/2022 | 31/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--PAC2B80 | TT_Task | QUOTATION STAGE CIRC. CW PUMP PAC | 30/01/2021 | 08/04/2021 | 30/01/2021 | 08/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MKC4-25 | TT_Task | TRANSPORT TRANSFORMERS 20MKC/MBJ | 30/04/2022 | 24/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAY9-35 | TT_Task | ST PROTECTION | 15/06/2023 | 21/06/2023 |  |  | 40 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20QFB8-25 | TT_Task | COLD COMMISSIONING ST CONTROL AIR SYSTEM QFB | 10/06/2023 | 14/06/2023 |  |  | 40 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAL8-25 | TT_Task | COLD COMMISSIONING ST DRAIN SYSTEM MAL | 18/06/2023 | 26/06/2023 |  |  | 48 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAX8-70 | TT_FinMile | 20MAX READY FOR PRESSURE TEST LBA10/80 | 16/02/2023 | 16/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LBH4D25 | TT_Task | TRANSPORT BLOW DOWN TANK 20LBH | 11/03/2022 | 08/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LBH3D25 | TT_Task | DETAIL DESIGN / MANUFACTURING BLOW DOWN TANK 20LBH | 28/01/2021 | 09/02/2022 | 28/01/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SP--MB-2C05 | TT_FinMile | PROCESS INSTRUMENTATION DIAGRAMS (PID'S) GTGT-AUX. (EIF) | 05/03/2021 | 05/03/2021 | 05/03/2021 | 05/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2B-20 | TT_FinMile | (F) DETAIL DESIGN STEEL STRUCTURE WITH CONTRACTOR 20UBA1110/20 | 18/08/2022 | 18/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2B-10 | TT_Task | DETAIL DESIGN STEEL STRUCTURE 20UBA1110/20 | 30/11/2021 | 13/01/2022 | 30/11/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--BZP2-80 | TT_Task | QUOTATION STAGE FOR CABLE SUPPORT SYSTEM BZP | 11/08/2021 | 30/09/2021 | 11/08/2021 | 30/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--BZP2-88 | TT_Mile | RFQ CABLE SUPPORT SYSTEM BZP | 11/08/2021 | 11/08/2021 | 11/08/2021 | 11/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MAJ7A15 | TT_Task | ELECTRICAL ERECTION PIPES / VALVES MAJ | 01/12/2022 | 14/12/2022 |  |  | 992 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGM8-10 | TT_FinMile | (TOP-20SGM-02) FF INERTGAS SYSTEM IN UBA7110/7120/7410 SGM INSIDE CONTAINERS | 26/02/2023 | 26/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HAD8F10 | TT_FinMile | (TOP-20HAD50) HRSG IP SYSTEM | 28/04/2023 | 28/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HAD8E10 | TT_FinMile | (TOP-20HAD10) HRSG HP SYSTEM | 28/04/2023 | 28/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-6-40 | TT_Mile | (RFP) READY FOR PIPE CONNECTION TERMINAL POINTS | 25/07/2022 | 25/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LCB4B40 | TT_FinMile | (OTD-OS) ON SITE CONDENSATE EXTRACTION PUMP 20LCB | 27/07/2022 | 27/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LCB4B25 | TT_Task | TRANSPORT CONDENSATE EXTRACTION PUMP 20LCB | 02/06/2022 | 27/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI---2S6-05 | TT_Mile | START WORK ON PIPING ACTIVITIES | 07/04/2022 | 07/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI---3S6-05 | TT_Mile | START WORK IN TURBINE PACKAGES | 16/07/2022 | 16/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SA-6-20 | TT_Mile | START WORK FOR HVAC ACTIVITIES | 03/11/2022 | 03/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--B--2-81 | TT_Task | PROJECT SPECIFIC ADAPTION OF ELECTRICAL REQUIREMENTS FOR HRSG | 13/08/2020 | 07/10/2020 | 13/08/2020 | 07/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MA-4-25 | TT_Task | TRANSPORT STEAM TURBINE (HI-L) | 07/05/2022 | 30/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LAC8B25 | TT_Task | COLD COMMISSIONING FEEDWATER SYSTEM 20LAB/C | 15/04/2023 | 28/04/2023 |  |  | 112 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--UBA2A75 | TT_FinMile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION UBA7910/7920 | 12/04/2022 | 12/04/2022 |  |  | 208 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAA2-80 | TT_Task | QUOTATION STAGE COOLING TOWER COARSE SCREEN 20PAA (MPA) | 04/08/2021 | 28/09/2021 | 04/08/2021 | 28/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAA2-77 | TT_Task | PREPARATION RFQ COOLING TOWER COARSE SCREEN 20PAA (MPA) | 14/07/2021 | 03/08/2021 | 14/07/2021 | 03/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20QJ-3B80 | TT_FinMile | (RFS) READY FOR SHIPMENT CENTRAL GAS SUPPLY (H2,CO2) QJ_ | 05/01/2022 | 05/01/2022 |  |  | 1400 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20QJ-4B25 | TT_Task | TRANSPORT CENTRAL GAS SUPPLY (H2,CO2) QJ_ | 30/06/2022 | 24/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20QJ-3B25 | TT_Task | DETAIL DESIGN, MANUFACTURING, SHOP TEST CENTRAL GAS SUPPLY (H2,CO2) QJ_ | 23/05/2021 | 08/12/2021 | 23/05/2021 | 08/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MAG6-11 | TT_Task | INSTALLING PROTECTIVE COVER FOR COOLING TUBES IN THE STEAM SHELL (UPPER) MAG20 | 03/06/2022 | 05/06/2022 |  |  | 40 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA4J25 | TT_Task | TRANSPORT ELECTRICAL MODULES 20UBA7610/20 (TO SITE) | 02/05/2022 | 26/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LCB3B28 | TT_Task | MANUFACTURING / SHOP TEST CONDENSATE EXTRACTION PUMP 20LCB | 09/04/2021 | 04/05/2022 | 09/04/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--UBF2-60 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UBE/UBF | 05/06/2021 | 05/06/2021 | 05/06/2021 | 05/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UBF2-70 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE 20UBE/UBF | 22/06/2021 | 09/08/2021 | 22/06/2021 | 09/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UBF2A75 | TT_FinMile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION 20UBE/UBF | 24/11/2021 | 24/11/2021 | 24/11/2021 | 24/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20LCL6A15 | TT_Task | ERECTION, NDT, PT PIPES / VALVES 20LCL | 20/10/2022 | 01/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LCL6A45 | TT_Task | INSULATION PIPES / VALVES STEAM GENERATOR DRAINS 20LCL | 02/02/2023 | 01/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---6A15 | TT_Task | ERECTION, NDT, PT / VALVES INTERCON. PIPING 20EK/MB/AUX. SYSTEM | 16/10/2022 | 31/12/2022 |  |  | 560 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZL8B12 | TT_FinMile | (TOP-20BZL-03) LIGHTING / SMALL POWER IN UBA/UBF/UBE | 10/04/2023 | 10/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAG8-10 | TT_FinMile | (TOP-20MAG) CONDENSATION SYSTEM | 17/04/2023 | 17/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20CY-7-15 | TT_Task | ERECTION COMMUNICATION SYSTEMs IN 20UMC | 01/12/2022 | 18/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-8-18 | TT_FinMile | INLET DUCT GAS SYSTEM READY HRSG20 | 24/07/2022 | 24/07/2022 |  |  | 2136 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20QU-7H15 | TT_Task | ELECTRICAL ERECTION / VALVES DOSING SYSTEM 20QU | 10/03/2023 | 16/03/2023 |  |  | 464 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBA8A10 | TT_FinMile | (TOP-20MBH5) GT AIR BLOCK SYSTEM FOR FUEL GAS | 26/04/2023 | 26/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBX8E10 | TT_FinMile | (TOP-20MBX) GT HYDRAULIC OIL SYSTEM | 26/04/2023 | 26/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBX8-10 | TT_FinMile | (TOP-20MBX2) GT PNEUMATIC SYSTEM MBX21 | 26/04/2023 | 26/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAX8-10 | TT_FinMile | (TOP-20MAX) ST HYDRAULIC SYSTEM | 06/06/2023 | 06/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--SG-2-85 | TT_Mile | CONTRACT INTO FORCE FIRE FIGHTING SYSTEMS SG- | 10/09/2021 | 10/09/2021 | 10/09/2021 | 10/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--SG-2-42 | TT_FinMile | (DF) PID'S FOR FIRE FIGHTING SYSTEMS AVAILABLE SG- | 18/06/2021 | 18/06/2021 | 18/06/2021 | 18/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20GKB8A10 | TT_FinMile | (TOP-20GKB) DRINKING WATER DISTRIBUTION SYSTEM | 28/04/2023 | 28/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--G--2-20 | TT_Mile | WATER BALANCE DIAGRAM AVAILABLE | 17/10/2020 | 17/10/2020 | 17/10/2020 | 17/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP--MB-2-85 | TT_Mile | CONTRACT INTO FORCE GAS TURBINE INCL. GT ENGINEERING | 15/01/2021 | 15/01/2021 | 15/01/2021 | 15/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP--MB-2-86 | TT_Mile | ORDER ACCEPTANCE MEETING GTGT-AUX (AEG) / R2 REVIEW | 06/02/2021 | 06/02/2021 | 06/02/2021 | 06/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP--MB-2-10 | TT_Mile | TECHNICAL REQUIREMENTS FOR GT SYSTEMS (EID FINAL / INTERFACE CLARIFICATION) | 05/03/2021 | 05/03/2021 | 05/03/2021 | 05/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--C--2-50 | TT_Mile | (ICSY2) PRELIMINARY FUNCTION DESCRIPTIONS, LOGICS AND HMI GRAPHICS | 05/09/2021 | 05/09/2021 | 05/09/2021 | 05/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--M--2D00 | TT_Mile | SYSTEM DOCUMENTS [initial] | 03/03/2021 | 03/03/2021 | 03/03/2021 | 03/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20CPC8A27 | TT_Task | IC FIELD COMMISSIONING WSC (1) CPC | 11/04/2023 | 08/05/2023 |  |  | 32 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20QC-2-75 | TT_Task | PREPARATION RFQ DOSING CONTAINER QC | 23/04/2021 | 29/04/2021 | 23/04/2021 | 29/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MA-9-06 | TT_Mile | 1ST. TURNING GEAR ST | 20/06/2023 | 20/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBA2D80 | TT_Task | QUOTATION STAGE WASH WATER TANK 20MBA | 02/06/2021 | 15/09/2021 | 02/06/2021 | 15/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MBA2D75 | TT_Task | CONTRACT REVIEW / PREP. RFQ WASH WATER TANK 20MBA | 05/05/2021 | 01/06/2021 | 05/05/2021 | 01/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--CKA2-00 | TT_Task | PROJECT DEFINITION / SYSTEM DESCRIPTION FOR THE CUSTOMER | 24/06/2021 | 21/07/2021 | 24/06/2021 | 21/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20UBA3H25 | TT_Task | MANUFACTURING ELECTRICAL MODULES 20UBA7910/20 | 16/09/2021 | 16/02/2022 | 16/09/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--BAW3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT IN- / OUTDOOR GROUNDING BAW | 23/04/2022 | 23/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAW5C23 | TT_Task | ERECTION OUTDOOR EARTHING/LIGHTNING 20ULA/UHA AREA | 11/08/2022 | 05/10/2022 |  |  | 1320 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MB-4E25 | TT_Task | TRANSPORT GT ACCESSORY EQUIPMENT MB | 30/04/2022 | 23/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MB-8-25 | TT_Task | COLD COMMISSIONING GT AUXILIARIES 20MB- | 22/06/2023 | 28/06/2023 |  |  | 16 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MB-4A25 | TT_Task | TRANSPORT INTERCONNECTING PIPING 20MB- | 11/06/2022 | 10/07/2022 |  |  | 104 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20QU-6H15 | TT_Task | ERECTION, NDT, PT / VALVES SAMPLING QU | 20/01/2023 | 09/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6B02 | TT_Task | PRE-ASSEMBLING/ ERECTION LP1-OUTER CASING MA | 11/07/2022 | 31/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBR7-15 | TT_Task | ELECTRICAL INSTALLATION OF EXHAUST GAS SYSTEM DIFFUSER 20MBR | 20/10/2022 | 02/11/2022 |  |  | 1400 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAD7-15 | TT_Task | ELECTRICAL ERECTION ST BEARING CASINGS | 29/09/2022 | 19/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LCB7B15 | TT_Task | ELECTRICAL ERECTION CONDENSATE EXTRACTION PUMP 20LCB | 01/10/2022 | 14/10/2022 |  |  | 1568 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAW7-15 | TT_Task | ELECTRICAL ERECTION SEAL/LEAK STEAM SYSTEM MAW | 01/12/2022 | 14/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SMM4-40 | TT_FinMile | (OTD-OS) ON SITE CRANE SMM01/02/03 FOR 20UMC | 30/03/2022 | 30/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SCA2-60 | TT_FinMile | (DF) INPUT FOR MS3 AIR COMPRESSOR SYSTEM SCA | 14/05/2021 | 14/05/2021 | 14/05/2021 | 14/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20SCA2-66 | TT_FinMile | (DF) INPUT FOR M2 AIR COMPRESSOR SYSTEM SCA (MPA) | 30/07/2021 | 30/07/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20SCA2-85 | TT_Mile | CONTRACT INTO FORCE AIR COMPRESSOR SYSTEM SCA | 21/09/2021 | 21/09/2021 | 21/09/2021 | 21/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20EK-8-10 | TT_FinMile | (TOP-01EK) FUEL GAS RECEIVING AND MIXING SYSTEM 01EK | 15/05/2023 | 15/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-3G80 | TT_FinMile | (RFS) READY FOR SHIPMENT HEATING SURFACES HRSG20 MOD1 (Incl. Hangers/Baffles/ Installation Material) | 02/04/2022 | 02/04/2022 |  |  | 96 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-5-26 | TT_Task | GROUTING OF FRONT AND REAR HP-BEARING PEDESTALS MA | 26/06/2022 | 03/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6-35 | TT_Task | ALIGNMENT REAR LP1-BEARING PEDESTAL TO DRAWING AND DEFLECTION CURVE MA | 22/06/2022 | 30/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6B47 | TT_Task | PLACING LP1-TURBINE PEDESTALS MA | 12/06/2022 | 21/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MB-3-251 | TT_Task | DESIGN / MANUFACTURING GT ACCESSORY EQUIPMENT / CCR / IN-LINE COMPONENTS GT-PIPING MB | 27/11/2021 | 01/04/2022 | 27/11/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--ZTA2A75 | TT_Task | PREPARATION RFQ CHEMICAL CLEANING SYSTEM ZTA | 30/11/2021 | 10/01/2022 | 30/11/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--HB-3C15 | TT_Task | DESIGN SECONDARY STEEL STRUCTURE HRSG | 13/03/2021 | 15/07/2021 | 13/03/2021 | 15/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP--MKA2-86 | TT_Mile | CONTRACT INTO FORCE GENERATOR MKA INCL. COOLER MKA70 | 15/01/2021 | 15/01/2021 | 15/01/2021 | 15/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6B37 | TT_Task | AXIAL AND RADIAL ALIGNMENT LP1-BOTTOM HALF INNER CASING TO SHAFT AND BLADING CLEARANCE MA | 17/09/2022 | 30/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--CYA4-40 | TT_FinMile | (OTD-OS) ON SITE TELECOMM. SUBCONTR. / MATERIAL CYA | 30/11/2022 | 30/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SAM6E15 | TT_Task | ERECTION EQUIPMENT HVAC SYSTEM FOR UMC/USA 20SA | 03/11/2022 | 28/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SAM6F15 | TT_Task | ERECTION DUCTS FOR HVAC SYSTEM UMC | 29/12/2022 | 11/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20S--3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT DUCT FOR HVAC SYSTEM UMC 20SA | 21/07/2022 | 21/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SAM4-25 | TT_Task | TRANSPORT DUCT FOR HVAC SYSTEM UMC 20SA | 22/07/2022 | 12/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BZP2-85 | TT_Mile | CONTRACT INTO FORCE CABLE SUPPORT SYSTEM BZP | 30/09/2021 | 30/09/2021 | 30/09/2021 | 30/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20SGJ4-80 | TT_FinMile | (RFS) READY FOR SHIPMENT (NORTH SEA PORT) FIRE FIGHTING / GAS DETECTION 20SGJ / 20CYQ / 20CYE | 25/02/2022 | 25/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20--P8-14 | TT_Mile | START CHEMICAL CLEANING HRSG20 / 20 STEAM LINES TO ST | 13/05/2023 | 13/05/2023 |  |  | 168 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20M--9-50 | TT_Mile | START BYPASS OPERATION ST20 | 25/07/2023 | 25/07/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKA6E13 | TT_Task | INSTALLING OF HIGH VOLTAGE BUSHINGS MKA | 07/09/2022 | 08/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20GHC6-90 | TT_Mile | DEMIN. WATER AVAILABLE / REQUIRED (PERMANENT) | 18/03/2023 | 18/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BZP2-50 | TT_FinMile | FINAL BOQ CABLE SUPPORT SYSTEM BZP | 07/05/2022 | 07/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BZP3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT CABLE SUPPORT SYSTEM BZP (LOT 1) | 25/03/2022 | 25/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKA6-34 | TT_Task | FIXING OF GENERATOR IN POSITION MKA | 08/09/2022 | 21/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKA5-26 | TT_Task | GROUTING ANCHOR BOLTS MKA | 18/01/2023 | 24/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20QJ-8B12 | TT_FinMile | (TOP-20QJA-01) H2 CENTRAL SUPPLY SYSTEM | 23/02/2023 | 23/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20QJ-6B45 | TT_Task | ERECTION GAS SUPPLY BOTTLES FOR H2 | 22/10/2022 | 28/10/2022 |  |  | 944 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5I45 | TT_FinMile | (RFE) STEEL STRUCTURE ANNEX 20UMC | 02/05/2022 | 02/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEN2-95 | TT_Task | PREPARATION FOUNDATION GROUNDING DWGS 01UEN | 22/09/2021 | 12/12/2021 | 22/09/2021 | 12/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--BZL2-88 | TT_Mile | SPECIFICATION READY LIGHTING/SMALL POWER BZL | 15/05/2021 | 15/05/2021 | 15/05/2021 | 15/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6B12 | TT_Task | FITTING/WELDING/ASSEMBLING CROSS OVER PIPE LP1 MA | 08/10/2022 | 28/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6B39 | TT_Task | FIT AND WELDING LP1-STEAM INLET LINES (incl. DISSASSEMBLING) MA | 29/10/2022 | 18/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6B38 | TT_Task | INSTALLING GUIDE BLADE RINGS AND LP1-TOP HALF INNER CASING AND LP1-TOP HALF OUTER CASING MA | 17/09/2022 | 07/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6B36 | TT_Task | PRELIMINARY ALIGNMENT LP1-TURBINE SHAFT AND LP1-SEALING CASING AND LP1-BOTTOM HALF INNER CASING MA | 10/09/2022 | 16/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6B14 | TT_Task | SET DOWN AND ALIGNMENT LP1-BOTTOM HALF INNER CASING IN LP1-BOTTOM HALF OUTER CASING MA | 04/09/2022 | 07/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--3331-31 | TT_Task | PROJECT SPECIFIC ADAPTION OF GENERAL TCCs | 01/08/2020 | 21/08/2020 | 01/08/2020 | 21/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--3331-30 | TT_Mile | PROJECT INSTRUCTIONS RELEVANT FOR PURCHASE ORDERS AVAILABLE | 10/01/2021 | 10/01/2021 | 10/01/2021 | 10/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA4G25 | TT_Task | TRANSPORT ELECTRICAL MODULES 20UBA7110/20/30 (TO SITE) | 28/04/2022 | 22/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA3E57 | TT_Task | INSTALL. COMP., INT. CABLING, FIRE PROT., SHOP TEST ELECTRICAL MODULES 20UBA7110/20/30 | 19/01/2022 | 06/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UHX2-15 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE 20UHX (if required) | 20/02/2022 | 05/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LBH6D15 | TT_Task | ERECTION BLOW DOWN TANK 20LBH | 22/05/2022 | 20/06/2022 |  |  | 520 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBF5D15 | TT_Task | CONSTRUCTION FENCING FINISHING WORKS 20UBE/UBF | 18/10/2022 | 07/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBF5D45 | TT_FinMile | (RFE) FENCING, FINISHING WORKS 20UBE/UBF | 07/11/2022 | 07/11/2022 |  |  | 288 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBF3D25 | TT_Task | PURCHASING, TRANSPORT FENCING, FINISHING WORKS MATERIAL 20UBF | 14/06/2022 | 05/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBF5B10 | TT_Mile | (HS) START ERECTION STEEL STRUCTURE 20UBE/UBF | 24/05/2022 | 24/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2G75 | TT_FinMile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION 20UBA8110/20 | 10/03/2022 | 10/03/2022 |  |  | 448 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LBA7H15 | TT_Task | ELECTRICAL ERECTION PIPE / VALVES 20LBA10 | 10/03/2023 | 16/03/2023 |  |  | 256 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKA6-40 | TT_FinMile | (RFP) READY FOR PIPE CONNECTION GENERATOR SKIDS READY FOR PIPE CONNECTION MKA | 27/08/2022 | 27/08/2022 |  |  | 1256 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BFT2-80 | TT_Task | QUOTATION STAGE LV-TRANSFORMERS BFT | 30/07/2021 | 21/09/2021 | 30/07/2021 | 21/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--BFT2-15 | TT_Task | BASIC DESIGN / SPECIFICATION LV-TRANSFORMERS BFT | 18/05/2021 | 29/07/2021 | 18/05/2021 | 29/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MB-9-10 | TT_Task | SAFETY VALVES TESTING, 1ST. BASELOAD GT20 | 03/07/2023 | 04/07/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--PAD2-85 | TT_Mile | CONTRACT INTO FORCE COOLING TOWER EQUIPMENT PAD (GFK) | 19/02/2021 | 19/02/2021 | 19/02/2021 | 19/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--PAD2-60 | TT_FinMile | (DF) INPUT FOR MS3 COOLING TOWER PAD | 05/03/2021 | 05/03/2021 | 05/03/2021 | 05/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--PAD2-80 | TT_Task | QUOTATION STAGE COOLING TOWER EQUIPMENT PAD (GFK) | 20/12/2020 | 18/02/2021 | 20/12/2020 | 18/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAD8-55 | TT_Task | COMMISSIONING COOLING WATER SYSTEM | 20/05/2023 | 23/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAA7-05 | TT_Task | ERECTION CURRENT TRANSFORMER 20BAA | 09/09/2022 | 22/09/2022 |  |  | 1712 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BBA2-80 | TT_Task | QUOTATION STAGE MV SWITCHGEAR 20/90BBA/BBB | 01/05/2021 | 13/08/2021 | 01/05/2021 | 13/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20EK-8-97 | TT_Mile | INSPECTIONS EK SYSTEM WITH NOTIFIED BODY | 23/05/2023 | 23/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGJ8-21 | TT_Task | COLD COMMISSIONING FF CO2 SYSTEM FOR 20MPB NOISE ENCLOSURE SGJ | 25/05/2023 | 07/06/2023 |  |  | 64 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--M--2D20 | TT_FinMile | (DF) SYSTEM DOCUMENTS [external interfaces final] | 07/05/2021 | 07/05/2021 | 07/05/2021 | 07/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--B--2-68 | TT_Mile | 80% CABLE PULLING DATA TRANSFER TO SITE | 20/12/2021 | 20/12/2021 | 20/12/2021 | 20/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PGB6H15 | TT_Task | ERECTION, NDT, PT PIPES / VALVES 20PGB | 31/07/2022 | 08/10/2022 |  |  | 1504 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PGB6H17 | TT_Task | INSULATION NDT, PT PIPES / VALVES 20PGB | 01/02/2023 | 21/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--ZTA2-80 | TT_Task | QUOTATION STAGE CHEMICAL CLEANING | 18/06/2022 | 12/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--ZTA2-75 | TT_Task | PREPARATION RFQ CHEMICAL CLEANING | 21/05/2022 | 17/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--L--2-70 | TT_FinMile | (DF) IC DATA L SYSTEMS | 06/07/2021 | 06/07/2021 | 06/07/2021 | 06/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--G--2I35 | TT_Mile | DESIGN DATA SHEETS SAFETY / CONTROL VALVES G-/S- SYSTEMS | 06/08/2021 | 06/08/2021 | 06/08/2021 | 06/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--G--2-80 | TT_FinMile | (DF) IC DATA G-/S- SYSTEMS | 04/09/2021 | 04/09/2021 | 04/09/2021 | 04/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--CYA8-10 | TT_FinMile | (TOP-20CY) COMMUNICATION SYSTEMS | 26/05/2023 | 26/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--ZTA2A00 | TT_Mile | FIX CHEMICAL CLEANING CONCEPT | 18/03/2021 | 18/03/2021 | 18/03/2021 | 18/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--ZTA4A25 | TT_Task | TRANSPORT EQUIPMENT/ MOBILIZATION CHEMICAL CLEANING SYSTEM ZTA | 21/01/2023 | 17/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--ZTA3A25 | TT_Task | DESIGN, PROC. TEMP. PIPING / VALVES FOR CHEMICAL CLEANING SYSTEM ZTA | 13/08/2022 | 12/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--ZTA2A20 | TT_FinMile | (DF) MATERIAL TAKE OFF FOR TEMPORARY PIPING AND VALVES | 16/09/2022 | 16/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--ZTA2A85 | TT_Mile | CONTRACT INTO FORCE CHEMICAL CLEANING PIPING | 13/08/2022 | 13/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LBH8D25 | TT_Task | COLD COMMISSIONING BLOW DOWN TANK (FOR CHEM. CLEANING) 20LBH | 18/04/2023 | 24/04/2023 |  |  | 144 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--SMM2-80 | TT_Task | QUOTATION STAGE CRANES 20SMM01/02 FOR 20UMC | 02/02/2021 | 29/03/2021 | 02/02/2021 | 29/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20GHC8H16 | TT_Task | COMMISSIONING PIPES / VALVES DEMIN WATER 00GHC | 07/04/2023 | 21/04/2023 |  |  | 168 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SMG2-80 | TT_Task | QUOTATION STAGE OTHER CRANES AND HOIST | 07/01/2022 | 17/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA8G25 | TT_Task | ELECTRICAL COMMISSIONING 20UBA7910/20 | 14/03/2023 | 27/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20CH-8A25 | TT_Task | COMMISSIONING ELECTRICAL INTERFACE GRID/PLANT (GT20) | 28/03/2023 | 10/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20GM-6B40 | TT_FinMile | (RFP) READY FOR PIPE CONNECTION SUMP PUMP GM UBF | 14/07/2022 | 14/07/2022 |  |  | 104 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20GM-6B15 | TT_Task | M-ERECTION SUMP PUMPS GM FOR UBF | 08/07/2022 | 21/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20GM-6E15 | TT_Task | M-ERECTION SUMP PUMPS/OIL SEPARATOR GM FOR 20UBH01 | 21/07/2022 | 03/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20GM-6E40 | TT_FinMile | (RFP) READY FOR PIPE CONNECTION SUMP PUMP GM FOR 20UBH01 | 27/07/2022 | 27/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20GM-8E25 | TT_Task | COLD COMMISSIONING PLANT DRAINAGE SYSTEM GM | 22/04/2023 | 28/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--UEN2-60 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UEN | 11/07/2021 | 11/07/2021 | 11/07/2021 | 11/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--BZK2-15 | TT_Task | BASIC DESIGN / SPECIFICATION MV/LV CABLES BZK | 27/07/2021 | 23/08/2021 | 27/07/2021 | 23/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--CKA2-04 | TT_FinMile | APPLICATION SERVER READY FOR INTEGRATION IN ELECTRICAL MODULES | 27/03/2022 | 27/03/2022 |  |  | 304 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-4F40 | TT_FinMile | (OTD-OS) ON SITE OUTLET DUCT HRSG 20 | 19/04/2022 | 19/04/2022 |  |  | 1056 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAD8-26 | TT_Mile | START COLD COMMISSIONING ST 20 | 18/04/2023 | 18/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-4C40 | TT_FinMile | (OTD-OS) ON SITE VALVES &gt; 2 HRSG20 | 30/03/2022 | 30/03/2022 |  |  | 1168 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-3C80 | TT_FinMile | (RFS) READY FOR SHIPMENT VALVES HRSG20 | 16/02/2022 | 16/02/2022 |  |  | 176 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-4C25 | TT_Task | TRANSPORT VALVES &gt; 2 HRSG20 | 11/03/2022 | 30/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAG6-58 | TT_Task | FINAL INSPECTION MAG20 | 29/09/2022 | 01/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAG6-56 | TT_Task | FINAL WORKS AND CLEANING MAG20 | 24/09/2022 | 28/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAG6-46 | TT_Task | ASSEMBLING AND WELDING OF THE CONDENSER NECK STRUCTURE ON BYPASS STEAM REGION MAG20 | 15/08/2022 | 24/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAG6-34 | TT_Task | VACUUM TEST WATER SIDE MAG20 | 04/07/2022 | 10/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAG6-52 | TT_Task | WELDING OF CONDENSER TO LP TURBINE MAG20 | 08/09/2022 | 23/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAD6-71 | TT_FinMile | FINALISATION ERECTION N-TURBINE OUTER CASING ST 40 | 01/04/2023 | 01/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-6-50 | TT_Mile | START PRESSURE TEST HRSG20 | 18/03/2023 | 18/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAT3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT MAIN TRANSFORMERS 20BAT | 13/07/2022 | 13/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAT4-25 | TT_Task | TRANSPORT MAIN TRANSFORMERS 20BAT | 14/07/2022 | 12/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20QU-2-65 | TT_FinMile | (DF) INPUT FOR M2 SAMPLING CONTAINER 20QU | 06/08/2021 | 06/08/2021 | 06/08/2021 | 06/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MB-4-25 | TT_Task | TRANSFER / PREPARATION LIFT / SKID SYSTEM FOR GT20 | 23/07/2022 | 29/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBX2-20 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE 20UBX/20UBG03 | 20/09/2021 | 06/12/2021 | 20/09/2021 | 06/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UBX2-50 | TT_Task | PREPARATION FOUNDATION GROUNDING DWGS 20UBX/20UBG03 | 21/10/2021 | 06/12/2021 | 21/10/2021 | 06/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UBF2B75 | TT_FinMile | (F) DETAIL DESIGN STEEL STRUCTURE WITH CONTRACTOR UBF/UBE | 28/02/2022 | 28/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--UBF2B70 | TT_Task | DETAIL DESIGN STEEL STRUCTURE UBF/UBE | 22/06/2021 | 09/08/2021 | 22/06/2021 | 09/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--HA-2-81 | TT_Task | PROJECT SPECIFIC ADAPTION OF HRSG SPECIFICATION | 01/08/2020 | 14/08/2020 | 01/08/2020 | 14/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--HB-2B60 | TT_FinMile | (DF) INPUT FOR MS3 HRSG | 26/02/2021 | 26/02/2021 | 26/02/2021 | 26/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--HB-2A05 | TT_Mile | GENERAL ARRANGMENT DRAWINGS PRELIMINARY UHA | 05/11/2020 | 05/11/2020 | 05/11/2020 | 05/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20GM-6H17 | TT_Task | ERECTION PIPES DRAINAGE SYSTEM 00GM FROM GAS TURBINE TO UBH01 | 23/10/2022 | 03/12/2022 |  |  | 1056 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20GHD8A10 | TT_FinMile | (TOP-20GHD) SERVICE WATER DISTRIBUTION SYSTEM | 22/04/2023 | 22/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBR4-40 | TT_FinMile | (OTD-OS) ON SITE DIFFUSOR 20MBR | 21/04/2022 | 21/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---9-90 | TT_Mile | START RELIABILITY RUN | 17/12/2023 | 17/12/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--HA-9-45 | TT_Mile | START STEAM BLOWING | 03/07/2023 | 03/07/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---9-75 | TT_Mile | START PERFORMANCE TEST COMBINED CYCLE POWER PLANT | 05/12/2023 | 05/12/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20USX5-10 | TT_Task | WORK PREPARATION, EXCAVATION 20USX | 27/05/2022 | 31/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGA6-15 | TT_Task | ERECTION FIRE FIGHTING INDOOR HYDRANTS SGA 20UMC | 31/07/2022 | 10/09/2022 |  |  | 304 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAR8-06 | TT_FinMile | (TOP-20PAR) COOLING TOWER MAKE UP WATER SYSTEM | 20/04/2023 | 20/04/2023 |  |  | 568 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--URD2-60 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20URD xx | 13/05/2021 | 13/05/2021 | 13/05/2021 | 13/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--URD2-70 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE 20URD xx | 30/05/2021 | 13/07/2021 | 30/05/2021 | 13/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--URA2-75 | TT_FinMile | ATKINS DD DETAIL DESIGN SUBSTRUCTURE-20URA/URD | 01/06/2021 | 01/06/2021 | 01/06/2021 | 01/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20HA-6C22 | TT_Task | ERECTION AND LIFTING MODULE (INCLUDING ALIGNMENT) HRSG20 | 01/04/2022 | 28/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-6C23 | TT_Task | REMAINING SECONDARY PLATFORMS LADDERS etc. HRSG20 | 06/08/2022 | 28/10/2022 |  |  | 160 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--UBA2-70 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE UBA7910/7920 | 24/06/2021 | 07/01/2022 | 24/06/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20MBH8-10 | TT_FinMile | (TOP-20MBH2) GT SECONDARY AIR SYSTEM | 26/04/2023 | 26/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBF3B25 | TT_Task | FABRICATION DESIGN FABRICATION TRANSPORT STEEL STRUCTURE 20UBE/UBF | 01/03/2022 | 23/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2-20 | TT_Task | PREPARATION FOUNDATION GROUNDING DWGS 20UBA1110/20 | 19/08/2021 | 22/10/2021 | 19/08/2021 | 22/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MB-3-25 | TT_Task | DESIGN / PROCUREMENT / MANUFACTURING GAS TURBINE 20MB- | 15/01/2021 | 01/04/2022 | 15/01/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SP20MB-3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT (NORTH SEA PORT) GAS TURBINE 20MB- | 29/04/2022 | 29/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MA-3C81 | TT_FinMile | DELIVERY ST LP OUTER CASING MA- | 18/02/2022 | 18/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAW5A16 | TT_Task | ERECTION OUTDOOR EARTHING 20UBF AREA | 07/11/2022 | 15/01/2023 |  |  | 504 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BAW3-25 | TT_Task | MANUFACTURING / SHOP TEST IN- / OUTDOOR GROUNDING BAW | 30/01/2022 | 26/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BAW4-25 | TT_Task | TRANSPORT IN- / OUTDOOR GROUNDING BAW | 24/04/2022 | 18/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SCA4-40 | TT_FinMile | (OTD-OS) ON SITE AIR COMPRESSOR SYSTEM 20SCA | 05/09/2022 | 05/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SCA2-80 | TT_Task | QUOTATION STAGE AIR COMPRESSOR SYSTEM SCA - ABORTED, DUE TO CLP DECISION TO CHANGE TO OIL FREE | 01/05/2021 | 17/07/2021 | 01/05/2021 | 17/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6E41 | TT_FinMile | (RFP) READY FOR PIPE CONNECTION STEAM TURBINE - MAX/LBA/LBB/LBC | 05/01/2023 | 05/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6A50 | TT_Mile | LP-FLAP READY FOR PRE-ASSEMBLING LBA80-PIPING | 19/11/2022 | 19/11/2022 |  |  | 168 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAH6H15 | TT_Task | ERECTION, NDT, PT / VALVES 20PAH | 30/11/2022 | 10/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PA-6H70 | TT_Task | PRESSURE TEST PAB / 20PAH | 08/04/2023 | 14/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBV8H25 | TT_Task | COLD COMMISSIONING OIL MODULE 20MBV (INCL: FLUSHING) | 01/06/2023 | 07/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBH8-25 | TT_Task | COLD COMMISSIONING TURBINE COOLING SYSTEM 20MBH | 22/06/2023 | 28/06/2023 |  |  | 16 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--P--2-05 | TT_Task | PREPARATION PID'S P-SYSTEMS (INPUT FOR M1) | 08/11/2020 | 14/02/2021 | 08/11/2020 | 14/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--P--2I45 | TT_Mile | DESIGN DATA SHEETS SAFETY / CONTROL VALVES P SYSTEMS | 23/04/2021 | 23/04/2021 | 23/04/2021 | 23/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20LBG2C65 | TT_FinMile | (DF) INPUT FOR M2 EL. SUPERHEATER LBG | 28/05/2021 | 28/05/2021 | 28/05/2021 | 28/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BAA7L55 | TT_Task | CALIBRATING OF CKA SYSTEM (SUPERVISOR) | 03/01/2023 | 05/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAA7-65 | TT_Task | HIGH VOLTAGE/PRESSURE TEST IPB 20BAA | 27/12/2022 | 02/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B95 | TT_FinMile | (RFE) BUILDING FOUNDATION READY FOR ERECTION MAIN STEEL WORK 20UMC | 24/02/2022 | 24/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA8-50 | TT_Task | FEEDER COMMISSIONING LV SWITCHGEAR 20UBA8110/20 | 18/04/2023 | 05/06/2023 |  |  | 200 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--SA-2-05 | TT_Mile | CONCEPT DESIGN HVAC SYSTEM SA COMPLETE | 05/03/2021 | 05/03/2021 | 05/03/2021 | 05/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--SA-2-20 | TT_FinMile | (DF) BASIC DESIGN HVAC SYSTEM SA | 29/04/2021 | 29/04/2021 | 29/04/2021 | 29/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--SA-2-16 | TT_Task | BASIC DESIGN after DF (part II) HVAC SYSTEM SA | 30/04/2021 | 06/05/2021 | 30/04/2021 | 06/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--SA-2-01 | TT_Task | CONCEPT DESIGN HVAC SYSTEM SA | 15/01/2021 | 04/03/2021 | 15/01/2021 | 04/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--SA-2-15 | TT_Task | BASIC DESIGN before DF (part I) HVAC SYSTEM SA | 05/03/2021 | 29/04/2021 | 05/03/2021 | 29/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20EK-8H13 | TT_FinMile | (TOP-20EK) FUEL GAS METERING SYSTEM FOR GT20 | 17/05/2023 | 17/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-4D25 | TT_Task | TRANSPORT DRUMS HRSG20 | 15/04/2022 | 24/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-3D26 | TT_Task | MANUFACTURING DRUMS HRSG20 | 28/02/2021 | 10/01/2022 | 28/02/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20HA-3C25 | TT_Task | DETAIL DESIGN / MANUFACTURING HEATING SURFACES HRSG20 MODULE 1,2,3,4,5,6 | 28/01/2021 | 10/03/2022 | 28/01/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20HAD8G25 | TT_Task | COLD COMMISSIONING HRSG LP STEAM (FOR CHEM. CLEANING) 20HAD80 | 29/04/2023 | 12/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5D40 | TT_FinMile | (RFE) FINISHING WORKS 20UMC | 03/09/2022 | 03/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP--MBK2-80 | TT_Task | PREPARE TEC RFQ DOC TURNING DEVICE MBK | 14/08/2021 | 10/09/2021 | 14/08/2021 | 10/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BFT8-10 | TT_FinMile | (TOP-20BFT01) LV-TRANSFORMER 20BFT01 | 20/02/2023 | 20/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LBH8D10 | TT_FinMile | (TOP-20LBH) HRSG START-UP / SHUT-DOWN STEAM SYSTEM | 17/04/2023 | 17/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--HA-2-59 | TT_Task | DESIGN REVIEW INCL. SIL-STUDY HRSG-SYSTEMS | 19/03/2021 | 22/04/2021 | 19/03/2021 | 22/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--HA-2-05 | TT_Task | PREPARATION PID'S HRSG - SYSTEMS (INPUT FOR M1) | 12/12/2020 | 29/01/2021 | 12/12/2020 | 29/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--SA-2-26 | TT_Mile | FINAL BASIC DESIGN DWGS HVAC SYSTEM SA AVAILABLE (RELEASED FOR DD) | 07/05/2021 | 07/05/2021 | 07/05/2021 | 07/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--ZTA4-25 | TT_Task | TRANSPORT, MOBILIZATION CHEMICAL CLEANING EQUIPMENT | 07/01/2023 | 03/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--ZTA3-25 | TT_Task | DESIGN, PROCUREMENT CHEMICAL CLEANING | 13/08/2022 | 11/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--ZTA2-35 | TT_FinMile | (DF) TEMPORARY PIPING AND PROCEDURE CHEMICAL CLEANING | 11/11/2022 | 11/11/2022 |  |  | 672 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBA4-26 | TT_Task | TRANSPORT GAS TURBINE 20MB- | 30/04/2022 | 23/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--SG-2-40 | TT_Task | PREPARATION FINAL FIRE PROTECTION CONCEPT ESCAPE ROUTE AND FIRE PROTECTION DWGS | 06/06/2021 | 03/07/2021 | 06/06/2021 | 03/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20LBG7A17 | TT_Task | ELECTRICAL ERECTION / VALVES FOR STEAM SYSTEM 20LBG | 18/12/2022 | 24/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LBG7A15 | TT_Task | ELECTRICAL ERECTION / VALVES FOR STEAM SYSTEM 20LBG | 18/12/2022 | 24/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LBA7J15 | TT_Task | ELECTRICAL ERECTION / VALVES 20LBA80 | 03/03/2023 | 09/03/2023 |  |  | 256 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20ZT-6A00 | TT_Task | TEMPORARY INSERTS INSTALLATION FOR EMERGENCY STOP VALVES | 22/04/2023 | 12/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--HA-2E15 | TT_Mile | PREL. PIPING DESIGN BASIC REPORT (PDBR) | 12/12/2020 | 12/12/2020 | 12/12/2020 | 12/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--P--2-70 | TT_FinMile | (DF) IC DATA P SYSTEMS | 06/07/2021 | 06/07/2021 | 06/07/2021 | 06/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--P--2-65 | TT_FinMile | (DF) PROCESS FINAL / INPUT FOR M2 P-SYSTEMS | 04/05/2021 | 04/05/2021 | 04/05/2021 | 04/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BAW2-30 | TT_Task | DETAIL DESIGN LIGHTNING PROTECTION BLDGS | 06/05/2021 | 03/12/2021 | 06/05/2021 | 03/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BAW3-25 | TT_Task | MANUFACTURING,TRANSPORT MATERIAL LIGHTNING PROTECTION | 30/06/2022 | 24/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAW2-75 | TT_FinMile | (F) LIGHTNING PROT. DESIGN BLDGS (YE01) ON SITE, RELEASED FOR EXECUTION | 03/12/2021 | 03/12/2021 | 03/12/2021 | 03/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MBQ6H45 | TT_Task | INSULATION PIPES / VALVES FOR STEAM SYSTEM 20MBQ | 26/02/2023 | 25/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBA4-27 | TT_Task | TRANSPORT GT SUPPORTS 20MB- | 30/04/2022 | 24/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--B--2-30 | TT_Task | DETAIL DESIGN CABLE ROUTING | 01/10/2021 | 19/12/2021 | 01/10/2021 | 19/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--C--2-05 | TT_Mile | GT PLANT ROOM NUMBERING SYSTEM FROM PLANT LAYOUT | 18/04/2021 | 18/04/2021 | 18/04/2021 | 18/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--HA-2A56 | TT_Task | REVIEW PIPE STRESS CALCULATION FOR HRSG-SYSTEMS LAB/LBA10/LBB/C | 23/01/2021 | 12/02/2021 | 23/01/2021 | 12/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MKA9-10 | TT_Task | START UP TEST WITH MBJ 20MBA | 26/06/2023 | 28/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBY9-35 | TT_Task | GT PROTECTION GT20 | 23/06/2023 | 25/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKA9-35 | TT_Task | GT GENERATOR PROTECTION TEST 20MKA | 01/07/2023 | 02/07/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BUK8-50 | TT_Mile | 24V DC CONTROL VOLTAGE / 230V UPS AVAILABLE | 21/02/2023 | 21/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBN5-15 | TT_Mile | (H) START PLACING FORMWORK 20UBN | 23/06/2022 | 23/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-4C25 | TT_Task | TRANSPORT SECONDARY STEEL STRUCTURE HRSG20_Last Part | 31/03/2022 | 29/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA3G80 | TT_FinMile | (RFS) READY FOR SHIPMENT TO SITE ELECTRICAL MODULES 20UBA7110/20/30 (TO SITE) | 27/04/2022 | 27/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20CJF4-40 | TT_FinMile | (OTD-OS) ON SITE ELECTRICAL / IC EQUIPMENT HRSG20 | 18/05/2022 | 18/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20CJF3-80 | TT_FinMile | (RFS) READY FOR SHIPMENTELECTRICAL / IC EQUIPMENT HRSG20 | 18/04/2022 | 18/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-4G40 | TT_FinMile | (OTD-OS) ON SITE HEATING SURFACES HRSG20 MODULE6 | 22/03/2022 | 22/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-4G25 | TT_Task | TRANSPORT HEATING SURFACES HRSG20 MODULE 2-6 | 13/03/2022 | 22/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--URA2-70 | TT_Task | ATKINS DD DETAIL DESIGN SUPERSTRUCTURE -20URA/URD | 30/05/2021 | 24/06/2021 | 30/05/2021 | 24/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--3332-60 | TT_Mile | TCC PREPARATION OF ASSEMBLY DOCUMENTS AVAILABLE | 15/08/2020 | 15/08/2020 | 15/08/2020 | 15/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC3E25 | TT_Task | FABRICATION DESIGN, FABRICATION, TRANSPORT STEEL PLATFORMS LOT1 20UMC | 07/11/2021 | 12/03/2022 | 07/11/2021 |  | 72 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--UHA2-50 | TT_Task | PREPARATION FOUNDATION GROUNDING DWGS UHA | 16/07/2021 | 29/07/2021 | 16/07/2021 | 29/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--BBA2-15 | TT_Task | BASIC DESIGN / SPECIFICATION MV SWITCHGEAR 20/90BBA/BBB | 05/02/2021 | 30/04/2021 | 05/02/2021 | 30/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--L--2-05 | TT_Task | PREPARATION PID'S L-SYSTEMS (INPUT FOR M1) | 29/11/2020 | 15/02/2021 | 29/11/2020 | 15/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--L--2-10 | TT_Task | ENGINEERING PID'S L-SYSTEMS | 12/12/2020 | 29/01/2021 | 12/12/2020 | 29/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--L--2-25 | TT_Task | DESIGN REVIEW INTERFACE ST / L-SYSTEMS | 12/04/2021 | 02/05/2021 | 12/04/2021 | 02/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20GHD7H15 | TT_Task | ELECTRICAL ERECTION PIPES GHD FOR UGD IN UMC | 25/12/2022 | 31/12/2022 |  |  | 896 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7-160 | TT_Task | ERECTION CABLE TRAYS BELOW ELECTRICAL MODULES 20UBA76xx/77xx/7410/73xx/7210/7110 | 21/04/2022 | 25/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20QC-6-40 | TT_FinMile | (RFP) READY FOR PIPE CONNECTION DOSING CONTAINER QC | 03/09/2022 | 03/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2B75 | TT_FinMile | (F) DETAIL DESIGN STEEL STRUCTURE WITH CONTRACTOR 20UMC | 21/10/2021 | 21/10/2021 | 21/10/2021 | 21/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BAW2-27 | TT_Task | RFQ FOR LIGHTNING PROTECTION | 04/12/2021 | 10/12/2021 | 04/12/2021 | 10/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BAW2-85 | TT_Mile | CONTRACT INTO FORCE FOR LIGHTNING PROTECTION | 25/12/2021 | 25/12/2021 | 25/12/2021 | 25/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHA2B-12 | TT_FinMile | (RFS) READY FOR SHIPMENT EMBEDDED PARTS HRSG20 | 03/08/2021 | 03/08/2021 | 03/08/2021 | 03/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20GM-8E10 | TT_FinMile | (TOP-20GM-02) COLLECTION SUMPS AND DRAIN IN BUILDING STRUCTURES | 10/04/2023 | 10/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--PAC3B26 | TT_Task | MANUFACTURING / SHOP TEST CIRC. CW PUMP 20PAC | 09/04/2021 | 02/04/2022 | 09/04/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--UHA2-60 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE UHA | 09/05/2021 | 09/05/2021 | 09/05/2021 | 09/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20LBG4C40 | TT_FinMile | (OTD-OS) ON SITE EL.SUPERHEATER 20LBG | 05/05/2022 | 05/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LBG4C25 | TT_Task | TRANSPORT EL.SUPERHEATER 20LBG | 11/03/2022 | 05/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LBG3C26 | TT_Task | PROCURMENT / PRE-FABRICATION EL.SUPERHEATER 20LBG | 28/06/2021 | 03/10/2021 | 28/06/2021 | 03/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MB-3D80 | TT_FinMile | DELIVERY GT SUPPORTS 20MB- EX WORKS | 01/04/2022 | 01/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MB-3C25 | TT_Task | PROCUREMENT / MANUFACTURING GT SPECIAL TOOLS 20MB- | 23/12/2021 | 01/04/2022 | 23/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SP20MB-3D25 | TT_Task | PROCUREMENT / MANUFACTURING GT SUPPORTS 20MB- | 04/10/2021 | 01/04/2022 | 04/10/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20PAC4B40 | TT_FinMile | (OTD-OS) ON SITE CIRC. CW PUMP 20PAC | 30/05/2022 | 30/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAD4-25 | TT_Task | TRANSPORT ST BEARINGS 20MAD | 08/04/2022 | 02/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAR7A16 | TT_Task | ELECTRICAL ERECTION 10/20 PAR MAKE UP WATER PIPES FOR COOLING TOWER | 15/11/2022 | 28/11/2022 |  |  | 1144 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAR6A15 | TT_Task | ERECTION, NDT, PT / VALVES (MECHANICAL) 20PAR MAKE UP WATER PIPES FOR COOLING TOWER | 04/07/2022 | 14/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5-46 | TT_FinMile | (RFE) FINISHING WORKS 20UBA8110/20 | 28/06/2022 | 28/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5-11 | TT_Mile | (H) START PLACING FORMWORK 20UBA8110/20 | 24/05/2022 | 24/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAD4-40 | TT_FinMile | (OTD-OS) ON SITE ST BEARINGS 20MAD | 02/06/2022 | 02/06/2022 |  |  | 56 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT COOLING TOWER EQUIPMENT (EU) 20PAD FILL BATCH 1 | 22/06/2022 | 22/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD4-25 | TT_Task | TRANSPORT (EU) 20PAD FILL BATCH 1 | 23/06/2022 | 10/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MA-4C25 | TT_Task | TRANSPORT ST LP OUTER CASING MA- | 23/03/2022 | 21/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MA-3C80 | TT_FinMile | (RFS) READY FOR SHIPMENT ST LP OUTER CASING MA- | 20/03/2022 | 20/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BAW2-14 | TT_Task | GROUNDING MEASUREMENT / GROUNDING DESIGN REPORT | 26/02/2021 | 22/04/2021 | 26/02/2021 | 22/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--BZL2-86 | TT_Task | BASIC DESIGN, SPECIFICATION LIGHTING/SMALL POWER BZL | 20/02/2021 | 14/05/2021 | 20/02/2021 | 14/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20EK-7I15 | TT_Task | ELECTRICAL ERECTION / VALVES 20EKG70 | 26/02/2023 | 11/03/2023 |  |  | 152 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B35 | TT_FinMile | (RFE) RELEASED PROTOCOL CRANE RAIL AVAILABLE 20UMC | 16/04/2022 | 16/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20QU-7-15 | TT_Task | ELECTRICAL ERECTION SAMPLING CONTAINER 20QU | 02/12/2022 | 08/12/2022 |  |  | 1192 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MB-7H15 | TT_Task | ELECTRICAL ERECTION / VALVES 20MB (BOP) | 29/01/2023 | 04/02/2023 |  |  | 648 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI---1P6A05 | TT_Task | PREFABRICATION ON SITE ALL SYSTEMS - LOT 4 | 28/04/2022 | 19/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-4B25 | TT_Task | TRANSPORT SECONDARY STEEL STRUCTURE HRSG20_1st Part incl. Drum Supports | 15/02/2022 | 06/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20QJ-8B11 | TT_FinMile | (TOP-20QJA-02) CO2 CENTRAL SUPPLY SYSTEM | 24/04/2023 | 24/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UVM5-11 | TT_Mile | (H) START PLACING FORMWORK 20UVM01 | 25/05/2022 | 25/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LAC7B15 | TT_Task | ELECTRICAL ERECTION FEEDWATER PUMPS 20LAC | 20/08/2022 | 14/10/2022 |  |  | 96 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20L--8-35 | TT_Task | COLD COMMISSIONING WATER SYSTEMS AFTER CHEMICAL CLEANING 20LAA/LCA30/EKT30 | 05/06/2023 | 11/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LBA8-35 | TT_Task | FINAL COLD COMMISSIONING STEAM SYSTEM 20LBA | 12/06/2023 | 18/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKA5-25 | TT_Task | FIRST GROUTING OF FIXATORS MKA | 03/07/2022 | 09/07/2022 |  |  | 128 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKA6-18 | TT_Mile | GENERATOR READY FOR Cable Trays / E and IC / Fire Fighting / Enclosure | 10/09/2022 | 10/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20EK-3-26 | TT_Task | DESIGN / MANUFACTURING / PRE ERECTION / SHOP TEST GAS FINAL FILTER/ PREHEATER 20EKG | 28/06/2021 | 19/07/2022 | 28/06/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20HA-9A45 | TT_Mile | START STEAM BLOWING HRSG 20 | 03/07/2023 | 03/07/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBA6-40 | TT_Mile | (RFP) READY FOR PIPE CONNECTION GT20 MBA | 16/10/2022 | 16/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--CYA2-80 | TT_Task | QUOTATION STAGE TELECOMMUNICATION CYA | 31/01/2022 | 29/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BZP2-30 | TT_Task | DETAIL DESIGN CABLE SUPPORT SYSTEM BZP | 08/01/2022 | 01/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--SA-2-27 | TT_FinMile | INPUT FOR HEAT LOADS DC HVAC-SYS. SA | 04/03/2021 | 04/03/2021 | 04/03/2021 | 04/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MBX4C25 | TT_Mile | SUPPLY GT HYDRAULIC OIL 20MBX | 12/02/2023 | 12/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BZL2-80 | TT_Task | QUOTATION STAGE LIGHTING SMALL POWER BZL | 13/05/2021 | 15/12/2021 | 13/05/2021 | 15/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BTA3-25 | TT_Task | DETAIL DESIGN / MANUFACTURING / SHOP TEST BATTERIES RACKS BTA | 18/11/2021 | 20/02/2022 | 18/11/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20BTA3A25 | TT_Task | DETAIL DESIGN / MANUFACTURING / SHOP TEST BATTERIES BTA | 18/11/2021 | 18/05/2022 | 18/11/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20HB-4D40 | TT_FinMile | (OTD-OS) ON SITE STACK HRSG20 | 19/04/2022 | 19/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--EK-8-08 | TT_Mile | FUEL GAS REQUIRED FROM CUSTOMER | 26/04/2023 | 26/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--HA-2A11 | TT_Task | PROJECT SPEC. PREL. PIPE ROUTING AND SUPPORT CONCEPT HRSG | 31/10/2020 | 11/12/2020 | 31/10/2020 | 11/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--HA-2A55 | TT_Task | STRESS ANALYSIS BY MTEC FOR HRSG-SYSTEMS LAB/LBA10/LBB/C | 12/12/2020 | 22/01/2021 | 12/12/2020 | 22/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--HA-2A09 | TT_Mile | PREL. PIPE STRESS ANALYSIS REPORT FOR HRSG-SYSTEMS LAB/LBA10/LBB/C AVAILABLE | 23/01/2021 | 23/01/2021 | 23/01/2021 | 23/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2B45 | TT_Task | BASIC DESIGN / STEEL COLUMN ANCHORING DWG, STATIC ANALYSIS 20UMC | 24/01/2021 | 02/03/2021 | 24/01/2021 | 02/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA3G25 | TT_Task | MANUFACTURING ELECTRICAL MODULES 20UBA7110/20/30 | 18/08/2021 | 18/01/2022 | 18/08/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20LCA8M25 | TT_Task | COLD COMMISSIONING MAIN COND. SYSTEM IN MIN. FLOW OPERATION (FOR CHEM. CLEANING) LCA/LCB | 29/04/2023 | 06/05/2023 |  |  | 48 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20EKG6I15 | TT_Task | ERECTION, NDT, PT PIPES - 20EKG | 05/01/2023 | 23/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20XKA8-25 | TT_Task | COMMISSIONING EMERGENCY POWER GENERATOR XKA | 27/05/2023 | 02/06/2023 |  |  | 104 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20XKA3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT EMERGENCY DIESEL GEN.SET XKA | 13/07/2022 | 13/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20XKA4-25 | TT_Task | TRANSPORT EMERGENCY DIESEL GEN.SET 00XKA | 14/07/2022 | 07/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BFA8-10 | TT_FinMile | (TOP-20BFA) LV SWITCHGEAR 20BFA/BMA/BFB | 06/02/2023 | 06/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKA7-42 | TT_Mile | GENERATOR READY FOR BAA CONNECTION 20MKA | 18/08/2022 | 18/08/2022 |  |  | 176 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAG6-14 | TT_Task | PLACING STEAM SHELL (LOWER PART) AND CONNECTION/WELDING TO HOTWELL MAG20 | 24/05/2022 | 02/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAG6-30 | TT_Task | ASSEMBLING AND WELDING OF NOZZLES INTO THE STEAM DOME MAG20 | 11/07/2022 | 17/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAG6-42 | TT_Task | FITTING AND BOLTING OF FRONT AND REAR COVER WITH SEAL MAG20 | 21/07/2022 | 30/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAG6-38 | TT_Task | CHECKING THE CORROSION PROTECTION OF THE COOLING WATER SPACES MAG20 | 18/07/2022 | 20/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAG6-40 | TT_FinMile | (RFP) READY FOR PIPE CONNECTION CONDENSER - PAB | 13/08/2022 | 13/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAG6-48 | TT_Task | CIRCULATING WATER SIDE LEAK TEST MAG20 | 07/08/2022 | 13/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBX5B10 | TT_Mile | (HS) START ERECTION STEEL STRUCTURE 20UBX/20UBG | 22/07/2022 | 22/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBX5B45 | TT_FinMile | (RFE) STEEL STRUCTURE 20UBX/20UBG | 04/08/2022 | 04/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20CFE7-16 | TT_Task | ERECTION CONTINIOUS EMISSION MONITORING SYSTEM HRSG20 | 14/07/2022 | 27/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20GHC7H17 | TT_Task | ERECTION, NDT, PT / VALVES DEMIN WATER 20GHC IN UHY (UNDER HRSG INLET DUCT) | 15/11/2022 | 28/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2G03 | TT_Mile | E-AND IC- MANUALS FOR COMP.INSTALL.AVAILABLE ELECTRICAL MODULES 20UBA7110/20/30 | 22/12/2021 | 22/12/2021 | 22/12/2021 | 22/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MAG8-25 | TT_Task | COLD COMMISSIONING CONDENSING/ ST DRAIN SYSTEM MAG/MAL | 26/04/2023 | 28/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6-14 | TT_Mile | START CHEMICAL CLEANING | 13/05/2023 | 13/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BFT2-75 | TT_Mile | RFQ LV-TRANSFORMERS LV-TRANSFORMERS BFT | 30/07/2021 | 30/07/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20LBA6H15 | TT_Task | ERECTION, NDT PIPE / VALVES 10LBA10 (BOP) | 24/08/2022 | 16/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--3335-62 | TT_Task | SSM OFFICE ERECTION | 01/05/2021 | 08/06/2021 | 01/05/2021 | 08/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--3335-65 | TT_Task | CONSTRUCTION OF SIEMENS SITE CONTRACTOR OFFICE AREA | 01/07/2021 | 27/09/2021 | 01/07/2021 | 28/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20CR-8-10 | TT_FinMile | (TOP-20CR) CONTROL ROOM EQUIPMENT | 20/02/2023 | 20/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-6-70 | TT_FinMile | HRSG20 - READY FOR HOT GAS | 23/06/2023 | 23/06/2023 |  |  | 56 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2H02 | TT_Mile | E-AND IC- MANUALS FOR COMP.INSTALL.AVAILABLE ELECTRICAL MODULES 20UBA7310/30 | 21/10/2021 | 21/10/2021 | 21/10/2021 | 21/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA3H55 | TT_Task | INSTALL. COMP., INT. CABLING, FIRE PROT., SHOP TEST ELECTRICAL MODULES 20UBA7310/30 | 19/11/2021 | 27/01/2022 | 19/11/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20BBT8-25 | TT_Task | COMMISSIONING AUX. TRANSFORMER 20BBT01 | 07/03/2023 | 13/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BBT4-25 | TT_Task | TRANSPORT AUX. TRANSFORMER 20BBT | 14/07/2022 | 12/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAA2-62 | TT_FinMile | (DF) INPUT FOR MS3 COOLING TOWER COARSE SCREEN 20PAA (MPA) | 06/05/2021 | 06/05/2021 | 06/05/2021 | 06/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-74 | TT_Mile | (H) START PLACING FORMWORK 20UTG07 | 02/05/2022 | 02/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGC8-25 | TT_Task | COLD COMMISSIONING SPRAY DELUGE SYSTEM UNDER ELECTRICAL MODULES 20UBA76xx/77xx/7410/73xx/7210/7110 20SGC | 27/02/2023 | 05/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20M--7A15 | TT_Task | ELECTRICAL ERECTION FOR MKC01/MBJ01 | 11/07/2022 | 28/08/2022 |  |  | 1520 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BAW2-74 | TT_Mile | TENDER BOQ IN- / OUTDOOR GROUNDING | 19/12/2021 | 19/12/2021 | 19/12/2021 | 19/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20HB-4A41 | TT_FinMile | (OTD-OS) ON SITE MAIN STEEL STRUCTURE HRSG20 (FRAME / CASING) | 03/01/2022 | 03/01/2022 |  |  | 88 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-3A81 | TT_FinMile | (RFS) READY FOR SHIPMENT MAIN STEEL STRUCTURE HRSG20 (Incl. Installation Material) | 29/12/2021 | 29/12/2021 | 29/12/2021 | 29/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA4H25 | TT_Task | TRANSPORT ELECTRICAL MODULES 20UBA7910/20 | 02/06/2022 | 27/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAW4-25 | TT_Task | TRANSPORT GLAND STEAM CONDENSER 20MAW | 30/04/2022 | 24/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBF5B45 | TT_FinMile | (RFE) STEEL STRUCTURE 20UBE/UBF | 13/06/2022 | 13/06/2022 |  |  | 480 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LBF6H47 | TT_Task | ASSEMBLY / ERECTION, BYPASS STATION 20LBF | 20/08/2022 | 16/09/2022 |  |  | 480 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20QCB8-10 | TT_FinMile | (TOP-20QCB) CARBOHYDRAZIDE DOSING SYSTEM FOR CCW | 10/04/2023 | 10/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-8-35 | TT_Task | FINAL COLD COMMISSIONING HRSG 20HAD/LBH | 12/06/2023 | 18/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-8-25 | TT_Task | COLD COMMISSIONING DISTRIBUTION PANEL HRSG 20HA | 18/04/2023 | 24/04/2023 |  |  | 384 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BFT8-75 | TT_Mile | ENERGISING LV-TRANSFORMERS 20BFT01 | 07/03/2023 | 07/03/2023 |  |  | 336 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BFT8-25 | TT_Task | COMMISSIONING LV-TRANSFORMERS 20BFT01 | 21/02/2023 | 06/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAV6-40 | TT_FinMile | (RFP) READY FOR PIPE CONNECTION LUBE OIL MODUL MAV | 10/08/2022 | 10/08/2022 |  |  | 296 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAH7-25 | TT_Task | E- AND IC-ERECTION CONDENSER TUBE CLEANING SYSTEM 20PAH | 22/10/2022 | 04/11/2022 |  |  | 1504 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LBA8J10 | TT_FinMile | (TOP-20LBA80) LP MAIN STEAM SYSTEM | 17/04/2023 | 17/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BFT7-15 | TT_Task | ERECTION LV-TRANSFORMERS 20BFT01/02 | 29/06/2022 | 19/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGY6-15 | TT_Task | ERECTION FIRE FIGTHING SYSTEM 20SGA | 04/09/2022 | 01/10/2022 |  |  | 1472 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAJ7B15 | TT_Task | ELECTRICAL ERECTION VACUUM PUMP UNIT MAJ | 01/12/2022 | 14/12/2022 |  |  | 768 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAX7-15 | TT_Task | ELECTRICAL ERECTION HYDRAULIC SYSTEM MAX | 15/12/2022 | 28/12/2022 |  |  | 1280 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-6-43 | TT_Task | ERECTION STACK HRSG20_1st part | 11/06/2022 | 17/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LBB6J73 | TT_Task | PT, RE-INSTALLATION PIPES / VALVES LBB-LBC80 | 04/02/2023 | 16/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LAC6B16 | TT_Task | ERECTION OF NOISE ENCLOSURE FEEDWATER PUMPS 20LAC | 18/08/2022 | 26/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--LCB2B80 | TT_Task | QUOTATION STAGE CONDENSATE EXTRACTION PUMP LCB | 05/02/2021 | 08/04/2021 | 05/02/2021 | 08/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--LCB2B65 | TT_FinMile | (DF) INPUT FOR M2 CONDENSATE EXTRACTION PUMPS LCB | 21/05/2021 | 21/05/2021 | 21/05/2021 | 21/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6C00 | TT_Task | CLEANING K-TURBINE AND PREPARATION OF ASSEMBLY MA | 31/07/2022 | 03/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAJ6-25 | TT_Task | PLACING, ALIGNMENT AND GROUTING MAJ-SKID (VACUUM-PUMPS) | 31/05/2022 | 02/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--UBA2G85 | TT_Mile | CONTRACT INTO FORCE ELECTRICAL MODULES UBA (all) | 18/05/2021 | 18/05/2021 | 18/05/2021 | 18/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UBA2G75 | TT_Mile | RFQ ELECTRICAL MODULES UBA | 01/03/2021 | 01/03/2021 | 01/03/2021 | 01/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MBP8-10 | TT_FinMile | (TOP-20MBP) GT FUEL GAS SYSTEM | 26/04/2023 | 26/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAJ6A15 | TT_Task | ERECTION, NDT, PT PIPES / VALVES MAJ | 08/07/2022 | 18/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LBG7C15 | TT_Task | E- AND IC-ERECTION EL.SUPERHEATER 20LBG | 01/10/2022 | 07/10/2022 |  |  | 1536 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LBG6C15 | TT_Task | ERECTION EL.SUPERHEATER 20LBG | 06/05/2022 | 02/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LBG6C40 | TT_FinMile | (RFP) READY FOR PIPE CONNECTION EL.SUPERHEATER 20LBG | 12/05/2022 | 12/05/2022 |  |  | 56 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20QCD8-10 | TT_FinMile | (TOP-20QCD) AMMONIA DOSING SYSTEM FOR CONDENSATE | 22/04/2023 | 22/04/2023 |  |  | 176 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20QCC8-10 | TT_FinMile | (TOP-20QCH) CAUSTIC SODA DOSING SYSTEM FOR CONDENSATE | 22/04/2023 | 22/04/2023 |  |  | 176 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LBG2C80 | TT_Task | QUOTATION STAGE EL. SUPERHEATER LBG | 12/03/2021 | 06/06/2021 | 12/03/2021 | 06/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20LBG2C75 | TT_Task | CONTRACT REVIEW / PREP. RFQ EL. SUPERHEATER LBG | 12/02/2021 | 11/03/2021 | 12/02/2021 | 11/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20SCA6-40 | TT_FinMile | (RFP) READY FOR PIPE CONNECTION COMPRESSED AIR/INSTRUMENT AIR SYSTEM SCA/QFA | 19/09/2022 | 19/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SCA4-25 | TT_Task | TRANSPORT AIR COMPRESSOR SYSTEM 20SCA | 12/07/2022 | 05/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20CJT3-25 | TT_Task | MANUFACTURING SFC CUBICLES 20CJT | 01/06/2021 | 21/02/2022 | 01/06/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--UBF2-50 | TT_Task | PREPARATION FOUNDATION GROUNDING DWGS UBF/UBE | 27/07/2021 | 09/08/2021 | 27/07/2021 | 09/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--B--2-92 | TT_Task | CABLE SPIDER | 05/02/2021 | 19/03/2021 | 05/02/2021 | 19/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5D45 | TT_Task | COMPLETION FINISHING WORKS 20UMC | 04/09/2022 | 01/10/2022 |  |  | 3648 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5D35 | TT_Task | CONSTRUCTION FINISHING WORKS 20UMC | 10/07/2022 | 03/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBN2-15 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE 20UBN | 07/01/2022 | 20/02/2022 |  |  | 928 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--LDK2B05 | TT_Task | BASIC DESIGN / PREPARATION PID'S CONDENSATE POLISHING PLANT 20LD | 03/02/2021 | 02/03/2021 | 03/02/2021 | 02/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20HAD8G10 | TT_FinMile | (TOP-20HAD80) HRSG LP SYSTEM | 28/04/2023 | 28/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6C15 | TT_Task | CLEANING MAIN K-BEARING AND PLACING AUXILIARY K-BEARINGS MA | 06/08/2022 | 07/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6A10 | TT_Mile | PLACING K-TURBINE ON BEARING PEDESTALS MA | 31/07/2022 | 31/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6B82 | TT_Mile | PLACING LP1-TURBINE SHAFT MA | 08/09/2022 | 08/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAA6A45 | TT_Task | INSULATION PIPES / VALVES FOR STEAM SYSTEM MAA-C | 19/11/2022 | 23/12/2022 |  |  | 920 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAA6A15 | TT_Task | ERECTION, NDT, PT PIPES / VALVES MAA-C | 17/09/2022 | 18/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LBG2C85 | TT_Mile | CONTRACT INTO FORCE EL. SUPERHEATER LBG | 07/06/2021 | 07/06/2021 | 07/06/2021 | 07/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20CHY3-25 | TT_Task | DETAIL DESIGN /MANUFACTURING / SHOP TEST PROT./ SYNCHR./METERING 20CHA/CHY/CJN | 09/09/2021 | 14/02/2022 | 09/09/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--SG-2-20 | TT_FinMile | PRELIMINARY FIRE- EXPLOSION PROTECTION CONCEPT AVAILABLE | 28/09/2020 | 28/09/2020 | 28/09/2020 | 28/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--SG-2-10 | TT_Task | PREPARATION FIRE-/ EXPLOSION PROTECTION CONCEPT | 01/09/2020 | 28/09/2020 | 01/09/2020 | 28/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBX5-10 | TT_Mile | (H) START PLACING FORMWORK 20UBX/20UBG03 | 12/05/2022 | 12/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBX5-05 | TT_Task | WORK PREPARATION / EXCAVATION / PILE TRIMMING / PLATE WELDING 20UBX/20UBG03 | 05/05/2022 | 11/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-6A17 | TT_Mile | START ERECTION SUPP. STEEL STRUCTURE HRSG20 | 15/01/2022 | 15/01/2022 |  |  | 3640 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B45 | TT_Task | FINISHING WORKS / CURING TIME BUILDING FOUNDATION 20UMC | 18/02/2022 | 24/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAG3M70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) MODULE 20MAG50Y | 19/02/2022 | 19/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAG3M80 | TT_FinMile | (RFS) READY FOR SHIPMENT MODULE 20MAG50Y | 18/03/2022 | 18/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UPY4M10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION MODULE 20UPY00Y | 20/06/2022 | 17/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UPY3M70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) MODULE 20UPY00Y | 19/06/2022 | 19/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UPY3M80 | TT_FinMile | (RFS) READY FOR SHIPMENT MODULE 20UPY00Y | 17/07/2022 | 17/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PCB4M10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION MODULE 20PCB10Y | 20/03/2022 | 16/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PCB3M70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) MODULE 20PCB10Y | 20/03/2022 | 20/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PGB4M10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION MODULE 20PGB10Y | 20/03/2022 | 16/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PGB3M70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) MODULE 20PGB10Y | 20/03/2022 | 20/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LDK4M10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION MODULE 20LDK00Y | 19/02/2022 | 18/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LDK3M70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) MODULE 20LDK00Y | 19/02/2022 | 19/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MKA4-11 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION GENERATOR SKIDS 20MKA | 02/04/2022 | 29/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MKA3-71 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) GENERATOR SKIDS 20MKA | 01/04/2022 | 01/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MA-4-11 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION ST LP OUTER CASING MA- | 19/02/2022 | 20/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MA-3-71 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) ST LP OUTER CASING MA- | 18/02/2022 | 18/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MA-4-10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION STEAM TURBINE (HI-L) | 16/04/2022 | 06/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MA-3-70 | TT_Mile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) STEAM TURBINE (HI-L) | 16/04/2022 | 16/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MAD4-10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION ST BEARINGS 20MAD | 11/03/2022 | 07/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MAD3-70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) ST BEARINGS 20MAD | 10/03/2022 | 10/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MKA4-10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION GEN. 20MKA | 02/04/2022 | 29/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MKA3-70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) ST GEN. 20MKA | 02/04/2022 | 02/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MAX4-10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION ST HYDRAULIC SYSTEM 20MAX | 02/04/2022 | 29/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MAX3-70 | TT_Mile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) ST HYDRAULIC SYSTEM 20MAX | 02/04/2022 | 02/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MAW4-10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION GLAND STEAM CONDENSER 20MAW | 02/04/2022 | 29/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MAW3-70 | TT_Mile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) GLAND STEAM CONDENSER 20MAW | 02/04/2022 | 02/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MBR4-10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION DIFFUSER 20MBR | 23/02/2022 | 22/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MBR3-70 | TT_Mile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) DIFFUSER 20MBR | 23/02/2022 | 23/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC2B-35 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION - EMBEDDED PARTS (UMC) | 16/06/2021 | 13/07/2021 | 16/06/2021 | 13/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC2B-30 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) - EMBEDDED PARTS (UMC) | 16/06/2021 | 16/06/2021 | 16/06/2021 | 16/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC2B-40 | TT_FinMile | (RFS) READY FOR SHIPMENT EMBEDDED PARTS (UMC) | 13/07/2021 | 13/07/2021 | 13/07/2021 | 13/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MAL4M10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION MODULE 20MAL00YC | 19/02/2022 | 18/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAL3M70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) MODULE 20MAL00YC | 19/02/2022 | 19/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAG4M10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION MODULE 20MAG50Y | 19/02/2022 | 18/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MAV4-10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION LUBE OIL MODULE 20MAV | 02/04/2022 | 29/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MAV3-70 | TT_Mile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) LUBE OIL MODULE 20MAV | 02/04/2022 | 02/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MAN4-10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION ST BYPASS VALVES 20MAN | 29/04/2022 | 26/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MAN3-70 | TT_Mile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) ST BYPASS VALVES 20MAN | 29/04/2022 | 29/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MAJ4-10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION AIR REMOVAL SYSTEM 20MAJ | 15/02/2022 | 14/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MAJ3-70 | TT_Mile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) AIR REMOVAL SYSTEM 20MAJ | 15/02/2022 | 15/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MAG4-11 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION ST CONDENSER 20MAG | 22/02/2022 | 21/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MAG3-70 | TT_Mile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) ST CONDENSER 20MAG | 22/02/2022 | 22/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PCB3M80 | TT_FinMile | (RFS) READY FOR SHIPMENT MODULE 20PCB10Y | 16/04/2022 | 16/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--PCB2B76 | TT_Mile | RFQ / TECHN. SPEC. READY SERVICE COOLING WATER BOOSTER PUMP PCB | 07/02/2021 | 07/02/2021 | 07/02/2021 | 07/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PCB3B80 | TT_FinMile | (RFS) READY FOR SHIPMENT SERVICE COOLING WATER BOOSTER PUMP 20PCB | 16/11/2021 | 16/11/2021 | 16/11/2021 | 16/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--PCB2B75 | TT_Task | CONTRACT REVIEW / PREP. RFQ SERVICE COOLING WATER BOOSTER PUMP PCB | 10/01/2021 | 06/02/2021 | 10/01/2021 | 06/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--PCB2B85 | TT_Mile | CONTRACT INTO FORCE SERVICE COOLING WATER BOOSTER PUMP PCB | 31/03/2021 | 31/03/2021 | 31/03/2021 | 31/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--PCB2B80 | TT_Task | QUOTATION STAGE SERVICE COOLING WATER BOOSTER PUMP PCB | 07/02/2021 | 30/03/2021 | 07/02/2021 | 30/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PCB3B31 | TT_Task | MANUFACTURING / SHOP TEST SERVICE COOLING WATER BOOSTER PUMP 20PCB | 31/03/2021 | 19/10/2021 | 31/03/2021 | 19/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PCB4B25 | TT_Task | TRANSPORT TO SKIDDER SERVICE COOLING WATER PUMP 20PCB (AIR CARGO, needs to arrive at Skidder 30.12.21) | 17/11/2021 | 10/01/2022 | 17/11/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20PCB4M25 | TT_Task | TRANSPORT MODULE 20PCB10Y | 17/04/2022 | 10/05/2022 |  |  | 88 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PCB4M24 | TT_FinMile | DELIVERY OF COMPONENTS MODULE_PCB PUMP / DEBRIS FILTER | 10/01/2022 | 10/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LCA6A16 | TT_Task | ERECTION, NDT, PIPES / VALVES 20LCA - UNDER HRSG INLET DUCT | 04/07/2022 | 17/07/2022 |  |  | 304 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP--B--2-60 | TT_Mile | FUPs AVAILABLE | 21/08/2021 | 21/08/2021 | 21/08/2021 | 21/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA7-25 | TT_Task | CABLING INTERNAL ELECTRICAL MODULES 20UBA7910/20- PART OF ELECTRICAL MODULES ASSEMBLY | 21/08/2022 | 03/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA7-104 | TT_Task | CABLING INTERNAL 20UBA7710/20 - PART OF ELECTRICAL MODULES ASSEMBLY | 02/09/2022 | 15/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BFA8-36 | TT_Mile | TEMPORARY POWER AVAILABLE FOR COMMISSIONING (400A/400V) | 07/02/2023 | 07/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAC3B80 | TT_FinMile | (RFS) READY FOR SHIPMENT CIRC. CW PUMP 20PAC | 30/04/2022 | 30/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAS4B10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION - CT MAKE-UP WATER PUMP PAS | 07/01/2022 | 03/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAS3B70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) - CT MAKE-UP WATER PUMP PAS | 06/01/2022 | 06/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LCA4B10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION CONDENSATE RECIRC.PUMP 20LCA51 | 20/10/2021 | 16/11/2021 | 20/10/2021 | 16/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20LCA3B70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) CONDENSATE RECIRC.PUMP 20LCA51 | 19/10/2021 | 19/10/2021 | 19/10/2021 | 19/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20LBF4B10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION - BYPASS STATION 20LBF | 07/03/2022 | 03/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LBF3B70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) - BYPASS STATION 20LBF | 06/03/2022 | 06/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LBH4B10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION BLOW DOWN TANK 20LBH | 10/02/2022 | 09/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LBH3B70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) BLOW DOWN TANK 20LBH | 09/02/2022 | 09/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBY5-48 | TT_FinMile | (RFE) FOUNDATION 20UBY01 | 14/07/2022 | 14/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBY5-06 | TT_Task | WORK PREPARATION, EXCAVATION 20UBY01 | 17/06/2022 | 23/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBY5-10 | TT_Mile | (H) START PLACING FORMWORK 20UBY01 | 24/06/2022 | 24/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--CYA4-10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION TELECOMMUNICATION CYA | 02/10/2022 | 31/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--CYA3-70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) TELECOMMUNICATION CYA | 01/10/2022 | 01/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BZP4-12 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION LIGHTING SMALL POWER BZL HIGHBAY, 20UMC | 08/04/2022 | 05/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BZL3-70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) LIGHTING SMALL POWER BZL HIGHBAY, 20UMC | 07/04/2022 | 07/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BZP4-10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION CABLE SUPPORT SYSTEM BZP (LOT 1) | 12/03/2022 | 25/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BZP3-70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) CABLE SUPPORT SYSTEM BZP (LOT 1) | 11/03/2022 | 11/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BAW4-10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION IN- / OUTDOOR GROUNDING BAW | 27/03/2022 | 23/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BAW3-70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) IN- / OUTDOOR GROUNDING BAW | 26/03/2022 | 26/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20UBA3H80 | TT_FinMile | (RFS) READY FOR SHIPMENT ELECTRICAL MODULES 20UBA7910/20 | 01/06/2022 | 01/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PDB4B10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION DEBRIS FILTER 20PDB | 03/12/2021 | 16/12/2021 | 03/12/2021 | 16/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PDB3B70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) DEBRIS FILTER 20PDB | 03/12/2021 | 03/12/2021 | 03/12/2021 | 03/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAH4B10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION CONDENSER TUBE CLEANING SYSTEM 20PAH (BALL STRAINER) | 29/11/2021 | 26/12/2021 | 29/11/2021 | 26/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAH3B70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) CONDENSER TUBE CLEANING SYSTEM 20PAH (BALL STRAINER) | 26/12/2021 | 26/12/2021 | 26/12/2021 | 26/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20SCA4B10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION AIR COMPRESSOR SYSTEM 20SCA | 14/06/2022 | 11/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SCA3B70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) AIR COMPRESSOR SYSTEM 20SCA | 13/06/2022 | 13/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LBG4C10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION EL.SUPERHEATER 20LBG | 11/02/2022 | 10/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LBG3C70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) EL.SUPERHEATER 20LBG | 10/02/2022 | 10/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LCL4B10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION BOILER BLOWDOWN PUMP 20LCL | 29/04/2022 | 26/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LCL3B70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) BOILER BLOWDOWN PUMP 20LCL | 28/04/2022 | 28/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBR8-27 | TT_Task | COLD COMMISSIONING EXHAUST DIFFUSER 20MBR | 08/06/2023 | 14/06/2023 |  |  | 8 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBR8-26 | TT_FinMile | (TOP-20MBR) GT EXHAUST DIFFUSER 20MBR | 26/04/2023 | 26/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--HA-2-95 | TT_Mile | PREL. ELECTRICAL LOAD DATA (VEL) LV HRSG | 22/01/2021 | 22/01/2021 | 22/01/2021 | 22/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--5552-85 | TT_Mile | CONTRACT INTO FORCE MAIN CIVIL WORKS | 14/05/2021 | 14/05/2021 | 14/05/2021 | 14/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--5552-81 | TT_Task | QUOTATION STAGE MAIN CIVIL WORKS | 01/02/2021 | 13/05/2021 | 01/02/2021 | 13/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--5552-11 | TT_Task | PREPARE RFQ MAIN CIVIL WORKS | 13/12/2020 | 31/01/2021 | 13/12/2020 | 31/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--5555-15 | TT_Task | MOBILISATION OF CONTRACTOR (MAIN CIVIL WORKS) | 01/06/2021 | 01/07/2021 | 01/06/2021 | 01/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MKC4-10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION SEE/SFC TRANSFORMER 20MKC / 20MBJ | 02/04/2022 | 29/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MKC3-70 | TT_Mile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) SEE/SFC TRANSFORMER 20MKC / 20MBJ | 02/04/2022 | 02/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MB-4-12 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION GT ACCESSORY EQUIPMENT MB | 02/04/2022 | 29/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MB-3-72 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) GT ACCESSORY EQUIPMENT / CCR / IN-LINE COMPONENTS GT-PIPING MB | 01/04/2022 | 01/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAW4M10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION MODULE MAW10Y | 19/02/2022 | 18/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAW3M70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) MODULE 20MAW10Y | 19/02/2022 | 19/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MB-4-10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION GT SUPPORTS 20MB- | 02/04/2022 | 29/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MB-3-70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) GT SUPPORTS 20MB- | 01/04/2022 | 01/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP--MB-4-10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION GT INSULATION MB- | 02/04/2022 | 29/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP--MB-3-70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) GT INSULATION MB- | 01/04/2022 | 01/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BFT4-10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION LV-TRANSFORMERS BFT | 01/04/2022 | 28/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BFT3-70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) LV-TRANSFORMERS BFT | 31/03/2022 | 31/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20XKA4-10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION EMERGENCY DIESEL GEN.SET XKA | 16/06/2022 | 13/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20XKA3-70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) EMERGENCY DIESEL GEN.SET 00XKA | 15/06/2022 | 15/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAC4-10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION GEN. CIRCUIT BREAKER 20BAC | 23/05/2022 | 19/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAC3-70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) GEN. CIRCUIT BREAKER 20BAC | 28/04/2022 | 28/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BBT4-10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION AUX. TRANSFORMER 20BBT | 23/04/2022 | 20/05/2022 |  |  | 432 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BBT3-70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) AUX. TRANSFORMER 20BBT | 22/04/2022 | 22/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAA4-10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION IPB 20BAA | 07/06/2022 | 04/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAA3-70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) IPB 20BAA | 06/06/2022 | 06/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20UBA4-10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION ELECTRICAL MODULES 20UBA7910/20 | 05/05/2022 | 01/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20UBA3-70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) ELECTRICAL MODULES 20UBA7910/20 | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20SGJ4-10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION - FIRE FIGHTING / GAS DETECTION 20SGJ / 20CYQ / 20CYE | 29/01/2022 | 25/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20SGJ3-70 | TT_Mile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) - FIRE FIGHTING / GAS DETECTION 20SGJ / 20CYQ / 20CYE | 29/01/2022 | 29/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGA4-10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION FIRE FIGHTING INDOOR HYRDANTS SGA 20UMC | 18/03/2022 | 14/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGA3-70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) FIRE FIGHTING INDOOR HYRDANTS SGA 20UMC | 17/03/2022 | 17/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MKW4-10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION MK- AUXILIARIES SYSTEMS | 02/04/2022 | 29/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MKW3-70 | TT_Mile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) MK- AUXILIARIES SYSTEMS | 02/04/2022 | 02/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MBX4-10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION INSTRUMENT AIR SKID TANK MBX | 02/04/2022 | 29/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MBX3-70 | TT_Mile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) INSTRUMENT AIR SKID TANK MBX | 02/04/2022 | 02/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MBP4-11 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION GT FUEL GAS STRAINER SKID MBP | 02/04/2022 | 29/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MBP3-71 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) GT FUEL GAS STRAINER SKID MBP | 01/04/2022 | 01/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MBL4-10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION AIR INTAKE SYSTEM 20MBL | 21/04/2022 | 18/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MBL3-70 | TT_Mile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) AIR INTAKE SYSTEM 20MBL | 21/04/2022 | 21/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MB-4A40 | TT_FinMile | (OTD-OS) ON SITE GT INTERCONNECTING PIPING 20MB- | 23/07/2022 | 23/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MBX4A40 | TT_FinMile | (OTD-OS) ON SITE INSTRUMENT AIR SKID TANK MBX | 23/07/2022 | 23/07/2022 |  |  | 256 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKW4-40 | TT_FinMile | (OTD-OS) ON SITE SEAL OIL SYSTEM 20MKW | 23/07/2022 | 23/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKW4-25 | TT_Task | TRANSPORT SEAL OIL SYSTEM 20MKW | 30/04/2022 | 23/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MKW2-10 | TT_Task | PREPARE TEC RFQ DOC MK- AUXILIARIES SYSTEMS | 24/02/2021 | 11/06/2021 | 24/02/2021 | 11/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MKW3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT (NORTH SEA PORT) MK- AUXILIARIES SYSTEMS | 29/04/2022 | 29/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MKW2-85 | TT_Mile | CONTRACT INTO FORCE MK- AUXILIARIES SYSTEMS | 30/07/2021 | 30/07/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MKW2-80 | TT_Task | QUOTATION STAGE MK- AUXILIARIES SYSTEMS | 12/06/2021 | 29/07/2021 | 12/06/2021 | 29/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MKW3-89 | TT_Task | DESIGN / MANUFACTURING MK- AUXILIARIES SYSTEMS | 30/07/2021 | 01/04/2022 | 30/07/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20MKQ4-40 | TT_FinMile | (OTD-OS) ON SITE EXHAUST GAS SYSTEM FOR GENERATOR 20MKQ | 23/07/2022 | 23/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKQ4-25 | TT_Task | TRANSPORT EXHAUST GAS SYSTEM FOR GENERATOR 20MKQ | 30/04/2022 | 23/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--HA-2-10 | TT_Task | TECHNICAL CLARIFICATION HRSG | 01/08/2020 | 30/12/2020 | 01/08/2020 | 30/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--HA-2-93 | TT_FinMile | PROJECT SPEC. EL.SPECS. (MOTORS,...) | 15/01/2021 | 15/01/2021 | 15/01/2021 | 15/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--HA-2-94 | TT_Mile | FULL ENGINEERING RELEASE HRSG FOR BUILDING BLOCK ENGINEERING | 13/11/2020 | 13/11/2020 | 13/11/2020 | 13/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20SMG4-10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION OTHER CRANES AND HOIST | 08/07/2022 | 04/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SMG3-70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) OTHER CRANES AND HOIST | 07/07/2022 | 07/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--SGA4A10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION FIRE FIGHTING RING MAIN SGA | 11/03/2022 | 07/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--SGA3A70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) FIRE FIGHTING RING MAIN SGA | 10/03/2022 | 10/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGY4A10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION FIRE FIGHTING DETECTION SYSTEM SGY | 04/03/2022 | 31/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGY3A70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) FIRE FIGHTING DETECTION SYSTEM SGY | 03/03/2022 | 03/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SG-4-10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION FIRE FIGHTING SYSTEMS 20SGC/SGE/SGF/SGJ | 25/02/2022 | 24/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SG-3-70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) FIRE FIGHTING SYSTEMS 20SGC/SGE/SGF/SGJ | 24/02/2022 | 24/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--GM-3B70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) SUMP PUMP GM | 14/04/2022 | 14/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--GM-4B10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION SUMP PUMP GM | 15/04/2022 | 12/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MBP2A81 | TT_Task | QUOTATION STAGE FUEL GAS STRAINER SKID MBP | 06/08/2021 | 16/09/2021 | 06/08/2021 | 16/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MBP2A80 | TT_Task | ENGINEERING / PREPARE RFQ FUEL GAS STRAINER SKID MBP | 25/05/2021 | 21/06/2021 | 25/05/2021 | 21/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MBP3A80 | TT_FinMile | (RFS) READY FOR SHIPMENT GT FUEL GAS STRAINER SKID MBP | 29/04/2022 | 29/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MBP3A81 | TT_Task | DESIGN / MANUFACTURING GT FUEL GAS STRAINER SKID MBP | 16/10/2021 | 01/04/2022 | 16/10/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20MKA7-89 | TT_Mile | GENERATOR READY FOR CURRENT TRANSFORMER | 18/08/2022 | 18/08/2022 |  |  | 176 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZL7E18 | TT_Task | LIGHTING AND SMALL POWER INSTALLATION 20URA LAST 4 CELLS | 12/04/2023 | 02/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZL7E17 | TT_Task | LIGHTING AND SMALL POWER INSTALLATION 20URA FIRST 4 CELLS | 23/02/2023 | 15/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZL7E16 | TT_Task | LIGHTING AND SMALL POWER INSTALLATION 20URD | 05/08/2022 | 15/09/2022 |  |  | 1280 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--2226-57 | TT_Task | ERECTION KKS PLANT LABELLING (REQUIRED FOR REM. PLANT) | 22/04/2023 | 08/09/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--2226-56 | TT_Task | ERECTION KKS PLANT LABELLING (REQUIRED FOR 1ST FIRE) | 30/01/2023 | 18/06/2023 |  |  | 40 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP--MKA2-87 | TT_Mile | GENERATOR DATA EXCHANGE LIST (+diverse curves) | 14/02/2021 | 14/02/2021 | 14/02/2021 | 14/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20HSJ6-17 | TT_Task | ERECTION AMMONIA STORAGE / SUPPLY SYTEM | 17/06/2022 | 30/06/2022 |  |  | 2800 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--L--2I46 | TT_Mile | DESIGN DATA SHEETS SAFETY / CONTROL VALVES L SYSTEMS (off rack/Yard) | 14/05/2021 | 14/05/2021 | 14/05/2021 | 14/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--L--2-65 | TT_FinMile | (DF) PROCESS FINAL / INPUT FOR M2 L-SYSTEMS | 04/05/2021 | 04/05/2021 | 04/05/2021 | 04/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MKG4-40 | TT_FinMile | (OTD-OS) ON SITE GAS COOLING SUPPLY SYSTEM 20MKG | 23/07/2022 | 23/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKG4-25 | TT_Task | TRANSPORT GAS COOLING SUPPLY SYSTEM 20MKG | 30/04/2022 | 23/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKG8-26 | TT_FinMile | (TOP-20MKG) GT GENERATOR GAS SUPPLY SYSTEM | 24/04/2023 | 24/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKG6A16 | TT_Task | PIPING GAS COOLING SUPPLY SYSTEM 20MKG | 07/10/2022 | 22/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKG6-15 | TT_Task | ERECTION GAS COOLING SUPPLY SYSTEM 20MKG | 11/09/2022 | 24/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKF8-11 | TT_FinMile | (TOP-20MKF) GENERATOR PRIMARY WATER COOLING SYSTEM | 24/04/2023 | 24/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBA4-10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION WASH WATER TANK 20MBA | 02/04/2022 | 29/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBA3-70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) WASH WATER TANK 20MBA | 01/04/2022 | 01/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBA4-40 | TT_FinMile | (OTD-OS) ON SITE GT WASH WATER TANK 20MBA | 23/07/2022 | 23/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBA4-25 | TT_Task | TRANSPORT GT WASH WATER TANK 20MBA | 30/04/2022 | 23/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBA3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT WASH WATER TANK 20MBA | 29/04/2022 | 29/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBA3-84 | TT_Task | PROCURMENT / PRE-FABRICATION WASH WATER TANK 20MBA | 09/10/2021 | 01/04/2022 | 09/10/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20MAW6-16 | TT_Task | MECHANICAL ERECTION SEAL/LEAK STEAM SYSTEM MAW | 25/06/2022 | 08/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEN2-60 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 01UEN | 01/08/2021 | 01/08/2021 | 01/08/2021 | 01/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20LCB4B10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION CONDENSATE EXTRACTION PUMP 20LCB | 05/05/2022 | 01/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LCB3B70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) CONDENSATE EXTRACTION PUMP 20LCB | 05/05/2022 | 05/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK4-41 | TT_FinMile | (OTD-OS) ON SITE IC CABLES 20/00BZK (LOT1) | 20/08/2022 | 20/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA4-63 | TT_FinMile | DELIVERY OF ELECTRICAL MODULESs AND COMPONENTS FOR ASSEMBLY IN TEST FACILITY 20UBA7320 | 24/02/2022 | 24/02/2022 |  |  | 80 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20QJ-4B10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION - CENTRAL GAS SUPPLY (H2,CO2) QJ_ | 09/12/2021 | 05/01/2022 | 09/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20QJ-3B70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) - CENTRAL GAS SUPPLY (H2,CO2) QJ_ | 08/12/2021 | 08/12/2021 | 08/12/2021 | 08/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20EK-4B10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION FUEL GAS RECEIVING AND MIXING SYSTEM 01EK | 21/04/2022 | 18/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20EK-3B70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) FUEL GAS RECEIVING AND MIXING SYSTEM 01EK | 20/04/2022 | 20/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---4-17 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION GT SPECIAL TOOLS 20MB- | 02/04/2022 | 29/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---3-77 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) GT SPECIAL TOOLS 20MB- | 01/04/2022 | 01/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---4M12 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION MODULES LOT 3 | 21/04/2022 | 18/05/2022 |  |  | 8 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---3M72 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) FOR SHIPMENT LOT 3 | 21/04/2022 | 21/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---4M11 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION MODULES LOT 2 | 20/03/2022 | 16/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---3M71 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) FOR SHIPMENT LOT 2 | 20/03/2022 | 20/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---4M10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION MODULES LOT 1 | 19/02/2022 | 18/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---3M70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) FOR SHIPMENT LOT 1 | 19/02/2022 | 19/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAC4B10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION CIRC. CW PUMP 20PAC | 03/04/2022 | 30/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAC3B70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) CIRC. CW PUMP 20PAC | 02/04/2022 | 02/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAA4B10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION COOLING TOWER COARSE SCREEN 20PAA | 01/06/2022 | 28/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAA3B70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) COOLING TOWER COARSE SCREEN 20PAA | 31/05/2022 | 31/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---3G71 | TT_FinMile | START OF STEELWORK PREFABRICATION SHIPMENT LOT 1 | 07/09/2021 | 07/09/2021 | 07/09/2021 | 07/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAD4B10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION - (EU) 20PAD FILL BATCH 1 | 26/05/2022 | 22/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--PAD4B10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION - PARTS EMB. INTO RISERES 20PAD | 13/07/2021 | 09/08/2021 | 13/07/2021 | 09/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--PAD3B70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) - PARTS EMB. INTO RISERES 20PAD | 12/07/2021 | 12/07/2021 | 12/07/2021 | 12/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAD3B70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) - (EU) 20PAD FILL BATCH 1 | 26/05/2022 | 26/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA4B13 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION ELECTRICAL MODULES 20UBA8110/20 | 26/08/2022 | 22/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA3B73 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) ELECTRICAL MODULES 20UBA8110/20 | 26/08/2022 | 26/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--ZTB4B10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION - PIPING / VALVES FOR STEAM BLOWING SYSTEM ZTB | 10/12/2022 | 06/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--ZTB3B70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) - PIPING / VALVES FOR STEAM BLOWING SYSTEM ZTB | 09/12/2022 | 09/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--ZTA4B10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION - TEMP. PIPING / VALVES FOR CHEMICAL CLEANING SYSTEM ZTA | 13/12/2022 | 09/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--ZTA3B70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) - TEMP. PIPING / VALVES FOR CHEMICAL CLEANING SYSTEM ZTA | 12/12/2022 | 12/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK4-10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION MV/LV CABLES20/00BZK (LOT 1) | 24/04/2022 | 21/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK3-70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) MV/LV CABLES20/00BZK (LOT 1) | 23/04/2022 | 23/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--ZTA3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT CHEMICAL CLEANING | 06/01/2023 | 06/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--ZTA4B11 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION - CHEMICAL CLEANING | 10/12/2022 | 06/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--ZTA3B71 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) - CHEMICAL CLEANING | 11/11/2022 | 11/11/2022 |  |  | 224 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBL6-26 | TT_Task | PREFABRICATION BEFORE ERECTION FILTERHOUSE 20MBL | 12/07/2022 | 01/08/2022 |  |  | 432 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-05 | TT_Task | WORK PREPARATION, EXCAVATION 20URA | 08/07/2021 | 17/09/2021 | 08/07/2021 | 18/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-----1-09 | TT_FinMile | (PAC) PROVISIONAL ACCEPTANCE CERTIFICATE - READY FOR COMMERCIAL OPERATION | 31/12/2023 | 31/12/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MAN3-26 | TT_Task | DESIGN / MANUFACTURING ST BYPASS MODULE 20MAN | 03/08/2021 | 28/04/2022 | 03/08/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SP--B--2-59 | TT_Mile | CMI's AVAILABLE FOR IC | 30/06/2021 | 30/06/2021 | 30/06/2021 | 30/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAS6B15 | TT_Task | ERECTION CT MAKE-UP WATER PUMP PAS | 08/04/2022 | 19/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAC6-06 | TT_Task | ELECTRICAL ERECTION PAC/PSB-PUMPS | 17/11/2022 | 14/12/2022 |  |  | 784 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAG6-60 | TT_Task | ELECTRICAL ERECTION CONDENSER MAG20 | 29/09/2022 | 26/10/2022 |  |  | 1384 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MBX2A85 | TT_Mile | CONTRACT INTO FORCE INSTRUMENT AIR SKID TANK MBX | 27/11/2021 | 27/11/2021 | 27/11/2021 | 27/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MBX2A81 | TT_Task | QUOTATION STAGE INSTRUMENT AIR SKID TANK MBX | 23/10/2021 | 26/11/2021 | 23/10/2021 | 26/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MBX2A80 | TT_Task | PREPARE TEC RFQ DOC INSTRUMENT AIR SKID TANK MBX | 25/09/2021 | 22/10/2021 | 25/09/2021 | 22/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MBX3A80 | TT_FinMile | (RFS) READY FOR SHIPMENT INSTRUMENT AIR SKID TANK MBX | 29/04/2022 | 29/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MBX3A83 | TT_Task | DESIGN / MANUFACTURING INSTRUMENT AIR SKID TANK MBX | 27/11/2021 | 01/04/2022 | 27/11/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SP20MBP2A85 | TT_Mile | CONTRACT INTO FORCE FUEL GAS STRAINER SKID MBP | 17/09/2021 | 17/09/2021 | 17/09/2021 | 17/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BZK7B27 | TT_Task | CABLING WORKS 20UBA (10x) to 20UMX02/01UEN | 02/01/2023 | 29/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAS2A80 | TT_Task | QUOTATION STAGE, BASIC DESIGN CT MAKE-UP WATER PUMP PAS | 18/03/2021 | 12/05/2021 | 18/03/2021 | 12/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAS2A85 | TT_Mile | CONTRACT INTO FORCE CT MAKE-UP WATER PUMP PAS | 15/06/2021 | 15/06/2021 | 15/06/2021 | 15/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAS2A91 | TT_Task | PREPARATION RFQ CT MAKE-UP WATER PUMP PAS | 05/02/2021 | 18/03/2021 | 05/02/2021 | 18/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MB-6-57 | TT_Task | INSULATION / COMPLETE ERECTION GT20 - AFTER BURNERS INSTALLATION | 13/11/2022 | 03/12/2022 |  |  | 96 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-5 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UTG01 | 15/08/2021 | 15/08/2021 | 15/08/2021 | 15/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBD2-05 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UBD01/02 | 29/07/2021 | 29/07/2021 | 29/07/2021 | 29/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBD2-15 | TT_Task | DETAIL DESIGN CONCRETE - 20UBD01/02 | 20/08/2021 | 06/12/2021 | 20/08/2021 | 06/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBD2-75 | TT_FinMile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION 20UBD01/02 | 17/03/2022 | 17/03/2022 |  |  | 216 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBD2E60 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UBD03/04 | 29/07/2021 | 29/07/2021 | 29/07/2021 | 29/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBD2E73 | TT_Task | DETAIL DESIGN, CHECKER CONCRETE STRUCTURE 20UBD03/04 | 04/09/2021 | 14/11/2021 | 04/09/2021 | 14/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBD2E75 | TT_FinMile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION 20UBD03/04 | 10/03/2022 | 10/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UPY2-5 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UPY | 01/05/2021 | 01/05/2021 | 01/05/2021 | 01/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UPY2-35 | TT_FinMile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION 20UPY | 07/09/2021 | 07/09/2021 | 07/09/2021 | 07/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UPY2-15 | TT_Task | DETAIL DESIGN, CHECKER CONCRETE STRUCTURE 20UPY | 30/05/2021 | 15/07/2021 | 30/05/2021 | 15/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UEN5-23 | TT_Mile | (RFE) FOUNDATION 01UEN | 30/04/2022 | 30/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEN5-21 | TT_Mile | (H) START PLACING FORMWORK 01UEN | 03/02/2022 | 03/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MB-6-56 | TT_Task | BURNERS INSTALLATION ERECTION GT20 | 16/10/2022 | 12/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20CJ-4-10 | TT_Task | TRANSPORT TO HEGELE BOP IC CABINETS FOR ELECTRICAL MODULES�S-20CPC41+20CPC21 | 02/02/2022 | 07/02/2022 |  |  | 8 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20CJ-3-25 | TT_Task | MANUFACTURING IC CABINETS AND OM EQUIP.-20CPC21 | 31/08/2021 | 31/01/2022 | 31/08/2021 |  | 8 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20CJ-2-50 | TT_FinMile | (DF) BOP IC HW FOR ELECTRICAL MODULES | 19/07/2021 | 19/07/2021 | 19/07/2021 | 19/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20CJ-3-52 | TT_Task | MANUFACTURING BOP AP Server + PLC/CS3000 - Cabinets (Protection)-20CPC41 | 31/08/2021 | 01/02/2022 | 31/08/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20CJ-2-51 | TT_FinMile | (DF) BOP Server + AP - Cabinets (Protection) | 19/07/2021 | 19/07/2021 | 19/07/2021 | 19/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20CJ-3-20 | TT_Task | DETAIL DESIGN HW ENGINEERING HRSG IC CABINETS FOR ELECTRICAL MODULES's AND OM EQUIP. FOR PRECOMMISSIONING TEST | 26/04/2021 | 17/07/2021 | 26/04/2021 | 18/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20CJP2-70 | TT_Mile | (DF) DESIGN FREEZE GT IC (INPUT TO GT AUTOMATION) | 19/07/2021 | 19/07/2021 | 19/07/2021 | 19/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--C--2A70 | TT_FinMile | (DF) BOP IC HW FOR FIELD EQUIPMENT AND CABINETS | 17/12/2021 | 17/12/2021 | 17/12/2021 | 17/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--C--2B00 | TT_Mile | SETUP T3000 DB | 28/05/2021 | 28/05/2021 | 28/05/2021 | 28/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MAG4-10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION CONDENSER FOUNDATION PARTS | 10/06/2021 | 07/07/2021 | 10/06/2021 | 07/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MAG3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT CONDENSER FOUNDATION PARTS | 07/07/2021 | 07/07/2021 | 07/07/2021 | 07/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MAG4B40 | TT_FinMile | (OTD-OS) ON SITE CONDENSER FOUNDATION PARTS | 05/09/2021 | 05/09/2021 | 05/09/2021 | 05/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MAG4B25 | TT_Task | TRANSPORT CONDENSER FOUNDATION PARTS | 08/07/2021 | 05/09/2021 | 08/07/2021 | 05/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--HA-2A85 | TT_Mile | CONTRACT INTO FORCE HRSG (Cockpit) | 27/01/2021 | 27/01/2021 | 27/01/2021 | 27/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20HA-2-85 | TT_Mile | CONTRACT INTO FORCE HRSG | 27/01/2021 | 27/01/2021 | 27/01/2021 | 27/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MKA9-42 | TT_Mile | 1ST. SYNCHRONIZATION GT GENERATOR 20MKA | 03/07/2023 | 03/07/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HSJ6-15 | TT_Task | ERECTION SCR SKID HSJ/HSK | 30/08/2022 | 10/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HSJ4-25 | TT_Task | TRANSPORT SCR SKID HSJ/HSK | 07/06/2022 | 01/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HS-2-88 | TT_Task | BASIC DESIGN SCR SKID HSJ/HSK | 27/01/2021 | 18/03/2021 | 27/01/2021 | 18/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20HSJ3-81 | TT_Task | DESIGN, MANUFACTURING, SHOP TEST SCR SKID HSJ/HSK | 17/09/2021 | 09/05/2022 | 17/09/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20HSJ3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT SCR SKID HSJ/HSK (Incl. Equipment / Material belonging to it) | 06/06/2022 | 06/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HSJ8-26 | TT_Task | COLD COMMISSIONING SCR AMMONIA STORAGE SUPPLY HSJ/HSK | 16/06/2023 | 22/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HSJ8-11 | TT_FinMile | (TOP-20HSJ) CHEMICAL SUPPLY SYSTEM FOR SCR-CAT | 15/06/2023 | 15/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HS-2-89 | TT_FinMile | (DF) PID'S SCR SKID HSJ/HSK | 18/03/2021 | 18/03/2021 | 18/03/2021 | 18/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20HS-2-87 | TT_FinMile | (DF) INPUT FOR MS3 SCR SKID HSJ/HSK | 01/04/2021 | 01/04/2021 | 01/04/2021 | 01/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20HS-2-65 | TT_FinMile | (DF) INPUT FOR M2 SCR SKID HSJ/HSK | 18/03/2021 | 18/03/2021 | 18/03/2021 | 18/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20HSJ4-40 | TT_FinMile | (OTD-OS) ON SITE SCR SKID HSJ/HSK | 01/08/2022 | 01/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--SMM2-86 | TT_FinMile | (DF) MS3 INPUT FOR CRANES 20SMM01/02 FOR 20UMC | 03/05/2021 | 03/05/2021 | 03/05/2021 | 03/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20QC-3-25 | TT_Task | DETAIL DESIGN DOSING CONTAINER 20QC | 31/08/2021 | 18/10/2021 | 31/08/2021 | 18/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20ULY4M10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION MODULE 20ULY00Y | 19/02/2022 | 18/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20ULY3M70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) MODULE 20ULY00Y | 19/02/2022 | 19/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20ULY3M80 | TT_FinMile | (RFS) READY FOR SHIPMENT MODULE 20ULY00Y | 18/03/2022 | 18/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MB-3-26 | TT_Task | PROJECT SPECIFIC DESIGN AND INTERFACE CLARIFICATIONS | 11/12/2020 | 14/01/2021 | 11/12/2020 | 14/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7-115 | TT_Task | ERECTION CABLE TRAYS ON 20ULY01 | 04/08/2022 | 10/08/2022 |  |  | 768 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20QU-4B10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION SAMPLING CONTAINER 20QU | 18/01/2022 | 14/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20QU-3B70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) SAMPLING CONTAINER 20QU | 17/01/2022 | 17/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MA-4C40 | TT_FinMile | (OTD-OS) ON SITE ST LP OUTER CASING MA- | 21/04/2022 | 21/04/2022 |  |  | 112 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MAN4-40 | TT_FinMile | (OTD-OS) ON SITE ST BYPASS VALVES MA | 21/07/2022 | 21/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MAV4-40 | TT_FinMile | (OTD-OS) ON SITE LUBE OIL MODULE 20MAV | 23/07/2022 | 23/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGM8-34 | TT_FinMile | (TOP-20SGM-04) FF INERTGAS SYSTEM IN 20UBA8110/20 SGM INSIDE CONTAINERS | 10/04/2023 | 10/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGM6-18 | TT_Task | ERECTION FF INERTGAS SYSTEM IN 20UBA8110/20 SGM | 08/12/2022 | 14/12/2022 |  |  | 96 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGM8-33 | TT_Task | COLD COMMISSIONING FF INERTGAS SYSTEM IN 20UBA8110/20 SGM INSIDE CONTAINERS | 11/04/2023 | 17/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7-85 | TT_Task | ERECTION CABLE TRAYS BELOW ELECTRICAL MODULES 20UBA8110/20 | 27/10/2022 | 02/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGY6-22 | TT_Task | ERECTION FIRE DETECTION SYSTEM IN 20UBA8110/20 SGY | 22/12/2022 | 28/12/2022 |  |  | 880 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD7-33 | TT_FinMile | E- AND IC-CONNECTION AVAILABLE 20PAD LAST 4 CELLS | 11/05/2023 | 11/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LDK7H16 | TT_Task | ELECTRICAL ERECTION PIPES / VALVES 20LDK | 02/02/2023 | 15/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAS2B10 | TT_FinMile | (DF) INPUT FOR MS3 CT MAKE-UP WATER PUMP PAS | 27/06/2021 | 27/06/2021 | 27/06/2021 | 27/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAS2B65 | TT_FinMile | (DF) INPUT FOR M2 CT MAKE-UP WATER PUMP PAS | 19/07/2021 | 19/07/2021 | 19/07/2021 | 19/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP--CJT2-88 | TT_Task | ORDERING / NEGOTIATIONS SEE CUBICLES CJT | 02/04/2021 | 27/05/2021 | 02/04/2021 | 27/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP--CJT2-76 | TT_Task | PREPARATION OF SPEC. / ORDER DOCU. SEE CUBICLES CJT | 19/02/2021 | 01/04/2021 | 19/02/2021 | 01/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP--CJT2-86 | TT_Mile | CONTRACT INTO FORCE SEE CUBICLES CJT | 28/05/2021 | 28/05/2021 | 28/05/2021 | 28/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20CJT4-10 | TT_Task | TRANSPORT SEE CUBICLES 20CJT TO WORKSHOP | 03/02/2022 | 04/02/2022 |  |  | 152 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20CJT3-81 | TT_Task | MANUFACTURING SEE CUBICLES 20CJT | 08/07/2021 | 02/02/2022 | 08/07/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UMC2B55 | TT_FinMile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION 20UMC | 31/08/2021 | 31/08/2021 | 31/08/2021 | 31/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC2B20 | TT_Task | DETAIL DESIGN CONCRETE BUILDING FOUNDATION 20UMC | 29/05/2021 | 15/07/2021 | 29/05/2021 | 15/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--6662-26 | TT_Mile | PROJECT SETUP DONE, CONTRACT AND DESIGN CRITERIA AVAIL., TERMINAL POINTS FIXED | 29/01/2021 | 29/01/2021 | 29/01/2021 | 29/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--BZP4-11 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION CABLE SUPPORT SYSTEM BZP (LOT 2) | 03/07/2022 | 16/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BZP3-71 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) CABLE SUPPORT SYSTEM BZP (LOT 2) | 02/07/2022 | 02/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BZP2-86 | TT_Mile | CONTRACT INTO FORCE CABLE SUPPORT SYSTEM BZP (LOT 2) | 08/05/2022 | 08/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BZP3-81 | TT_FinMile | (RFS) READY FOR SHIPMENT CABLE SUPPORT SYSTEM BZP (LOT 2) | 16/07/2022 | 16/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BZP3-26 | TT_Task | MANUFACTURING / SHOP TEST CABLE SUPPORT SYSTEM BZP (LOT 2) | 08/05/2022 | 02/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BZP4-26 | TT_Task | TRANSPORT CABLE SUPPORT SYSTEM BZP (LOT 2) | 17/07/2022 | 30/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BZP4B41 | TT_FinMile | (OTD-OS) ON SITE CABLE SUPPORT SYSTEM BZP (LOT 2) | 30/07/2022 | 30/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BZK4-40 | TT_FinMile | (OTD-OS) ON SITE MV/LV CABLES20/00BZK (LOT 2) | 25/10/2022 | 25/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BZK2-89 | TT_Mile | BOQ INFO TO SUPPLIER | 26/03/2022 | 26/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BA-8-11 | TT_FinMile | (TOP-20BA) ISOLATED GENERATOR BUSDUCT BAA INCL. BAB, BAC | 27/02/2023 | 27/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAA7-66 | TT_Task | ERECTION IPB PART 2 - 20BAC TO 20MKA | 18/10/2022 | 26/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAC8-26 | TT_Task | COMMISSIONING CIRCUIT BREAKER/ ISOLATED GEN BUSDUCT | 07/03/2023 | 13/03/2023 |  |  | 112 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BZK4-10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION MV/LV CABLE 20/00BZK (LOT2) | 03/08/2022 | 30/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BZK3-70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) MV/LV CABLE 20/00BZK (LOT2) | 02/08/2022 | 02/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BZK3-25 | TT_Task | MANUFACTURING / SHOP TEST MV/LV CABLE 20/00BZK (LOT2) | 26/03/2022 | 02/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BZK3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT MV/LV CABLE 20/00BZK (LOT2) | 30/08/2022 | 30/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BZK4-25 | TT_Task | TRANSPORT MV/LV CABLE 20/00BZK (LOT2) | 31/08/2022 | 25/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--B--2-66 | TT_Task | BASIC DESIGN CABLE - OVERALL CABLE ROUTING DWG YD16 - FIRST SUBMISSION | 20/03/2021 | 02/04/2021 | 20/03/2021 | 02/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--EK-2-20 | TT_FinMile | (DF) BASIC DESIGN GAS FINAL FILTER/ PREHEATER 20EKG | 25/03/2021 | 25/03/2021 | 25/03/2021 | 25/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--PAD2-20 | TT_FinMile | (DF) BASIC DESIGN COOLING TOWER EQUIPMENT PAD (GFK) | 19/12/2020 | 19/12/2020 | 19/12/2020 | 19/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20SGY8A26 | TT_Task | COLD COMMISSIONING FIRE DETECTION SYSTEM INSIDE 20UMC SGY | 08/06/2023 | 14/06/2023 |  |  | 8 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGY8A25 | TT_FinMile | (TOP-20SGY) FIRE DETECTION SYSTEM - MAIN ALARM PANEL | 07/06/2023 | 07/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-----1-05 | TT_Mile | (NTP) NOTICE TO PROCEED | 15/01/2021 | 15/01/2021 | 15/01/2021 | 15/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20M--9-75 | TT_Task | COMBINED CYCLE POWER PLANT LOAD TESTS - 2ND 3RD GAS | 30/09/2023 | 20/10/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20L--9I81 | TT_Task | INSTALLATION SCR MODULES IN HRSG | 10/07/2023 | 24/07/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20--P6-76 | TT_Task | COLD COMMISSIONING FOR CHEMICAL CLEANING HRSG | 22/04/2023 | 12/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--2222-103 | TT_Task | 1 -BD (BUILDING DEPARTMENT) - GBP 1st DRAFT SUBMISSION (INCL. WITHDRAW RESUBMIT) | 16/01/2021 | 15/04/2021 | 16/01/2021 | 15/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--2222-102 | TT_Task | CLIENT - REVIEW - GENERAL BUILDING PLAN | 16/01/2021 | 09/02/2021 | 16/01/2021 | 09/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--2222-101 | TT_Task | GENERAL BUILDING PLAN PREPARATION - FIRST DRAFT | 31/10/2020 | 15/01/2021 | 31/10/2020 | 15/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--2222-100 | TT_Mile | GENERAL BUILDING PLAN (GBP) DOCUMENTS RECEIVED FROM CLIENT | 31/10/2020 | 31/10/2020 | 31/10/2020 | 31/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--2222-104 | TT_Task | BD - APPROVAL LETTER AWARD FOR GBP | 16/04/2021 | 13/05/2021 | 16/04/2021 | 13/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-----5-21 | TT_Mile | START MAIN CIVIL WORKS | 01/07/2021 | 01/07/2021 | 01/07/2021 | 01/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UHA2-79 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE - RESUBMISSION 20UHA(2ND PACKAGE) | 24/05/2021 | 09/06/2021 | 24/05/2021 | 10/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UHA2-80 | TT_Task | CLIENT - REVIEW - HRSG DETAIL DESIGN CONCRETE 20UHA | 30/07/2021 | 23/08/2021 | 30/07/2021 | 23/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UHA2-81 | TT_Task | BD - CONSENT LETTER HRSG DETAIL DESIGN CONCRETE 20UHA | 15/06/2021 | 22/07/2021 | 15/06/2021 | 23/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--URA2-76 | TT_Task | BASIC DESIGN COOLING TOWER FOUNDATION 20URA To be used/cancel xx | 02/02/2021 | 29/03/2021 | 02/02/2021 | 29/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--URA2-83 | TT_FinMile | COORDINATION OF TERMINAL POINTS SUBSTRUCTURE-20URA/URD | 31/07/2021 | 31/07/2021 | 31/07/2021 | 31/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--URA2-82 | TT_Task | PREPARATION FOUNDATION GROUNDING DWGS 20URA/URD | 11/06/2021 | 24/06/2021 | 11/06/2021 | 24/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--URA2-85 | TT_Task | BD - SUBMISSION APPROVAL SUBSTRUCTURE AMENDMENT SUBMISSION 20URA/URD- | 22/07/2021 | 11/08/2021 | 22/07/2021 | 12/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--URA2-84 | TT_Task | CLIENT REVIEW DETAIL DESIGN SUBSTRUCTURE AND CATHODIC PROTECTION-20URA/URD | 26/07/2021 | 05/08/2021 | 26/07/2021 | 05/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--URA2-87 | TT_Task | BD - CONSENT LETTER SUBSTRUCTURE -20URA/URD(1STPACKAGE) | 28/06/2021 | 20/07/2021 | 28/06/2021 | 21/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAD7-35 | TT_Task | E - AND IC CABLING COOLING TOWER LAST 4 CELLS 20PAD | 20/04/2023 | 17/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7-155 | TT_Task | ERECTION CABLE TRAYS FOR 20URA AREA PART 2 | 29/03/2023 | 11/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URD5-47 | TT_Task | FINISHING WORKS / ROOF CONSTRUCTION 20URD | 25/02/2022 | 07/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--URD2-78 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE 20URD xxxx | 14/07/2021 | 11/09/2021 | 14/07/2021 | 11/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--URD2-79 | TT_Task | BD - CONSENT LETTER DETAIL DESIGN CONCRETE 20URD xx | 15/05/2021 | 25/06/2021 | 15/05/2021 | 25/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--ULA2-78 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE RESUBMISSION 20ULA(2NDPACKES) | 24/05/2021 | 09/06/2021 | 24/05/2021 | 10/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--ULA2-79 | TT_Task | BD - CONSENT LETTER DETAIL DESIGN CONCRETE 20ULA | 15/06/2021 | 22/07/2021 | 15/06/2021 | 23/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20HB-3A82 | TT_FinMile | (RFS) READY FOR SHIPMENT CASING HRSG20 (Incl. Installation Material) | 29/12/2021 | 29/12/2021 | 29/12/2021 | 29/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20HB-4B16 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION CASING HRSG20 | 11/11/2021 | 29/12/2021 | 11/11/2021 | 29/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20HB-3B76 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) CASING HRSG20 | 10/11/2021 | 10/11/2021 | 10/11/2021 | 10/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20HB-3A83 | TT_Task | MANUFACTURING CASING HRSG20 | 14/04/2021 | 10/11/2021 | 14/04/2021 | 10/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2A77 | TT_Task | BD - SUBMISSION APPROVAL - TURBOSET DETAIL DESIGN CONCRETE - 1ST AMMENDMENT (PILE CAP) | 28/06/2021 | 20/07/2021 | 28/06/2021 | 21/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2A79 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN CONCRETE - CEP/LDK - PIT 20UMC | 19/02/2021 | 15/03/2021 | 19/02/2021 | 15/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2A80 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE - 1ST SUBMISSION CEP/LDK - PIT (1STPACKAGE) | 16/03/2021 | 12/05/2021 | 16/03/2021 | 13/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2A81 | TT_Task | BD - CONSENT LETTER DETAIL DESIGN CONCRETE CEP/LDK PIT (1ST PACKAGE) | 28/06/2021 | 20/07/2021 | 28/06/2021 | 21/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5A46 | TT_Task | FINISHING WORKS / CURING TIME TURBOSET FOUNDATION 20UMC | 21/01/2022 | 29/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Z46 | TT_Task | WORK PREPARATION / PILE TRIMMING / PLATE WELDING TURBOSET AREA 20UMC | 08/07/2021 | 11/08/2021 | 08/07/2021 | 11/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2B79 | TT_Task | BD - SUBMISSION APPROVAL - STEEL STRUCTURE 20UMC (Incl. Crane Walkawy) | 17/05/2021 | 11/07/2021 | 17/05/2021 | 12/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2B80 | TT_Task | BD -CONSENT LETTER UMC PACKAGES(Steel,topslab,CEP/LDK screen wall,turbine plinth/wall) 20UMC | 18/08/2021 | 20/10/2021 | 18/08/2021 | 21/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--2222-109 | TT_Task | PILE CAP FOUNDATION DESIGN (WITH PREL. DESIGN FOR ALL AREAS) | 01/08/2020 | 28/02/2021 | 01/08/2020 | 28/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--2222-108 | TT_Task | (MS2) LOADING DATA COMPILATION FOR PILE CAP DESIGN | 01/08/2020 | 30/10/2020 | 01/08/2020 | 30/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-----5-22 | TT_Mile | ACCESS TO SITE FROM CLIENT | 01/07/2021 | 01/07/2021 | 01/07/2021 | 01/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B47 | TT_Task | ERECTION STEEL STRUCTURE ANNEX 20UMC | 22/03/2022 | 02/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2B83 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN - CLADDING 20UMC | 14/08/2021 | 07/09/2021 | 14/08/2021 | 07/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2B82 | TT_Task | DETAIL DESIGN CLADDING 20UMC | 15/06/2021 | 13/08/2021 | 15/06/2021 | 13/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC3B26 | TT_Task | FABRICATION DESIGN/FABRICATION/TRANSPORT CLADDING 20UMC | 17/11/2021 | 07/04/2022 | 17/11/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2B85 | TT_FinMile | (F) DETAIL DESIGN CLADDING WITH CONTRACTOR 20UMC | 30/11/2021 | 30/11/2021 | 30/11/2021 | 30/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2B84 | TT_Task | BD - SUBMISSION APPROVAL - STANDING SEAM ROOF/WALL/PANELS - CLADDING 20UMC | 17/11/2021 | 25/11/2021 | 17/11/2021 | 26/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2B86 | TT_Task | BD - CONSENT LETTER - STANDING SEAM ROOF/WALL/PANELS - CLADDING 20UMC | 22/02/2022 | 21/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2B87 | TT_Task | BD - SUBMISSION APPROVAL - STEEL PLATFORMS LOT1 20UMC GENO ST | 15/07/2021 | 06/11/2021 | 15/07/2021 | 06/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2B88 | TT_Task | BD - CONSENT LETTER STEEL PLATFORMS LOT1 20UMC | 07/11/2021 | 23/12/2021 | 07/11/2021 | 23/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2B89 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN - STEEL STRUCTURE LOT1 20UMC | 17/06/2021 | 11/07/2021 | 17/06/2021 | 11/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MAG6-61 | TT_Mile | START ERECTION CONDENSER | 12/05/2022 | 12/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--URA2-89 | TT_Task | BD - CONSENT LETTER SUPERSTRUCTURE 20URA/URD | 22/11/2021 | 03/12/2021 | 22/11/2021 | 03/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MA-3-82 | TT_Task | ENGINEERING / PREPARATION RFQ STEAM TURBINE | 16/11/2020 | 14/01/2021 | 16/11/2020 | 14/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6B83 | TT_FinMile | BEARINGS READY FOR PLACING STEAM TURBINE | 16/07/2022 | 16/07/2022 |  |  | 112 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKA6-81 | TT_Task | MEASUREMENT OF AXIAL ALIGNMENT OF SHAFT TO ST MKA | 16/01/2023 | 17/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKA6F16 | TT_Task | TEMPORARY COUPLING AND SWING CHECK OF SLIPRING SHAFT OF SLIPRING SET MKA | 07/09/2022 | 08/09/2022 |  |  | 944 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--HB-2-16 | TT_Task | BD - HRSG PACKAGES SUBMISSION APPROVAL | 16/05/2021 | 02/08/2021 | 16/05/2021 | 03/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--HB-2-17 | TT_Task | BD - CONSENT LETTER HRSG PACKAGES | 10/12/2021 | 08/01/2022 | 10/12/2021 |  | 48 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UHA2B-11 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION EMBEDDED PART HRSG20 | 07/07/2021 | 03/08/2021 | 07/07/2021 | 03/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHA2B-10 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) EMBEDDED PART HRSG20 | 06/07/2021 | 06/07/2021 | 06/07/2021 | 06/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20ZTA6A0 | TT_Task | PREPARATION MAIN PIPING SYSTEMS FOR CHEMICAL CLEANING | 15/04/2023 | 12/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--U--2-87 | TT_Mile | (B) PREL. GENERAL ARRANGEMENT DWGS AVAILABLE - FOR MAIN CIVIL WORKS | 15/01/2021 | 15/01/2021 | 15/01/2021 | 15/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-UZA2-65 | TT_Task | BD - SUBMISSION APPROVAL -UNDERGROUND (U/G) DRAINAGE RC PLANS | 21/05/2021 | 10/10/2021 | 21/05/2021 | 10/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-UZA2-55 | TT_Task | CLIENT - REVIEW - RING ROAD INCL. UNDERGROUND (U/G) DRAINAGE | 30/05/2021 | 23/06/2021 | 30/05/2021 | 23/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MBL2-96 | TT_Task | BD SUBMISSION APPROVAL - AIR INTAKE EXTERNAL / INTERNAL PORTION | 16/08/2021 | 30/09/2021 | 16/08/2021 | 30/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MBL2-97 | TT_Task | BD APPROVAL LETTER - AIR INTAKE EXTERNAL / INTERNAL PORTION | 01/10/2021 | 28/10/2021 | 01/10/2021 | 28/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--2222-132 | TT_Task | 1(a) - BD - GBP 2ND AMENDMENT SUBMISSION (INCL. MIC UNITS) - CONSENT LETTER | 14/05/2021 | 18/06/2021 | 14/05/2021 | 18/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UBF2-80 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE - RESUBMISSION 20UBE/UBF(2NDPACKAGES) | 24/05/2021 | 09/06/2021 | 24/05/2021 | 10/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UBF2-81 | TT_Task | BD - CONSENT LETTER DESIGN 20UBE/UBF | 15/06/2021 | 22/07/2021 | 15/06/2021 | 23/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UBF2-82 | TT_Task | BD - SUBMISSION APPROVAL - GEN TRAFO PLATFORM 20UBF | 03/12/2021 | 31/01/2022 | 03/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--UBF2-83 | TT_Task | BD - CONSENT LETTER GEN TRAFO PLATFORM 20UBF | 01/02/2022 | 28/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBE5E46 | TT_Task | CONSTRUCTION WALLS 20UBE | 10/03/2022 | 20/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBF5-19 | TT_Task | CONSTRUCTION BASEPLATE 20UBF - Capping plate and U rebar installation | 18/01/2022 | 22/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEN2-100 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE 01UEN | 13/12/2021 | 10/02/2022 | 13/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UEN2-99 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN CONCRETE 01UEN | 10/09/2021 | 12/12/2021 | 10/09/2021 | 12/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UEN2-105 | TT_Task | BD - CONSENT LETTER DETAIL DESIGN CONCRETE 01UEN | 11/02/2022 | 10/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20EKG6H16 | TT_Task | ERECTION, NDT, PT (PT PIGGING) PIPES / VALVES 00EKG (TP-M1A/B - 00UEN03/04) | 19/07/2022 | 16/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HSJ6-16 | TT_Task | PREPARATION INSTALLATION SCR SKID HSJ/HSK | 02/08/2022 | 29/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEN2-80 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE 20UEN RESUBMISSION | 13/12/2021 | 11/01/2022 | 13/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UEN2-69 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN CONCRETE 20UEN | 02/08/2021 | 15/09/2021 | 02/08/2021 | 15/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UEN2-77 | TT_Task | BD - CONSENT LETTER DETAIL DESIGN CONCRETE 20UEN | 12/01/2022 | 08/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEN2-85 | TT_Task | BD - SUBMISSION APPROVAL - PLATFORM DESIGN 20UEN | 28/02/2022 | 28/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEN2-82 | TT_Task | BD - CONSENT LETTER PLATFORM DESIGN 20UEN | 29/04/2022 | 26/05/2022 |  |  | 920 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--SG-2-86 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN FIRE FIGHTING | 20/04/2021 | 14/05/2021 | 20/04/2021 | 14/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--SG-2-87 | TT_Task | FINALIZATION OF FIRE FIGHTING DESIGN | 15/05/2021 | 18/06/2021 | 15/05/2021 | 18/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--SG-2-88 | TT_Task | BD - REVIEW APPROVAL - FIRE FIGHTING DESIGN | 28/05/2021 | 23/07/2021 | 28/05/2021 | 23/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--C--3E86 | TT_Task | DEVELOPMENT CENTRAL CONTROL ROOM IC EQUIPMENT CONCEPT PLAN | 15/01/2021 | 14/05/2021 | 15/01/2021 | 14/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--C--3E87 | TT_Task | DETAIL DESIGN / LAYOUT FOR CCR / CONNECTION TO EXISTING CCR / REVIEW / APPROVAL | 15/05/2021 | 09/12/2021 | 15/05/2021 | 09/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BZK7B28 | TT_Task | INTERCONNECTING IC CABLING TO EXISTING DCS IN 00UCA (D1) - 20UBA90xx TO UCA(C) / D1 | 15/11/2022 | 13/05/2023 |  |  | 384 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UCA7-16 | TT_Mile | ACCESS TO CONTROL ROOM FOR INSTALLATION WORKS UCA | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBX2-30 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE - RESUBMISSION 20UBX/20UBG03(2NDPACKAGES) | 24/05/2021 | 09/06/2021 | 24/05/2021 | 10/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBX2-35 | TT_Task | BD - CONSENT LETTER - DESIGN 20UBX/20UBG03 | 15/06/2021 | 22/07/2021 | 15/06/2021 | 23/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UBA2-84 | TT_Task | BD - SUBMISSION APPROVAL - STEEL STRUCTURE 20UBA7xxx | 02/08/2021 | 30/09/2021 | 02/08/2021 | 30/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UBA2-85 | TT_Task | BD - CONSENT LETTER - STEEL STRUCTURE 20UBA7xxx | 01/10/2021 | 28/10/2021 | 01/10/2021 | 28/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2B90 | TT_Task | BD - SUBMISSION APPROVAL - LOUVRES - CLADDING 20UMC | 17/11/2021 | 25/11/2021 | 17/11/2021 | 26/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2B91 | TT_Task | BD - CONSENT LETTER - LOUVRES - CLADDING 20UMC | 30/11/2021 | 27/12/2021 | 30/11/2021 | 27/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA7-102 | TT_Task | PLACING 20UBA7710/20 | 23/06/2022 | 23/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA7-26 | TT_Task | PLACING ELECTRICAL MODULES 20UBA7910/20 | 28/07/2022 | 30/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2-25 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN CONCRETE - 20UBA1110/20 | 30/09/2021 | 24/10/2021 | 30/09/2021 | 24/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2-30 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE - 20UBA1110/20 | 31/01/2022 | 31/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2-35 | TT_Task | BD - CONSENT LETTER - DESIGN 20UBA1110/20 | 01/04/2022 | 28/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2B-30 | TT_Task | BD - SUBMISSION APPROVAL - STEEL STRUCTURE 20UBA1110/20 | 28/02/2022 | 28/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2B-35 | TT_Task | BD - CONSENT LETTER - STEEL STRUCTURE 20UBA1110/20 | 29/04/2022 | 26/05/2022 |  |  | 672 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBD2-20 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN CONCRETE - 20UBD01/02 | 19/10/2021 | 06/12/2021 | 19/10/2021 | 06/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBD2-25 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE - 20UBD01/02 | 13/12/2021 | 10/02/2022 | 13/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UBD2-30 | TT_Task | BD - CONSENT LETTER - DESIGN 20UBD01/02 | 11/02/2022 | 10/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBD2-10 | TT_Task | BASIC DESIGN CONCRETE - 20UBD01/02 | 30/07/2021 | 19/08/2021 | 30/07/2021 | 19/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UBA2-89 | TT_Task | CLIENT - REVIEW - STEELWORK - 20UBX/20UBG | 03/02/2022 | 27/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBX2-65 | TT_Task | BD - SUBMISSION APPROVAL - STEELWORK - 20UBX/20UBG | 28/02/2022 | 28/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBX2-70 | TT_Task | BD - CONSENT LETTER - STEELWORK 20UBX/20UBG | 29/04/2022 | 26/05/2022 |  |  | 448 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--UBA2-92 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN CONCRETE - UBA7xxx | 28/07/2021 | 21/08/2021 | 28/07/2021 | 21/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UBA2-93 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE - RESUBMISSION UBA7xxx(2NDPACKAGE) | 24/05/2021 | 09/06/2021 | 24/05/2021 | 10/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UBA2-94 | TT_Task | BD - CONSENT LETTER - DESIGN UBA7xxx | 15/06/2021 | 22/07/2021 | 15/06/2021 | 23/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UBA2-95 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN CONCRETE - UBA7910/7920 | 23/08/2021 | 16/09/2021 | 23/08/2021 | 16/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UBA2-96 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE - UBA7910/7920 | 15/01/2022 | 15/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--UBA2-97 | TT_Task | BD - CONSENT LETTER - DESIGN UBA7910/7920 | 16/03/2022 | 12/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UVM2-77 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN CONCRETE - 20UVM01 | 02/08/2021 | 26/08/2021 | 02/08/2021 | 26/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UVM2-80 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE - RESUBMISSION 20UVM01(2NDPACKAGE) | 24/05/2021 | 09/06/2021 | 24/05/2021 | 10/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UVM2-85 | TT_Task | BD - CONSENT LETTER - DESIGN 20UVM01 | 15/06/2021 | 23/07/2021 | 15/06/2021 | 23/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UVM2-76 | TT_Task | BASIC DESIGN CONCRETE 20UVM01 | 21/05/2021 | 17/06/2021 | 21/05/2021 | 17/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB6A17 | TT_Task | ERECTION, NDT, PT / VALVES (MECHANICAL) 20PAB01 TO PAC PUMPS | 28/06/2022 | 08/08/2022 |  |  | 784 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--UBA2-101 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN CONCRETE - 20UBA8110/20 | 24/06/2021 | 02/09/2021 | 24/06/2021 | 03/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UBA2-102 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE - 20UBA8110/20 | 13/12/2021 | 10/02/2022 | 13/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--UBA2-103 | TT_Task | BD - CONSENT LETTER - DESIGN 20UBA8110/20 | 11/02/2022 | 10/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA3K81 | TT_FinMile | (OTD-OS) ON SITE ELECTRICAL MODULES 20UBA8110/20 | 17/11/2022 | 17/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--UBA2-104 | TT_Task | BD - SUBMISSION APPROVAL - STEEL STRUCTURE 20UBA8110/20 | 28/02/2022 | 28/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--UBA2-105 | TT_Task | BD - CONSENT LETTER - STEEL STRUCTURE 20UBA8110/20 | 29/04/2022 | 26/05/2022 |  |  | 1344 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBD2E90 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN CONCRETE - 20UBD03/04 | 21/10/2021 | 06/12/2021 | 21/10/2021 | 06/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBD2E91 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE - 20UBD03/04 | 13/12/2021 | 10/02/2022 | 13/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UBD2E92 | TT_Task | BD - CONSENT LETTER - DESIGN 20UBD03/04 | 11/02/2022 | 10/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2C78 | TT_Task | BASIC BUILDING DESIGN INCL. 3D MODEL 20UBD03/04 | 30/07/2021 | 03/09/2021 | 30/07/2021 | 03/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA7-27 | TT_Task | PLACING ELECTRICAL MODULES 20UBA8110/20 | 18/11/2022 | 20/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-35 | TT_Mile | PIPING TRENCH / CHANNEL AVAILABLE FROM CLIENT 20PAB01/02 | 01/07/2021 | 01/07/2021 | 01/07/2021 | 01/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB4-50 | TT_FinMile | (RFS) READY FOR SHIPMENT PIPING SYSTEM (OUTSIDE) 20PAB (FIRST DELIVERY) | 27/05/2021 | 27/05/2021 | 27/05/2021 | 27/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB4-55 | TT_Task | TRANSPORT PIPING SYSTEM (OUTSIDE) 20PAB (FIRST DELIVERY) | 27/05/2021 | 07/07/2021 | 27/05/2021 | 07/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-90 | TT_Task | PRESSURE TEST 20PAB41-PIPES OUTSIDE | 15/12/2021 | 07/01/2022 | 15/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20PAD8-56 | TT_Task | FILLING OF COOLING WATER SYSTEM PAB | 04/06/2023 | 10/06/2023 |  |  | 160 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UPY6M11 | TT_Task | CONNECTION PAB MODULE PIPING TO PAB CIVIL PIPING | 21/08/2022 | 01/10/2022 |  |  | 1560 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMY2-50 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN CONCRETE - 20ULY/UMY | 14/07/2021 | 07/08/2021 | 14/07/2021 | 07/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMY2-55 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE - RESUBMISSION 20ULY/UMY(2NDPACKAGES) | 24/05/2021 | 09/06/2021 | 24/05/2021 | 10/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMY2-60 | TT_Task | BD - CONSENT LETTER - DESIGN 20ULY/UMY | 15/06/2021 | 22/07/2021 | 15/06/2021 | 23/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MBR2B64 | TT_Task | BD - SUBMISSION APPROVAL - EXHAUST DIFFUSER FRAME 20MBR | 14/07/2021 | 11/09/2021 | 14/07/2021 | 11/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MBR2B65 | TT_Task | BD - APPROVAL AWARD EXHAUST DIFFUSER FRAME 20MBR | 12/09/2021 | 09/10/2021 | 12/09/2021 | 09/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MKA6-82 | TT_Task | ALIGNMENT OF GENERATOR TO GAS TURBINE MKA | 27/07/2022 | 01/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBH2-93 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN CONCRETE - 20UBH01 | 23/07/2021 | 16/08/2021 | 23/07/2021 | 16/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBH2-94 | TT_Task | BD - SUBMISSION APPROVAL - 20UBH01 | 17/08/2021 | 15/10/2021 | 17/08/2021 | 15/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBH2-95 | TT_Task | BD - CONSENT LETTER - 20UBH01 | 05/12/2021 | 01/01/2022 | 05/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UBH2-81 | TT_Task | BASIC DESIGN INCL. 3D MODEL, OIL COLLECTING PIT / OIL SEPARATOR 20UBH01 | 28/05/2021 | 17/06/2021 | 28/05/2021 | 17/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20EKG6H17 | TT_Task | ERECTION, NDT, PT (PT PIGGING) PIPES / VALVES 20EKG (00UEN03/04 - 20UEN VIA UEYxx) | 29/09/2022 | 25/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY2-55 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE 20UEY03-05 | 13/12/2021 | 10/02/2022 | 13/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UEY2-52 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN CONCRETE 20UEY03-05 | 06/12/2021 | 30/12/2021 | 06/12/2021 | 30/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UEY2-62 | TT_Task | BD - CONSENT LETTER DETAIL DESIGN CONCRETE 20UEY03-05 | 11/02/2022 | 10/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY2-30 | TT_Task | BASIC DESIGN / BASIC BUILDING DESIGN INCL. 3D MODEL 20UEY01 | 11/05/2021 | 07/06/2021 | 11/05/2021 | 07/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UEY2-35 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UEY01 | 11/05/2021 | 11/05/2021 | 11/05/2021 | 11/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UEY5-100 | TT_FinMile | (RFE) FOUNDATION 20UEY01 PART 1 | 14/01/2022 | 14/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY5-95 | TT_Mile | (H) START PLACING FORMWORK 20UEY01 PART 1 | 26/12/2021 | 26/12/2021 | 26/12/2021 | 26/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UEY5-85 | TT_Task | WORK PREPARATION / EXCAVATION / PILE TRIMMING / PLATE WELDING 20UEY01 PART 1 | 12/11/2021 | 25/11/2021 | 12/11/2021 | 25/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UEY2-64 | TT_Task | PREPARATION FOUNDATION GROUNDING DWGS 20UEY01 | 13/07/2021 | 26/07/2021 | 13/07/2021 | 26/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UEY2-45 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE 20UEY01 | 08/06/2021 | 26/07/2021 | 08/06/2021 | 26/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UEY2-80 | TT_FinMile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION 20UEY01 | 12/11/2021 | 12/11/2021 | 12/11/2021 | 12/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UEY2-66 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE - RESUBMISSION 20UEY01 (1STPACKAGE) | 24/05/2021 | 09/06/2021 | 24/05/2021 | 10/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UEY2-65 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN CONCRETE 20UEY01 | 27/07/2021 | 20/08/2021 | 27/07/2021 | 20/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UEY2-79 | TT_Task | BD - CONSENT LETTER DETAIL DESIGN CONCRETE 20UEY01(1STPACKAGE) | 28/06/2021 | 20/07/2021 | 28/06/2021 | 21/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UEY4-125 | TT_Task | TRANSPORT MODULE 20UEY01/02Y | 19/05/2022 | 11/06/2022 |  |  | 8 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY4-130 | TT_FinMile | (OTD-OS) ON SITE MODULE 20UEY01/02Y | 12/06/2022 | 12/06/2022 |  |  | 104 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY6-60 | TT_Task | ERECTION RACK TOWER T4 - 20UEY01 | 21/06/2022 | 25/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY6-40 | TT_Task | PRE-ASSEMBLY RACK TOWER T2 - 20UEY01 | 29/05/2022 | 02/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY6-30 | TT_Task | PRE-ASSEMBLY RACK TOWER T3 - 20UEY01 | 03/06/2022 | 07/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY6-10 | TT_Task | PRE-ASSEMBLY RACK TOWER T4 - 20UEY01 | 16/06/2022 | 20/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY6-100 | TT_Task | PLACING AND ALIGNMENT OF MODULE- 20UEY01 UNIT 1 (ACROSS ROAD 20UZA01) | 05/07/2022 | 06/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY6-110 | TT_Task | PLACING AND ALIGNMENT OF MODULE- 20UEY01 UNIT 3 (20UMX - 20UMY) | 07/07/2022 | 08/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY6-105 | TT_Task | PLACING AND ALIGNMENT OF MODULE- 20UEY01 UNIT 2 (ACROSS DIFFUSER) | 26/06/2022 | 27/06/2022 |  |  | 72 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY6-80 | TT_Task | ERECTION RACK TOWER T2 - 20UEY01 (South of 20UMX) | 03/06/2022 | 07/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY6-65 | TT_Task | ERECTION RACK TOWER T3 - 20UEY01 (North of 20UMX) | 08/06/2022 | 12/06/2022 |  |  | 104 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY4-115 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION MODULE 20UEY01/02Y | 21/04/2022 | 18/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY3-110 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) MODULE 20UEY01/02Y | 21/04/2022 | 21/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY4-120 | TT_FinMile | (RFS) READY FOR SHIPMENT MODULE 20UEY01/02Y | 18/05/2022 | 18/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--2M-11 | TT_Task | BD - SUBMISSION APPROVAL - SUPPORTING FRAME FOR MODULES LOT 1 (UMY00Y/ULY00Y) | 17/06/2021 | 01/09/2021 | 17/06/2021 | 01/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--2M-31 | TT_Task | BD - CONSENT LETTER - SUPPORTING FRAME FOR MODULES LOT 1 | 02/09/2021 | 29/11/2021 | 02/09/2021 | 30/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-----2E90 | TT_Mile | PRECONDITION FOR ORDERING OF PREFAB MODULES FULLFILLED | 05/02/2021 | 05/02/2021 | 05/02/2021 | 05/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-----2E89 | TT_Task | PREPARATION RFQ / QUOTATION / ORDERING PREFAB. MODULES | 05/02/2021 | 30/04/2021 | 05/02/2021 | 30/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-----2E91 | TT_Mile | CONTRACT INTO FORCE PREFAB. MODULES | 01/05/2021 | 01/05/2021 | 01/05/2021 | 01/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMY2-85 | TT_Task | DETAIL DESIGN / DELTA ENGINEERING MODULAR PIPE RACK 20UMY00Y | 20/04/2021 | 31/05/2021 | 20/04/2021 | 31/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---3B91 | TT_Task | MODULE ASSEMBLY (WITH PIPES) | 21/12/2021 | 18/02/2022 | 21/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20-1P341 | TT_Task | MANUFACTURING / TRANSPORT PIPES FOR MODULE 20UMY00Y | 24/05/2021 | 20/12/2021 | 24/05/2021 | 26/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---3M87 | TT_Task | PREPARE SHOP DRAWINGS / MANUFACTURING MODULE STEELWORKS 20UMY00Y | 02/09/2021 | 11/10/2021 | 02/09/2021 | 12/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---3M88 | TT_Task | MANUFACTURING MODULE STEELWORKS 20UMY00Y | 12/10/2021 | 20/12/2021 | 12/10/2021 | 20/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20HB-6-48 | TT_Task | INSTALL PIPING SUPPORTS HRSG20 | 29/04/2022 | 24/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-8-26 | TT_Task | ERECTION DRUM END ENCLOSURE / CANOPY HRSG20 | 04/08/2022 | 12/10/2022 |  |  | 1080 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LAC6M16 | TT_Task | ELECTRICAL IC ERECTION MODULE 20LAC10Y | 16/06/2022 | 27/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LAC2-10 | TT_Task | DETAIL DESIGN / DELTA ENGINEERING MODULE 20LAC10Y | 01/05/2021 | 25/06/2021 | 01/05/2021 | 25/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---3B92 | TT_Task | MODULE ASSEMBLY (WITH PIPES) 20LAC10Y | 30/11/2021 | 21/02/2022 | 30/11/2021 |  | 208 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20-1P342 | TT_Task | MANUFACTURING / TRANSPORT PIPES FOR MODULE 20LAC10Y | 18/11/2021 | 17/02/2022 | 18/11/2021 |  | 32 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20---3M89 | TT_Task | PREPARE SHOP DRAWINGS / MANUFACTURING MODULE STEELWORKS 20LAC10Y | 03/09/2021 | 28/10/2021 | 03/09/2021 | 28/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---3M90 | TT_Task | MANUFACTURING MODULE STEELWORKS 20LAC10Y | 29/10/2021 | 27/01/2022 | 29/10/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20TP-140 | TT_Mile | TP-M15A - COOLING TOWER MAKE UP WATER | 01/02/2022 | 01/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LCL6B41 | TT_Task | PLACING BOILER BLOWDOWN PUMP 20LCL | 22/07/2022 | 22/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LBH6D16 | TT_Task | PLACING BOILER BLOW DOWN TANK 20LBH | 09/04/2022 | 09/04/2022 |  |  | 320 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI11LBA6H46 | TT_Task | INSULATION PIPES / VALVES FOR STEAM SYSTEM 20LBA10 | 02/02/2023 | 08/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LBA7H16 | TT_Task | ELECTRICAL ERECTION PIPE / VALVES 20LBA10 | 02/03/2023 | 08/03/2023 |  |  | 320 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI11LBA6H71 | TT_Task | ERECTION, NDT PIPE / VALVES 11LBA10 (TURBOSET) | 02/12/2022 | 19/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LBA6J72 | TT_Task | INSULATION PIPES / VALVES FOR STEAM SYSTEM 11LBA80 (TURBOSET) | 20/01/2023 | 23/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LBA6J71 | TT_Task | ERECTION, NDT PIPE / VALVES 11LBA80 (TURBOSET) | 16/12/2022 | 19/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LBA7J16 | TT_Task | ELECTRICAL ERECTION / VALVES 11LBA80 | 17/02/2023 | 23/02/2023 |  |  | 424 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY2-10 | TT_Task | DETAIL DESIGN / DELTA ENGINEERING MODULAR PIPE RACK 20UEY01/02 | 25/05/2021 | 02/08/2021 | 25/05/2021 | 02/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UEY3-105 | TT_Task | MODULE ASSEMBLY (WITH PIPES) | 25/02/2022 | 21/04/2022 |  |  | 128 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY3-50 | TT_Task | MANUFACTURING / TRANSPORT PIPES FOR MODULE 20UEY01/02Y | 07/09/2021 | 04/04/2022 | 07/09/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UEY3-25 | TT_Task | PREPARE SHOP DRAWINGS / MANUFACTURING MODULE STEELWORKS 20UEY01/02Y | 02/10/2021 | 26/11/2021 | 02/10/2021 | 26/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UEY3-55 | TT_Task | MANUFACTURING MODULE STEELWORKS 20UEY01/02Y | 27/11/2021 | 23/02/2022 | 27/11/2021 |  | 8 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UBG2-50 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN CONCRETE - 20UBG01/02 | 31/01/2022 | 24/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBG2-40 | TT_Task | BASIC DESIGN / BASIC BUILDING DESIGN INCL. 3D MODEL 20UBG01/02 | 29/08/2021 | 25/09/2021 | 29/08/2021 | 25/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBG2-35 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UBG01/02 | 28/08/2021 | 28/08/2021 | 28/08/2021 | 28/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBG2-45 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE 20UBG01/02 | 26/09/2021 | 30/01/2022 | 26/09/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--UBF2A76 | TT_FinMile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION 20UBG01/02 | 13/04/2022 | 13/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--UBF2-88 | TT_Task | PREPARATION FOUNDATION GROUNDING DWGS 20UBG01/02 | 17/01/2022 | 30/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBG2-55 | TT_Task | BD - APPROVAL - DETAIL DESIGN CONCRETE 20UBG01/02 | 31/01/2022 | 31/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBG2-60 | TT_Task | BD - CONSENT LETTER DESIGN 20UBG01/02 | 01/04/2022 | 28/04/2022 |  |  | 104 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAT2-86 | TT_FinMile | (DF) INPUT FOR MS3 MAIN TRANSFORMER MKC / MBJ | 28/08/2021 | 28/08/2021 | 28/08/2021 | 28/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MBJ7-11 | TT_Task | PLACING 20MKC02-TRANSFORMER (on UBG03) | 09/07/2022 | 09/07/2022 |  |  | 96 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BFT4-41 | TT_FinMile | (OTD-OS) ON SITE (ET7) SEE/SFC-TRANSFORMERS 20MKC / 20MBJ | 24/06/2022 | 24/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBD5-63 | TT_FinMile | (RFE) FOUNDATION 20UBG01/02 | 01/06/2022 | 01/06/2022 |  |  | 296 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBD5-62 | TT_Mile | (H) START PLACING FORMWORK 20UBG01/02 | 12/05/2022 | 12/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBD5-60 | TT_Task | WORK PREPARATION, EXCAVATION 20UBG01/02 | 28/04/2022 | 11/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY6-5 | TT_Task | PRE-ASSEMBLY RACK TOWER T1 - 20UEY01 | 24/05/2022 | 28/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY6-15 | TT_Task | ERECTION RACK TOWER T1 - 20UEY01 (connection to 20UMY) | 29/05/2022 | 02/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY6-35 | TT_Task | PRE-ASSEMBLY RACK TOWER T2 - 20UEY02 | 27/06/2022 | 01/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY6-20 | TT_Task | PRE-ASSEMBLY RACK TOWER T3 - 20UEY02 | 27/06/2022 | 01/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY6-85 | TT_Task | PLACING AND ALIGNMENT OF MODULE- 20UEY02 UNIT 1 | 09/07/2022 | 10/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY6-90 | TT_Task | PLACING AND ALIGNMENT OF MODULE- 20UEY02 UNIT 2 | 11/07/2022 | 12/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY6-70 | TT_Task | ERECTION RACK TOWER T2 - 20UEY02 (east of 20UGU03) | 05/07/2022 | 07/07/2022 |  |  | 8 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY6-50 | TT_Task | ERECTION RACK TOWER T3 - 20UEY02 (connection to 20UEY01 20UEY05) | 02/07/2022 | 04/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY6-25 | TT_Task | PRE-ASSEMBLY RACK TOWER T1 - 20UEY02 | 22/06/2022 | 26/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY6-55 | TT_Task | ERECTION RACK TOWER T1 - 20UEY02 (connection to 20UEY03) | 27/06/2022 | 29/06/2022 |  |  | 72 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LCA6A46 | TT_Task | ERECTION, NDT, PIPES / VALVES 20LCA ON PIPE BRIDGES | 11/06/2022 | 16/12/2022 |  |  | 728 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY6-115 | TT_FinMile | (RFP) READY FOR PIPING PIPE BRIDGE 20UEY01 | 08/07/2022 | 08/07/2022 |  |  | 656 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY6-95 | TT_FinMile | (RFP) READY FOR PIPING PIPE BRIDGE 20UEY02 | 12/07/2022 | 12/07/2022 |  |  | 624 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MA-3-83 | TT_Task | ENGINEERING / PREPARATION RFQ ST CONDENSER | 15/01/2021 | 25/03/2021 | 15/01/2021 | 25/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-UZA2-60 | TT_Task | BD - SUBMISSION APPROVAL - RING ROAD | 21/05/2021 | 30/08/2021 | 21/05/2021 | 30/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-UZA2-70 | TT_Task | BD - CONSENT LETTER UNDERGROUND (U/G) DRAINAGE | 11/10/2021 | 07/11/2021 | 11/10/2021 | 07/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UPY2-10 | TT_Task | BASIC DESIGN, CHECKER CONCRETE STRUCTURE 20UPY | 02/05/2021 | 29/05/2021 | 02/05/2021 | 29/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UPY2-20 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN CONCRETE 20UPY | 16/07/2021 | 09/08/2021 | 16/07/2021 | 09/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UPY2-30 | TT_Task | BD - CONSENT LETTER DETAIL DESIGN CONCRETE 20UPY (1STPACKAGE) | 28/06/2021 | 20/07/2021 | 28/06/2021 | 21/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UPY2-25 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE - RESUBMISSION 20UPY(1STPACKAGE) | 24/05/2021 | 09/06/2021 | 24/05/2021 | 10/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5C56 | TT_Task | WALL AND ROOF CLADDING MAIN PART 20UMC | 08/04/2022 | 20/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--SG-2-36 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN FIRE MAIN RING | 06/08/2021 | 30/08/2021 | 06/08/2021 | 30/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--SG-2-38 | TT_Task | BD - CONSENT LETTER - HYDRAULIC SUBMISSION APPROVAL (FSI/314 SCHEMATIC DWGS SUBMISSION) | 06/12/2021 | 02/01/2022 | 06/12/2021 |  | 736 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--SG-2-37 | TT_Task | BD - SUBMISSION APPROVAL - HYDRAULIC SUBMISSION APPROVAL (FSI/314 SCHEMATIC DWGS SUBMISSION) | 31/08/2021 | 05/12/2021 | 31/08/2021 | 05/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--SG-2-89 | TT_Task | DETAIL DESIGN FIRE MAIN RING / OVERALL FIRE WATER DEMAND MINIMUM CALCULATION | 25/06/2021 | 05/08/2021 | 25/06/2021 | 05/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMX2-55 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN CONCRETE 20UMX-To be deleted | 10/09/2021 | 04/10/2021 | 10/09/2021 | 04/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMX2-65 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE 20UMX-deleted | 10/09/2021 | 08/11/2021 | 10/09/2021 | 08/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMX2-85 | TT_Task | BD - CONSENT LETTER - DETAIL DESIGN CONCRETE 20UMX-deleted | 09/11/2021 | 15/11/2021 | 09/11/2021 | 15/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7-150 | TT_Task | ERECTION CABLE TRAYS AIR INTAKE SYSTEM 20MBL | 27/11/2022 | 10/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20B--8-10 | TT_Mile | BACK ENERGISING | 11/04/2023 | 11/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKA6-83 | TT_Task | MEASUREMENT OF AXIAL ALIGNMENT OF SHAFT TO GT MKA | 02/08/2022 | 03/08/2022 |  |  | 1336 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6B84 | TT_Task | COMMON FINAL AXIAL MEASUREMENT TURBOSET | 16/12/2022 | 05/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAG6-62 | TT_Task | PREPARATION OF BYPASS STATION INSTALLATION | 15/07/2022 | 16/07/2022 |  |  | 40 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAX6H16 | TT_Task | ERECTION, NDT, PT PIPES / VALVES MAX BEFORE ST CONNECTION AVAILABLE | 05/11/2022 | 25/11/2022 |  |  | 328 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6B85 | TT_Task | FINISHING CASING ASSEMBLY MA | 19/11/2022 | 23/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6D81 | TT_Task | INSTALLATION ST INSULATION (FIRST LAYER) MA | 26/11/2022 | 23/12/2022 |  |  | 296 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKA6F17 | TT_Task | ERECTION OF SLIPRING SET MKA | 28/08/2022 | 31/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKA6F18 | TT_Task | FINISH INSTALLATION OF SLIPRING SET MKA | 05/01/2023 | 18/01/2023 |  |  | 32 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--LCB2B86 | TT_Mile | (DF) INPUT FOR VEL CONDENSATE EXTRACTION PUMP LCB | 07/05/2021 | 07/05/2021 | 07/05/2021 | 07/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--GM-2B89 | TT_Mile | (DF) INPUT FOR VEL SUMP PUMP GM | 29/05/2021 | 29/05/2021 | 29/05/2021 | 29/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--LDK2B87 | TT_Mile | (DF) INPUT FOR VEL CONDENSATE POLISHING PUMP 20LDK | 07/05/2021 | 07/05/2021 | 07/05/2021 | 07/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--PGB2B86 | TT_Mile | (DF) INPUT FOR VEL CCW PUMP PGB | 17/04/2021 | 17/04/2021 | 17/04/2021 | 17/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BAT2-87 | TT_Mile | PRELIMINARY MS2 INPUT AVAILABLE MAIN TRANSFORMER BAT/BBT | 26/02/2021 | 26/02/2021 | 26/02/2021 | 26/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--PCB2B86 | TT_Mile | (DF) INPUT FOR VEL SERVICE COOLING WATER BOOSTER PUMP PCB | 17/04/2021 | 17/04/2021 | 17/04/2021 | 17/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20LCL2B88 | TT_Mile | (DF) INPUT FOR VEL BOILER BLOWDOWN PUMP LCL | 31/05/2021 | 31/05/2021 | 31/05/2021 | 31/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--LAC2B86 | TT_Mile | (DF) INPUT FOR VEL FEEDWATER PUMP 20LAC | 05/05/2021 | 05/05/2021 | 05/05/2021 | 05/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--LCA2B86 | TT_Mile | (DF) INPUT FOR VEL CONDENSATE RECIRC.PUMP LCA51 | 07/05/2021 | 07/05/2021 | 07/05/2021 | 07/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--PAC2B87 | TT_Mile | (DF) INPUT FOR VEL CIRC. CW PUMP PAC | 07/05/2021 | 07/05/2021 | 07/05/2021 | 07/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAS2A92 | TT_Mile | (DF) INPUT FOR VEL CT MAKE-UP WATER PUMP PAS | 28/06/2021 | 28/06/2021 | 28/06/2021 | 28/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMX2-76 | TT_Task | BASIC BUILDING DESIGN INCL. 3D MODEL 20UMX02 | 18/06/2021 | 22/07/2021 | 18/06/2021 | 22/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMX2-50 | TT_Task | PREPARATION FOUNDATION GROUNDING DWGS 20UMX02 | 23/08/2021 | 05/09/2021 | 23/08/2021 | 05/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMX2-75 | TT_FinMile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION 20UMX02 | 10/03/2022 | 10/03/2022 |  |  | 440 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMX2-70 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE 20UMX02 | 23/07/2021 | 05/09/2021 | 23/07/2021 | 05/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMX2-60 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UMX02 | 17/06/2021 | 17/06/2021 | 17/06/2021 | 17/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMX5-12 | TT_FinMile | (RFE) FOUNDATION 20UMX02 | 03/07/2022 | 03/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMX5-11 | TT_Mile | (H) START PLACING FORMWORK 20UMX02 | 11/05/2022 | 11/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMX5-06 | TT_Task | WORK PREPARATION, EXCAVATION 20UMX02 | 05/05/2022 | 10/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
CLP20UMX2-77 | TT_FinMile | CUSTOMER INPUT FOR CIVIL DESIGN AVAILABLE 20UMX02 | 17/06/2021 | 17/06/2021 | 17/06/2021 | 17/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMX2-82 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE 20UMX02 | 13/12/2021 | 10/02/2022 | 13/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UMX2-80 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN CONCRETE 20UMX02 | 13/12/2021 | 06/01/2022 | 13/12/2021 |  | 280 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UMX2-84 | TT_Task | BD - CONSENT LETTER DETAIL DESIGN CONCRETE 20UMX02 | 11/02/2022 | 10/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SCA2-88 | TT_Mile | (DF) INPUT FOR VEL AIR COMPRESSOR SYSTEM SCA | 27/07/2021 | 27/07/2021 | 27/07/2021 | 27/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--HA-2-100 | TT_Mile | (DF) INPUT FOR VEL HRSG | 13/03/2021 | 13/03/2021 | 13/03/2021 | 13/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--EK-2-90 | TT_Mile | (DF) INPUT FOR VEL FUEL GAS RECEIVING AND MIXING SYSTEM EK | 05/07/2021 | 05/07/2021 | 05/07/2021 | 05/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--PAD2-87 | TT_Mile | (DF) INPUT FOR VEL COOLING TOWER EQUIPMENT PAD | 04/03/2021 | 04/03/2021 | 04/03/2021 | 04/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--LBF2B86 | TT_Mile | (DF) INPUT FOR VEL BYPASS STATION 20LBF | 13/02/2021 | 13/02/2021 | 13/02/2021 | 13/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--EK-2-91 | TT_Mile | (DF) INPUT FOR VEL GAS FINAL FILTER/ PREHEATER 20EKG | 28/06/2021 | 28/06/2021 | 28/06/2021 | 28/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--PDB2B86 | TT_Mile | (DF) INPUT FOR VEL DEBRIS FILTER 20PDB | 24/06/2021 | 24/06/2021 | 24/06/2021 | 24/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--PGB2C86 | TT_Mile | (DF) INPUT FOR VEL HEAT EXCHANGER PGB | 10/05/2021 | 10/05/2021 | 10/05/2021 | 10/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-----2E92 | TT_Task | PREPARATION MTO's FOR ORDERING OF PREFAB MODULES | 01/12/2020 | 04/02/2021 | 01/12/2020 | 04/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-25 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN CONCRETE 20UTG01 | 31/01/2022 | 24/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-30 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE 20UTG01 | 31/01/2022 | 31/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-35 | TT_Task | BD - CONSENT LETTER - DETAIL DESIGN CONCRETE 20UTG01 | 01/04/2022 | 28/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-22 | TT_Mile | (H) START PLACING FORMWORK 20UTG02 | 22/04/2022 | 22/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-26 | TT_FinMile | (RFE) FOUNDATION 20UTG02 | 13/05/2022 | 13/05/2022 |  |  | 664 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-32 | TT_Mile | (H) START PLACING FORMWORK 20UTG03 | 06/05/2022 | 06/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-36 | TT_FinMile | (RFE) FOUNDATION 20UTG03 | 26/05/2022 | 26/05/2022 |  |  | 1040 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-52 | TT_Mile | (H) START PLACING FORMWORK 20UTG05 | 06/05/2022 | 06/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-50 | TT_Task | WORK PREPARATION, EXCAVATION 20UTG05 | 29/04/2022 | 05/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-56 | TT_FinMile | (RFE) FOUNDATION 20UTG05 | 26/05/2022 | 26/05/2022 |  |  | 80 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-42 | TT_Mile | (H) START PLACING FORMWORK 20UTG04 | 08/04/2022 | 08/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-40 | TT_Task | WORK PREPARATION, EXCAVATION 20UTG04 | 01/04/2022 | 07/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-46 | TT_FinMile | (RFE) FOUNDATION 20UTG04 | 28/04/2022 | 28/04/2022 |  |  | 888 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-44 | TT_Task | CONSTRUCTION FOUNDATION 20UTG04 | 08/04/2022 | 21/04/2022 |  |  | 56 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA3C10 | TT_FinMile | ELECTRICAL MODULES READY FOR INSTALLATION OF COMP. ELECTRICAL MODULES UBA | 16/01/2022 | 16/01/2022 |  |  | 56 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA3C15 | TT_Mile | (ET4b) ELECTRICAL MODULES AT WORKSHOP READY FOR COMPONENT INSTALLATION ELECTRICAL MODULES 01UBA9010/20 | 24/01/2022 | 24/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA3C20 | TT_Task | INSTALL. COMP., INT. CABLING, FIRE PROT., SHOP TEST ELECTRICAL MODULES 01UBA9010/20 | 24/01/2022 | 10/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA3C5 | TT_Task | MANUFACTURING ELECTRICAL MODULES 01UBA9010/20 | 19/07/2021 | 16/01/2022 | 19/07/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UBA3C35 | TT_Task | TRANSPORT ELECTRICAL MODULES 01UBA9010/20 | 02/05/2022 | 26/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA3C40 | TT_FinMile | (RFS) READY FOR SHIPMENT ELECTRICAL MODULES 01UBA9010/20 | 01/05/2022 | 01/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA3C30 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION ELECTRICAL MODULES 01UBA9010/20 | 04/04/2022 | 01/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA3C25 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) ELECTRICAL MODULES 01UBA9010/20 | 04/04/2022 | 04/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2C-65 | TT_Task | HANDRAILS AND GRATING DWGS CONNECTION FORCE REPORT 01UBA9010/20 | 24/11/2021 | 01/02/2022 | 24/11/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2C-15 | TT_Task | BASIC BUILDING DESIGN INCL. 3D MODEL 01UBA9010/20 | 20/05/2021 | 09/06/2021 | 20/05/2021 | 09/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA7C-25 | TT_Task | ELECTRICAL COMMISSIONING 01UBA9010/20 | 27/02/2023 | 05/03/2023 |  |  | 64 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2C-5 | TT_FinMile | DESIGN INPUT (FINAL LOAD DATA) FROM VENDOR FOR 01UBA9010/20 AVAILABLE | 23/06/2021 | 23/06/2021 | 23/06/2021 | 23/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5C-45 | TT_FinMile | (RFE) STEEL STRUCTURE 01UBA9010/20 | 25/07/2022 | 25/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2C-55 | TT_FinMile | (MS3) STEEL STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 01UBA9010/20 | 11/05/2021 | 11/05/2021 | 11/05/2021 | 11/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2C-80 | TT_FinMile | (F) DETAIL DESIGN STEEL STRUCTURE WITH CONTRACTOR 01UBA9010/20 | 01/02/2022 | 01/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2C-60 | TT_Task | DETAIL DESIGN STEEL STRUCTURE 01UBA9010/20 | 31/10/2021 | 01/02/2022 | 31/10/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2C-10 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 01UBA9010/20 | 23/06/2021 | 23/06/2021 | 23/06/2021 | 23/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2C-30 | TT_Task | PREPARATION FOUNDATION GROUNDING DWGS 01UBA9010/20 | 25/07/2021 | 12/12/2021 | 25/07/2021 | 12/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2C-25 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE 01UBA9010/20 | 24/06/2021 | 12/12/2021 | 24/06/2021 | 12/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5C-30 | TT_Mile | (HS) START ERECTION STEEL STRUCTURE 01UBA9010/20 | 29/06/2022 | 29/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA3C-25 | TT_Task | FABRICATION DESIGN FABRICATION TRANSPORT STEEL STRUCTURE 01UBA9010/20 | 02/02/2022 | 10/05/2022 |  |  | 392 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA7C-15 | TT_Task | INSTALLATION ELECTRICAL MODULES 01UBA9010/20 | 09/07/2022 | 18/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA7C-20 | TT_FinMile | (TOP-90UBA9) POWER CONTROL CENTER (ELECTRICAL MODULES) - 01UBA9010/20 | 26/02/2023 | 26/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2C-20 | TT_FinMile | PLANT DESIGN INPUT FOR 01UBA9010/20 AVAILABLE | 09/06/2021 | 09/06/2021 | 09/06/2021 | 09/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2C-50 | TT_FinMile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION 01UBA9010/20 | 25/03/2022 | 25/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5C-20 | TT_FinMile | (RFE) FINISHING WORKS 01UBA9010/20 | 05/06/2022 | 05/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5C-5 | TT_Task | WORK PREPARATION / EXCAVATION FOUNDATION 01UBA9010/20 | 27/03/2022 | 02/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5C-15 | TT_Mile | (H) START PLACING FORMWORK 01UBA9010/20 | 03/04/2022 | 03/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7-45 | TT_Task | ERECTION CABLE TRAYS BELOW ELECTRICAL MODULES 01UBA9010/20 | 06/06/2022 | 19/06/2022 |  |  | 56 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2C-35 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN CONCRETE - 01UBA9010/20 | 13/12/2021 | 06/01/2022 | 13/12/2021 |  | 11632 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2C-40 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE - 01UBA9010/20 | 15/01/2022 | 15/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2C-45 | TT_Task | BD - CONSENT LETTER - DESIGN 01UBA9010/20 | 16/03/2022 | 12/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA4C-5 | TT_FinMile | (OTD-OS) ON SITE ELECTRICAL MODULES 01UBA9010/20 | 26/06/2022 | 26/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2C-70 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN STEEL 01UBA9010/20 | 02/04/2022 | 31/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2C-75 | TT_Task | BD - CONSENT LETTER - DETAIL DESIGN STEEL 01UBA9010/20 | 01/06/2022 | 28/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA7C-10 | TT_Task | PLACING ELECTRICAL MODULES 01UBA9010/20 | 06/07/2022 | 08/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-62 | TT_Mile | (H) START PLACING FORMWORK 20UTG06 | 13/04/2022 | 13/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-66 | TT_FinMile | (RFE) FOUNDATION 20UTG06 | 03/05/2022 | 03/05/2022 |  |  | 776 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBH5E49 | TT_FinMile | (RFE) FOUNDATION 20UBH02 | 05/07/2022 | 05/07/2022 |  |  | 1784 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBH5-25 | TT_Mile | (H) START PLACING FORMWORK 20UBH02 | 15/05/2022 | 15/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBH5-23 | TT_Task | WORK PREPARATION, EXCAVATION 20UBH02 | 05/05/2022 | 14/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SMG2-86 | TT_Mile | (DF) INPUT FOR VEL OTHER CRANES AND HOIST | 10/06/2021 | 10/06/2021 | 10/06/2021 | 10/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20SA-2-86 | TT_Mile | (DF) INPUT FOR VEL HVAC SYSTEM SA | 02/08/2021 | 02/08/2021 | 02/08/2021 | 02/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-----2E93 | TT_Mile | (DF) INPUT FOR VEL PIPING BUILDING BLOCK / ORDER MTO LONG LEAD ITEMS (80%) VALVES (INCL. CONTRACTUAL MTO) | 29/05/2021 | 29/05/2021 | 29/05/2021 | 29/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MPB2A98 | TT_Mile | (DF) INPUT FOR VEL ENCLOSURE 20MPB | 25/06/2021 | 25/06/2021 | 25/06/2021 | 25/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP--MB-2-87 | TT_Mile | (DF) INPUT FOR VEL (BZ) GT INCL. GT ENGINEERING | 02/07/2021 | 02/07/2021 | 02/07/2021 | 02/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MBL2-98 | TT_Mile | (DF) INPUT FOR VEL AIR INTAKE SYSTEM MBL | 18/06/2021 | 18/06/2021 | 18/06/2021 | 18/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MBP2A86 | TT_Mile | (DF) INPUT FOR VEL FUEL GAS STRAINER SKID MBP | 01/07/2021 | 01/07/2021 | 01/07/2021 | 01/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MKW2-86 | TT_Mile | (DF) INPUT FOR VEL MK- AUXILIARIES SYSTEMS | 18/06/2021 | 18/06/2021 | 18/06/2021 | 18/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MAJ2-86 | TT_Mile | (DF) INPUT FOR VEL AIR REMOVAL SYSTEM MAJ | 18/06/2021 | 18/06/2021 | 18/06/2021 | 18/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MAV2-86 | TT_Mile | (DF) INPUT FOR VEL LUBE OIL MODULE MAV | 18/06/2021 | 18/06/2021 | 18/06/2021 | 18/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MAW2-86 | TT_Mile | (DF) INPUT FOR VEL GLAND STEAM CONDENSER MAW | 18/06/2021 | 18/06/2021 | 18/06/2021 | 18/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MAX2-86 | TT_Mile | (DF) INPUT FOR VEL ST HYDRAULIC SYSTEM MAX | 12/06/2021 | 12/06/2021 | 12/06/2021 | 12/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAH2-87 | TT_Mile | (DF) INPUT FOR VEL CONDENSER TUBE CLEANING SYSTEM 20PAH | 24/06/2021 | 24/06/2021 | 24/06/2021 | 24/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20LBG2C87 | TT_Mile | (DF) INPUT FOR VEL EL. SUPERHEATER LBG | 24/06/2021 | 24/06/2021 | 24/06/2021 | 24/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--LDK2B88 | TT_Mile | (DF) INPUT FOR VEL CONDENSATE POLISHING PLANT 20LD | 16/06/2021 | 16/06/2021 | 16/06/2021 | 16/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20HSJ2-94 | TT_Mile | (DF) INPUT FOR VEL SCR SKID HSJ/HSK | 03/05/2021 | 03/05/2021 | 03/05/2021 | 03/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20ULY2-20 | TT_Task | PREPARATION FOUNDATION GROUNDING DWGS 20ULY01 | 21/08/2021 | 03/09/2021 | 21/08/2021 | 03/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20ULY2-10 | TT_Task | BASIC BUILDING DESIGN INCL. 3D MODEL 20ULY01 | 12/06/2021 | 08/07/2021 | 12/06/2021 | 08/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20ULY5-50 | TT_Mile | (H) START PLACING FORMWORK PIPE BRIDGE 20ULY01 | 21/04/2022 | 21/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20ULY5-60 | TT_FinMile | (RFE) FOUNDATION SLEEPER WAY 20ULY01 | 18/05/2022 | 18/05/2022 |  |  | 392 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20ULY2-5 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20ULY01 | 11/06/2021 | 11/06/2021 | 11/06/2021 | 11/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20ULY5-45 | TT_Task | WORK PREPARATION, EXCAVATION PIPE BRIDGE 20ULY01 | 14/04/2022 | 20/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20ULY2-40 | TT_FinMile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION 20ULY01 | 10/03/2022 | 10/03/2022 |  |  | 272 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20ULY2-15 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE 20ULY01 | 09/07/2021 | 06/12/2021 | 09/07/2021 | 06/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20ULY2-25 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN CONCRETE - 20ULY01 | 04/09/2021 | 28/09/2021 | 04/09/2021 | 28/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20ULY2-30 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE - 20ULY01 | 13/12/2021 | 10/02/2022 | 13/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20ULY2-35 | TT_Task | BD - CONSENT LETTER - DESIGN 20ULY01 | 11/02/2022 | 10/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20ULY5-145 | TT_Task | ERECTION STEEL STRUCTURE 20ULY01 | 14/07/2022 | 03/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBY2-20 | TT_Task | PREPARATION FOUNDATION GROUNDING DWGS UBY01 | 20/09/2021 | 03/10/2021 | 20/09/2021 | 03/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBY2-10 | TT_Task | BASIC BUILDING DESIGN INCL. 3D MODEL UBY01 | 30/07/2021 | 19/08/2021 | 30/07/2021 | 19/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBY2-5 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE UBY01 | 30/07/2021 | 30/07/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBY2-40 | TT_FinMile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION UBY01 | 16/06/2022 | 16/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBY2-15 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE UBY01 | 20/08/2021 | 03/10/2021 | 20/08/2021 | 03/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBY2-25 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN CONCRETE - UBY01 | 04/10/2021 | 28/10/2021 | 04/10/2021 | 28/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBY2-30 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE - UBY01 | 28/02/2022 | 28/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBY2-35 | TT_Task | BD - CONSENT LETTER - DESIGN UBY01 | 29/04/2022 | 26/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7-90 | TT_Task | ERECTION CABLE TRAYS ON 20UBY01 | 15/07/2022 | 28/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBY5-52 | TT_FinMile | (RFE) FOUNDATION 20UBY02(NotExisting) | 30/06/2022 | 30/06/2022 |  |  | 224 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBY5-50 | TT_Task | CONSTRUCTION FOUNDATION 20UBY02(NotExisting) | 17/06/2022 | 30/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBY5-49 | TT_Task | WORK PREPARATION, EXCAVATION 20UBY02(NotExisting) | 03/06/2022 | 16/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBY5-51 | TT_Mile | (H) START PLACING FORMWORK 20UBY02(NotExisting) | 17/06/2022 | 17/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEX2-15 | TT_Task | BASIC BUILDING DESIGN INCL. 3D MODEL 20UEX01 | 17/12/2021 | 06/01/2022 | 17/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UEX2-25 | TT_Task | PREPARATION FOUNDATION GROUNDING DWGS 20UEX01 | 04/01/2022 | 17/01/2022 |  |  | 520 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEX2-70 | TT_FinMile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION 20UEX01 | 19/06/2022 | 19/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEX2-20 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE 20UEX01 | 07/01/2022 | 23/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEX2-10 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UEX01 | 17/12/2021 | 17/12/2021 | 17/12/2021 | 17/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UEX2-100 | TT_FinMile | (RFE) FOUNDATION 20UEX01 | 17/07/2022 | 17/07/2022 |  |  | 392 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEX2-85 | TT_Mile | (H) START PLACING FORMWORK 20UEX01 | 04/07/2022 | 04/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEX2-75 | TT_Task | WORK PREPARATION, EXCAVATION 20UEX01 | 20/06/2022 | 03/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEX2-40 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN CONCRETE 20UEX01 | 24/03/2022 | 17/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEX2-50 | TT_Task | BD - CONSENT LETTER DETAIL DESIGN CONCRETE 20UEX01 | 30/05/2022 | 26/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBN2-25 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN CONCRETE 20UBN | 31/01/2022 | 24/02/2022 |  |  | 224 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBN2-35 | TT_Task | BD - CONSENT LETTER - DESIGN 20UBN | 29/04/2022 | 26/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BAA2-86 | TT_Task | AUDIT AT IPB MANUFACTURER | 02/05/2021 | 29/05/2021 | 02/05/2021 | 29/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7-120 | TT_Task | ERECTION CABLE TRAYS ON 20UBY02 INCL.UBN | 29/07/2022 | 02/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BBT7-16 | TT_Task | ERECTION AUX. TRANSFORMER 20BBT | 25/08/2022 | 07/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20EGx2-40 | TT_Mile | ERECTION MANUALS ON SITE FUEL OIL DAY TANK EGx | 11/08/2022 | 11/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20EGx3-5 | TT_Task | DETAIL DESIGN / MANUFACTURING / SHOP TEST FUEL OIL DAY TANK EGx | 17/12/2021 | 15/06/2022 | 17/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20EGx2-30 | TT_FinMile | (DF) INPUT FOR MS3 FUEL OIL DAY TANK EGx | 17/12/2021 | 17/12/2021 | 17/12/2021 | 17/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20EGx4-15 | TT_FinMile | (OTD-OS) ON SITE FUEL OIL DAY TANK EGx | 07/09/2022 | 07/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20EGx6-65 | TT_Task | ERECTION / PIPING FUEL OIL DAY TANK EGx | 17/09/2022 | 21/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20EGx3-15 | TT_FinMile | (RFS) READY FOR SHIPMENT FUEL OIL DAY TANK EGx | 13/07/2022 | 13/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20EGx4-10 | TT_Task | TRANSPORT FUEL OIL DAY TANK EGx | 14/07/2022 | 07/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20EGx4-5 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION FUEL OIL DAY TANK EGx | 16/06/2022 | 13/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20EGx3-10 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) FUEL OIL DAY TANK EGx | 15/06/2022 | 15/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBY5-56 | TT_FinMile | (RFE) FOUNDATION 20UBY05 | 17/04/2022 | 17/04/2022 |  |  | 592 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBY5-53 | TT_Task | WORK PREPARATION, EXCAVATION 20UBY05 | 21/03/2022 | 26/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBY5-55 | TT_Mile | (H) START PLACING FORMWORK 20UBY005 | 27/03/2022 | 27/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7-5 | TT_Task | ERECTION CABLE TRAYS ON 20UBY04 | 06/09/2022 | 03/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBY5-60 | TT_FinMile | (RFE) FOUNDATION 20UBY03 | 17/06/2022 | 17/06/2022 |  |  | 1048 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBY5-57 | TT_Task | WORK PREPARATION, EXCAVATION 20UBY03 | 27/05/2022 | 02/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBY5-59 | TT_Mile | (H) START PLACING FORMWORK 20UBY03 | 03/06/2022 | 03/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BTA3A26 | TT_Task | PLACEMENT OF BATTERIES INTO RACKS BATTERIES BTA | 14/12/2022 | 20/12/2022 |  |  | 184 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA4B41 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION ELECTRICAL MODULES 20UBA7410 (TO SITE) | 31/03/2022 | 27/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA3B74 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) ELECTRICAL MODULES 20UBA7410 | 31/03/2022 | 31/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA4-64 | TT_Mile | (ET4b) ELECTRICAL MODULES AT WORKSHOP READY FOR COMPONENT INSTALLATION 20UBA7410 | 19/01/2022 | 19/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2G61 | TT_FinMile | (DF) INPUT FOR MS3 ELECTRICAL MODULES 20UBA7410 | 23/06/2021 | 23/06/2021 | 23/06/2021 | 23/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA4G52 | TT_Task | TRANSPORT ELECTRICAL MODULES 20UBA7410 (TO SITE) | 28/04/2022 | 22/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA3G82 | TT_Task | INSTALL. COMP., INT. CABLING, FIRE PROT., SHOP TEST ELECTRICAL MODULES 20UBA7410 | 19/01/2022 | 06/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA3G83 | TT_FinMile | (RFS) READY FOR SHIPMENT TO SITE ELECTRICAL MODULES 20UBA7410 (TO SITE) | 27/04/2022 | 27/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA3G81 | TT_Task | MANUFACTURING ELECTRICAL MODULES 20UBA7410 | 18/08/2021 | 17/01/2022 | 18/08/2021 |  | 8 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2G76 | TT_Mile | E-AND IC- MANUALS FOR COMP.INSTALL.AVAILABLE ELECTRICAL MODULES 20UBA7410 | 22/12/2021 | 22/12/2021 | 22/12/2021 | 22/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA4B42 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION ELECTRICAL MODULES 20UBA7710/20 (TO SITE) | 31/03/2022 | 27/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA3B75 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) ELECTRICAL MODULES 20UBA7710/20 | 31/03/2022 | 31/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA4-65 | TT_Mile | (ET4b) ELECTRICAL MODULES AT WORKSHOP READY FOR COMPONENT INSTALLATION 20UBA7710/20 | 23/02/2022 | 23/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2G62 | TT_FinMile | (DF) INPUT FOR MS3 ELECTRICAL MODULES 20UBA7710/20 | 23/06/2021 | 23/06/2021 | 23/06/2021 | 23/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA4G54 | TT_Task | TRANSPORT ELECTRICAL MODULES 20UBA7710/20 (TO SITE) | 28/04/2022 | 22/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA3G85 | TT_Task | INSTALL. COMP., INT. CABLING, FIRE PROT., SHOP TEST ELECTRICAL MODULES 20UBA7710/20 | 19/01/2022 | 06/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA3G86 | TT_FinMile | (RFS) READY FOR SHIPMENT TO SITE ELECTRICAL MODULES 20UBA7710/20 (TO SITE) | 27/04/2022 | 27/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA3G84 | TT_Task | MANUFACTURING ELECTRICAL MODULES 20UBA7710/20 | 18/08/2021 | 17/01/2022 | 18/08/2021 |  | 288 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2G77 | TT_Mile | E-AND IC- MANUALS FOR COMP.INSTALL.AVAILABLE ELECTRICAL MODULES 20UBA7710/20 | 22/12/2021 | 22/12/2021 | 22/12/2021 | 22/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--SMM2-87 | TT_FinMile | (DF) INPUT FOR VEL CRANES 20SMM01/02 FOR 20UMC | 26/04/2021 | 26/04/2021 | 26/04/2021 | 26/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20SMG2-87 | TT_Task | BASIC DESIGN MECHANICAL / ELECTRICAL OTHER CRANES AND HOISTS | 15/04/2021 | 09/06/2021 | 15/04/2021 | 09/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20LBA6J73 | TT_Task | PT, RE-INSTALLATION PIPES / VALVES 20LBA80 (BOP) | 31/12/2022 | 12/01/2023 |  |  | 736 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LBA6H71 | TT_Task | PT, RE-INSTALLATION PIPES / VALVES 11LBA10 (TURBOSET) | 20/01/2023 | 01/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6A61 | TT_FinMile | (RFS) READY FOR SHIPMENT TO FABRICATOR ST VALVE FOR MAL00Y, MAW10Y, MAW50Y | 21/12/2021 | 21/12/2021 | 21/12/2021 | 21/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MA-4-42 | TT_FinMile | (OTD-OS) ARRIVAL AT FABRICATOR ST VALVES | 31/12/2021 | 31/12/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-4-41 | TT_Task | TRANSPORT ST VALVES TO FABRICATOR | 22/12/2021 | 31/12/2021 | 22/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SP20MA2B42 | TT_Mile | (M1) PIDs FOR ST / GENERATOR AUXILIARIES AVAILABLE | 15/01/2021 | 15/01/2021 | 15/01/2021 | 15/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MA2B43 | TT_Mile | (M2) PIDs FOR ST / GENERATOR AUXILIARIES AVAILABLE | 02/02/2021 | 02/02/2021 | 02/02/2021 | 02/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PUR3J25 | TT_Task | DETAIL DESIGN / MANUFACTURING CATHODIC PROTECTION 20PUR | 20/10/2021 | 16/07/2022 | 20/10/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20PUR3J80 | TT_FinMile | (RFS) READY FOR SHIPMENT CATHODIC PROTECTION 20PUR | 13/08/2022 | 13/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PUR4J40 | TT_FinMile | (OTD-OS) ON SITE CATHODIC PROTECTION 20PUR | 08/10/2022 | 08/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PUR2J85 | TT_Mile | CONTRACT INTO FORCE CATHODIC PROTECTION 20PUR | 24/05/2021 | 24/05/2021 | 24/05/2021 | 24/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PUR2J80 | TT_Task | QUOTATION STAGE CATHODIC PROTECTION 20PUR | 23/04/2021 | 23/05/2021 | 23/04/2021 | 23/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PUR8-25 | TT_FinMile | (TOP-20PUR-03) CATHODIC PROTECTION SYSTEM FOR COOLING TOWER STRUCTURE | 18/09/2022 | 18/09/2022 |  |  | 1184 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PUR2J75 | TT_Task | PREPARATION RFQ CATHODIC PROTECTION 20PUR | 12/02/2021 | 22/04/2021 | 12/02/2021 | 22/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PUR4J25 | TT_Task | TRANSPORT CATHODIC PROTECTION 20PUR | 14/08/2022 | 08/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PUR7J15 | TT_Task | ELECTRICAL ERECTION CATHODIC PROTECTION CONDENSER | 23/10/2022 | 20/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PUR4B10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION CATHODIC PROTECTION 20PUR | 17/07/2022 | 13/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PUR3B70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) CATHODIC PROTECTION 20PUR | 16/07/2022 | 16/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--PAD2-89 | TT_Mile | (DF) INPUT FOR MS3 CATHODIC PROTECTION 20PUR (MPA) | 13/05/2021 | 13/05/2021 | 13/05/2021 | 13/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--PAD2-88 | TT_Mile | (DF) INPUT FOR VEL CATHODIC PROTECTION 20PUR | 18/06/2021 | 18/06/2021 | 18/06/2021 | 18/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--PAD2-91 | TT_Mile | ENGINEERING INPUT FROM COARSE SCREEN / PAC PUMPS AVAILABLE (DETAILED LAYOUT) | 20/10/2021 | 20/10/2021 | 20/10/2021 | 20/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--PAD2-90 | TT_Mile | ENGINEERING INPUT FROM CONDENSER AVAILABLE (DETAILED LAYOUT) | 16/04/2021 | 16/04/2021 | 16/04/2021 | 16/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MA-2-82 | TT_Mile | CONTRACT INTO FORCE ST CONDENSER 20MAG | 26/03/2021 | 26/03/2021 | 26/03/2021 | 26/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-42 | TT_Task | BASIC BUILDING DESIGN INCL. 3D MODEL 20UTG07 | 29/06/2021 | 29/11/2021 | 29/06/2021 | 29/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-44 | TT_Task | PREPARATION FOUNDATION GROUNDING DWGS UTG 20UTG07 | 27/08/2021 | 09/09/2021 | 27/08/2021 | 09/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-43 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE 20UTG07 | 30/11/2021 | 24/01/2022 | 30/11/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-48 | TT_FinMile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION 20UTG07 | 31/03/2022 | 31/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-41 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UTG07 | 28/06/2021 | 28/06/2021 | 28/06/2021 | 28/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-45 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN CONCRETE 20UTG07 | 10/09/2021 | 04/10/2021 | 10/09/2021 | 04/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-46 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE SLAB 20UTG07 | 31/01/2022 | 31/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-47 | TT_Task | BD - CONSENT LETTER - DETAIL DESIGN CONCRETE SLAB 20UTG07 | 01/04/2022 | 28/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-50 | TT_Task | BASIC BUILDING DESIGN INCL. 3D MODEL 20UTG04 | 16/08/2021 | 05/09/2021 | 16/08/2021 | 05/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-52 | TT_Task | PREPARATION FOUNDATION GROUNDING DWGS UTG 20UTG04 | 30/11/2021 | 13/12/2021 | 30/11/2021 | 13/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-51 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE 20UTG04 | 06/09/2021 | 12/12/2021 | 06/09/2021 | 12/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-56 | TT_FinMile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION 20UTG04 | 11/03/2022 | 11/03/2022 |  |  | 160 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-49 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UTG04 | 15/10/2021 | 15/10/2021 | 15/10/2021 | 15/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-53 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN CONCRETE 20UTG04 | 14/12/2021 | 07/01/2022 | 14/12/2021 |  | 11624 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-54 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE 20UTG04 | 14/12/2021 | 11/02/2022 | 14/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-55 | TT_Task | BD - CONSENT LETTER - DETAIL DESIGN CONCRETE 20UTG04 | 12/02/2022 | 11/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-58 | TT_Task | BASIC BUILDING DESIGN INCL. 3D MODEL 20UTG02 | 11/06/2021 | 01/07/2021 | 11/06/2021 | 01/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-60 | TT_Task | PREPARATION FOUNDATION GROUNDING DWGS UTG 20UTG02 | 02/08/2021 | 15/08/2021 | 02/08/2021 | 15/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-59 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE 20UTG02 | 02/07/2021 | 15/08/2021 | 02/07/2021 | 15/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-64 | TT_FinMile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION 20UTG02 | 13/04/2022 | 13/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-57 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UTG02 | 10/06/2021 | 10/06/2021 | 10/06/2021 | 10/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-61 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN CONCRETE 20UTG02 | 16/08/2021 | 30/01/2022 | 16/08/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-62 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE 20UTG02 | 31/01/2022 | 31/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-63 | TT_Task | BD - CONSENT LETTER - DETAIL DESIGN CONCRETE 20UTG02 | 01/04/2022 | 28/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-66 | TT_Task | BASIC BUILDING DESIGN INCL. 3D MODEL 20UTG03 | 01/05/2021 | 21/05/2021 | 01/05/2021 | 21/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-68 | TT_Task | PREPARATION FOUNDATION GROUNDING DWGS UTG 20UTG03 | 22/06/2021 | 05/07/2021 | 22/06/2021 | 05/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-67 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE 20UTG03 | 22/05/2021 | 05/07/2021 | 22/05/2021 | 05/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-72 | TT_FinMile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION 20UTG03 | 27/04/2022 | 27/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-65 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UTG03 | 30/04/2021 | 30/04/2021 | 30/04/2021 | 30/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-69 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN CONCRETE 20UTG03 | 06/07/2021 | 30/07/2021 | 06/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-70 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE 20UTG03 | 31/01/2022 | 31/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-71 | TT_Task | BD - CONSENT LETTER - DETAIL DESIGN CONCRETE 20UTG03 | 01/04/2022 | 28/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-74 | TT_Task | BASIC BUILDING DESIGN INCL. 3D MODEL 20UTG05 | 16/08/2021 | 05/09/2021 | 16/08/2021 | 05/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-76 | TT_Task | PREPARATION FOUNDATION GROUNDING DWGS UTG 20UTG05 | 07/10/2021 | 20/10/2021 | 07/10/2021 | 20/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-75 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE 20UTG05 | 06/09/2021 | 20/10/2021 | 06/09/2021 | 20/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-80 | TT_FinMile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION 20UTG05 | 28/04/2022 | 28/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-73 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UTG05 | 05/07/2021 | 05/07/2021 | 05/07/2021 | 05/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-77 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN CONCRETE 20UTG05 | 21/10/2021 | 06/12/2021 | 21/10/2021 | 06/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-78 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE 20UTG05 | 31/01/2022 | 31/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-79 | TT_Task | BD - CONSENT LETTER - DETAIL DESIGN CONCRETE 20UTG05 | 01/04/2022 | 28/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-82 | TT_Task | BASIC BUILDING DESIGN INCL. 3D MODEL 20UTG06 | 16/08/2021 | 05/09/2021 | 16/08/2021 | 05/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-84 | TT_Task | PREPARATION FOUNDATION GROUNDING DWGS UTG 20UTG06 | 15/12/2021 | 28/12/2021 | 15/12/2021 | 28/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-83 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE 20UTG06 | 06/09/2021 | 28/12/2021 | 06/09/2021 | 28/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-88 | TT_FinMile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION 20UTG06 | 05/04/2022 | 05/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-81 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UTG06 | 26/07/2021 | 26/07/2021 | 26/07/2021 | 26/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-85 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN CONCRETE 20UTG06 | 29/12/2021 | 22/01/2022 | 29/12/2021 |  | 11504 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-86 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE 20UTG06 | 15/01/2022 | 15/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-87 | TT_Task | BD - CONSENT LETTER - DETAIL DESIGN CONCRETE 20UTG06 | 16/03/2022 | 12/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7-35 | TT_Task | ERECTION CABLE TRAYS ON 20UBY03 | 27/10/2022 | 02/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBY2-44 | TT_Task | PREPARATION FOUNDATION GROUNDING DWGS UBY02(NotExisting) | 02/08/2021 | 15/08/2021 | 02/08/2021 | 15/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBY2-42 | TT_Task | BASIC BUILDING DESIGN INCL. 3D MODEL UBY02(NotExisting) | 01/09/2021 | 14/10/2021 | 01/09/2021 | 14/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBY2-41 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE UBY02(NotExisting) | 01/09/2021 | 01/09/2021 | 01/09/2021 | 01/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBY2-48 | TT_FinMile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION UBY02(NotExisting) | 01/12/2021 | 01/12/2021 | 01/12/2021 | 01/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBY2-43 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE UBY02(NotExisting) | 30/09/2021 | 13/11/2021 | 30/09/2021 | 13/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBY2-45 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN CONCRETE - UBY02(NotExisting) | 16/08/2021 | 09/09/2021 | 16/08/2021 | 09/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBY2-46 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE - AMENDMENT UBY02(NotExisting) | 01/12/2021 | 30/12/2021 | 01/12/2021 | 30/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBY2-47 | TT_Task | BD - CONSENT LETTER - DESIGN UBY02(NotExisting) | 27/10/2021 | 30/11/2021 | 27/10/2021 | 30/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBY2-52 | TT_Task | PREPARATION FOUNDATION GROUNDING DWGS UBY03 | 05/10/2021 | 18/10/2021 | 05/10/2021 | 18/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBY2-50 | TT_Task | BASIC BUILDING DESIGN INCL. 3D MODEL UBY03 | 30/07/2021 | 03/09/2021 | 30/07/2021 | 03/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBY2-49 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE UBY03 | 30/07/2021 | 30/07/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBY2-56 | TT_FinMile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION UBY03 | 26/05/2022 | 26/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBY2-51 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE UBY03 | 04/09/2021 | 18/10/2021 | 04/09/2021 | 18/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBY2-53 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN CONCRETE - UBY03 | 19/10/2021 | 06/12/2021 | 19/10/2021 | 06/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBY2-54 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE - UBY03 | 28/02/2022 | 28/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBY2-55 | TT_Task | BD - CONSENT LETTER - DESIGN UBY03 | 29/04/2022 | 26/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBY2-60 | TT_Task | PREPARATION FOUNDATION GROUNDING DWGS UBY04/05 | 25/07/2021 | 06/12/2021 | 25/07/2021 | 06/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBY2-58 | TT_Task | BASIC BUILDING DESIGN INCL. 3D MODEL UBY04/05 | 03/06/2021 | 23/06/2021 | 03/06/2021 | 23/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBY2-57 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE UBY04/05 | 02/06/2021 | 02/06/2021 | 02/06/2021 | 02/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBY2-64 | TT_FinMile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION UBY04/05 | 10/03/2022 | 10/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBY2-59 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE UBY04/05 | 24/06/2021 | 06/12/2021 | 24/06/2021 | 06/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBY2-61 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN CONCRETE - UBY04/05 | 21/10/2021 | 06/12/2021 | 21/10/2021 | 06/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBY2-62 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE - UBY04/05 | 13/12/2021 | 10/02/2022 | 13/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UBY2-63 | TT_Task | BD - CONSENT LETTER - DESIGN UBY04/05 | 11/02/2022 | 10/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20USX2-30 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE 20USX | 28/02/2022 | 28/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20USX2-25 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN CONCRETE 20USX | 28/02/2022 | 24/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20USX2-35 | TT_Task | BD - CONSENT LETTER - DETAIL DESIGN CONCRETE 20USX | 29/04/2022 | 26/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK7A28 | TT_Task | CABLING ELECTRICAL MODULES 20UBA (10x) TO TRANSFORMER AREA (BAT/BBT/BAC/GIL) | 26/10/2022 | 13/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20ACA2-45 | TT_Mile | ERECTION MANUALS ON SITE GIL 400kV 20ACA | 16/08/2022 | 16/08/2022 |  |  | 152 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20ACA3-50 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION GIL 400kV 20ACA | 12/06/2022 | 09/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20ACA3-40 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) GIL 400kV 20ACA | 11/06/2022 | 11/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20ACA2-10 | TT_Task | QUOTATION STAGE GIL 400kV 20ACA | 26/03/2021 | 17/06/2021 | 26/03/2021 | 17/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20ACA2-15 | TT_Mile | RFQ GIL 400kV 20ACA | 26/03/2021 | 26/03/2021 | 26/03/2021 | 26/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20ACA2-5 | TT_Task | BASIC DESIGN / SPECIFICATION GIL 400kV 20ACA | 14/02/2021 | 25/03/2021 | 14/02/2021 | 25/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20ACA7-70 | TT_Task | ERECTION GIL 400kV 20ACA | 26/09/2022 | 20/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20ACA3-25 | TT_Task | DETAIL DESIGN / MANUFACTURING / SHOP TEST GIL 400kV 20ACA | 18/06/2021 | 11/06/2022 | 18/06/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20ACA9-85 | TT_Task | COMMISSIONING GIL 400kV 20ACA | 28/02/2023 | 13/03/2023 |  |  | 224 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20ACA2-30 | TT_Mile | CONTRACT INTO FORCE GIL 400kV 20ACA | 18/06/2021 | 18/06/2021 | 18/06/2021 | 18/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20ACA7-65 | TT_Task | PLACEMENT GIL 400kV 20ACA | 24/09/2022 | 25/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20ACA2-35 | TT_FinMile | (DF) INPUT FOR MS3 GIL 400kV 20ACA | 09/08/2021 | 09/08/2021 | 09/08/2021 | 09/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20ACA3-55 | TT_FinMile | (RFS) READY FOR SHIPMENT GIL 400kV 20ACA | 09/07/2022 | 09/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20ACA4-60 | TT_Task | TRANSPORT GIL 400kV 20ACA | 10/07/2022 | 03/09/2022 |  |  | 160 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20ACA2-20 | TT_Mile | PRELIMINARY MS2 INPUT AVAILABLE GIL 400kV 20ACA | 26/03/2021 | 26/03/2021 | 26/03/2021 | 26/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
CL20ACA7-80 | TT_Task | PULLING HV CABLES TO GIL BY CUSTOMER | 05/12/2022 | 15/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20--P6-77 | TT_Task | PREPARATION CHEMICAL CLEANING WSC | 15/04/2023 | 12/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20--P6-78 | TT_Task | COLD COMMISSIONING FOR CHEMICAL CLEANING WSC | 22/04/2023 | 12/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
CL20UGX5-40 | TT_Mile | PROVISION OF TANK FOR CHEMICAL CLEANING WATER BY CLIENT | 01/04/2023 | 01/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UGX8-45 | TT_Task | CLEAN OUT TANK (WATER AND SLUDGE) | 03/06/2023 | 16/06/2023 |  |  | 1584 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQX5-50 | TT_Mile | (H) START PLACING FORMWORK 20UQX | 11/04/2022 | 11/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQX5-45 | TT_Task | WORK PREPARATION, EXCAVATION 20UQX | 06/04/2022 | 10/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQX5-60 | TT_FinMile | (RFE) FOUNDATION 20UQX | 07/05/2022 | 07/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQX2-10 | TT_Task | BASIC BUILDING DESIGN INCL. 3D MODEL 20UQX | 11/06/2021 | 01/07/2021 | 11/06/2021 | 01/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UQX2-20 | TT_Task | PREPARATION FOUNDATION GROUNDING DWGS UTG 20UQX | 02/09/2021 | 06/12/2021 | 02/09/2021 | 06/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UQX2-15 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE 20UQX | 02/07/2021 | 06/12/2021 | 02/07/2021 | 06/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UQX2-40 | TT_FinMile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION 20UQX | 05/04/2022 | 05/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQX2-5 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UQX | 11/06/2021 | 11/06/2021 | 11/06/2021 | 11/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UQX2-25 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN CONCRETE 20UQX | 07/12/2021 | 31/12/2021 | 07/12/2021 |  | 11680 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UQX2-30 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE 20UQX | 15/01/2022 | 15/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQX2-35 | TT_Task | BD - CONSENT LETTER - DETAIL DESIGN CONCRETE 20UQX | 16/03/2022 | 12/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20ULY4-105 | TT_Task | TRANSPORT STEEL STRUCTURE 20ULY01 | 02/06/2022 | 06/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20ULY4-110 | TT_FinMile | (OTD-OS) ON SITE STEEL STRUCTURE 20ULY01 | 06/07/2022 | 06/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20ULY4-95 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION STEEL STRUCTURE 20ULY01 | 05/05/2022 | 01/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20ULY4-90 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) STEEL STRUCTURE 20ULY01 | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20ULY4-100 | TT_FinMile | (RFS) READY FOR SHIPMENT STEEL STRUCTURE 20ULY01 | 01/06/2022 | 01/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20ULY2-65 | TT_Task | BASIC DESIGN STEEL STRUCTURE 20ULY01 | 11/06/2021 | 17/07/2021 | 11/06/2021 | 18/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20ULY2-70 | TT_Task | BD - SUBMISSION APPROVAL - STEEL STRUCTURE 20ULY01 | 28/02/2022 | 28/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20ULY2-80 | TT_Task | BD - CONSENT LETTER - STEEL STRUCTURE 20ULY01 | 29/04/2022 | 26/05/2022 |  |  | 328 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20ULY2-75 | TT_Task | PREPARE SHOP DRAWINGS STEELWORKS 20ULY01 | 29/01/2022 | 25/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20ULY3-85 | TT_Task | MANUFACTURING STEEL STRUCTURE 20ULY01 | 24/02/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20ULY5-115 | TT_Task | PREPARATION ERECTION STEEL STRUCTURE 20ULY01 | 07/07/2022 | 13/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7-55 | TT_Task | ERECTION CABLE TRAYS ON 20UQY01 | 27/10/2022 | 09/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY2-84 | TT_Task | PREPARATION FOUNDATION GROUNDING DWGS 20UQY01 | 26/09/2021 | 09/10/2021 | 26/09/2021 | 09/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UQY2-82 | TT_Task | BASIC BUILDING DESIGN INCL. 3D MODEL 20UQY01 | 11/06/2021 | 01/07/2021 | 11/06/2021 | 01/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-147 | TT_Mile | (H) START PLACING FORMWORK PIPE / CABLE TRENCH 20UQY01 | 20/04/2022 | 20/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-149 | TT_FinMile | (RFE) FOUNDATION PIPE / CABLE TRENCH 20UQY01 | 18/05/2022 | 18/05/2022 |  |  | 568 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY2-81 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UQY01 | 10/06/2021 | 10/06/2021 | 10/06/2021 | 10/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-146 | TT_Task | WORK PREPARATION, EXCAVATION PIPE / CABLE TRENCH 20UQY01 (TO BE ALIGNED WITH CLP) | 13/04/2022 | 19/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY2-88 | TT_FinMile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION 20UQY01 | 12/04/2022 | 12/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY2-83 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE 20UQY01 | 02/07/2021 | 09/10/2021 | 02/07/2021 | 09/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UQY2-85 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN CONCRETE - 20UQY01 | 10/10/2021 | 06/12/2021 | 10/10/2021 | 06/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UQY2-86 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE - 20UQY01 | 15/01/2022 | 15/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY2-87 | TT_Task | BD - CONSENT LETTER - DESIGN 20UQY01 | 16/03/2022 | 12/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQZ2-96 | TT_Task | PREPARATION FOUNDATION GROUNDING DWGS 20UQZ | 02/09/2021 | 03/01/2022 | 02/09/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UQZ2-94 | TT_Task | BASIC BUILDING DESIGN INCL. 3D MODEL 20UQZ | 11/06/2021 | 01/07/2021 | 11/06/2021 | 01/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UQZ5-155 | TT_Mile | (H) START PLACING FORMWORK PIPE CABLE TRENCH 20UQZ | 15/02/2022 | 15/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQZ5-157 | TT_FinMile | (RFE) FOUNDATION PIPE CABLE TRENCH 20UQZ | 01/04/2022 | 01/04/2022 |  |  | 144 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQZ2-93 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UQZ | 10/06/2021 | 10/06/2021 | 10/06/2021 | 10/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UQZ5-154 | TT_Task | WORK PREPARATION, EXCAVATION PIPE CABLE TRENCH 20UQZ (TO BE ALIGNED WITH CLP) | 01/02/2022 | 14/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQZ2-100 | TT_Mile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION 20UQZ | 01/02/2022 | 01/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQZ2-95 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE 20UQZ | 02/07/2021 | 03/01/2022 | 02/07/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UQZ2-97 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN CONCRETE - 20UQZ | 15/09/2021 | 03/01/2022 | 15/09/2021 |  | 11656 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UQZ2-98 | TT_Task | BD - AMENDMENT SUBMISSION - DETAIL DESIGN CONCRETE - 20UQZ | 04/01/2022 | 31/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQZ2-104 | TT_Task | PREPARATION FOUNDATION GROUNDING DWGS CIVIL ADAPTION WORKS AT SCW PUMP HOUSE 20UQB | 26/09/2021 | 05/12/2021 | 26/09/2021 | 05/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UQZ5-159 | TT_Mile | (H) START PLACING FORMWORK CIVIL ADAPTION WORKS AT SCW PUMP HOUSE 20UQB | 04/03/2022 | 04/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQZ5-161 | TT_FinMile | (RFE) READY FOR ERECTION CIVIL ADAPTION WORKS AT SCW PUMP HOUSE 20UQB | 20/03/2022 | 20/03/2022 |  |  | 144 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQZ5-158 | TT_Task | WORK PREPARATION, EXCAVATION CIVIL ADAPTION WORKS AT SCW PUMP HOUSE 20UQB | 25/02/2022 | 03/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQZ2-108 | TT_FinMile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION CIVIL ADAPTION WORKS AT SCW PUMP HOUSE 20UQB | 24/02/2022 | 24/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQZ2-103 | TT_Task | DETAIL DESIGN CONCRETE CIVIL ADAPTION WORKS AT SCW PUMP HOUSE 20UQB | 02/07/2021 | 05/12/2021 | 02/07/2021 | 05/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UQZ2-105 | TT_Task | CLIENT - REVIEW - CIVIL ADAPTION WORKS AT SCW PUMP HOUSE 20UQB | 06/12/2021 | 30/12/2021 | 06/12/2021 | 30/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UQZ2-106 | TT_Task | BD - SUBMISSION APPROVAL - CIVIL ADAPTION WORKS AT SCW PUMP HOUSE 20UQB | 06/12/2021 | 03/02/2022 | 06/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UQZ2-107 | TT_Task | BD - CONSENT LETTER - CIVIL ADAPTION WORKS AT SCW PUMP HOUSE 20UQB | 04/02/2022 | 03/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-----5-23 | TT_Mile | START OF CLIENTS OUTAGE AT EXISTING SCW PUMP HOUSE | 01/02/2022 | 01/02/2022 |  |  | 192 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--2M-22 | TT_Task | BD - SUBMISSION APPROVAL - SUPPORTING FRAME FOR MODULES LOT 2 (UMCM1Y/UMCL1Y) | 05/07/2021 | 02/09/2021 | 05/07/2021 | 02/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--2M-32 | TT_Task | BD - CONSENT LETTER - SUPPORTING FRAME FOR MODULES LOT 2 | 03/09/2021 | 30/11/2021 | 03/09/2021 | 30/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--2M-23 | TT_Task | BD - SUBMISSION APPROVAL - SUPPORTING FRAME FOR MODULES LOT 3 (UEY01Y/UEY02Y/UPY00Y) | 03/08/2021 | 01/10/2021 | 03/08/2021 | 01/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--2M-33 | TT_Task | BD - CONSENT LETTER - SUPPORTING FRAME FOR MODULES LOT 3 (UEY02) | 02/10/2021 | 30/01/2022 | 02/10/2021 |  | 376 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7-75 | TT_Task | ERECTION CABLE TRAYS BEFORE LIFTING OF MODULE 20UEY01 | 29/05/2022 | 25/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7D18 | TT_Task | FINALIZE CABLE TRAYS ON 20UEY01 | 09/07/2022 | 15/07/2022 |  |  | 808 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-100 | TT_Mile | TP-M1A - FUEL GAS SUPPLY - PCI AND LNG BLEND | 12/07/2022 | 12/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-105 | TT_Mile | TP-M2C - FUEL OIL SUPPLY - STANDBY DIESEL GENERATOR | 17/09/2022 | 17/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-115 | TT_Mile | TP-M4A - RESERVE FEED WATER SYSTEM | 18/05/2022 | 18/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-120 | TT_Mile | TP-M7A - HYDROGEN SUPPLY | 18/06/2022 | 18/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-130 | TT_Mile | TP-M9B - SERVICE AIR INTERCONNECTION TO BPPS SERVICE AIR SYSTEM | 18/05/2022 | 18/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-133 | TT_Mile | TP-M13A - FIRST UREA TANK 10HSJ20BB001 - LIQUID UREA SUPPLY | 01/07/2022 | 01/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-259 | TT_Mile | TP-E2 - D2 6.6kV INTERCONNECTIORS (D2 Site) | 09/07/2022 | 09/07/2022 |  |  | 2208 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SD-110 | TT_Task | SHUTDOWN PERIOD FOR TP INTEGRATION (COMBUSTION INSPECTION D1) 2022 | 04/05/2022 | 25/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SD-120 | TT_Task | SHUTDOWN PERIOD AT EXISTING SCW PUMP HOUSE | 01/02/2022 | 30/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-----8-7 | TT_FinMile | MV AVAILABLE (BACK ENERGISING 6,6kV) (possibility to reduce risks if it can be achieved earlier) | 28/03/2023 | 28/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UHA2B-7 | TT_FinMile | CONTRACT INTO FORCE FOR EMBEDDED PARTS HRSG | 03/05/2021 | 03/05/2021 | 03/05/2021 | 03/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHA2B-6 | TT_Task | QUOTATION FOR EMBEDDED PARTS HRSG | 23/03/2021 | 03/05/2021 | 23/03/2021 | 03/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHA2B-5 | TT_Task | RFQ FOR EMBEDDED PARTS HRSG | 27/01/2021 | 22/03/2021 | 27/01/2021 | 22/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20SD-121 | TT_Task | SHUTDOWN PERIOD FOR TP INTEGRATION (COMBUSTION INSPECTION D1) 2021 | 29/04/2021 | 02/05/2021 | 29/04/2021 | 02/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20SD-122 | TT_Task | SHUTDOWN PERIOD FOR TP INTEGRATION (TB2 OUTAGE D1) | 28/02/2021 | 29/03/2021 | 28/02/2021 | 29/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20SMM6-71 | TT_Task | CERTIFICATES FOR LIFTING APPLIANCES, LIFTING GEARS CRANES 20SMM01/02/03 | 17/05/2022 | 15/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UHW2-5 | TT_Task | BASIC DESIGN / BASIC BUILDING DESIGN INCL. 3D MODEL UHW | 13/05/2021 | 02/06/2021 | 13/05/2021 | 02/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHW2-15 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE UHW | 03/06/2021 | 17/07/2021 | 03/06/2021 | 17/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHW5-75 | TT_FinMile | (RFE) FOUNDATION 20UHW | 06/02/2022 | 06/02/2022 |  |  | 168 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UHW2-40 | TT_FinMile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION UHW | 22/07/2021 | 22/07/2021 | 22/07/2021 | 22/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHW5-60 | TT_Mile | (H) START PLACING FORMWORK 20UHW | 13/10/2021 | 13/10/2021 | 13/10/2021 | 13/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHW2-25 | TT_Task | PREPARATION FOUNDATION GROUNDING DWGS UHW | 04/07/2021 | 17/07/2021 | 04/07/2021 | 17/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHW2-10 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE UHW | 12/05/2021 | 12/05/2021 | 12/05/2021 | 12/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHW2-45 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE - RESUBMISSION HRSG 20UHW(2NDPACKAGE) | 24/05/2021 | 09/06/2021 | 24/05/2021 | 10/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHW2-30 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN CONCRETE - HRSG BLOWDOWN PIT 20UHW | 18/07/2021 | 11/08/2021 | 18/07/2021 | 11/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHW2-50 | TT_Task | BD - CONSENT LETTER HRSG BLOWDOWN PIT DESIGN 20UHW | 15/06/2021 | 30/07/2021 | 15/06/2021 | 31/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHW5-65 | TT_Task | CONSTRUCTION BASE PLATE HRSG BLOWDOWN PIT 20UHW | 24/10/2021 | 13/11/2021 | 24/10/2021 | 13/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBH8-27 | TT_Task | COMMISSIONING OIL COLLECTION PIT / OIL SEPARATOR 20UBH01 | 11/04/2023 | 17/04/2023 |  |  | 32 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC2B66 | TT_Mile | (MS3) HVAC / LOUVERS / EXHAUST OPENINGS INPUT AVAILABLE | 15/06/2021 | 15/06/2021 | 15/06/2021 | 15/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--PAD2-92 | TT_FinMile | (DF) INPUT FOR M2 COOLING TOWER PAD | 24/03/2021 | 24/03/2021 | 24/03/2021 | 24/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PCC4B43 | TT_FinMile | (OTD-OS) ON SITE SERVICE CW PUMPS PCC | 20/04/2022 | 20/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PCC3B81 | TT_Task | DETAIL DESIGN, MANUFACTURING, SHOP TEST SERVICE CW PUMPS PCC | 15/06/2021 | 26/01/2022 | 15/06/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20PCC3B83 | TT_FinMile | (RFS) READY FOR SHIPMENT SERVICE CW PUMPS PCC | 23/02/2022 | 23/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PCC4B42 | TT_Task | TRANSPORT SERVICE CW PUMPS PCC | 24/02/2022 | 20/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PCC4B41 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION - SERVICE CW PUMPS PCC | 27/01/2022 | 23/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PCC3B82 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) - SERVICE CW PUMPS PCC | 26/01/2022 | 26/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PCC6B16 | TT_Task | ERECTION SERVICE CW PUMPS PCC | 05/05/2022 | 15/06/2022 |  |  | 360 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PCC2A94 | TT_Task | QUOTATION STAGE, BASIC DESIGN SERVICE CW PUMPS PCC | 18/03/2021 | 12/05/2021 | 18/03/2021 | 12/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PCC2A95 | TT_Mile | CONTRACT INTO FORCE SERVICE CW PUMPS PCC | 15/06/2021 | 15/06/2021 | 15/06/2021 | 15/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PCC2A93 | TT_Task | PREPARATION RFQ SERVICE CW PUMPS PCC | 05/02/2021 | 18/03/2021 | 05/02/2021 | 18/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PCC2B66 | TT_FinMile | (DF) INPUT FOR MS3 SERVICE CW PUMPS PCC | 13/05/2021 | 13/05/2021 | 13/05/2021 | 13/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PCC2B67 | TT_FinMile | (DF) INPUT FOR M2 SERVICE CW PUMPS PCC | 04/05/2021 | 04/05/2021 | 04/05/2021 | 04/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PCC2A96 | TT_Mile | (DF) INPUT FOR VEL SERVICE CW PUMPS PCC | 28/06/2021 | 28/06/2021 | 28/06/2021 | 28/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBH2-84 | TT_Task | DETAIL DESIGN, CHECKER CONCRETE STRUCTURE 20UBH02 | 18/06/2021 | 22/07/2021 | 18/06/2021 | 22/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBH2-86 | TT_FinMile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION 20UBH02 | 04/12/2021 | 04/12/2021 | 04/12/2021 | 04/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBH2-82 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UBH02 | 28/05/2021 | 28/05/2021 | 28/05/2021 | 28/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBH2-85 | TT_Task | PREPARATION FOUNDATION GROUNDING DWGS 20UBH02 | 09/07/2021 | 22/07/2021 | 09/07/2021 | 22/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBH2-90 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN CONCRETE - 20UBH02 | 23/07/2021 | 16/08/2021 | 23/07/2021 | 16/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBH2-91 | TT_Task | BD - SUBMISSION APPROVAL - 20UBH02 | 17/08/2021 | 15/10/2021 | 17/08/2021 | 15/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBH2-92 | TT_Task | BD - CONSENT LETTER - 20UBH02 | 16/10/2021 | 04/12/2021 | 16/10/2021 | 04/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBH2-83 | TT_Task | BASIC DESIGN INCL. 3D MODEL, OIL COLLECTING PIT / OIL SEPARATOR 20UBH02 | 28/05/2021 | 17/06/2021 | 28/05/2021 | 17/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ5-64 | TT_FinMile | (RFE) FOUNDATION 20UBZ01 | 16/06/2022 | 16/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ5-61 | TT_Task | WORK PREPARATION, EXCAVATION 20UBZ01 | 12/05/2022 | 18/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ5-63 | TT_Mile | (H) START PLACING FORMWORK 20UBZ01 | 19/05/2022 | 19/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ2-68 | TT_Task | PREPARATION FOUNDATION GROUNDING DWGS 20UBZ01 | 03/08/2021 | 16/08/2021 | 03/08/2021 | 16/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ2-66 | TT_Task | BASIC BUILDING DESIGN INCL. 3D MODEL 20UBZ01 | 06/06/2021 | 02/07/2021 | 06/06/2021 | 02/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ2-65 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UBZ01 | 05/06/2021 | 05/06/2021 | 05/06/2021 | 05/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ2-72 | TT_FinMile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION 20UBZ01 | 11/05/2022 | 11/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ2-67 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE 20UBZ01 | 03/07/2021 | 16/08/2021 | 03/07/2021 | 16/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ2-69 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN CONCRETE - 20UBZ01 | 17/08/2021 | 10/09/2021 | 17/08/2021 | 10/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ2-70 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE - 20UBZ01 | 13/12/2021 | 10/02/2022 | 13/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ2-71 | TT_Task | BD - CONSENT LETTER - DESIGN 20UBZ01 | 11/02/2022 | 10/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ5-68 | TT_FinMile | (RFE) FOUNDATION 20UBZ04 | 02/06/2022 | 02/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ5-65 | TT_Task | WORK PREPARATION, EXCAVATION 20UBZ04 | 22/04/2022 | 28/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ5-67 | TT_Mile | (H) START PLACING FORMWORK 20UBZ04 | 29/04/2022 | 29/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ2-76 | TT_Task | PREPARATION FOUNDATION GROUNDING DWGS 20UBZ04 | 02/08/2021 | 15/08/2021 | 02/08/2021 | 15/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ2-74 | TT_Task | BASIC BUILDING DESIGN INCL. 3D MODEL 20UBZ04 | 11/06/2021 | 01/07/2021 | 11/06/2021 | 01/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ2-73 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UBZ04 | 10/06/2021 | 10/06/2021 | 10/06/2021 | 10/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ2-80 | TT_FinMile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION 20UBZ04 | 10/04/2022 | 10/04/2022 |  |  | 88 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ2-75 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE 20UBZ04 | 02/07/2021 | 29/12/2021 | 02/07/2021 | 29/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ2-77 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN CONCRETE - 20UBZ04 | 16/08/2021 | 09/09/2021 | 16/08/2021 | 09/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ2-78 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE - 20UBZ04 | 30/12/2021 | 27/02/2022 | 30/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ2-79 | TT_Task | BD - CONSENT LETTER - DESIGN 20UBZ04 | 28/02/2022 | 10/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ5-72 | TT_FinMile | (RFE) FOUNDATION 20UBZ02 | 02/04/2022 | 02/04/2022 |  |  | 432 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ5-70 | TT_Task | CONSTRUCTION FOUNDATION 20UBZ02 | 06/03/2022 | 02/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ5-71 | TT_Mile | (H) START PLACING FORMWORK 20UBZ02 | 15/02/2022 | 15/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ2-84 | TT_Task | PREPARATION FOUNDATION GROUNDING DWGS 20UBZ02 | 02/08/2021 | 15/08/2021 | 02/08/2021 | 15/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ2-81 | TT_Task | BASIC BUILDING DESIGN INCL. 3D MODEL 20UBZ02 | 31/05/2021 | 26/06/2021 | 31/05/2021 | 26/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ2-82 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UBZ02 | 14/05/2021 | 14/05/2021 | 14/05/2021 | 14/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ2-88 | TT_Mile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION 20UBZ02 | 04/02/2022 | 04/02/2022 |  |  | 32 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ2-83 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE 20UBZ02 | 28/06/2021 | 15/08/2021 | 28/06/2021 | 15/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ2-85 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN CONCRETE - 20UBZ02 | 16/08/2021 | 03/01/2022 | 16/08/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ2-86 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE - 20UBZ02 | 04/01/2022 | 31/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ2-87 | TT_Task | BD - CONSENT LETTER - DESIGN 20UBZ02 | 01/02/2022 | 28/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
CLP20UBZ5-76 | TT_FinMile | (RFE) FOUNDATION 20UBZ03 (CLP Scope) | 01/07/2021 | 01/07/2021 | 01/07/2021 | 01/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7-105 | TT_Task | ERECTION CABLE TRAYS ON 20ULZ01 | 29/07/2022 | 04/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
CLP20UEZ5-80 | TT_FinMile | (RFE) FOUNDATION 20UEZ01 (CLP Scope) | 30/06/2021 | 30/06/2021 | 30/06/2021 | 30/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
CLP20ULZ5-82 | TT_FinMile | (RFE) FOUNDATION 20ULZ01 (CLP Scope) | 01/07/2021 | 01/07/2021 | 01/07/2021 | 01/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20EK-6-41 | TT_Task | TEMPORARY PLACEMENT OF CRANE ON 20UEN FOR INSTALLATION WORKS ON 20UEN | 02/04/2022 | 11/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY2-92 | TT_Task | PREPARATION FOUNDATION GROUNDING DWGS 20UQY02 | 26/09/2021 | 09/10/2021 | 26/09/2021 | 09/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UQY2-90 | TT_Task | BASIC BUILDING DESIGN INCL. 3D MODEL 20UQY02 | 11/06/2021 | 01/07/2021 | 11/06/2021 | 01/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-151 | TT_Mile | (H) START PLACING FORMWORK PIPE / CABLE TRENCH 20UQY02 | 13/04/2022 | 13/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-153 | TT_FinMile | (RFE) FOUNDATION PIPE / CABLE TRENCH 20UQY02 | 11/05/2022 | 11/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY2-89 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UQY02 | 10/06/2021 | 10/06/2021 | 10/06/2021 | 10/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-150 | TT_Task | WORK PREPARATION, EXCAVATION PIPE / CABLE TRENCH 20UQY02 (TO BE ALIGNED WITH CLP) | 06/04/2022 | 12/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY2-96 | TT_FinMile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION 20UQY02 | 15/03/2022 | 15/03/2022 |  |  | 168 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY2-91 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE 20UQY02 | 02/07/2021 | 09/10/2021 | 02/07/2021 | 09/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UQY2-93 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN CONCRETE - 20UQY02 | 10/10/2021 | 06/12/2021 | 10/10/2021 | 06/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UQY2-94 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE - 20UQY02 | 15/01/2022 | 15/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY2-95 | TT_Task | BD - CONSENT LETTER - DESIGN 20UQY02 | 16/03/2022 | 12/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY2-100 | TT_Task | PREPARATION FOUNDATION GROUNDING DWGS 20UQY03 | 26/09/2021 | 06/12/2021 | 26/09/2021 | 06/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UQY2-98 | TT_Task | BASIC BUILDING DESIGN INCL. 3D MODEL 20UQY03 | 11/06/2021 | 01/07/2021 | 11/06/2021 | 01/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-155 | TT_Mile | (H) START PLACING FORMWORK PIPE / CABLE TRENCH 20UQY03 | 20/04/2022 | 20/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-157 | TT_FinMile | (RFE) FOUNDATION PIPE / CABLE TRENCH 20UQY03 | 18/05/2022 | 18/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY2-97 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UQY03 | 10/06/2021 | 10/06/2021 | 10/06/2021 | 10/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-154 | TT_Task | WORK PREPARATION, EXCAVATION PIPE / CABLE TRENCH 20UQY03 (TO BE ALIGNED WITH CLP) | 13/04/2022 | 19/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY2-104 | TT_FinMile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION 20UQY03 | 15/03/2022 | 15/03/2022 |  |  | 224 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY2-99 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE 20UQY03 | 02/07/2021 | 06/12/2021 | 02/07/2021 | 06/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UQY2-101 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN CONCRETE - 20UQY03 | 07/12/2021 | 31/12/2021 | 07/12/2021 |  | 11680 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UQY2-102 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE - 20UQY03 | 15/01/2022 | 15/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY2-103 | TT_Task | BD - CONSENT LETTER - DESIGN 20UQY03 | 16/03/2022 | 12/04/2022 |  |  | 112 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7-65 | TT_Task | ERECTION CABLE TRAYS ON 20UQY02 | 10/08/2022 | 16/08/2022 |  |  | 720 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7-70 | TT_Task | ERECTION CABLE TRAYS ON 20UQY03 | 17/08/2022 | 30/08/2022 |  |  | 512 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGC6J16 | TT_Task | ERECTION SPRAY DELUGE SYSTEM UNDER ELECTRICAL MODULES 20UBA8110/20 20SGC | 08/12/2022 | 21/12/2022 |  |  | 40 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGC8-26 | TT_Task | COLD COMMISSIONING SPRAY DELUGE SYSTEM UNDER ELECTRICAL MODULES 20UBA8110/20 20SGC | 29/03/2023 | 04/04/2023 |  |  | 48 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGJ6-16 | TT_Task | ERECTION FF INERTGAS SYSTEM IN 20UBA1110/20 SGM | 01/12/2022 | 14/12/2022 |  |  | 96 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGY7A16 | TT_Task | ERECTION FIRE DETECTION SYSTEM IN 20UBA1110/20 SGY | 23/02/2023 | 08/03/2023 |  |  | 264 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGC6J17 | TT_Task | ERECTION SPRAY DELUGE SYSTEM UNDER ELECTRICAL MODULES 20UBA1110/20 | 01/12/2022 | 14/12/2022 |  |  | 64 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGJ8-30 | TT_Task | COLD COMMISSIONING FF INERTGAS SYSTEM IN 20UBA1110/20 SGM INSIDE CONTAINERS | 11/04/2023 | 17/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGJ8-29 | TT_FinMile | (TOP-20SGM-01) FF INERTGAS SYSTEM IN 20UBA1110/20 SGM INSIDE CONTAINERS | 03/04/2023 | 03/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGC8-27 | TT_Task | COLD COMMISSIONING SPRAY DELUGE SYSTEM UNDER ELECTRICAL MODULES 20UBA1110/20 | 04/04/2023 | 10/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGM6-17 | TT_Task | ERECTION FF INERTGAS SYSTEM IN 01UBA9010/20 SGM | 09/08/2022 | 22/08/2022 |  |  | 720 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGY7A17 | TT_Task | ERECTION FIRE DETECTION SYSTEM IN 01UBA9010/20 SGY | 09/08/2022 | 22/08/2022 |  |  | 456 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGC6J18 | TT_Task | ERECTION SPRAY DELUGE SYSTEM UNDER ELECTRICAL MODULES 01UBA9010/20 20SGC | 19/07/2022 | 01/08/2022 |  |  | 1168 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGM8-32 | TT_Task | COLD COMMISSIONING FF INERTGAS SYSTEM IN 01UBA9010/20 SGM INSIDE CONTAINERS | 07/02/2023 | 13/02/2023 |  |  | 160 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGM8-31 | TT_FinMile | (TOP-20SGM-05) FF INERTGAS SYSTEM IN 01UBA9010/20 SGM INSIDE CONTAINERS | 06/02/2023 | 06/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGC8-28 | TT_Task | COLD COMMISSIONING SPRAY DELUGE SYSTEM UNDER ELECTRICAL MODULES 01UBA9010/20 20SGC | 07/02/2023 | 13/02/2023 |  |  | 160 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA4C-6 | TT_FinMile | (OTD-OS) ON SITE ELECTRICAL MODULES 20UBA1110/20 | 17/11/2022 | 17/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA7C-31 | TT_Task | PLACING ELECTRICAL MODULES 20UBA1110/20 | 18/11/2022 | 20/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20CJT8-20 | TT_Task | COLD COMMISSIONING SFC CUBICLE 20CJT | 29/03/2023 | 11/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20CJT8A20 | TT_Task | COLD COMMISSIONING SEE CUBICLE 20CJT | 14/03/2023 | 27/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGM6-20 | TT_Task | ERECTION FF INERTGAS SYSTEM IN 20UBA7910/20 SGM | 04/09/2022 | 17/09/2022 |  |  | 512 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGC6J20 | TT_Task | ERECTION SPRAY DELUGE SYSTEM UNDER ELECTRICAL MODULES 20UBA7910/20 20SGC | 04/09/2022 | 17/09/2022 |  |  | 248 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGM8-40 | TT_Task | COLD COMMISSIONING FF INERTGAS SYSTEM IN 20UBA7910/20 SGM INSIDE CONTAINERS | 21/02/2023 | 27/02/2023 |  |  | 168 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGM8-35 | TT_FinMile | (TOP-20SGM-06) FF INERTGAS SYSTEM IN 20UBA7910/20 SGM INSIDE CONTAINERS | 20/02/2023 | 20/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGC8-30 | TT_Task | COLD COMMISSIONING SPRAY DELUGE SYSTEM UNDER ELECTRICAL MODULES20UBA7910/20 20SGC | 14/03/2023 | 20/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGC6J21 | TT_Task | ERECTION SPRAY DELUGE SYSTEM FOR 20BFT03/04 20SGC | 13/12/2022 | 26/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGC8-31 | TT_Task | COLD COMMISSIONING SPRAY DELUGE SYSTEM FOR 20BFT03/04 20SGC | 11/04/2023 | 17/04/2023 |  |  | 232 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGC6J22 | TT_Task | ERECTION SPRAY DELUGE SYSTEM FOR 20BFT01/02 20SGC | 20/07/2022 | 02/08/2022 |  |  | 880 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGC8-32 | TT_Task | COLD COMMISSIONING SPRAY DELUGE SYSTEM FOR 20BFT01/02 20SGC | 07/02/2023 | 13/02/2023 |  |  | 56 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGY7A18 | TT_Task | ERECTION FIRE DETECTION SYSTEM FOR 20BFT01/02 SGY | 20/07/2022 | 02/08/2022 |  |  | 616 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGC6J23 | TT_Task | ERECTION SPRAY DELUGE SYSTEM FOR 20BBT01/02 20SGC | 08/09/2022 | 21/09/2022 |  |  | 480 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGY7A19 | TT_Task | ERECTION FIRE DETECTION SYSTEM FOR 20BAT SGY | 24/09/2022 | 07/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGY7A20 | TT_Task | ERECTION FIRE DETECTION SYSTEM FOR 20BBT SGY | 08/09/2022 | 21/09/2022 |  |  | 216 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGC6J24 | TT_Task | ERECTION SPRAY DELUGE SYSTEM FOR 20MKC02 20SGC | 12/12/2022 | 25/12/2022 |  |  | 8 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGY7A21 | TT_Task | ERECTION FIRE DETECTION SYSTEM FOR 20MKC02 SGY | 01/10/2022 | 14/10/2022 |  |  | 32 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGC6J25 | TT_Task | ERECTION SPRAY DELUGE SYSTEM FOR 20MKC01/MBJ01 20SGC | 12/12/2022 | 25/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGY7A22 | TT_Task | ERECTION FIRE DETECTION SYSTEM FOR 20MKC01/20MBJ01 SGY | 01/10/2022 | 14/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGY7A23 | TT_Task | ERECTION FIRE DETECTION SYSTEM IN 20XKA11 SGY | 22/10/2022 | 04/11/2022 |  |  | 1256 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGM6-21 | TT_Task | ERECTION FF INERTGAS SYSTEM IN 20XKA11 SGM | 24/09/2022 | 07/10/2022 |  |  | 352 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGM8-42 | TT_Task | COLD COMMISSIONING FF INERTGAS SYSTEM IN 20XKA11 SGM | 11/04/2023 | 17/04/2023 |  |  | 312 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGM8-41 | TT_FinMile | (TOP-20SGM-03) FF INERTGAS EXTINGHISHING SYSTEM UBN | 10/04/2023 | 10/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGY7-18 | TT_Task | ERECTION FIRE DETECTION SYSTEM IN 20BFT03/04 SGY | 19/12/2022 | 25/12/2022 |  |  | 1136 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGY7-19 | TT_Task | ERECTION FIRE DETECTION SYSTEM IN 20UBZ02 SGY | 17/06/2022 | 23/06/2022 |  |  | 936 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BHT7-15 | TT_Task | PLACING LV TRANSFORMER 20BFT03/04 | 21/11/2022 | 21/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7-40 | TT_Task | ERECTION CABLE TRAYS ON 20UBZ02 | 03/06/2022 | 16/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGY7A24 | TT_Task | ERECTION FIRE DETECTION SYSTEM IN 20UEN SGY | 12/02/2023 | 25/02/2023 |  |  | 648 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGY7A25 | TT_Task | ERECTION FIRE DETECTION SYSTEM IN 20UEX01 SGY | 22/10/2022 | 04/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGC6J26 | TT_Task | ERECTION SPRAY DELUGE SYSTEM FOR 20UEX01 20SGC | 22/10/2022 | 04/11/2022 |  |  | 416 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGY7A26 | TT_Task | ERECTION FIRE DETECTION SYSTEM IN 20QU SGY | 02/12/2022 | 15/12/2022 |  |  | 1192 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGY7A27 | TT_Task | ERECTION FIRE DETECTION SYSTEM IN LAC ENCLOSURES SGY | 27/10/2022 | 09/11/2022 |  |  | 1216 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGC6J27 | TT_Task | ERECTION SPRAY DELUGE SYSTEM IN LAC ENCLOSURES SGC | 27/10/2022 | 09/11/2022 |  |  | 88 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGC8-33 | TT_Task | COLD COMMISSIONING SPRAY DELUGE SYSTEM IN LAC ENCLOSURES SGC | 11/04/2023 | 17/04/2023 |  |  | 592 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGY7A28 | TT_Task | ERECTION FIRE DETECTION SYSTEM IN GT ENCLOSURE 20MPB SGY | 24/11/2022 | 07/12/2022 |  |  | 976 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGY7A29 | TT_Task | ERECTION FIRE DETECTION SYSTEM FOR TS AUXILIARY OIL SYSTEMS / H2 SYSTEMS SGY | 25/08/2022 | 19/10/2022 |  |  | 1440 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGY7A30 | TT_Task | ERECTION FIRE DETECTION SYSTEM FOR FOR LCB / LDK PUMP AREA SGY | 27/08/2022 | 09/09/2022 |  |  | 1704 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGC6J28 | TT_Task | ERECTION SPRAY DELUGE SYSTEM FOR LCB / LDK PUMP AREA SGC | 20/10/2022 | 02/11/2022 |  |  | 144 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGC8-34 | TT_Task | COLD COMMISSIONING SPRAY DELUGE SYSTEM FOR LCB / LDK PUMP AREA SGC | 11/04/2023 | 17/04/2023 |  |  | 592 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGY7A31 | TT_Task | ERECTION FIRE DETECTION SYSTEM IN 20UBA7910/20 SGY | 04/09/2022 | 17/09/2022 |  |  | 248 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--5552-86 | TT_Task | PREPARE MAINTENANCE CONCEPT | 31/07/2021 | 27/08/2021 | 31/07/2021 | 27/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UEX2-55 | TT_Task | CONSTRUCTION FINISHING WORKS 20UEX01 | 24/09/2022 | 14/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEX2-65 | TT_FinMile | (RFE) FINISHING WORKS 20UEX01 | 14/10/2022 | 14/10/2022 |  |  | 56 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEX2-35 | TT_Task | PURCHASING, TRANSPORT FINISHING WORKS MATERIAL 20UEX01 | 02/07/2022 | 23/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEX2-30 | TT_FinMile | (F) FINISHING WORKS DWGS ON SITE RELEASED FOR EXEC. 20UEX01 | 01/07/2022 | 01/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEX2-5 | TT_Task | DETAIL DESIGN FINISHING WORKS 20UEX01 | 17/02/2022 | 23/03/2022 |  |  | 800 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZL7A17 | TT_Task | LIGHTING AND SMALL POWER INSTALLATION 20UEX01/20UBN | 17/09/2022 | 14/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-116 | TT_FinMile | (OTD-OS) FIRST PIPES ON SITE PIPING SYSTEM (OUTSIDE) 20PAB (LAST DELIVERY) | 21/08/2021 | 21/08/2021 | 21/08/2021 | 21/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB4-56 | TT_FinMile | (RFS) READY FOR SHIPMENT PIPING SYSTEM (OUTSIDE) 20PAB (LAST DELIVERY) | 26/06/2021 | 26/06/2021 | 26/06/2021 | 26/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB4-57 | TT_Task | TRANSPORT PIPING SYSTEM (OUTSIDE) 20PAB (LAST DELIVERY) | 27/06/2021 | 21/08/2021 | 27/06/2021 | 21/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBE5E47 | TT_Task | DRYING PERIOD FOR CONCRETE BEFORE OIL RESISTANT PAINT 20UBE | 21/04/2022 | 27/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAS6B16 | TT_Mile | (RFP) READY FOR PIPING CT MAKE-UP WATER PUMP PAS | 29/04/2022 | 29/04/2022 |  |  | 360 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-UZA2-50 | TT_FinMile | (F) RING ROAD INCL. UNDERGROUND (U/G) DRAINAGE DRAWINGS REMAINING AREAS PART 3 | 29/05/2021 | 29/05/2021 | 29/05/2021 | 29/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-UZA2-90 | TT_Task | SUMMARY SUBBASE RING ROAD INCL.(U/G) SYSTEM - PART 3 | 26/07/2022 | 04/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7-170 | TT_Task | ERECTION CABLE TRAYS ON 20UQZ | 27/10/2022 | 09/11/2022 |  |  | 40 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HSJ3-82 | TT_FinMile | (RFS) READY FOR SHIPMENT SCR CATALYST MODULES | 06/04/2023 | 06/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HSJ4B11 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION - SCR CATALYST MODULES | 10/03/2023 | 06/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HSJ3B71 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) - SCR CATALYST MODULES | 09/03/2023 | 09/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HSJ4-41 | TT_Task | TRANSPORT SCR CATALYST MODULES | 07/04/2023 | 01/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HSJ4-42 | TT_FinMile | (OTD-OS) ON SITE SCR CATALYST MODULES | 01/06/2023 | 01/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-3B83 | TT_FinMile | (RFS) READY FOR SHIPMENT INSULATION MATERIAL HRSG20 (PIPES, DRUMS, VESSELS) | 23/12/2022 | 23/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-3B84 | TT_FinMile | (RFS) READY FOR SHIPMENT INSULATION MATERIAL HRSG20 (OUTLET DUCT SEALING AREAS STACK) | 12/05/2022 | 12/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-4B43 | TT_Task | TRANSPORT INSULATION MATERIAL HRSG20 (PIPES, DRUMS, VESSELS) | 14/01/2023 | 17/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-4B44 | TT_FinMile | (OTD-OS) ON SITE INSULATION MATERIAL HRSG20 (PIPES, DRUMS, VESSELS) | 17/02/2023 | 17/02/2023 |  |  | 448 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-4B45 | TT_Task | TRANSPORT INSULATION MATERIAL HRSG20 (OUTLET DUCT SEALING AREAS STACK) | 13/05/2022 | 16/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-4B46 | TT_FinMile | (OTD-OS) ON SITE INSULATION MATERIAL HRSG20 (OUTLET DUCT SEALING AREAS STACK) | 16/06/2022 | 16/06/2022 |  |  | 1336 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-4D20 | TT_FinMile | (RFS) READY FOR SHIPMENT HRSG REMAINING MATERIAL | 30/03/2022 | 30/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HSJ4-43 | TT_Task | TRANSPORT SCR SCR EQUIPMENT TO BE INSTALLED INSIDE HRSG CASING | 09/12/2021 | 07/01/2022 | 09/12/2021 |  | 1872 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20HSJ3-83 | TT_FinMile | (RFS) READY FOR SHIPMENT SCR EQUIPMENT TO BE INSTALLED INSIDE HRSG CASING | 08/12/2021 | 08/12/2021 | 08/12/2021 | 08/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--LDK2B89 | TT_FinMile | (DF) PREL. INPUT FOR BB MS3 CONDENSATE POLISHING PUMP LDK (LOADS / SIZE) | 09/04/2021 | 09/04/2021 | 09/04/2021 | 09/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--LCA2B87 | TT_FinMile | (DF) PREL. INPUT FOR BB MS3 CONDENSATE RECIRC.PUMP LCA51 (LOADS / SIZE) | 09/04/2021 | 09/04/2021 | 09/04/2021 | 09/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UGU2-51 | TT_Task | BASIC DESIGN / BASIC BUILDING DESIGN INCL. 3D MODEL 20UGU01 | 28/05/2021 | 16/06/2021 | 28/05/2021 | 16/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UGU2-53 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE 20UGU01 | 17/06/2021 | 31/07/2021 | 17/06/2021 | 31/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UGU5-81 | TT_FinMile | (RFE) FOUNDATION 20UGU01 | 19/05/2022 | 19/05/2022 |  |  | 392 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UGU2-58 | TT_Mile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION 20UGU01 | 16/03/2022 | 16/03/2022 |  |  | 176 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UGU5-78 | TT_Mile | (H) START PLACING FORMWORK 20UGU01 | 13/04/2022 | 13/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UGU2-54 | TT_Task | PREPARATION FOUNDATION GROUNDING DWGS 20UGU01 | 18/07/2021 | 31/07/2021 | 18/07/2021 | 31/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UGU2-52 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UGU01 | 28/05/2021 | 28/05/2021 | 28/05/2021 | 28/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UGU2-56 | TT_Task | BD - SUBMISSION APPROVAL - PUMP PIT DESIGN 20UGU01 | 15/01/2022 | 15/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UGU2-55 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN CONCRETE - PUMP PIT 20UGU01 | 01/08/2021 | 25/08/2021 | 01/08/2021 | 25/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UGU2-57 | TT_Task | BD - CONSENT LETTER PUMP PIT DESIGN 20UGU01 | 16/03/2022 | 12/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UGU2-60 | TT_Task | BASIC DESIGN / BASIC BUILDING DESIGN INCL. 3D MODEL 20UGU02 | 31/05/2021 | 20/06/2021 | 31/05/2021 | 20/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UGU2-61 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE 20UGU02 | 02/07/2021 | 15/08/2021 | 02/07/2021 | 15/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UGU5-87 | TT_FinMile | (RFE) FOUNDATION 20UGU02 | 07/05/2022 | 07/05/2022 |  |  | 2704 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UGU2-66 | TT_FinMile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION 20UGU02 | 20/03/2022 | 20/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UGU5-84 | TT_Mile | (H) START PLACING FORMWORK 20UGU02 | 13/04/2022 | 13/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UGU2-62 | TT_Task | PREPARATION FOUNDATION GROUNDING DWGS 20UGU02 | 02/08/2021 | 15/08/2021 | 02/08/2021 | 15/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UGU2-59 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UGU02 | 28/05/2021 | 28/05/2021 | 28/05/2021 | 28/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UGU2-64 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE 20UGU02 | 15/01/2022 | 15/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UGU2-63 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN CONCRETE - DRAINAGE PIT 20UGU02 | 16/08/2021 | 14/01/2022 | 16/08/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UGU2-65 | TT_Task | BD - CONSENT LETTER DETAIL DESIGN CONCRETE 20UGU02 | 16/03/2022 | 12/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
CLP20ULZ5-80 | TT_FinMile | (RFE) FOUNDATION 20ULZ02 (CLP Scope) | 30/06/2021 | 30/06/2021 | 30/06/2021 | 30/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
CLP20ULZ5-78 | TT_Task | CONSTRUCTION FOUNDATION 20ULZ02 (CLP Scope) | 03/06/2021 | 30/06/2021 | 03/06/2021 | 30/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
CLP20ULZ5-77 | TT_Task | WORK PREPARATION, EXCAVATION 20ULZ02 (CLP Scope) | 20/05/2021 | 02/06/2021 | 20/05/2021 | 02/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
CLP20ULZ5-79 | TT_Mile | (H) START PLACING FORMWORK 20ULZ02 (CLP Scope) | 03/06/2021 | 03/06/2021 | 03/06/2021 | 03/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
CLP20ULZ2-100 | TT_Task | PREPARATION FOUNDATION GROUNDING DWGS 20ULZ02 (CLP Scope) | 13/01/2021 | 26/01/2021 | 13/01/2021 | 26/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
CLP20ULZ2-98 | TT_Task | BASIC BUILDING DESIGN INCL. 3D MODEL 20ULZ02 (CLP Scope) | 12/11/2020 | 08/12/2020 | 12/11/2020 | 08/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
CLP20ULZ2-97 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20ULZ02 (CLP Scope) | 11/11/2020 | 11/11/2020 | 11/11/2020 | 11/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
CLP20ULZ2-104 | TT_FinMile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION 20ULZ02 (CLP Scope) | 19/05/2021 | 19/05/2021 | 19/05/2021 | 19/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
CLP20ULZ2-99 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE 20ULZ02 (CLP Scope) | 09/12/2020 | 26/01/2021 | 09/12/2020 | 26/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
CLP20ULZ2-101 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN CONCRETE - 20ULZ02 (CLP Scope) | 27/01/2021 | 20/02/2021 | 27/01/2021 | 20/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
CLP20ULZ2-102 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE - 20ULZ02 (CLP Scope) | 21/02/2021 | 21/04/2021 | 21/02/2021 | 21/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
CLP20ULZ2-103 | TT_Task | BD - CONSENT LETTER - DESIGN 20ULZ02 (CLP Scope) | 22/04/2021 | 19/05/2021 | 22/04/2021 | 19/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2Y82 | TT_FinMile | (MS2) PRELIMINARY DESIGN INPUT AVAILABLE CEP/LDK PIT 20UMC | 31/12/2020 | 31/12/2020 | 31/12/2020 | 31/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHX2-25 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN CONCRETE - 20UHX | 29/09/2021 | 23/10/2021 | 29/09/2021 | 23/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHX2-30 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE 20UHX | 31/01/2022 | 31/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UHX2-35 | TT_Task | BD - CONSENT LETTER - DETAIL DESIGN CONCRETE 20UHX | 01/04/2022 | 28/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5-82 | TT_FinMile | (RFE) READY FOR PLACING ELECTRICAL MODULESs 20UBA1110/20 | 24/10/2022 | 24/10/2022 |  |  | 192 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5-85 | TT_FinMile | (RFE) READY FOR PLACING ELECTRICAL MODULESs 20UBA7910/20 | 23/06/2022 | 23/06/2022 |  |  | 272 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5-87 | TT_Task | FINISHING WORKS 20UBA7910/20 | 13/06/2022 | 16/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5-89 | TT_Task | FINISHING WORKS 20UBA1110/20 | 12/05/2022 | 15/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5-90 | TT_FinMile | (RFE) READY FOR PLACING ELECTRICAL MODULESs 20UBA7xxx | 18/06/2022 | 18/06/2022 |  |  | 32 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5-92 | TT_Task | FINISHING WORKS 20UBA7xxx | 04/04/2022 | 13/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5-93 | TT_FinMile | (RFE) READY FOR PLACING ELECTRICAL MODULESs 20UBA8110/20 | 02/11/2022 | 02/11/2022 |  |  | 120 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5-95 | TT_Task | FINISHING WORKS 20UBA8110/20 | 25/06/2022 | 28/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5-96 | TT_FinMile | (RFE) READY FOR PLACING ELECTRICAL MODULESs 01UBA9010/20 | 26/06/2022 | 26/06/2022 |  |  | 72 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5-98 | TT_Task | FINISHING WORKS 01UBA9010/20 | 09/05/2022 | 05/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAT2-88 | TT_Task | AUDIT AT TRANSFORMER MANUFACTURER | 07/04/2021 | 04/05/2021 | 07/04/2021 | 04/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP--B--2-61 | TT_Mile | FINAL ELECTRICAL LOAD DATA (VEL) FOR LV (HRSG/BOP) | 18/06/2021 | 18/06/2021 | 18/06/2021 | 18/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--BAW2-86 | TT_Task | FINALIZE VEL INPUT DATA (before ELV3) | 18/06/2021 | 30/06/2021 | 18/06/2021 | 30/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BRU3-26 | TT_Task | DETAIL DESIGN / MANUFACTURING / SHOP TEST AC-DC CONVERTER BUK | 30/09/2021 | 04/01/2022 | 30/09/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20BTL4-11 | TT_Task | TRANSPORT TO WORKSHOP AC-DC CONVERTER BUK (TO ST. INGBERT-INSTALL INTO ELECTRICAL MODULES) | 05/01/2022 | 06/01/2022 |  |  | 376 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA3-89 | TT_FinMile | (RFS) READY FOR SHIPMENT TESTED IC CUBICLES FOR 20UBA1110/20-20CJF01 | 04/04/2022 | 04/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA4-68 | TT_Task | TRANSPORT IC CUBICLES TO FEAG ELECTRICAL MODULE 20UBA1110/20-20CJF01 | 24/06/2022 | 30/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA3-86 | TT_Task | TEST PREPARATION ASSEMBLY IC CUBICLES TEST FACILITY 20UBA1110/20-20CJF01 | 08/02/2022 | 21/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA4-66 | TT_FinMile | DELIVERY OF CUBICLES AND COMPONENTS FOR ASSEMBLY IN TEST FACILITY 20UBA1110/20-20CJF01 | 07/02/2022 | 07/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA3-87 | TT_Task | PRECOMMISSIONING TEST IC CUBICLES TEST FACILITY 20UBA1110/20-20CJF01 | 22/02/2022 | 28/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA3-88 | TT_Task | CLEANING AND PACKING IC CUBICLES TEST FACILITY 20UBA1110/20-20CJF01 | 29/03/2022 | 04/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA3G56 | TT_Task | INSTALL. TESTED IC CUBICLES., CABLING ELECTRICAL MODULES 20UBA1110/20 | 01/07/2022 | 04/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA4B43 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION ELECTRICAL MODULES 20UBA1110/20 (TO SITE) | 26/08/2022 | 22/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA3B76 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) ELECTRICAL MODULES 20UBA1110/20 | 26/08/2022 | 26/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA4G55 | TT_Task | TRANSPORT ELECTRICAL MODULES 20UBA1110/20 (TO SITE) | 23/09/2022 | 17/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA3G88 | TT_FinMile | (RFS) READY FOR SHIPMENT TO SITE ELECTRICAL MODULES 20UBA1110/1120 (TO SITE) | 22/09/2022 | 22/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA3G57 | TT_Task | PACKING / LOGISTICS PLANNING CABLING ELECTRICAL MODULES 20UBA1110/20 | 05/08/2022 | 01/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA4-69 | TT_Mile | (ET4b) ELECTRICAL MODULES AT WORKSHOP READY FOR COMPONENT INSTALLATION 20UBA1110/20 | 16/06/2022 | 16/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA4G56 | TT_Mile | (ET4a) IC CUBICLES AT WORKSHOP READY FOR COMPONENT INSTALLATION 20UBA1110/20 | 01/07/2022 | 01/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2G78 | TT_Mile | E-AND IC- MANUALS FOR COMP.INSTALL.AVAILABLE ELECTRICAL MODULES 20UBA1110/20 | 19/05/2022 | 19/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKW4-41 | TT_Task | TRANSPORT SEAL OIL TANK TO MODULE SKIDDER 20MKW | 29/10/2021 | 23/12/2021 | 29/10/2021 | 23/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MKW4-11 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION SEAL OIL TANK | 01/10/2021 | 28/10/2021 | 01/10/2021 | 28/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MKW3-90 | TT_Mile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) SEAL OIL TANK | 01/10/2021 | 01/10/2021 | 01/10/2021 | 01/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MKW3-91 | TT_FinMile | (RFS) READY FOR SHIPMENT (NORTH SEA PORT) SEAL OIL TANK | 28/10/2021 | 28/10/2021 | 28/10/2021 | 28/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAH4-42 | TT_FinMile | (OTD-OS) ARRIVAL ON SITE CONDENSER TUBE CLEANING SYSTEM 20PAH (REMAINING SYSTEM) | 05/08/2022 | 05/08/2022 |  |  | 8 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAH4-41 | TT_Task | TRANSPORT TO SITE CONDENSER TUBE CLEANING SYSTEM (REMAINING SYSTEM) 20PAH | 11/06/2022 | 05/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAH3-81 | TT_FinMile | (RFS) READY FOR SHIPMENT CONDENSER TUBE CLEANING SYSTEM 20PAH (REMAINING SYSTEM) | 10/06/2022 | 10/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAH4B11 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION CONDENSER TUBE CLEANING SYSTEM 20PAH (REMAINING SYSTEM) | 14/05/2022 | 10/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MAG4B41 | TT_FinMile | (OTD-OS) ON SITE CONDENSER MAG | 21/04/2022 | 21/04/2022 |  |  | 160 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAH3B71 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) CONDENSER TUBE CLEANING SYSTEM 20PAH (REMAINING SYSTEM) | 26/12/2021 | 26/12/2021 | 26/12/2021 | 26/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7-171 | TT_Task | ERECTION CABLE TRAYS BEFORE LIFTING OF MODULE 20UEY02 | 19/06/2022 | 02/07/2022 |  |  | 48 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7D19 | TT_Task | FINALIZE CABLE TRAYS ON 20UEY02 | 13/07/2022 | 19/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7-172 | TT_Task | ERECTION LOOSE STEEL SUPPORTS FOR CABLE TRAYS BEFORE LIFTING OF MODULE 20UEY01 | 15/05/2022 | 28/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7-173 | TT_Task | ERECTION LOOSE STEEL SUPPORTS FOR CABLE TRAYS BEFORE LIFTING OF MODULE 20UEY02 | 05/06/2022 | 18/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--2222-133 | TT_Task | NOISE PROTECTION CONCEPT REVIEW / COMMENTS BY CUSTOMER | 02/03/2021 | 26/03/2021 | 02/03/2021 | 26/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--2222-134 | TT_Task | NOISE PROTECTION CONCEPT FINALISATION | 27/03/2021 | 10/04/2021 | 27/03/2021 | 10/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--SG-2-90 | TT_Task | FIRE PROTECTION CONCEPT FOR CLIENT REVIEW | 20/04/2021 | 14/05/2021 | 20/04/2021 | 14/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--SG-2-91 | TT_Task | UPDATED FIRE PROTECTION CONCEPT AFTER ALIGNMENT WITH CLIENT | 15/05/2021 | 21/05/2021 | 15/05/2021 | 21/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--SG-2-92 | TT_Task | FIRE PROTECTION CONCEPT FOR FSD APPROVAL | 22/05/2021 | 29/05/2021 | 22/05/2021 | 29/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--SG-2-93 | TT_Task | UPDATED FIRE PROTECTION CONCEPT AFTER ALIGNMENT WITH FSD | 30/05/2021 | 05/06/2021 | 30/05/2021 | 05/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--SG-2-94 | TT_Task | UPDATE FIRE MAIN RING MAIN PID's | 03/03/2021 | 16/03/2021 | 03/03/2021 | 16/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UE-2E36 | TT_FinMile | (C) BASIC DESIGN PLANT LAYOUT DWGS (UE) FUEL GAS AREA AVAILABLE | 16/04/2021 | 16/04/2021 | 16/04/2021 | 16/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UE2-86 | TT_FinMile | (MS2) DESIGN LOAD DATA, DIMENSIONS CLEAN DIRTY OIL TANK AREA AVAILABLE | 22/02/2021 | 22/02/2021 | 22/02/2021 | 22/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UE2-E37 | TT_FinMile | (C) BASIC DESIGN PLANT LAYOUT DWGS (UE) CLEAN DIRTY OIL TANK AREA AVAILABLE | 16/04/2021 | 16/04/2021 | 16/04/2021 | 16/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P222-62 | TT_Task | 65 - CONSTRUCTION APPROVAL (CA) APPLICATION | 05/10/2021 | 03/12/2021 | 05/10/2021 | 03/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P222-63 | TT_Task | 66 - USE APPROVAL (UA) APPLICATION | 22/01/2023 | 21/04/2023 |  |  | 248 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P222-64 | TT_Task | 67 - PILOT SCHEME FOR COOLING TOWER APPROVED TO EMSD | 16/05/2021 | 14/07/2021 | 16/05/2021 | 14/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P222-65 | TT_Task | 68 - HELPDESK SUBMISSION OF CONCEPTUAL DESIGN | 15/06/2021 | 14/07/2021 | 15/06/2021 | 14/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P222-66 | TT_Task | 69 - SPRINKLER LOCAL APPLICATION | 19/10/2022 | 15/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P222-67 | TT_Task | 70 - AFA DETECTION ALARM | 19/10/2022 | 17/12/2022 |  |  | 1376 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P222-70 | TT_Task | 73 - OVERALL FIRE WATER DEMAND MAXIMUM DEMAND CALCULATION | 12/08/2022 | 10/09/2022 |  |  | 1752 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P222-72 | TT_Task | 75 - INSPECTION PROCEDURES AND SEQUENCING (TESTING STANDARDS FOR ALL SYSTEMS) | 12/08/2022 | 10/09/2022 |  |  | 1752 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P222-73 | TT_Task | 76 - HYDRAULIC SUBMISSION APPROVAL (FSI/314 SCHEMATIC DRAWINGS SUBMISSION) | 19/10/2022 | 17/11/2022 |  |  | 1208 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P222-74 | TT_Task | 77 - FSI/314 SCHEMATIC DRAWINGS (VAC/AFA/FSI APPROVAL) | 12/08/2022 | 07/02/2023 |  |  | 552 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P222-75 | TT_Task | 78 - SEAWATER DIVERSION OF OUTDDOR FIRE HYDRANTS | 19/10/2022 | 17/11/2022 |  |  | 1208 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P222-77 | TT_Task | 80 - LICENSE FOR STORAGE OF DANGEROUS GOODS | 16/06/2021 | 14/08/2021 | 16/06/2021 | 14/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P222-78 | TT_Task | 81- APPLICATION FOR STORAGE/USE/MANUF. OF DANGEROUS GOODS UNDER DG ORDINACE FOR ISSUANCE OF FIRE SAFETY REQUIREMENTS | 18/10/2022 | 15/01/2023 |  |  | 720 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P222-79 | TT_Task | 82 - DANGEROUS GOODS LICENSE INSPECTION APPLICATIONS | 16/01/2023 | 16/03/2023 |  |  | 2320 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P222-80 | TT_Task | 83 - REPORT OF COMPLIANCE | 24/03/2023 | 22/04/2023 |  |  | 240 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P222-81 | TT_Task | 84 - PRESSURE VESSELS (FOR CONSTRUCTION WORKS) | 01/07/2021 | 29/08/2021 | 01/07/2021 | 29/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P222-82 | TT_Task | 85 - CERTIFICATES FOR LIFTING APPLIANCES, LIFTING GEARS | 17/05/2022 | 15/07/2022 |  |  | 4272 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P222-83 | TT_Task | 86 - CERTIFICATES FOR BOILERS, PRESSURE VESSELS | 15/01/2023 | 15/03/2023 |  |  | 352 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P222-84 | TT_Task | 87 - NOTIFICATION OF CONSTRUCTION WORKS AND REGISTRATION OF WORKERS TO LD | 01/06/2021 | 30/06/2021 | 01/06/2021 | 30/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P222-85 | TT_Task | 88 - IMPORTATION OF WORKERS AND WORKING VISA APPLICATION TO IMMD | 01/06/2021 | 27/11/2021 | 01/06/2021 | 27/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P222-76 | TT_Task | 79 - EM LOCK (ELECTROMAGNETIC DOOR LOCK) | 19/10/2022 | 17/11/2022 |  |  | 1208 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P222-86 | TT_Task | 89 - BILLING ACCOUNT FOR CONSTRUCTION WASTE DISPOSAL | 16/03/2021 | 14/04/2021 | 16/03/2021 | 14/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P222-87 | TT_Task | 90 - CONSTRUCTION NOISE PERMIT | 02/06/2021 | 01/07/2021 | 02/06/2021 | 01/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P222-88 | TT_Task | 91 - WASTE WATER DISCHARGE LICENSE | 09/04/2021 | 07/06/2021 | 09/04/2021 | 07/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P222-89 | TT_Task | 92 - WASTE CHEMICAL DISPOSAL | 02/06/2021 | 31/07/2021 | 02/06/2021 | 31/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P222-91 | TT_Task | 94 - SITE SUPERVISION PLANS UNDER AP/RSE/RGE STREAMS | 02/06/2021 | 22/06/2021 | 02/06/2021 | 22/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P222-92 | TT_Task | 95 - SITE SUPERVISION PLANS UNDER RGBC/RSC STREAM | 02/06/2021 | 22/06/2021 | 02/06/2021 | 22/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P222-93 | TT_Task | 96 - NOTICE OF COMMENCEMENT OF CONSTRUCTION WORKS (FORM1) TO CIC | 01/06/2021 | 01/06/2021 | 01/06/2021 | 01/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P222-94 | TT_Task | 97 - NOTICE OF INTERIM PAYMENT (FORM2) TO CIC | 01/06/2021 | 01/06/2021 | 01/06/2021 | 01/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P222-95 | TT_Task | 98 - NOTICE OF FINAL PAYMENT (FORM2) TO CIC | 01/06/2021 | 01/06/2021 | 01/06/2021 | 01/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P222-96 | TT_Task | 99 - NOTICE TO COMPLETION OF CONSTRUCTION WORKS (FORM3) TO CIC | 31/12/2023 | 31/12/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P222-97 | TT_Task | 100 - NOTICE OF COMMENCEMENT OF CONSTRUCTION OPERATIONS (FORM1B) TO PCFB | 01/06/2021 | 01/06/2021 | 01/06/2021 | 01/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P222-98 | TT_Task | 101 - NOTICE OF INTERIM PAYMENT (FORM2B) TO PCFB | 01/06/2021 | 01/06/2021 | 01/06/2021 | 01/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P222-99 | TT_Task | 102 - NOTICE OF FINAL PAYMENT (FORM3B) TO PCFB | 01/06/2021 | 01/06/2021 | 01/06/2021 | 01/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P222-100 | TT_Task | 103 - DESTINATION CONTROL STATEMENT: FIREWALL IMPORT LICENSE | 20/12/2021 | 19/01/2022 | 20/12/2021 |  | 784 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI-P222-101 | TT_Task | 104 - LICENSE ISSUE | 20/01/2022 | 19/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P222-102 | TT_Task | 105 - IMPORT LICENSE FOR RADIOACTIVE SUBSTANCE | 20/01/2022 | 18/02/2022 |  |  | 1400 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P222-103 | TT_Task | 106 - RADIOACTIVE SUBSTANCE LICENSE (BPPS) | 20/01/2022 | 18/02/2022 |  |  | 1400 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P222-104 | TT_Task | 107 - WSD FORM 542 SUBMISSION (TOWN WATER DOMESTIC WATER SUPPLY) | 16/06/2021 | 12/12/2021 | 16/06/2021 | 12/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P222-105 | TT_Task | 108 - APPROVAL OF WSD FORM 542 SUBMISSION (TOWN WATER DOMESTIC WATER SUPPLY) | 13/12/2021 | 13/12/2021 | 13/12/2021 | 13/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P222-106 | TT_Task | 109 - WSD FORM 46 PART1/2 (TOWN WATER DOMESTIC WATER SUPPLY) | 21/08/2022 | 18/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P222-107 | TT_Task | 110 - WSD FORM 46 PART 3 (TOWN WATER DOMESTIC WATER SUPPLY) | 19/11/2022 | 19/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P222-108 | TT_Task | 111 - WSD FINAL AMENDMENT PLAN SUBMISSION (TOWN WATER DOMESTIC WATER SUPPLY) | 14/12/2021 | 11/02/2022 | 14/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI-P222-109 | TT_Task | 112 - APPROVAL OF WSD FINAL AMENDMENT PLAN SUBMISSION (TOWN WATER DOMESTIC WATER SUPPLY) | 12/02/2022 | 12/02/2022 |  |  | 2248 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P222-110 | TT_Task | 113 - WSD FORM 46 PART 4 (TOWN WATER DOMESTIC WATER SUPPLY) | 15/01/2023 | 14/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P222-111 | TT_Task | 114 - WSD FORM 46 PART 5 (TOWN WATER DOMESTIC WATER SUPPLY) | 15/04/2023 | 13/06/2023 |  |  | 136 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P222-112 | TT_Task | 115 - WSD FORM 542 SUBMISSION (TOWN WATER SERVICES SYSTEM) | 16/06/2021 | 12/12/2021 | 16/06/2021 | 12/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P222-113 | TT_Task | 116 - APPROVAL OF WSD FORM 542 SUBMISSION (TOWN WATER SERVICES SYSTEM) | 13/12/2021 | 13/12/2021 | 13/12/2021 | 13/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P222-114 | TT_Task | 117 - WSD FORM 46 PART 1/2 (TOWN WATER SERVICES SYSTEM) | 12/05/2022 | 09/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P222-115 | TT_Task | 118 - WSD FORM 46 PART 3 (TOWN WATER SERVICES SYSTEM) | 10/08/2022 | 10/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P222-116 | TT_Task | 119 - WSD FINAL AMENDMENT PLAN SUBMISSION (TOWN WATER SERVICES SYSTEM) | 07/07/2022 | 04/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P222-117 | TT_Task | 120 - APPROVAL OF WSD FINAL AMENDMENT PLAN SUBMISSION (TOWN WATER SERVICES SYSTEM) | 05/09/2022 | 05/09/2022 |  |  | 3856 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P222-118 | TT_Task | 121 - WSD FORM 46 PART 4 (TOWN WATER SERVICES SYSTEM) | 15/01/2023 | 14/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P222-119 | TT_Task | 122 - WSD FORM 46 PART 5 (TOWN WATER SERVICES SYSTEM) | 15/04/2023 | 13/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P222-120 | TT_Task | 123 - WSD FORM 542 SUBMISSION (FRESH FIRE WATER SUPPLY) | 18/08/2021 | 13/02/2022 | 18/08/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI-P222-121 | TT_Task | 124 - APPROVAL OF WSD FORM 542 SUBMISSION (FRESH FIRE WATER SUPPLY) | 14/02/2022 | 14/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P222-122 | TT_Task | 125 - WSD FORM 46 PART 1/2 (FRESH FIRE WATER SUPPLY) | 15/02/2022 | 15/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P222-123 | TT_Task | 126 - WSD FORM 46 PART 3 (FRESH FIRE WATER SUPPLY) | 16/04/2022 | 16/04/2022 |  |  | 136 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P222-124 | TT_Task | 127 - WSD FINAL AMENDMENT PLAN SUBMISSION (FRESH FIRE WATER SUPPLY) | 07/07/2022 | 04/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P222-125 | TT_Task | 128 - APPROVAL OF WSD FINAL AMENDMENT PLAN SUBMISSION (FRESH FIRE WATER SUPPLY) | 05/09/2022 | 05/09/2022 |  |  | 920 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P222-126 | TT_Task | 129 - WSD FORM 46 PART 4 (FRESH FIRE WATER SUPPLY) | 30/12/2022 | 29/03/2023 |  |  | 128 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P222-127 | TT_Task | 130 - WSD FORM 46 PART 5 (FRESH FIRE WATER SUPPLY) | 15/04/2023 | 13/06/2023 |  |  | 152 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P222-128 | TT_Task | 131 - FORM BA14 - CERTIFICATE ON COMPLETION OF BUILDING WORKS (PILE FOUNDATION) | 31/05/2021 | 29/06/2021 | 31/05/2021 | 29/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P222-130 | TT_Task | 133 - CERTIFICATE OF COMPLETION OF DRAIN TESTS | 26/01/2023 | 24/02/2023 |  |  | 768 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P222-133 | TT_Task | 136 - FORM FSI/314 SUBMISSION OF AS-BUILT DWGS | 02/01/2023 | 31/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P222-134 | TT_Task | 137 - FORM FS/314 SUBMISSION TO REQUEST FSD INSPECTION | 02/01/2023 | 15/01/2023 |  |  | 608 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P222-135 | TT_Task | 138 - FIRE SERVICES WATER COMPLIANCE ADVICE | 27/12/2022 | 24/02/2023 |  |  | 48 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P222-136 | TT_Task | 139 - ISSUE FIRE SERVICE CERTIFICATE FOR OP (F.S.172) | 02/01/2023 | 01/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P222-137 | TT_Task | 140 - AP UNDERTAKING LETTERS | 02/04/2023 | 15/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P222-138 | TT_Task | 141 - FORM BA13 - APPLICATION OF OP | 02/04/2023 | 30/06/2023 |  |  | 192 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P222-139 | TT_Task | 142 - MASTER LAYOUT PLAN REVISION | 01/06/2021 | 29/08/2021 | 01/06/2021 | 29/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P222-140 | TT_Task | 142a - LANDSCAPE MASTER PLAN REVISION | 02/01/2023 | 01/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P222-141 | TT_Task | 144 - BPPS APCL - AMENDMENT TO EXISTING LICENSE | 08/07/2022 | 03/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P222-142 | TT_Task | 145 - AIR MODEL TEST | 14/07/2021 | 14/07/2021 | 14/07/2021 | 14/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P222-143 | TT_Task | 146 - LICENSE OBTAINED | 15/07/2021 | 15/07/2021 | 15/07/2021 | 15/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P222-144 | TT_Task | 147 - BPPS WPCL - AMENDMENT TO EXISTING LICENSE | 04/01/2023 | 04/01/2023 |  |  | 2888 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P222-145 | TT_Task | 148 - EFFLUENT DISCHARGE PLAN | 25/01/2023 | 24/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMY6M71 | TT_Mile | (RFP) READY FOR PIPING PIPE BRIDGE 20UMY00Y/ULY00Y | 22/05/2022 | 22/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2A02 | TT_Task | BASIC BUILDING DESIGN CONCRETE TS FOUNDATION - PRELIMINARY - 20UMC | 15/01/2021 | 10/02/2021 | 15/01/2021 | 10/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2A04 | TT_Task | BD - SUBMISSION APPROVAL-DETAIL DESIGN- TURBOSET 1ST SUBMISSION (2NDPACKAGE) | 20/04/2021 | 12/05/2021 | 20/04/2021 | 13/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2A03 | TT_Task | DETAIL DESIGN CONCRETE TS FOUNDATION - PRELIMINARY - 20UMC | 29/01/2021 | 15/04/2021 | 29/01/2021 | 15/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2A01 | TT_FinMile | (MS2*) PRELIMINARY INPUTS AVAILABLE TS FOUND. 20UMC | 14/01/2021 | 14/01/2021 | 14/01/2021 | 14/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC2B02 | TT_Task | BASIC BUILDING DESIGN CONCRETE STRUCTURE - PRELIMINARY - 20UMC | 15/01/2021 | 22/02/2021 | 15/01/2021 | 22/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC2B04 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE - 1ST SUBMISSION BUILDING (1STPACKAGE) | 16/03/2021 | 12/05/2021 | 16/03/2021 | 13/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC2B03 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE - PRELIMINARY - 20UMC | 29/01/2021 | 15/03/2021 | 29/01/2021 | 15/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC2B01 | TT_FinMile | (MS2*) PRELIMINARY INPUTS AVAILABLE BUILDING FOUNDATION 20UMC | 14/01/2021 | 14/01/2021 | 14/01/2021 | 14/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UPY2-02 | TT_Task | BASIC BUILDING DESIGN CONCRETE STRUCTURE - PRELIMINARY - 20UPY | 15/01/2021 | 10/02/2021 | 15/01/2021 | 10/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UPY2-04 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE - 1ST SUBMISSION 20UPY (1STPACKAGE) | 16/03/2021 | 12/05/2021 | 16/03/2021 | 13/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UPY2-03 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE - PRELIMINARY - 20UPY | 29/01/2021 | 15/03/2021 | 29/01/2021 | 15/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UPY2-01 | TT_FinMile | (MS2*) PRELIMINARY INPUTS AVAILABLE FOUNDATION 20UPY | 14/01/2021 | 14/01/2021 | 14/01/2021 | 14/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UEY2B02 | TT_Task | BASIC BUILDING DESIGN CONCRETE STRUCTURE - PRELIMINARY - 20UEY01 | 15/01/2021 | 10/02/2021 | 15/01/2021 | 10/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UEY2B04 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE - 1ST SUBMISSI0N 20UEY01(1STPACKAGE) | 16/03/2021 | 12/05/2021 | 16/03/2021 | 13/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UEY2B03 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE - PRELIMINARY - 20UEY01 | 29/01/2021 | 15/03/2021 | 29/01/2021 | 15/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UEY2B01 | TT_FinMile | (MS2*) PRELIMINARY INPUTS AVAILABLE FOUNDATION 20UEY01 | 14/01/2021 | 14/01/2021 | 14/01/2021 | 14/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URD2B02 | TT_Task | BASIC BUILDING DESIGN CONCRETE STRUCTURE - PRELIMINARY - 20URD xx | 15/01/2021 | 10/02/2021 | 15/01/2021 | 10/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URD2B04 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE - PRELIMINARY - 20URD xx | 16/03/2021 | 14/05/2021 | 16/03/2021 | 14/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URD2B03 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE - PRELIMINARY - 20URD xx | 29/01/2021 | 15/03/2021 | 29/01/2021 | 15/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URD2B01 | TT_FinMile | (MS2*) PRELIMINARY INPUTS AVAILABLE FOUNDATION 20URD xx | 14/01/2021 | 14/01/2021 | 14/01/2021 | 14/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URA2B02 | TT_Task | BASIC DESIGN SUBSTRUCTRURE-20URA/URD | 15/01/2021 | 22/02/2021 | 15/01/2021 | 22/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URA2B04 | TT_Task | PRELIM. COOLING TOWER COMP. SUPERSTRUCTURE-LAYOUTFIXING LOCATIONS | 11/06/2021 | 09/07/2021 | 11/06/2021 | 09/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URA2B03 | TT_Task | PRELIM. COOLING TOWER COMP. SUBSTRUCTURE-LAYOUTFIXING LOCATIONS | 11/06/2021 | 27/06/2021 | 11/06/2021 | 27/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URA2B01 | TT_FinMile | INPUT LOADS SUBSTRUCTURE-20URA/URD | 14/01/2021 | 14/01/2021 | 14/01/2021 | 14/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URA2B4 | TT_Task | BASIC DESIGN SUPERSTRUCTRURE-20URA/URD | 17/05/2021 | 29/05/2021 | 17/05/2021 | 29/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URA2B7 | TT_Task | BD - SUBMISSION APPROVAL SUPERSTRUCTURE- 1ST SUBMISSION 20URA/URD | 25/06/2021 | 19/08/2021 | 25/06/2021 | 20/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URA2B5 | TT_FinMile | INPUT LOADS SUPERSTRUCTURE-20URA/URD | 16/05/2021 | 16/05/2021 | 16/05/2021 | 16/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20ULA2B02 | TT_Task | BASIC BUILDING DESIGN CONCRETE STRUCTURE - PRELIMINARY - 20ULA | 01/02/2021 | 14/02/2021 | 01/02/2021 | 14/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20ULA2B04 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE - 1ST SUBMISSION 20ULA(2NDPACKAGES) | 16/04/2021 | 12/05/2021 | 16/04/2021 | 13/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20ULA2B03 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE - PRELIMINARY - 20ULA | 15/02/2021 | 15/04/2021 | 15/02/2021 | 15/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20ULA2B01 | TT_FinMile | (MS2*) PRELIMINARY INPUTS AVAILABLE FOUNDATION 20ULA | 31/01/2021 | 31/01/2021 | 31/01/2021 | 31/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHW2B02 | TT_Task | BASIC BUILDING DESIGN CONCRETE STRUCTURE - PRELIMINARY - 20UHW | 01/02/2021 | 14/02/2021 | 01/02/2021 | 14/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHW2B04 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE - 1ST SUBMISSION 20UHW(2NDPACKAGE) | 20/04/2021 | 12/05/2021 | 20/04/2021 | 13/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHW2B03 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE - PRELIMINARY - 20UHW | 15/02/2021 | 15/04/2021 | 15/02/2021 | 15/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHW2B01 | TT_FinMile | (MS2*) PRELIMINARY INPUTS AVAILABLE FOUNDATION 20UHW | 31/01/2021 | 31/01/2021 | 31/01/2021 | 31/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHA2B02 | TT_Task | BASIC BUILDING DESIGN CONCRETE STRUCTURE - PRELIMINARY - 20UHA | 01/02/2021 | 02/04/2021 | 01/02/2021 | 02/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHA2B04 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE - 1ST SUBMISSION 20UHA(2NDPACKAGE) | 20/04/2021 | 12/05/2021 | 20/04/2021 | 13/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHA2B03 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE - PRELIMINARY - 20UHA | 15/02/2021 | 15/04/2021 | 15/02/2021 | 15/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHA2B01 | TT_FinMile | (MS2*) PRELIMINARY INPUTS AVAILABLE FOUNDATION 20UHA | 31/01/2021 | 31/01/2021 | 31/01/2021 | 31/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UVM2B02 | TT_Task | BASIC BUILDING DESIGN CONCRETE STRUCTURE - PRELIMINARY - 20UVM01 | 01/02/2021 | 14/02/2021 | 01/02/2021 | 14/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UVM2B04 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE -1ST SUBMISSION 20UVM01(2NDPACKAGE) | 16/04/2021 | 12/05/2021 | 16/04/2021 | 13/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UVM2B03 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE - PRELIMINARY - 20UVM01 | 15/02/2021 | 15/04/2021 | 15/02/2021 | 15/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UVM2B01 | TT_FinMile | (MS2*) PRELIMINARY INPUTS AVAILABLE FOUNDATION 20UVM01 | 31/01/2021 | 31/01/2021 | 31/01/2021 | 31/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMY2B02 | TT_Task | BASIC BUILDING DESIGN CONCRETE STRUCTURE - PRELIMINARY - 20ULY/UMY | 01/02/2021 | 14/02/2021 | 01/02/2021 | 14/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMY2B04 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE - 1ST SUBMISSION 20ULY/UMY(2NDPACKAGES) | 16/04/2021 | 12/05/2021 | 16/04/2021 | 13/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMY2B03 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE - PRELIMINARY - 20ULY/UMY | 15/02/2021 | 15/04/2021 | 15/02/2021 | 15/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMY2B01 | TT_FinMile | (MS2*) PRELIMINARY INPUTS AVAILABLE FOUNDATION 20ULY/UMY | 31/01/2021 | 31/01/2021 | 31/01/2021 | 31/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBF2B02 | TT_Task | BASIC BUILDING DESIGN CONCRETE STRUCTURE - PRELIMINARY - 20UBE/UBF | 01/02/2021 | 14/02/2021 | 01/02/2021 | 14/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBF2B04 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE - 1ST SUBMISSION - 20UBE/UBF(2NDPACKAGES) | 16/04/2021 | 12/05/2021 | 16/04/2021 | 13/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBF2B03 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE - PRELIMINARY - 20UBE/UBF | 15/02/2021 | 15/04/2021 | 15/02/2021 | 15/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBF2B01 | TT_FinMile | (MS2*) PRELIMINARY INPUTS AVAILABLE FOUNDATION 20UBE/UBF | 31/01/2021 | 31/01/2021 | 31/01/2021 | 31/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2B02 | TT_Task | BASIC BUILDING DESIGN CONCRETE STRUCTURE - PRELIMINARY - UBA7xxx | 01/02/2021 | 14/02/2021 | 01/02/2021 | 14/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2B04 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE - 1ST SUBMISISION UBA7xxx(2NDPACKAGE) | 20/04/2021 | 12/05/2021 | 20/04/2021 | 13/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2B03 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE - PRELIMINARY - UBA7xxx | 15/02/2021 | 15/04/2021 | 15/02/2021 | 15/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2B01 | TT_FinMile | (MS2*) PRELIMINARY INPUTS AVAILABLE FOUNDATION UBA7xxx | 31/01/2021 | 31/01/2021 | 31/01/2021 | 31/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UEN2B02 | TT_Task | BASIC BUILDING DESIGN CONCRETE STRUCTURE - PRELIMINARY - 20UEN | 01/02/2021 | 14/02/2021 | 01/02/2021 | 14/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UEN2B04 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE - PRELIMINARY - 20UEN | 16/04/2021 | 14/06/2021 | 16/04/2021 | 14/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UEN2B03 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE - PRELIMINARY - 20UEN | 15/02/2021 | 15/04/2021 | 15/02/2021 | 15/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UEN2B01 | TT_FinMile | (MS2*) PRELIMINARY INPUTS AVAILABLE FOUNDATION 20UEN | 31/01/2021 | 31/01/2021 | 31/01/2021 | 31/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBX2B02 | TT_Task | BASIC BUILDING DESIGN CONCRETE STRUCTURE - PRELIMINARY - 20UBX/20UBG03 | 01/02/2021 | 14/02/2021 | 01/02/2021 | 14/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBX2B04 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE - 1ST SUBMISSION - 20UBX/20UBG03(2NDPACKGAES) | 16/04/2021 | 14/06/2021 | 16/04/2021 | 14/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBX2B03 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE - PRELIMINARY - 20UBX/20UBG03 | 15/02/2021 | 15/04/2021 | 15/02/2021 | 15/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBX2B01 | TT_FinMile | (MS2*) PRELIMINARY INPUTS AVAILABLE FOUNDATION 20UBX/20UBG03 | 31/01/2021 | 31/01/2021 | 31/01/2021 | 31/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBX2-71 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN STEEL STRUCTURE- 20UBE/UBF | 10/08/2021 | 06/10/2021 | 10/08/2021 | 06/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBX2-80 | TT_Task | BD - SUBMISSION APPROVAL- DETAIL DESIGN STEEL STRUCTURE 20UBE/UBF | 03/12/2021 | 31/01/2022 | 03/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UBX2-81 | TT_Task | BD - CONSENT LETTER DETAIL DESIGN STEEL STRUCTURE 20UBE/UBF | 01/02/2022 | 28/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEN2-7 | TT_Task | HANDRAILS AND GRATING DWGS CONNECTION FORCE REPORT 20UEN | 14/10/2021 | 21/02/2022 | 14/10/2021 |  | 48 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UEN2-5 | TT_FinMile | (MS3) STEEL STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UEN | 05/09/2021 | 05/09/2021 | 05/09/2021 | 05/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UEN2-10 | TT_FinMile | (F) DETAIL DESIGN STEEL STRUCTURE WITH CONTRACTOR 20UEN | 18/09/2022 | 18/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEN2-6 | TT_Task | DETAIL DESIGN STEEL STRUCTURE 20UEN | 20/09/2021 | 21/02/2022 | 20/09/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UEN2-8 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN STEEL STRUCTURE 20UEN | 28/02/2022 | 28/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEN2-9 | TT_Task | BD - CONSENT LETTER - DETAIL DESIGN STEEL STRUCTURE 20UEN | 29/04/2022 | 26/05/2022 |  |  | 920 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEN3-11 | TT_Task | FABRICATION DESIGN FABRICATION TRANSPORT STEEL STRUCTURE 20UEN | 19/09/2022 | 11/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEN3-12 | TT_Mile | (HS) START ERECTION STEEL STRUCTURE 20UEN | 12/12/2022 | 12/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEN3-14 | TT_FinMile | (RFE) STEEL STRUCTURE 20UEN | 25/12/2022 | 25/12/2022 |  |  | 384 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEN3-13 | TT_Task | ERECTION STEEL PLATFORMS 20UEN | 12/12/2022 | 25/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA2-15 | TT_FinMile | FIXING FOR COMPONENTS(PLUS CP),PIPING(MTECH) SUBSTRUCTURE-20URA/URD | 27/07/2021 | 27/07/2021 | 27/07/2021 | 27/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHW3-18 | TT_Task | HANDRAILS AND GRATING DWGS CONNECTION FORCE REPORT 20UHW | 23/06/2021 | 07/09/2021 | 23/06/2021 | 07/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHW3-22 | TT_Task | FABRICATION DESIGN FABRICATION TRANSPORT STEEL STRUCTURE 20UHW | 06/12/2021 | 27/02/2022 | 06/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UHW3-23 | TT_Mile | (HS) START ERECTION STEEL STRUCTURE 20UHW | 28/02/2022 | 28/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UHW3-25 | TT_FinMile | (RFE) STEEL STRUCTURE 20UHW | 13/03/2022 | 13/03/2022 |  |  | 552 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UHW3-24 | TT_Task | ERECTION STEEL PLATFORMS 20UHW | 28/02/2022 | 13/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UHW3-16 | TT_FinMile | (MS3) STEEL STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UHW | 12/05/2021 | 12/05/2021 | 12/05/2021 | 12/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHW3-21 | TT_FinMile | (F) DETAIL DESIGN STEEL STRUCTURE WITH CONTRACTOR 20UHW | 05/12/2021 | 05/12/2021 | 05/12/2021 | 05/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHW3-17 | TT_Task | DETAIL DESIGN STEEL STRUCTURE 20UHW | 09/06/2021 | 13/07/2021 | 09/06/2021 | 13/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHW3-19 | TT_Task | BD - SUBMISSION APPROVAL - STEEL STRUCTURE 20UHW | 13/09/2021 | 05/12/2021 | 13/09/2021 | 05/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHW3-20 | TT_Task | BD - CONSENT LETTER - STEEL STRUCTURE 20UHW | 06/12/2021 | 02/01/2022 | 06/12/2021 |  | 448 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20URA3-18 | TT_Task | HANDRAILS AND GRATING DWGS CONNECTION FORCE REPORT 20URA | 26/07/2021 | 03/09/2021 | 26/07/2021 | 03/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URA3-25 | TT_FinMile | (RFE) STEEL STRUCTURE 20URA | 21/09/2022 | 21/09/2022 |  |  | 504 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA3-16 | TT_FinMile | (MS3) STEEL STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20URA | 16/05/2021 | 16/05/2021 | 16/05/2021 | 16/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URA3-21 | TT_FinMile | (F) DETAIL DESIGN STEEL STRUCTURE WITH CONTRACTOR 20URA | 26/05/2022 | 26/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA3-17 | TT_Task | DETAIL DESIGN STEEL STRUCTURE 20URA | 02/07/2021 | 03/09/2021 | 02/07/2021 | 03/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URA3-23 | TT_Mile | (HS) START ERECTION STEEL STRUCTURE 20URA | 25/08/2022 | 25/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA3-24 | TT_Task | ERECTION STAIRTOWER / STEEL PLATFORMS 20URA | 25/08/2022 | 21/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA3-22 | TT_Task | FABRICATION DESIGN FABRICATION TRANSPORT STEEL STRUCTURE 20URA | 27/05/2022 | 24/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA3-19 | TT_Task | BD - SUBMISSION APPROVAL - STEEL STRUCTURE 20URA | 28/02/2022 | 28/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA3-20 | TT_Task | BD - CONSENT LETTER - STEEL STRUCTURE 20URA | 29/04/2022 | 26/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URD3-18 | TT_Task | HANDRAILS AND GRATING DWGS CONNECTION FORCE REPORT 20URD | 22/08/2021 | 08/01/2022 | 22/08/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20URD3-25 | TT_FinMile | (RFE) STEEL STRUCTURE 20URD | 26/04/2022 | 26/04/2022 |  |  | 64 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URD3-16 | TT_FinMile | (MS3) STEEL STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20URD | 26/05/2021 | 26/05/2021 | 26/05/2021 | 26/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URD3-21 | TT_FinMile | (F) DETAIL DESIGN STEEL STRUCTURE WITH CONTRACTOR 20URD | 30/11/2021 | 30/11/2021 | 30/11/2021 | 30/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URD3-17 | TT_Task | DETAIL DESIGN STEEL STRUCTURE 20URD | 25/07/2021 | 08/01/2022 | 25/07/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20URD3-23 | TT_Mile | (HS) START ERECTION STEEL STRUCTURE 20URD | 13/04/2022 | 13/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URD3-24 | TT_Task | ERECTION STEEL PLATFORMS 20URD | 13/04/2022 | 26/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URD3-22 | TT_Task | FABRICATION DESIGN FABRICATION TRANSPORT STEEL STRUCTURE 20URD | 30/11/2021 | 07/03/2022 | 30/11/2021 |  | 288 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20URD3-19 | TT_Task | BD - SUBMISSION APPROVAL - STEEL STRUCTURE 20URD | 15/01/2022 | 15/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URD3-20 | TT_Task | BD - CONSENT LETTER - STEEL STRUCTURE 20URD | 16/03/2022 | 12/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--UBA2B99 | TT_Task | HANDRAILS AND GRATING DWGS CONNECTION FORCE REPORT 20UBA7910/20 | 25/09/2021 | 15/10/2021 | 25/09/2021 | 15/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UBA2D79 | TT_Mile | (F) DETAIL DESIGN STEEL STRUCTURE WITH CONTRACTOR 20UBA7910/20 | 01/05/2022 | 01/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--UBA2B98 | TT_Task | DETAIL DESIGN STEEL STRUCTURE 20UBA7910/20 | 01/09/2021 | 15/10/2021 | 01/09/2021 | 15/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UBA2F61 | TT_FinMile | (MS3) STEEL STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UBA7910/20 | 11/05/2021 | 11/05/2021 | 11/05/2021 | 11/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA3B77 | TT_Task | FABRICATION DESIGN/FABRICATION/TRANSPORT STEEL STRUC.20UBA7910/20 | 01/05/2022 | 06/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--UBA2-106 | TT_Task | BD - SUBMISSION APPROVAL - STEEL STRUCTURE 20UBA7910/20 | 28/02/2022 | 28/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--UBA2-107 | TT_Task | BD - CONSENT LETTER - STEEL STRUCTURE 20UBA7910/20 | 29/04/2022 | 26/05/2022 |  |  | 576 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBD2C-83 | TT_Task | HANDRAILS AND GRATING DWGS CONNECTION FORCE REPORT 20UBD03/04 | 11/11/2021 | 01/12/2021 | 11/11/2021 | 01/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBD5C-48 | TT_FinMile | (RFE) STEEL STRUCTURE 20UBD03/04 | 23/06/2022 | 23/06/2022 |  |  | 1200 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBD2C-81 | TT_FinMile | (MS3) STEEL STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UBD03/04 | 06/10/2021 | 06/10/2021 | 06/10/2021 | 06/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBD2C-86 | TT_FinMile | (F) DETAIL DESIGN STEEL STRUCTURE WITH CONTRACTOR 20UBD03/04 | 04/03/2022 | 04/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBD2C-82 | TT_Task | DETAIL DESIGN STEEL STRUCTURE 20UBD03/04 | 14/10/2021 | 01/12/2021 | 14/10/2021 | 01/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBD5C-46 | TT_Mile | (HS) START ERECTION STEEL STRUCTURE 20UBD03/04 | 10/06/2022 | 10/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBD5C-47 | TT_Task | ERECTION STEEL PLATFORMS 20UBD03/04 | 10/06/2022 | 23/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBD3C-26 | TT_Task | FABRICATION DESIGN FABRICATION TRANSPORT STEEL STRUCTURE 20UBD03/04 | 05/03/2022 | 07/06/2022 |  |  | 16 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBD2C-84 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN STEEL 20UBD03/04 | 28/02/2022 | 28/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBD2C-85 | TT_Task | BD - CONSENT LETTER - DETAIL DESIGN STEEL 20UBD03/04 | 29/04/2022 | 26/05/2022 |  |  | 112 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBD2C-89 | TT_Task | HANDRAILS AND GRATING DWGS CONNECTION FORCE REPORT 20UBD01/02 | 17/09/2021 | 07/10/2021 | 17/09/2021 | 07/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBD5C-51 | TT_FinMile | (RFE) STEEL STRUCTURE 20UBD01/02 | 25/06/2022 | 25/06/2022 |  |  | 24 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBD2C-87 | TT_FinMile | (MS3) STEEL STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UBD01/02 | 12/08/2021 | 12/08/2021 | 12/08/2021 | 12/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBD2C-92 | TT_FinMile | (F) DETAIL DESIGN STEEL STRUCTURE WITH CONTRACTOR 20UBD01/02 | 13/03/2022 | 13/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBD2C-88 | TT_Task | DETAIL DESIGN STEEL STRUCTURE 20UBD01/02 | 20/08/2021 | 07/10/2021 | 20/08/2021 | 07/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBD5C-49 | TT_Mile | (HS) START ERECTION STEEL STRUCTURE 20UBD01/02 | 12/06/2022 | 12/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBD5C-50 | TT_Task | ERECTION STEEL PLATFORMS 20UBD01/02 | 12/06/2022 | 25/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBD3C-27 | TT_Task | FABRICATION DESIGN FABRICATION TRANSPORT STEEL STRUCTURE 20UBD01/02 | 14/03/2022 | 11/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBD2C-90 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN STEEL 20UBD01/02 | 28/02/2022 | 28/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBD2C-91 | TT_Task | BD - CONSENT LETTER - DETAIL DESIGN STEEL 20UBD01/02 | 29/04/2022 | 26/05/2022 |  |  | 128 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBN2D78 | TT_Task | HANDRAILS AND GRATING DWGS CONNECTION FORCE REPORT 20UBN | 04/02/2022 | 24/02/2022 |  |  | 960 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBN5B46 | TT_FinMile | (RFE) STEEL STRUCTURE 20UBN | 14/10/2022 | 14/10/2022 |  |  | 1792 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBN2J60 | TT_FinMile | (MS3) STEEL STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UBN | 30/12/2021 | 30/12/2021 | 30/12/2021 | 30/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBN2H75 | TT_FinMile | (F) DETAIL DESIGN STEEL STRUCTURE WITH CONTRACTOR 20UBN | 24/06/2022 | 24/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBN2D70 | TT_Task | DETAIL DESIGN STEEL STRUCTURE 20UBN | 07/01/2022 | 24/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBN5B12 | TT_Mile | (HS) START ERECTION STEEL STRUCTURE 20UBN | 01/10/2022 | 01/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBN5B17 | TT_Task | ERECTION STEEL PLATFORMS 20UBN | 01/10/2022 | 14/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBN3B27 | TT_Task | FABRICATION DESIGN FABRICATION TRANSPORT STEEL STRUCTURE 20UBN | 25/06/2022 | 30/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBN2-104 | TT_Task | BD - SUBMISSION APPROVAL - STEEL STRUCTURE 20UBN | 31/03/2022 | 29/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBN2-105 | TT_Task | BD - CONSENT LETTER - STEEL STRUCTURE 20UBN | 30/05/2022 | 26/06/2022 |  |  | 768 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMX2D78 | TT_Task | HANDRAILS AND GRATING DWGS CONNECTION FORCE REPORT 20UMX02 | 01/02/2022 | 21/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMX5B46 | TT_FinMile | (RFE) STEEL STRUCTURE 20UMX02 | 17/07/2022 | 17/07/2022 |  |  | 112 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMX2J60 | TT_FinMile | (MS3) STEEL STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UMX02 | 18/11/2021 | 18/11/2021 | 18/11/2021 | 18/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMX2H75 | TT_FinMile | (F) DETAIL DESIGN STEEL STRUCTURE WITH CONTRACTOR 20UMX02 | 21/02/2022 | 21/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMX2D70 | TT_Task | DETAIL DESIGN STEEL STRUCTURE 20UMX02 | 30/11/2021 | 21/02/2022 | 30/11/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UMX5B12 | TT_Mile | (HS) START ERECTION STEEL STRUCTURE 20UMX02 | 04/07/2022 | 04/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMX5B17 | TT_Task | ERECTION STEEL PLATFORMS 20UMX02 | 04/07/2022 | 17/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMX3B27 | TT_Task | FABRICATION DESIGN FABRICATION TRANSPORT STEEL STRUCTURE 20UMX02 | 22/02/2022 | 30/05/2022 |  |  | 272 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMX2-104 | TT_Task | BD - SUBMISSION APPROVAL - STEEL STRUCTURE 20UMX02 | 28/02/2022 | 28/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMX2-105 | TT_Task | BD - CONSENT LETTER - STEEL STRUCTURE 20UMX02 | 29/04/2022 | 26/05/2022 |  |  | 10512 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEX2D78 | TT_Task | HANDRAILS AND GRATING DWGS CONNECTION FORCE REPORT 20UEX01 | 10/03/2022 | 30/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEX5B46 | TT_FinMile | (RFE) STEEL STRUCTURE 20UEX01 | 18/09/2022 | 18/09/2022 |  |  | 40 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEX2J60 | TT_FinMile | (MS3) STEEL STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UEX01 | 16/01/2022 | 16/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEX2H75 | TT_FinMile | (F) DETAIL DESIGN STEEL STRUCTURE WITH CONTRACTOR 20UEX01 | 29/05/2022 | 29/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEX2D70 | TT_Task | DETAIL DESIGN STEEL STRUCTURE 20UEX01 | 07/02/2022 | 23/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEX5B12 | TT_Mile | (HS) START ERECTION STEEL STRUCTURE 20UEX01 | 05/09/2022 | 05/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEX5B17 | TT_Task | ERECTION STEEL PLATFORMS 20UEX01 | 05/09/2022 | 18/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEX3B27 | TT_Task | FABRICATION DESIGN FABRICATION TRANSPORT STEEL STRUCTURE 20UEX01 | 30/05/2022 | 04/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEX2-104 | TT_Task | BD - SUBMISSION APPROVAL - STEEL STRUCTURE 20UEX01 | 31/03/2022 | 29/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEX2-105 | TT_Task | BD - CONSENT LETTER - STEEL STRUCTURE 20UEX01 | 30/05/2022 | 26/06/2022 |  |  | 560 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UZJ5-62 | TT_Mile | (H) START PLACING FORMWORK FENCESGATES | 10/11/2022 | 10/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UZJ5-60 | TT_Task | WORK PREPARATION, EXCAVATION FENCESGATES | 27/10/2022 | 09/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UZJ5-66 | TT_FinMile | (RFE) FOUNDATION FENCESGATES | 22/02/2023 | 22/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UZJ2-82 | TT_Task | BASIC BUILDING DESIGN INCL. 3D MODEL FENCESGATES | 11/06/2021 | 01/07/2021 | 11/06/2021 | 01/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UZJ2-84 | TT_Task | PREPARATION FOUNDATION GROUNDING DWGS UTG FENCESGATES | 26/09/2021 | 14/01/2022 | 26/09/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UZJ2-83 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE FENCESGATES | 02/07/2021 | 14/01/2022 | 02/07/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UZJ2-88 | TT_FinMile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION FENCESGATES | 26/10/2022 | 26/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UZJ2-81 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE FENCESGATES | 10/06/2021 | 10/06/2021 | 10/06/2021 | 10/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UZJ2-85 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN CONCRETE FENCESGATES | 15/01/2022 | 08/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UZJ2-86 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE FENCESGATES | 15/01/2022 | 15/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UZJ2-87 | TT_Task | BD - CONSENT LETTER - DETAIL DESIGN CONCRETE FENCESGATES | 16/03/2022 | 12/04/2022 |  |  | 1576 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UZJ-99 | TT_Task | ERECTION FENCESGATES | 23/02/2023 | 03/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBL2C-65 | TT_Task | HANDRAILS AND GRATING DWGS CONNECTION FORCE REPORT 20UBL | 25/10/2021 | 06/12/2021 | 25/10/2021 | 06/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBL5C-45 | TT_FinMile | (RFE) STEEL STRUCTURE 20UBL | 07/10/2022 | 07/10/2022 |  |  | 80 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBL2C-55 | TT_FinMile | (MS3) STEEL STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UBL | 09/08/2021 | 09/08/2021 | 09/08/2021 | 09/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBL2C-80 | TT_FinMile | (F) DETAIL DESIGN STEEL STRUCTURE WITH CONTRACTOR 20UBL | 01/04/2022 | 01/04/2022 |  |  | 224 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBL2C-60 | TT_Task | DETAIL DESIGN STEEL STRUCTURE 20UBL | 30/09/2021 | 06/12/2021 | 30/09/2021 | 06/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBL5C-30 | TT_Mile | (HS) START ERECTION STEEL STRUCTURE 20UBL | 10/09/2022 | 10/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBL5C-35 | TT_Task | ERECTION STEEL STRUCTURE 20UBL | 10/09/2022 | 07/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBL3C-25 | TT_Task | FABRICATION DESIGN FABRICATION TRANSPORT STEEL STRUCTURE 20UBL | 30/04/2022 | 05/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBL2C-70 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN STEEL 20UBL | 07/12/2021 | 04/02/2022 | 07/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UBL2C-75 | TT_Task | BD - CONSENT LETTER - DETAIL DESIGN STEEL 20UBL | 05/02/2022 | 04/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BFF3-80 | TT_FinMile | (RFS) READY FOR SHIPMENT LV SWITCHGEAR FOR HRSG 20BFF/BMFF | 13/05/2022 | 13/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-122 | TT_Mile | TP-M8A - CARBON DIOXIDE SUPPLY | 18/06/2022 | 18/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-129 | TT_Mile | TP-M9A - INSTRUMENT AIR INTERCONNECTION TO BPPS INSTRUMENT AIR SYSTEM | 18/06/2022 | 18/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-135 | TT_Mile | TP-M14A - SECOND UREA TANK 10HSJ22BB001 - LIQUID UREA SUPPLY | 01/07/2022 | 01/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-131 | TT_Mile | TP-M10A - HYPOCHLORITE DOSING | 14/05/2022 | 14/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-118 | TT_Mile | TP-M6A - TOWNSWATER SERVICE SYSTEM (SERVICE WATER) | 26/08/2022 | 26/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-166 | TT_Mile | TP-M16A - COOLING TOWER BLOWDOWN DISCHARGE | 15/04/2022 | 15/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-167 | TT_Mile | TP-M17A - CLEAN LUBRICATING OIL SUPPY TO UNIT D1 | 12/06/2022 | 12/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-168 | TT_Mile | TP-M18A - USED OIL RETURN FROM UNIT D1 | 12/06/2022 | 12/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-183 | TT_Mile | NOT APPLICABLE - TP-M24A - D2 EFFLUENT COLLECTION (various locations) | 12/07/2022 | 12/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-185 | TT_Mile | TP-M26A - CONNECTION IN D2 FOR FUTURE SUPPLY AND RECEIVAL OF AUXILIARY STEAM TO D1 | 21/04/2022 | 21/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-186 | TT_Mile | TP-M28A - CONDENSATE POLISHING TREATMENT EXHAUSTED MIXED BED RESIN FROM D2 | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-187 | TT_Mile | TP-M29A - CONDENSATE POLISHING TREATMENT REGENERATED MIXED BED RESIN SUPPLY PIPE CONN. TO D2 | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-201 | TT_Mile | TP-C1A - STORM WATER CONNECTION | 01/10/2021 | 01/10/2021 | 01/10/2021 | 01/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TP-190 | TT_Mile | TP-F1A - FIRE FIGHTING FRESH WATER SUPPLY | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-193 | TT_Mile | TP-F2A - FIRE FIGHTING SEA WATER SUPPLY (various locations) | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-260 | TT_Mile | TP-E4 - D2 GSUT GIL CABLE BOX (D2 Generator Transformer Bay) | 05/12/2022 | 05/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P221-20 | TT_Mile | BD - SUBMISSION - BUILDING DETAIL DESIGN CONCRETE 20UMC | 11/06/2021 | 11/06/2021 | 11/06/2021 | 11/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-75 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE - 20UHA | 02/08/2021 | 02/08/2021 | 02/08/2021 | 02/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-255 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE 20URA | 30/06/2021 | 30/06/2021 | 30/06/2021 | 30/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-265 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE 20URD | 14/07/2021 | 14/07/2021 | 14/07/2021 | 14/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-105 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE 20ULA | 02/08/2021 | 02/08/2021 | 02/08/2021 | 02/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-10 | TT_Mile | BD - SUBMISSION - TURBOSET DETAIL DESIGN CONCRETE (AMENDMENT) 20UMC | 22/08/2021 | 22/08/2021 | 22/08/2021 | 22/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-150 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE 20UBE/UBF | 15/08/2021 | 15/08/2021 | 15/08/2021 | 15/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-275 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE 01UEN | 13/12/2021 | 13/12/2021 | 13/12/2021 | 13/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-95 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE 20UEN | 30/11/2021 | 30/11/2021 | 30/11/2021 | 30/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-80 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE - 20UBA1110/20 | 23/10/2021 | 23/10/2021 | 23/10/2021 | 23/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-165 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE - 20UBD01/02 | 13/12/2021 | 13/12/2021 | 13/12/2021 | 13/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-130 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE - UBA7xxx | 02/08/2021 | 02/08/2021 | 02/08/2021 | 02/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-135 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE - UBA7910/7920 | 04/01/2022 | 04/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P221-120 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE - 20UVM01 | 02/08/2021 | 02/08/2021 | 02/08/2021 | 02/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-220 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE - 20UBA8110/20 | 13/12/2021 | 13/12/2021 | 13/12/2021 | 13/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-225 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE - 20UBD03/04 | 13/12/2021 | 13/12/2021 | 13/12/2021 | 13/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-310 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE - 20ULY/UMY | 02/08/2021 | 02/08/2021 | 02/08/2021 | 02/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-280 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE 20UEY03-05 | 13/12/2021 | 13/12/2021 | 13/12/2021 | 13/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-300 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE 20UEY01 | 27/07/2021 | 27/07/2021 | 27/07/2021 | 27/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-30 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE 20UPY | 11/06/2021 | 11/06/2021 | 11/06/2021 | 11/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-45 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE 20UMX | 10/09/2021 | 10/09/2021 | 10/09/2021 | 10/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-290 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE 20UMX02 | 13/12/2021 | 13/12/2021 | 13/12/2021 | 13/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-35 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE 20UTG01 | 31/01/2022 | 31/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P221-315 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE - 01UBA9010/20 | 15/01/2022 | 15/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P221-210 | TT_Mile | 61 - BD - SUBMISSION - DETAIL DESIGN CONCRETE - 20ULY01 | 13/12/2021 | 13/12/2021 | 13/12/2021 | 13/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-200 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE - UBY01 | 28/02/2022 | 28/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P221-195 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE 20UEX01 | 31/03/2022 | 31/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P221-180 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE - 20UBN | 28/02/2022 | 28/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P221-40 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE 20UTG07 | 31/01/2022 | 31/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P221-85 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE 20UTG04 | 14/12/2021 | 14/12/2021 | 14/12/2021 | 14/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-140 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE 20UTG02 | 31/01/2022 | 31/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P221-160 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE 20UTG03 | 31/01/2022 | 31/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P221-240 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE 20UTG05 | 31/01/2022 | 31/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P221-320 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE 20UTG06 | 15/01/2022 | 15/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P221-185 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE - UBY02 (Not existing) | 10/10/2021 | 10/10/2021 | 10/10/2021 | 10/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-230 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE - UBY03 | 28/02/2022 | 28/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P221-270 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE - UBY04/05 | 13/12/2021 | 13/12/2021 | 13/12/2021 | 13/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-50 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE 20USX | 28/02/2022 | 28/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P221-340 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE 20UQX | 15/01/2022 | 15/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P221-345 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE - 20UQY01 | 04/01/2022 | 04/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P221-360 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE - 20UQZ | 04/01/2022 | 04/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P221-65 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE - HRSG BLOWDOWN PIT DESIGN 20UHW | 02/08/2021 | 02/08/2021 | 02/08/2021 | 02/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-205 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE - 20UBZ01 | 13/12/2021 | 13/12/2021 | 13/12/2021 | 13/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-190 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE - 20UBZ04 | 30/12/2021 | 30/12/2021 | 30/12/2021 | 30/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-235 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE - 20UBZ02 | 04/01/2022 | 04/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P221-350 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE - 20UQY02 | 04/01/2022 | 04/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P221-355 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE - 20UQY03 | 04/01/2022 | 04/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P221-285 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE 20UGU02 | 15/01/2022 | 15/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P221-110 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE 20UHX | 31/01/2022 | 31/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P221-5 | TT_Mile | BD - SUBMISSION - TURBOSET DETAIL DESIGN - PRELIMINARY - 20UMC | 16/04/2021 | 16/04/2021 | 16/04/2021 | 16/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-15 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE - PRELIMINARY - 20UMC | 16/03/2021 | 16/03/2021 | 16/03/2021 | 16/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-25 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE - PRELIMINARY - 20UPY | 16/03/2021 | 16/03/2021 | 16/03/2021 | 16/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-295 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE - PRELIMINARY - 20UEY01 | 16/03/2021 | 16/03/2021 | 16/03/2021 | 16/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-260 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE - PRELIMINARY - 20URD | 16/03/2021 | 16/03/2021 | 16/03/2021 | 16/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-245 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE FOUNDATION - PRELIMINARY - 20URA | 16/03/2021 | 16/03/2021 | 16/03/2021 | 16/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-250 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE SUPERSTRUCTURE - 1ST SUBMISSION - 20URA | 25/06/2021 | 25/06/2021 | 25/06/2021 | 25/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-100 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE - PRELIMINARY - 20ULA | 15/04/2021 | 15/04/2021 | 15/04/2021 | 15/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-60 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE - PRELIMINARY - 20UHW | 15/04/2021 | 15/04/2021 | 15/04/2021 | 15/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-70 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE - PRELIMINARY - 20UHA | 15/04/2021 | 15/04/2021 | 15/04/2021 | 15/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-115 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE - PRELIMINARY - 20UVM01 | 15/04/2021 | 15/04/2021 | 15/04/2021 | 15/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-305 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE - PRELIMINARY - 20ULY/UMY | 15/04/2021 | 15/04/2021 | 15/04/2021 | 15/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-145 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE - PRELIMINARY - 20UBE/UBF | 15/04/2021 | 15/04/2021 | 15/04/2021 | 15/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-125 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE - PRELIMINARY - UBA7xxx | 15/04/2021 | 15/04/2021 | 15/04/2021 | 15/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-90 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE - PRELIMINARY - 20UEN | 15/04/2021 | 15/04/2021 | 15/04/2021 | 15/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-170 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE - PRELIMINARY - 20UBX/20UBG03 | 15/04/2021 | 15/04/2021 | 15/04/2021 | 15/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-330 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE FENCESGATES | 15/01/2022 | 15/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P221-365 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE - CEP/LDK - PIT 20UMC | 16/03/2021 | 16/03/2021 | 16/03/2021 | 16/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-370 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE SUPERSTRUCTURE 20URA | 15/09/2021 | 15/09/2021 | 15/09/2021 | 15/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-415 | TT_Mile | BD - SUBMISSION - STANDING SEAM ROOF/WALL/PANELS - CLADDING 20UMC | 14/08/2021 | 14/08/2021 | 14/08/2021 | 14/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-430 | TT_Mile | 21 - BD - SUBMISSON HRSG STACK | 16/05/2021 | 16/05/2021 | 16/05/2021 | 16/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-380 | TT_Mile | BD - SUBMISSION - RING ROAD INCL. UNDERGROUND (U/G) DRAINAGE RC PLANS | 10/05/2021 | 10/05/2021 | 10/05/2021 | 10/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-450 | TT_Mile | BD - SUBMISSION - GEN TRAFO PLATFORM 20UBF | 15/08/2021 | 15/08/2021 | 15/08/2021 | 15/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-390 | TT_Mile | BD - REVIEW SUBMISSION- FIRE FIGHTING DESIGN | 28/05/2021 | 28/05/2021 | 28/05/2021 | 28/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-420 | TT_Mile | BD - SUBMISSION - LOUVRES - CLADDING 20UMC | 14/08/2021 | 14/08/2021 | 14/08/2021 | 14/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-425 | TT_Mile | 47 - BD - SUBMISSION -UMX SUPPORTING FRAME FOR DIFFUSER | 14/07/2021 | 14/07/2021 | 14/07/2021 | 14/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-440 | TT_Mile | BD - SUBMISSION - 20UBH01 | 17/08/2021 | 17/08/2021 | 17/08/2021 | 17/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-395 | TT_Mile | BD - SUBMISSION - SUPPORTING FRAME FOR MODULES LOT 1 (UMY00Y/ULY00Y) | 17/06/2021 | 17/06/2021 | 17/06/2021 | 17/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-375 | TT_Mile | BD - SUBMISSION - RING ROAD INCL. UNDERGROUND (U/G) DRAINAGE | 10/05/2021 | 10/05/2021 | 10/05/2021 | 10/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-385 | TT_Mile | BD - SUBMISSION - HYDRAULIC SUBMISSION APPROVAL (FSI/314 SCHEMATIC DWGS SUBMISSION) | 31/08/2021 | 31/08/2021 | 31/08/2021 | 31/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-460 | TT_Mile | 63 - BD - SUBMISSION - CIVIL ADAPTION WORKS AT SCW PUMP HOUSE 20UQB | 06/12/2021 | 06/12/2021 | 06/12/2021 | 06/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-400 | TT_Mile | BD - SUBMISSION - SUPPORTING FRAME FOR MODULES LOT 2 (UMCM1Y/UMCL1Y) | 05/07/2021 | 05/07/2021 | 05/07/2021 | 05/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-405 | TT_Mile | BD - SUBMISSION - SUPPORTING FRAME FOR MODULES LOT 3 (UEY01Y/UEY02Y/UPY00Y) | 03/08/2021 | 03/08/2021 | 03/08/2021 | 03/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-455 | TT_Mile | BD - SUBMISSION - 20UBH02 | 17/08/2021 | 17/08/2021 | 17/08/2021 | 17/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-445 | TT_Mile | BD - SUBMISSION - PUMP PIT DESIGN 20UGU01 | 15/01/2022 | 15/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P221-465 | TT_Mile | BD - SUBMISSION - STEEL STRUCTURE 20UMC (Incl. Crane Walkawy) (1st SUBMISSION) | 17/05/2021 | 17/05/2021 | 17/05/2021 | 17/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-470 | TT_Mile | BD - SUBMISSION - STEEL PLATFORMS 20UMC | 17/06/2021 | 17/06/2021 | 17/06/2021 | 17/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-490 | TT_Mile | BD - SUBMISSION - STEEL STRUCTURE 20UBA7xxx | 02/08/2021 | 02/08/2021 | 02/08/2021 | 02/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-480 | TT_Mile | BD - SUBMISSION - STEEL STRUCTURE 20UBA1110/20 | 28/02/2022 | 28/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P221-510 | TT_Mile | 45 - BD - SUBMISSION - STEELWORK - 20UBX/20UBG | 28/02/2022 | 28/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P221-535 | TT_Mile | BD - SUBMISSION - STEEL STRUCTURE 20UBA8110/20 | 28/02/2022 | 28/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P221-555 | TT_Mile | BD - SUBMISSION - STEEL STRUCTURE 01UBA9010/20 | 02/04/2022 | 02/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P221-530 | TT_Mile | BD - SUBMISSION - STEEL STRUCTURE 20ULY01 | 28/02/2022 | 28/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P221-500 | TT_Mile | 44 - BD - SUBMISSION- DETAIL DESIGN STEEL STRUCTURE 20UBE/UBF | 10/08/2021 | 10/08/2021 | 10/08/2021 | 10/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-485 | TT_Mile | 48 - BD - SUBMISSION - 20UEN PLATFORM | 28/02/2022 | 28/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P221-475 | TT_Mile | 46 - BD - SUBMISSION - STEEL STRUCTURE 20UHW | 13/09/2021 | 13/09/2021 | 13/09/2021 | 13/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-545 | TT_Mile | BD - SUBMISSION - STEEL STRUCTURE 20URD | 15/01/2022 | 15/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P221-495 | TT_Mile | BD - SUBMISSION - STEEL STRUCTURE 20UBA7910/20 | 28/02/2022 | 28/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P221-540 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN STEEL 20UBD03/04 | 28/02/2022 | 28/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P221-505 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN STEEL 20UBD01/02 | 28/02/2022 | 28/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P221-515 | TT_Mile | BD - SUBMISSION - STEEL STRUCTURE 20UBN | 31/03/2022 | 31/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P221-550 | TT_Mile | BD - SUBMISSION - STEEL STRUCTURE 20UMX02 | 28/02/2022 | 28/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P221-520 | TT_Mile | BD - SUBMISSION - STEEL STRUCTURE 20UEX01 | 31/03/2022 | 31/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P221-560 | TT_Mile | BD - SUBMISSION - STEEL STRUCTURE 20URA | 06/12/2021 | 06/12/2021 | 06/12/2021 | 06/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MPB3A94 | TT_Task | MANUFACTURING ENCLOSURE 20MPB | 02/12/2021 | 13/05/2022 | 02/12/2021 |  | 256 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20MPB6E83 | TT_Task | ERECTION OF STEELWORK FOR ENCLOSURE 20MPB | 08/09/2022 | 21/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBX2C-65 | TT_Task | DETAIL DESIGN CLADDING 20UBX | 13/05/2022 | 07/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MBL2-99 | TT_Mile | 27 - BD - SUBMISSION - AIR INTAKE INTERNAL PORTION | 16/08/2021 | 16/08/2021 | 16/08/2021 | 16/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-561 | TT_Mile | 22 - BD - SUBMISSON HRSG MAIN FRAME | 16/05/2021 | 16/05/2021 | 16/05/2021 | 16/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-562 | TT_Mile | 23 - BD - SUBMISSON HRSG LOWER PLATFORM | 30/11/2021 | 30/11/2021 | 30/11/2021 | 30/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-563 | TT_Mile | 24 - BD - SUBMISSON HRSG MAINTENANCE STAIRCASE | 30/11/2021 | 30/11/2021 | 30/11/2021 | 30/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-564 | TT_Mile | 25 - BD - SUBMISSON HRSG SIDE PLATFORM | 14/12/2021 | 14/12/2021 | 14/12/2021 | 14/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-565 | TT_Mile | 26 - BD - SUBMISSON HRSG ROOF CANOPY | 14/12/2021 | 14/12/2021 | 14/12/2021 | 14/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MBL2-100 | TT_Mile | 28 - BD - SUBMISSION - AIR INTAKE EXTERNAL PORTION | 16/08/2021 | 16/08/2021 | 16/08/2021 | 16/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-566 | TT_Mile | 29 - BD - SUBMISSION - DECOMPOSITION CHAMBER SUPPORTING FRAME | 08/07/2021 | 08/07/2021 | 08/07/2021 | 08/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-567 | TT_Mile | 30 - BD - SUBMISSION - HOT AIR BLOWER SUPPORTING FRAME | 08/07/2021 | 08/07/2021 | 08/07/2021 | 08/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-568 | TT_Mile | 49 - BD - SUBMISSION - CLEAN/DIRTY OIL TANK UMX | 30/09/2021 | 30/09/2021 | 30/09/2021 | 30/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-569 | TT_Mile | 36 - BD - SUBMISSION - CRANE WALKWAY PLATFORM 20UMC | 17/05/2021 | 17/05/2021 | 17/05/2021 | 17/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-570 | TT_Mile | 34 - BD - SUBMISSION - CEP PLATFORM 20UMC | 17/06/2021 | 17/06/2021 | 17/06/2021 | 17/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-571 | TT_Mile | 35 - BD - SUBMISSION - LDK PLATFORM 20UMC | 17/06/2021 | 17/06/2021 | 17/06/2021 | 17/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-572 | TT_Mile | 37 - BD - SUBMISSION - ENTRANCE PLATFORM 20UMC | 17/05/2021 | 17/05/2021 | 17/05/2021 | 17/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-573 | TT_Mile | 38 - BD - SUBMISSION - GENO ST PLATFORM 20UMC | 18/08/2021 | 18/08/2021 | 18/08/2021 | 18/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-574 | TT_Mile | 39 - BD - SUBMISSION - BUS DUCT SUPPORT STRUCTURE 20UBL | 07/12/2021 | 07/12/2021 | 07/12/2021 | 07/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-575 | TT_Mile | 40 - BD - SUBMISSION - CONDENSER MANHOLE ACCESS PLATFORM | 18/08/2021 | 18/08/2021 | 18/08/2021 | 18/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-576 | TT_Mile | 41 - BD - SUBMISSION - ST BEARING ACESS PLATFORM | 18/08/2021 | 18/08/2021 | 18/08/2021 | 18/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-578 | TT_Mile | 43 - BD - SUBMISSION - MISCELLANEOUS PLATFORMS (INSIDE BUILDING) 20UMC | 18/08/2021 | 18/08/2021 | 18/08/2021 | 18/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-579 | TT_Mile | 14 - BD - SUBMISSON EXTERNAL STEELWORK CANOPIES FOR UTG | 28/02/2022 | 28/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-PM-10 | TT_Mile | PM01 - NOTICE TO PROCEED RECEIVED | 15/01/2021 | 15/01/2021 | 15/01/2021 | 15/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-PM-15 | TT_Mile | PM02 - SITE TAKEOVER ACHIEVED | 01/07/2021 | 01/07/2021 | 01/07/2021 | 01/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-PM-20 | TT_Mile | PM03 - GT FOUNDATION COMPLETED | 30/01/2022 | 30/01/2022 |  |  | 488 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-PM-25 | TT_Mile | PM04 - COMPLETION OF GT FACTORY ACCEPTANCE TESTING | 01/04/2022 | 01/04/2022 |  |  | 1000 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-PM-30 | TT_Mile | PM05 - GAS TURBINE SET ON FOUNDATION | 04/08/2022 | 04/08/2022 |  |  | 1496 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-PM-35 | TT_Mile | PM06 - STEAM TURBINE SET ON FOUNDATION | 30/07/2022 | 30/07/2022 |  |  | 1536 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-PM-40 | TT_Mile | PM07 - MOBILISATION OF COMMISSIONING | 07/02/2023 | 07/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-PM-45 | TT_Mile | PM08 - FIRST FIRE ACHIEVED | 01/07/2023 | 01/07/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-PM-50 | TT_Mile | PM09 - SUBSTANTIAL COMPLETION ACHIEVED - PAC | 31/12/2023 | 31/12/2023 |  |  | 5848 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-PM-55 | TT_Mile | PM10 - FINAL COMPLETION ACHIEVED - FAC | 31/12/2025 | 31/12/2025 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-30 | TT_Mile | (HS) START ERECTION STEEL STRUCTURE 20UTG01 | 22/06/2022 | 22/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-38 | TT_FinMile | (RFE) STEEL STRUCTURE 20UTG01 | 05/07/2022 | 05/07/2022 |  |  | 832 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-32 | TT_Task | ERECTION STEELWORKS CANOPIES 20UTG01 | 22/06/2022 | 05/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-18 | TT_Task | HANDRAILS AND GRATING DWGS CONNECTION FORCE REPORT 20UTG01 | 27/11/2021 | 27/01/2022 | 27/11/2021 |  | 376 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-22 | TT_Mile | (F) DETAIL DESIGN STEEL STRUCTURE WITH CONTRACTOR 20UTG01 | 16/03/2022 | 16/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-6 | TT_Task | DETAIL DESIGN STEEL STRUCTURE 20UTG01 | 30/10/2021 | 27/01/2022 | 30/10/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-2 | TT_FinMile | (MS3) STEEL STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UTG01 | 20/09/2021 | 20/09/2021 | 20/09/2021 | 20/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-24 | TT_Task | FABRICATION DESIGN/FABRICATION/TRANSPORT STEEL STRUC.20UTG01 | 16/03/2022 | 21/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-10 | TT_Task | BD - SUBMISSION APPROVAL - STEEL STRUCTURE 20UTG01 | 28/02/2022 | 28/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-14 | TT_Task | BD - CONSENT LETTER - STEEL STRUCTURE 20UTG01 | 29/04/2022 | 26/05/2022 |  |  | 208 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-34 | TT_Mile | (HS) START ERECTION STEEL STRUCTURE 20UTG07 | 30/06/2022 | 30/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-40 | TT_FinMile | (RFE) STEEL STRUCTURE 20UTG07 | 13/07/2022 | 13/07/2022 |  |  | 768 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-36 | TT_Task | ERECTION STEELWORKS CANOPIES 20UTG07 | 30/06/2022 | 13/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-20 | TT_Task | HANDRAILS AND GRATING DWGS CONNECTION FORCE REPORT 20UTG07 | 28/11/2021 | 18/12/2021 | 28/11/2021 | 18/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-26 | TT_Mile | (F) DETAIL DESIGN STEEL STRUCTURE WITH CONTRACTOR 20UTG07 | 01/04/2022 | 01/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-8 | TT_Task | DETAIL DESIGN STEEL STRUCTURE 20UTG07(Change To Concrete Buidling | 31/10/2021 | 18/12/2021 | 31/10/2021 | 18/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-4 | TT_FinMile | (MS3) STEEL STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UTG07 | 20/09/2021 | 20/09/2021 | 20/09/2021 | 20/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-28 | TT_Task | FABRICATION DESIGN/FABRICATION/TRANSPORT STEEL STRUC.20UTG07 | 01/04/2022 | 29/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-12 | TT_Task | BD - SUBMISSION APPROVAL - STEEL STRUCTURE 20UTG07 | 01/04/2022 | 30/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-16 | TT_Task | BD - CONSENT LETTER - STEEL STRUCTURE 20UTG07 | 31/05/2022 | 27/06/2022 |  |  | 16 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-56 | TT_Mile | (HS) START ERECTION STEEL STRUCTURE 20UTG04 | 18/08/2022 | 18/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-60 | TT_FinMile | (RFE) STEEL STRUCTURE 20UTG04 | 31/08/2022 | 31/08/2022 |  |  | 376 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-58 | TT_Task | ERECTION STEELWORKS CANOPIES 20UTG04 | 18/08/2022 | 31/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-50 | TT_Task | HANDRAILS AND GRATING DWGS CONNECTION FORCE REPORT 20UTG04 | 07/02/2022 | 27/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-52 | TT_Mile | (F) DETAIL DESIGN STEEL STRUCTURE WITH CONTRACTOR 20UTG04 | 12/05/2022 | 12/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-44 | TT_Task | DETAIL DESIGN STEEL STRUCTURE 20UTG04 | 21/09/2021 | 06/12/2021 | 21/09/2021 | 06/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-42 | TT_FinMile | (MS3) STEEL STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UTG04 | 30/08/2021 | 30/08/2021 | 30/08/2021 | 30/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-54 | TT_Task | FABRICATION DESIGN/FABRICATION/TRANSPORT STEEL STRUC.20UTG04 | 12/05/2022 | 17/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-46 | TT_Task | BD - SUBMISSION APPROVAL - STEEL STRUCTURE 20UTG04 | 28/02/2022 | 28/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-48 | TT_Task | BD - CONSENT LETTER - STEEL STRUCTURE 20UTG04 | 29/04/2022 | 26/05/2022 |  |  | 664 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-76 | TT_Mile | (HS) START ERECTION STEEL STRUCTURE 20UTG02 | 05/08/2022 | 05/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-80 | TT_FinMile | (RFE) STEEL STRUCTURE 20UTG02 | 18/08/2022 | 18/08/2022 |  |  | 480 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-78 | TT_Task | ERECTION STEELWORKS CANOPIES 20UTG02 | 05/08/2022 | 18/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-70 | TT_Task | HANDRAILS AND GRATING DWGS CONNECTION FORCE REPORT 20UTG02 | 08/04/2022 | 28/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-72 | TT_Mile | (F) DETAIL DESIGN STEEL STRUCTURE WITH CONTRACTOR 20UTG02 | 29/04/2022 | 29/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-64 | TT_Task | DETAIL DESIGN STEEL STRUCTURE 20UTG02 | 10/01/2022 | 27/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-62 | TT_FinMile | (MS3) STEEL STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UTG02 | 11/11/2021 | 11/11/2021 | 11/11/2021 | 11/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-74 | TT_Task | FABRICATION DESIGN/FABRICATION/TRANSPORT STEEL STRUC.20UTG02 | 29/04/2022 | 04/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-66 | TT_Task | BD - SUBMISSION APPROVAL - STEEL STRUCTURE 20UTG02 | 28/02/2022 | 28/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-68 | TT_Task | BD - CONSENT LETTER - STEEL STRUCTURE 20UTG02 | 29/04/2022 | 26/05/2022 |  |  | 560 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-96 | TT_Mile | (HS) START ERECTION STEEL STRUCTURE 20UTG03 | 04/10/2022 | 04/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-100 | TT_FinMile | (RFE) STEEL STRUCTURE 20UTG03 | 17/10/2022 | 17/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-98 | TT_Task | ERECTION STEELWORKS CANOPIES 20UTG03 | 04/10/2022 | 17/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-90 | TT_Task | HANDRAILS AND GRATING DWGS CONNECTION FORCE REPORT 20UTG03 | 07/06/2022 | 27/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-92 | TT_Mile | (F) DETAIL DESIGN STEEL STRUCTURE WITH CONTRACTOR 20UTG03 | 28/06/2022 | 28/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-84 | TT_Task | DETAIL DESIGN STEEL STRUCTURE 20UTG03 | 11/02/2022 | 31/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-82 | TT_FinMile | (MS3) STEEL STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UTG03 | 11/11/2021 | 11/11/2021 | 11/11/2021 | 11/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-94 | TT_Task | FABRICATION DESIGN/FABRICATION/TRANSPORT STEEL STRUC.20UTG03 | 28/06/2022 | 03/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-86 | TT_Task | BD - SUBMISSION APPROVAL - STEEL STRUCTURE 20UTG03 | 01/04/2022 | 30/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-88 | TT_Task | BD - CONSENT LETTER - STEEL STRUCTURE 20UTG03 | 31/05/2022 | 27/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-116 | TT_Mile | (HS) START ERECTION STEEL STRUCTURE 20UTG05 | 06/06/2022 | 06/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-120 | TT_FinMile | (RFE) STEEL STRUCTURE 20UTG05 | 19/06/2022 | 19/06/2022 |  |  | 960 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-118 | TT_Task | ERECTION STEELWORKS CANOPIES 20UTG05 | 06/06/2022 | 19/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-110 | TT_Task | HANDRAILS AND GRATING DWGS CONNECTION FORCE REPORT 20UTG05 | 07/02/2022 | 27/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-112 | TT_Mile | (F) DETAIL DESIGN STEEL STRUCTURE WITH CONTRACTOR 20UTG05 | 28/02/2022 | 28/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-104 | TT_Task | DETAIL DESIGN STEEL STRUCTURE 20UTG05 | 20/09/2021 | 27/02/2022 | 20/09/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-102 | TT_FinMile | (MS3) STEEL STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UTG05 | 19/09/2021 | 19/09/2021 | 19/09/2021 | 19/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-114 | TT_Task | FABRICATION DESIGN/FABRICATION/TRANSPORT STEEL STRUC.20UTG05 | 28/02/2022 | 05/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-106 | TT_Task | BD - SUBMISSION APPROVAL - STEEL STRUCTURE 20UTG05 | 28/02/2022 | 28/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-108 | TT_Task | BD - CONSENT LETTER - STEEL STRUCTURE 20UTG05 | 29/04/2022 | 26/05/2022 |  |  | 80 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-136 | TT_Mile | (HS) START ERECTION STEEL STRUCTURE 20UTG06 | 09/08/2022 | 09/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-140 | TT_FinMile | (RFE) STEEL STRUCTURE 20UTG06 | 22/08/2022 | 22/08/2022 |  |  | 448 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-138 | TT_Task | ERECTION STEELWORKS CANOPIES 20UTG06 | 09/08/2022 | 22/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-130 | TT_Task | HANDRAILS AND GRATING DWGS CONNECTION FORCE REPORT 20UTG06 | 12/04/2022 | 02/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-132 | TT_Mile | (F) DETAIL DESIGN STEEL STRUCTURE WITH CONTRACTOR 20UTG06 | 03/05/2022 | 03/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-124 | TT_Task | DETAIL DESIGN STEEL STRUCTURE 20UTG06 | 30/11/2021 | 21/02/2022 | 30/11/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-122 | TT_FinMile | (MS3) STEEL STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UTG06 | 11/11/2021 | 11/11/2021 | 11/11/2021 | 11/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-134 | TT_Task | FABRICATION DESIGN/FABRICATION/TRANSPORT STEEL STRUC.20UTG06 | 03/05/2022 | 08/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-126 | TT_Task | BD - SUBMISSION APPROVAL - STEEL STRUCTURE 20UTG06 | 28/02/2022 | 28/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-128 | TT_Task | BD - CONSENT LETTER - STEEL STRUCTURE 20UTG06 | 29/04/2022 | 26/05/2022 |  |  | 592 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BAW2-87 | TT_Task | BASIC DESIGN IN-/ OUTDOOR GROUNDING | 29/06/2021 | 09/08/2021 | 29/06/2021 | 09/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--BAW2-88 | TT_Task | DETAIL DESIGN OUTDOOR GROUNDING-ATKINS | 10/08/2021 | 14/12/2021 | 10/08/2021 | 14/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA4B44 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION ELECTRICAL MODULES 20UBA7310 | 31/03/2022 | 27/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA3B78 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) ELECTRICAL MODULES 20UBA7310/30 | 30/03/2022 | 30/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA4G58 | TT_Task | TRANSPORT ELECTRICAL MODULES 20UBA7310/30 (TO SITE) | 28/04/2022 | 22/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA3G89 | TT_FinMile | (RFS) READY FOR SHIPMENT TO SITE ELECTRICAL MODULES 20UBA7310/30(TO SITE) | 27/04/2022 | 27/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA4G57 | TT_Mile | (ET4a) IC CUBICLES AT WORKSHOP READY FOR COMPONENT INSTALLATION 20UBA7310/30 | 19/11/2021 | 19/11/2021 | 19/11/2021 | 19/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20CJ-4-11 | TT_Task | TRANSPORT TO HEGELE BOP IC CABINETS FOR ELECTRICAL MODULES 20UBA7310/30-20CPC01+20CPC11 | 12/11/2021 | 17/11/2021 | 12/11/2021 | 17/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20CJ-3-53 | TT_Task | MANUFACTURING BOP IC CABINETS FOR ELECTRICAL MODULES 20UBA7310-20CPC01+20CPC11 | 31/08/2021 | 11/11/2021 | 31/08/2021 | 11/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20CJ-2-52 | TT_FinMile | (DF) GT/BOP IC CABINETS FOR ELECTRICAL MODULES 20UBA7310/20/30 | 31/08/2021 | 31/08/2021 | 31/08/2021 | 31/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20CJ-3-21 | TT_Task | DETAIL DESIGN HW ENGINEERING BOP IC CABINETS FOR ELECTRICAL MODULES 20UBA20UBA7310/30 | 26/04/2021 | 30/08/2021 | 26/04/2021 | 30/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA3-90 | TT_Task | TEST PREPARATION ASSEMBLY TEST FACILITY 20UBA7320 | 07/03/2022 | 20/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA3-91 | TT_Task | PRECOMMISSIONING TEST 20UBA7320 | 21/03/2022 | 10/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA3-92 | TT_Task | CLEANING AND PACKING TEST FACILITY 20UBA7320 | 18/04/2022 | 01/05/2022 |  |  | 10712 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA4B45 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION BATTERIES BTA (TO SITE) | 19/05/2022 | 15/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA3B79 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) BATTERIES BTA | 18/05/2022 | 18/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA4G59 | TT_Task | TRANSPORT BATTERIES BTA (TO SITE) | 19/10/2022 | 01/11/2022 |  |  | 336 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA3G90 | TT_FinMile | (RFS) READY FOR SHIPMENT TO SITE BATTERIES BTA (TO SITE) | 18/10/2022 | 18/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAA2-50 | TT_Mile | ERECTION MANUALS TO SITE BACK WASH STRAINER 20PAA11 | 10/04/2022 | 10/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAA2-15 | TT_Task | DETAIL DESIGN BACK WASH STRAINER 20PAA11 | 15/05/2021 | 24/06/2021 | 15/05/2021 | 24/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAA2-5 | TT_Task | PREPARATION RFQ BACK WASH STRAINER 20PAA11 | 15/01/2021 | 28/02/2021 | 15/01/2021 | 28/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAA2-60 | TT_FinMile | (RFS) READY FOR SHIPMENT BACK WASH STRAINER 20PAA11 | 12/03/2022 | 12/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAA2-30 | TT_FinMile | (DF) INPUT FOR MS3 BACK WASH STRAINER 20PAA11 | 15/06/2021 | 15/06/2021 | 15/06/2021 | 15/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAA2-35 | TT_FinMile | (DF) INPUT FOR M2 BACK WASH STRAINER 20PAA11 | 15/06/2021 | 15/06/2021 | 15/06/2021 | 15/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAA2-70 | TT_FinMile | (OTD-OS) ARRIVAL ON SITE BACK WASH STRAINER 20PAA11 | 07/05/2022 | 07/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAA2-65 | TT_Task | TRANSPORT TO SITEBACK WASH STRAINER 20PAA11 | 13/03/2022 | 07/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAA2-40 | TT_Task | MANUFACTURING / SHOP TEST / PACKING BACK WASH STRAINER 20PAA11 | 25/06/2021 | 09/01/2022 | 25/06/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20PAA2-20 | TT_Mile | CONTRACT INTO FORCE BACK WASH STRAINER 20PAA11 | 15/05/2021 | 15/05/2021 | 15/05/2021 | 15/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAA2-10 | TT_Task | QUOTATION STAGE BACK WASH STRAINER 20PAA11 | 01/03/2021 | 14/05/2021 | 01/03/2021 | 14/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAA2-55 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION BACK WASH STRAINER 20PAA11 | 13/02/2022 | 12/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAA2-45 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) BACK WASH STRAINER 20PAA11 | 09/01/2022 | 09/01/2022 |  |  | 272 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAA2-25 | TT_Mile | (DF) INPUT FOR VEL BACK WASH STRAINER 20PAA11 | 24/06/2021 | 24/06/2021 | 24/06/2021 | 24/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAA2-75 | TT_Task | ERECTION BACK WASH STRAINER 20PAA11 | 08/05/2022 | 04/06/2022 |  |  | 456 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BR2-20 | TT_Mile | CONTRACT INTO FORCE FREQUENCY CONVERTER 20BRx To be deleted. | 19/08/2021 | 19/08/2021 | 19/08/2021 | 19/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BR2-10 | TT_Task | QUOTATION STAGE FREQUENCY CONVERTER 20BR To be deleted. | 24/06/2021 | 18/08/2021 | 24/06/2021 | 18/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BR2-30 | TT_Task | TRANSPORT TO WORKSHOP FREQUENCY CONVERTER 20BRx (ST. INGBERT) To be deleted. | 14/06/2022 | 15/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BR2-15 | TT_Mile | RFQ FREQUENCY CONVERTER 20BRx To be deleted. | 24/06/2021 | 24/06/2021 | 24/06/2021 | 24/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BR2-5 | TT_Task | BASIC DESIGN / SPECIFICATION / PREPARE RFQ FREQUENCY CONVERTER 20BRx To be deleted. | 27/05/2021 | 23/06/2021 | 27/05/2021 | 23/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BR2-25 | TT_Task | DETAIL DESIGN /MANUFACTURING / SHOP TEST FREQUENCY CONVERTER 20BRx To be deleted. | 15/01/2022 | 13/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BR2-41 | TT_Mile | (DF) INPUT FROM PTEC AVAILABLE (PUMP SPEC/PUMP MOTOR SPEC) To be deleted. | 27/05/2021 | 27/05/2021 | 27/05/2021 | 27/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MBV2-07 | TT_Mile | ERECTION MANUALS ON SITE LUBE OIL TRANSFER SYSTEMS MBV90 | 04/07/2022 | 04/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBV2-81 | TT_Task | QUOTATION STAGE LUBE OIL TRANSFER SYSTEMS MBV90 | 09/04/2021 | 03/06/2021 | 09/04/2021 | 03/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MBV2-77 | TT_Task | BASIC DESIGN / PREP. LUBE OIL TRANSFER SYSTEMS MBV90 | 05/02/2021 | 08/04/2021 | 05/02/2021 | 08/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MBV3-27 | TT_Task | DETAIL DESIGN LUBE OIL TRANSFER SYSTEMS MBV90 | 04/06/2021 | 29/09/2021 | 04/06/2021 | 29/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MBV2-89 | TT_FinMile | (DF) INPUT FOR MS3 LUBE OIL TRANSFER SYSTEMS MBV90 | 17/06/2021 | 17/06/2021 | 17/06/2021 | 17/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MBV6-40 | TT_FinMile | (RFP) READY FOR PIPE CONNECTION CLEAN/DIRTY OIL TANK MBV90 | 28/08/2022 | 28/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBV6-15 | TT_Task | MECHANICAL ERECTION CLEAN/DIRTY OIL TANK MBV90 | 01/08/2022 | 02/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBV8-15 | TT_FinMile | (TOP-MBV90) ST CLEAN AND USED OIL TRANSFER SYSTEM MBV90 | 25/05/2023 | 25/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBV7-15 | TT_Task | ELECTRICAL ERECTION CLEAN/DIRTY OIL TANK MBV90 | 24/10/2022 | 30/10/2022 |  |  | 1656 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBV2-86 | TT_Mile | CONTRACT INTO FORCE LUBE OIL TRANSFER SYSTEMS MBV90 | 04/06/2021 | 04/06/2021 | 04/06/2021 | 04/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MBV2-67 | TT_FinMile | (DF) INPUT FOR M2 LUBE OIL TRANSFER SYSTEMS MBV90 | 17/06/2021 | 17/06/2021 | 17/06/2021 | 17/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MBV3-81 | TT_FinMile | (RFS) READY FOR SHIPMENT LUBE OIL TRANSFER SYSTEMS MBV90 | 29/05/2022 | 29/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBV4-41 | TT_FinMile | (OTD-OS) ON SITE LUBE OIL TRANSFER SYSTEMS MBV90 | 31/07/2022 | 31/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBV4-26 | TT_Task | TRANSPORT LUBE OIL TRANSFER SYSTEMS MBV90 | 30/05/2022 | 31/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBV3-82 | TT_Task | MANUFACTURING / SHOP TEST LUBE OIL TRANSFER SYSTEMS MBV90 | 13/12/2021 | 01/05/2022 | 13/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20MBV4B10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION LUBE OIL TRANSFER SYSTEMS MBV90 | 02/05/2022 | 29/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBV3B70 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) LUBE OIL TRANSFER SYSTEMS MBV90 | 01/05/2022 | 01/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBV2-90 | TT_Mile | (DF) INPUT FOR VEL LUBE OIL TRANSFER SYSTEMS MBV90 | 18/06/2021 | 18/06/2021 | 18/06/2021 | 18/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MBV6-80 | TT_FinMile | (RFP) READY FOR PIPE CONNECTION LUBE OIL TRANSFER PUMPS MBV90 | 11/09/2022 | 11/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBV6-75 | TT_Task | MECHANICAL ERECTION LUBE OIL TRANSFER PUMPS MBV90 | 29/08/2022 | 25/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBV7-20 | TT_Task | ELECTRICAL ERECTION LUBE OIL TRANSFER PUMPS MBV90 | 26/09/2022 | 23/10/2022 |  |  | 1712 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBV6-85 | TT_Task | ERECTION,NDT,PT LUBE OIL TRANSFER PIPING MBV90 | 12/09/2022 | 06/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBV7-25 | TT_Task | ELECTRICAL ERECTION LUBE OIL TRANSFER PIPING MBV90 | 24/10/2022 | 20/11/2022 |  |  | 1488 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBV8-155 | TT_Task | COLD COMMISSIONING LUBE OIL TRANSFER SYSTEM MBV90 | 26/05/2023 | 22/06/2023 |  |  | 64 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--SG-2-95 | TT_Mile | FINAL EXPLOSION PROTECTION CONCEPT ESCAPE ROUTE AND FIRE PROTECTION DWGS AVAILABLE | 04/07/2021 | 04/07/2021 | 04/07/2021 | 04/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--SG-2-96 | TT_Task | EXPLOSION PROTECTION CONCEPT FOR CLIENT REVIEW | 20/03/2021 | 13/04/2021 | 20/03/2021 | 13/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--SG-2-97 | TT_Task | UPDATED EXPLOSION PROTECTION CONCEPT AFTER ALIGNMENT WITH CLIENT | 14/04/2021 | 20/04/2021 | 14/04/2021 | 20/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--SG-2-102 | TT_Task | PREPARATION OF FIRE PROTECTION CONCEPT FOR SUBMISSION TO BD | 15/01/2021 | 04/02/2021 | 15/01/2021 | 04/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--SG-2-103 | TT_Task | PREPARATION OF EXPLOSION PROTECTION CONCEPT FOR SUBMISSION TO BD | 15/01/2021 | 19/03/2021 | 15/01/2021 | 19/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--SG-2-104 | TT_Task | BD - SUBMISSON APPROVAL - FIRE PROTECTION CONCEPT | 05/02/2021 | 05/04/2021 | 05/02/2021 | 05/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--SG-2-106 | TT_Task | UPDATE OF FIRE PROTECTION CONCEPT AFTER BD ALIGNMENT | 06/04/2021 | 19/04/2021 | 06/04/2021 | 19/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BAT3-81 | TT_FinMile | (OTD-OS) ON SITE MAIN TRANSFORMERS 20BAT | 12/08/2022 | 12/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAT4B11 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION TRANSFORMER OIL FOR 20BAT | 06/07/2022 | 02/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAT3B71 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) TRANSFORMER OIL FOR 20BAT | 05/07/2022 | 05/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAT3-82 | TT_FinMile | (RFS) READY FOR SHIPMENT TRANSFORMER OIL FOR 20BAT | 02/08/2022 | 02/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAT4-26 | TT_Task | TRANSPORT TRANSFORMER OIL FOR 20BAT | 03/08/2022 | 01/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAT3-83 | TT_FinMile | (OTD-OS) ON SITE TRANSFORMER OIL FOR 20BAT | 01/09/2022 | 01/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAT7-16 | TT_Mile | TRANSFORMER READY FOR OIL FILLING 20BAT | 02/09/2022 | 02/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAT7-17 | TT_Task | OIL FILLING GENERATOR TRANSFORMER 20BAT | 02/09/2022 | 08/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--5552-91 | TT_Mile | KICK OFF MEETING STEELWORK CLADDING | 28/05/2021 | 28/05/2021 | 28/05/2021 | 28/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--5552-89 | TT_Task | PREPARATION KICK OFF STEELWORK CLADDING | 14/05/2021 | 27/05/2021 | 14/05/2021 | 27/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--5552-90 | TT_Mile | CONTRACT INTO FORCE STEELWORK CLADDING | 14/05/2021 | 14/05/2021 | 14/05/2021 | 14/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--5552-87 | TT_Task | QUOTATION STAGE STEELWORK CLADDING | 29/01/2021 | 13/05/2021 | 29/01/2021 | 13/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--5552-93 | TT_Task | PREPARATION RFQ PAB PIPING SUPPLY | 15/01/2021 | 29/01/2021 | 15/01/2021 | 29/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--5552-95 | TT_Mile | CONTRACT INTO FORCE PAB PIPING SUPPLY | 15/03/2021 | 15/03/2021 | 15/03/2021 | 15/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--5552-92 | TT_Task | QUOTATION STAGE PAB PIPING SUPPLY | 30/01/2021 | 14/03/2021 | 30/01/2021 | 14/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--5552-102 | TT_Task | PREPARATION KICK OFF SITE INFRASTRUCTURE | 14/04/2021 | 27/04/2021 | 14/04/2021 | 27/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--5552-103 | TT_Mile | CONTRACT INTO FORCE SITE INFRASTRUCTURE | 14/04/2021 | 14/04/2021 | 14/04/2021 | 14/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--5552-101 | TT_Task | QUOTATION STAGE SITE INFRASTRUCTURE | 29/01/2021 | 13/04/2021 | 29/01/2021 | 13/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UZx-42 | TT_Task | BASIC BUILDING DESIGN TEMPORARY BUILDINGS 20UZx | 19/03/2021 | 20/04/2021 | 19/03/2021 | 20/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UZx5-49 | TT_FinMile | (RFE) TEMPORARY BUILDINGS 20UZx | 03/12/2021 | 03/12/2021 | 03/12/2021 | 03/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UZx5-46 | TT_Task | FABRICATION TEMPORARY BUILDINGS 20UZx | 20/06/2021 | 28/11/2021 | 20/06/2021 | 28/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UZx2-43 | TT_Task | DETAIL DESIGN TEMPORARY BUILDINGS (by subcontractor) 20UZx | 14/05/2021 | 30/05/2021 | 14/05/2021 | 30/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UZx2-46 | TT_Task | BD - SUBMISSION APPROVAL - TEMPORARY BUILDINGS 20UZx | 21/04/2021 | 19/06/2021 | 21/04/2021 | 19/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UZx2-47 | TT_Task | BD - CONSENT LETTER - TEMPORARY BUILDINGS 20UZx | 20/06/2021 | 17/07/2021 | 20/06/2021 | 17/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20HA-6A49 | TT_Task | INSULATION HRSG / PIPES HRSG20 AFTER CHEMICAL CLEANING | 03/06/2023 | 30/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MA-3-84 | TT_Task | MANUFACTURING MAL VALVES FOR SKIDDER | 26/05/2021 | 21/12/2021 | 26/05/2021 | 21/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MKF6A16 | TT_Task | PIPING ERECTION GENERATOR STATOR WATER SYSTEM 20MKF | 04/11/2022 | 19/01/2023 |  |  | 760 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKF6-16 | TT_Task | ERECTION GENERATOR STATOR WATER SYSTEM 20MKF | 25/09/2022 | 08/10/2022 |  |  | 208 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7-26 | TT_Mile | PRECONDITION FOR CABLE TRAY ACTIVITIES AVAILABLE | 14/04/2022 | 14/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MB-6-58 | TT_Task | FINAL INSPECTIONS CLOSING OF OPEN ITEMS BEFORE COMMISSIONING GT20 MB | 19/02/2023 | 01/04/2023 |  |  | 200 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6-66 | TT_Task | FINAL INSPECTIONS CLOSING OF OPEN ITEMS BEFORE COMMISSIONING MA | 06/03/2023 | 01/04/2023 |  |  | 128 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA7-29 | TT_Task | INSTALLATION ELECTRICAL MODULES 20UBA7110/7210/7410 | 01/07/2022 | 21/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA7-30 | TT_Task | CABLING INTERNAL 20UBA7110/7210/7410 - PART OF ELECTRICAL MODULES ASSEMBLY | 09/09/2022 | 22/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA7-28 | TT_Task | PLACING 20UBA7110/7210/7410 | 24/06/2022 | 24/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA7-32 | TT_Task | INSTALLATION ELECTRICAL MODULES 20UBA7310/30 | 08/07/2022 | 28/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA7-33 | TT_Task | CABLING INTERNAL 20UBA7310/30 - PART OF ELECTRICAL MODULES ASSEMBLY | 16/09/2022 | 29/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA7-31 | TT_Task | PLACING 20UBA7310/30 | 25/06/2022 | 25/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA7-35 | TT_Task | INSTALLATION ELECTRICAL MODULES 20UBA7610/20 | 15/07/2022 | 04/08/2022 |  |  | 112 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA7-36 | TT_Task | CABLING INTERNAL 20UBA7610/20 - PART OF ELECTRICAL MODULES ASSEMBLY | 23/09/2022 | 13/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA7-34 | TT_Task | PLACING 20UBA7610/20 | 27/06/2022 | 27/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7-174 | TT_Task | ERECTION CABLE TRAYS ON 20UEY04/05 | 28/05/2022 | 06/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BFT7-16 | TT_Task | PLACING LV-TRANSFORMERS 20BFT01/02 | 28/06/2022 | 28/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-----8-8 | TT_FinMile | MV AVAILABLE (BACK ENERGISING 400kV) | 10/04/2023 | 10/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20CFE8-36 | TT_Task | COMMISSIONING CONTINIOUS EMISSION MONITORING SYSTEM (1) HRSG20 | 16/06/2023 | 22/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAG6-63 | TT_Task | ASSEMBLY AND WELDING OF CONDENSATE DRAIN TANK MAG | 20/05/2022 | 23/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAG6-65 | TT_Mile | CONDENSER READY FOR PRE_ASSEMBLING MAG/LDK/LCA-PIPING | 11/06/2022 | 11/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK3-81 | TT_Task | MANUFACTURING / SHOP TEST IC CABLES BZK (LOT 1) | 02/12/2021 | 19/04/2022 | 02/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20BZK3-83 | TT_FinMile | (RFS) READY FOR SHIPMENT IC CABLES BZK (LOT 1) | 17/05/2022 | 17/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK4-44 | TT_Task | TRANSPORT IC CABLES BZK (LOT 1) | 18/05/2022 | 12/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK4-45 | TT_FinMile | (OTD-OS) ON SITE IC CABLES BZK (LOT 1) | 16/07/2022 | 16/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BZK2-91 | TT_Task | QUOTATION IC CABLES BZK | 23/09/2021 | 01/12/2021 | 23/09/2021 | 01/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--BZK2-92 | TT_Mile | RFQ IC CABLES BZK | 23/09/2021 | 23/09/2021 | 23/09/2021 | 23/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--BZK2-93 | TT_Mile | CONTRACT INTO FORCE IC CABLES BZK (LOT 1) | 02/12/2021 | 02/12/2021 | 02/12/2021 | 02/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--BZK2-90 | TT_Task | BASIC DESIGN / SPECIFICATION IC CABLES BZK | 26/08/2021 | 22/09/2021 | 26/08/2021 | 22/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BZK4-43 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION IC CABLES BZK (LOT 1) | 20/04/2022 | 17/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK3-82 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) IC CABLES BZK (LOT 1) | 19/04/2022 | 19/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P2I-16 | TT_Mile | ERECTION MANUALS ON SITE - INSULATION FOR ALL SYSTEMS | 27/06/2022 | 27/06/2022 |  |  | 448 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P2I-1 | TT_Task | PREPARE RFQ INSULATION FOR ALL SYSTEMS | 31/08/2021 | 11/10/2021 | 31/08/2021 | 11/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P2I-13 | TT_FinMile | (RFS) READY FOR SHIPMENT INSULATION FOR ALL SYSTEMS | 07/08/2022 | 07/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P2I-5 | TT_Mile | CONTRACT INTO FORCE INSULATION FOR ALL SYSTEMS | 05/02/2022 | 05/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P2I-4 | TT_Task | QUOTATION STAGE INSULATION FOR ALL SYSTEMS | 11/12/2021 | 04/02/2022 | 11/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI-P2I-6 | TT_Task | MANUFACTURING / SHOP TEST INSULATION FOR ALL SYSTEMS | 05/02/2022 | 10/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P2I-15 | TT_FinMile | (OTD-OS) ARRIIVAL ON SITE INSULATION FOR ALL SYSTEMS | 02/10/2022 | 02/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P2I-14 | TT_Task | TRANSPORT TO SITE INSULATION FOR ALL SYSTEMS | 08/08/2022 | 02/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P2I-12 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION INSULATION FOR ALL SYSTEMS | 11/07/2022 | 07/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P2I-11 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) INSULATION FOR ALL SYSTEMS | 10/07/2022 | 10/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK3-84 | TT_Task | MANUFACTURING / SHOP TEST IC CABLES BZK (LOT 2) | 26/03/2022 | 02/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK3-86 | TT_FinMile | (RFS) READY FOR SHIPMENT IC CABLES BZK (LOT 2) | 30/08/2022 | 30/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK4-47 | TT_Task | TRANSPORT IC CABLES BZK (LOT 2) | 31/08/2022 | 25/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK4-48 | TT_FinMile | (OTD-OS) ON SITE IC CABLES BZK (LOT 2) | 25/10/2022 | 25/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK4-46 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION IC CABLES BZK (LOT 2) | 03/08/2022 | 30/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK3-85 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) IC CABLES BZK (LOT 2) | 02/08/2022 | 02/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20CHY3-26 | TT_Task | MANUFACTURING / SHOP TEST HRSG PROTECTION CABINET FOR PRECOM TEST-20CJF01 | 09/09/2021 | 01/02/2022 | 09/09/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20CHY4-11 | TT_Task | TRANSPORT TO TESTING FACILITY HRSG PROTECTION CABINET (PRECOMMISSIONING TEST)-20CJF01 | 02/02/2022 | 07/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZL8B27 | TT_Task | COMMISSIONING LIGHTING/SMALL POWER INSIDE 20UMC | 18/04/2023 | 24/04/2023 |  |  | 464 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZL7F16 | TT_Task | LIGHTING AND SMALL POWER INSTALLATION IN ENCLOSURE 20UMC | 22/09/2022 | 05/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ5-76 | TT_FinMile | (RFE) FOUNDATION 20UBZ05 | 19/06/2022 | 19/06/2022 |  |  | 1344 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ5-73 | TT_Task | WORK PREPARATION, EXCAVATION 20UBZ05 | 12/05/2022 | 18/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ5-75 | TT_Mile | (H) START PLACING FORMWORK 20UBZ05 | 19/05/2022 | 19/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ2-92 | TT_Task | PREPARATION FOUNDATION GROUNDING DWGS 20UBZ05 | 03/08/2021 | 16/08/2021 | 03/08/2021 | 16/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ2-90 | TT_Task | BASIC BUILDING DESIGN INCL. 3D MODEL 20UBZ05 | 06/06/2021 | 02/07/2021 | 06/06/2021 | 02/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ2-89 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UBZ05 | 05/06/2021 | 05/06/2021 | 05/06/2021 | 05/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ2-96 | TT_FinMile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION 20UBZ05 | 11/05/2022 | 11/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ2-91 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE 20UBZ05 | 03/07/2021 | 16/08/2021 | 03/07/2021 | 16/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ2-93 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN CONCRETE - 20UBZ05 | 17/08/2021 | 10/09/2021 | 17/08/2021 | 10/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ2-94 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE - 20UBZ05 | 04/01/2022 | 04/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ2-95 | TT_Task | BD - CONSENT LETTER - DESIGN 20UBZ05 | 05/03/2022 | 01/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBR6-49 | TT_Task | INSTALLATION CABLE TRAYS DIFFUSER 20MBR | 06/10/2022 | 19/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAB2-9 | TT_Mile | ERECTION MANUALS ON SITE CT / GROUNDING CUBICLE 20BAB | 24/07/2022 | 24/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAB2-10 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION CT / GROUNDING CUBICLE 20BAB | 30/04/2022 | 27/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAB2-8 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) CT / GROUNDING CUBICLE 20BAB | 29/04/2022 | 29/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAB2-2 | TT_Task | QUOTATION STAGE CT / GROUNDING CUBICLE 20BAB | 01/07/2021 | 15/07/2021 | 01/07/2021 | 15/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BAB2-3 | TT_Mile | RFQ CT / GROUNDING CUBICLE 20BAB | 01/07/2021 | 01/07/2021 | 01/07/2021 | 01/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BAB2-1 | TT_Task | BASIC DESIGN / SPECIFICATION CT / GROUNDING CUBICLE 20BAB | 17/02/2021 | 30/06/2021 | 17/02/2021 | 30/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BAB2-5 | TT_Mile | CONTRACT INTO FORCE CT / GROUNDING CUBICLE 20BAB | 16/07/2021 | 16/07/2021 | 16/07/2021 | 16/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BAB2-7 | TT_FinMile | (DF) INPUT FOR MS3 CT / GROUNDING CUBICLE 20BAB | 16/07/2021 | 16/07/2021 | 16/07/2021 | 16/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BAB2-11 | TT_FinMile | (RFS) READY FOR SHIPMENT CT / GROUNDING CUBICLE 20BAB | 27/05/2022 | 27/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAB2-4 | TT_Mile | FINAL INPUT DWGS AVAILABLE CT / GROUNDING CUBICLE 20BAB | 16/07/2021 | 16/07/2021 | 16/07/2021 | 16/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BAB2-6 | TT_Task | DESIGN / MANUFACTURING CT / GROUNDING CUBICLE 20BAB | 14/05/2021 | 13/04/2022 | 14/05/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--9998-23 | TT_Mile | START COLD COMMISSIONING CW SYSTEMS | 31/03/2023 | 31/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20M--7A16 | TT_Task | ELECTRICAL ERECTION FOR MKC02 | 05/08/2022 | 18/08/2022 |  |  | 1656 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAC7-16 | TT_Task | ERECTION GEN. CIRCUIT BREAKER 20BAC | 09/09/2022 | 15/09/2022 |  |  | 256 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKC8-76 | TT_Mile | ENERGISATION SFC/SEE TRANSFORMER 20MKC02 | 19/04/2023 | 19/04/2023 |  |  | 360 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20M--8-66 | TT_Task | COLD COMMISSIONING SFC TRANSFORMER 20MKC02 | 12/04/2023 | 18/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20ACA7-71 | TT_Task | TESTING GIL BEFORE HV CABLE CONNECTION 400kV 20ACA | 21/11/2022 | 04/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK7-180 | TT_Task | ERECTION CABLING 20UBA1110/20 TO HRSG (AFTER ELECTRICAL MODULES INSTALLATION) | 22/12/2022 | 22/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA4B46 | TT_FinMile | (OTD-OS) ON SITE (ET4d) 20UBA7110/7210/7410 | 22/06/2022 | 22/06/2022 |  |  | 8 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA4B47 | TT_FinMile | (OTD-OS) ON SITE (ET4d) ELECTRICAL MODULES 20UBA7310/30 | 22/06/2022 | 22/06/2022 |  |  | 16 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA4B48 | TT_FinMile | (OTD-OS) ON SITE (ET4d) ELECTRICAL MODULES 20UBA7610/20 | 26/06/2022 | 26/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2K2 | TT_Mile | E-AND IC- MANUALS FOR COMP. INSTALL. AVAILABLE ELECTRICAL MODULES 01UBA9010/20 | 27/12/2021 | 27/12/2021 | 27/12/2021 | 27/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2K3 | TT_Mile | E-AND IC- MANUALS FOR COMP. INSTALL. AVAILABLE ELECTRICAL MODULES 20UBA7910/20 | 27/01/2022 | 27/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20ACA7-81 | TT_Task | DEGASING OF GIL FOR CABLE CONNECTION COMPARTMENT | 16/01/2023 | 17/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
CL20ACA7-82 | TT_Task | HV CABLE CONNECTION BY CUSTOMER | 18/01/2023 | 07/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20ACA7-83 | TT_Task | SF6 GASING FOR HV CABLE TESTING | 08/02/2023 | 09/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20ACA7-84 | TT_Task | DEGASING OF GIL - INSTALL LINKS BETWEEN CABLE TO GIL CONDUCTOR | 10/02/2023 | 23/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20ACA7-85 | TT_Task | GASING OF CABLE CONNECTION COMPARTMENT | 24/02/2023 | 25/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20ACA7-86 | TT_Task | FLANGE LEAKAGE TEST GIL | 26/02/2023 | 27/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--L--2-81 | TT_Task | SYSTEM DESCRIPTION L-SYSTEMS | 30/01/2021 | 28/02/2021 | 30/01/2021 | 28/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--P--2-81 | TT_Task | SYSTEM DESCRIPTION P-SYSTEMS | 26/01/2021 | 01/03/2021 | 26/01/2021 | 01/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--G--2-89 | TT_Task | SYSTEM DESCRIPTION G-SYSTEMS | 29/01/2021 | 27/02/2021 | 29/01/2021 | 27/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMY6M72 | TT_Task | PLACING AND ALIGNMENT OF MODULE - ULY UMY00K | 20/05/2022 | 21/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMY6M74 | TT_Task | ERECTION TOWER UMY STEEL STRUCTURE | 27/04/2022 | 01/05/2022 |  |  | 160 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMY6M73 | TT_Task | PRE-ASSEMBLY TOWER UMY STEEL STRUCTURE | 22/04/2022 | 26/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20B--8-51 | TT_Task | COMMISSIONING ELECTRICAL MODULES 20UBA1110/20 | 11/04/2023 | 24/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-3D5 | TT_Task | DETAIL DESIGN, MANUFACTURING, SHOP TEST HRSG REMAINING MATERIAL | 27/05/2021 | 02/03/2022 | 27/05/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20HA-4D15 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION - HRSG REMAINING MATERIAL | 03/03/2022 | 30/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-4D10 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) - HRSG REMAINING MATERIAL | 02/03/2022 | 02/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-4D30 | TT_FinMile | (OTD-OS) ON SITE HRSG REMAINING MATERIAL | 29/04/2022 | 29/04/2022 |  |  | 1720 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-4D35 | TT_Task | TRANSPORT HRSG REMAINING MATERIAL | 31/03/2022 | 29/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-180 | TT_Mile | ACCESS TO CONTROL ROOM IN D1 REQUIRED | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK7B33 | TT_Task | INTERCONNECTING CABLING WITH D1 (LBG/LDK) | 15/11/2022 | 20/03/2023 |  |  | 168 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-3D81 | TT_Task | DETAIL DESIGN, MANUFACTURING INSULATION MATERIAL HRSG20 (OUTLET DUCT SEALING AREAS STACK) | 26/10/2021 | 31/01/2022 | 26/10/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20HA-4D42 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION - INSULATION MATERIAL HRSG20 (OUTLET DUCT SEALING AREAS STACK) | 15/04/2022 | 12/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-4D41 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) - INSULATION MATERIAL HRSG20 (OUTLET DUCT SEALING AREAS STACK) | 14/04/2022 | 14/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-4D44 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION - INSULATION MATERIAL HRSG20 (PIPES, DRUMS, VESSELS) | 26/11/2022 | 23/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-4D43 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) INSULATION MATERIAL HRSG20 (PIPES, DRUMS, VESSELS) | 25/11/2022 | 25/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-3D82 | TT_Task | DETAIL DESIGN, MANUFACTURING INSULATION MATERIAL HRSG20 (PIPES, DRUMS, VESSELS) | 20/08/2022 | 25/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA8G28 | TT_Task | CHARGING BATTERIES | 14/02/2023 | 16/02/2023 |  |  | 32 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BBA8-37 | TT_Task | FEEDER COMMISSIONING MV SWITCHGEAR 20BBA | 29/03/2023 | 16/05/2023 |  |  | 104 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BBA8-36 | TT_Task | COMMISSIONING MV SWITCHGEAR 20BBA | 21/02/2023 | 06/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BFT8-77 | TT_Mile | ENERGISING LV-TRANSFORMERS 20BFT02 | 12/04/2023 | 12/04/2023 |  |  | 48 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BFT8-76 | TT_Task | COMMISSIONING LV-TRANSFORMERS 20BFT02 | 28/03/2023 | 10/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA3-94 | TT_Task | ELECTRICAL MODULES 20UBA7320 FAT WITH CLIENT | 11/04/2022 | 17/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7-181 | TT_Task | ERECTION CABLE TRAYS ON 20UEZ01 | 07/06/2022 | 20/06/2022 |  |  | 1112 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7-182 | TT_Task | ERECTION CABLE TRAYS ON 20ULZ02 | 29/07/2022 | 11/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK7F27 | TT_Task | CABLING TO GENERATOR 20MKA | 13/10/2022 | 09/11/2022 |  |  | 1328 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7-183 | TT_Task | ERECTION CABLE TRAYS FOR GENERATOR AREA 20MKA | 10/09/2022 | 30/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK7A34 | TT_Task | CABLING GT TO AIR INTAKE 20MBL | 11/12/2022 | 17/12/2022 |  |  | 1040 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK7F28 | TT_Task | CABLING GT TO EMERGENCY DIESEL | 22/10/2022 | 04/11/2022 |  |  | 1624 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEX2-106 | TT_FinMile | (RFE) ROOF 20UEX01 | 20/08/2022 | 20/08/2022 |  |  | 120 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7-184 | TT_Task | ERECTION CABLE TRAYS ON 20UBZ04 | 03/08/2022 | 16/08/2022 |  |  | 528 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7-185 | TT_Task | ERECTION CABLE TRAYS 20UMC ST TO LDK | 17/09/2022 | 30/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20C--7L16 | TT_Task | ERECTION JUNCTION BOXES / INSTRUMENTATION | 17/09/2022 | 28/10/2022 |  |  | 240 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7-186 | TT_Task | ERECTION JUNCTION BOXES INSTRUMENTATION HRSG20 | 16/06/2022 | 03/08/2022 |  |  | 656 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK7-187 | TT_Task | ERECTION CABLING HRSG TO CCR | 25/10/2022 | 14/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7-189 | TT_Task | ERECTION JUNCTION BOXES INSTRUMENTATION IN ULA | 20/08/2022 | 16/09/2022 |  |  | 304 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZL7A18 | TT_Task | LIGHTING AND SMALL POWER INSTALLATION 01UBA9010/20 | 16/08/2022 | 29/08/2022 |  |  | 1448 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZL7A19 | TT_Task | LIGHTING AND SMALL POWER INSTALLATION 20UBA1110/20 | 08/12/2022 | 21/12/2022 |  |  | 880 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKC8-77 | TT_Mile | ENERGISATION START UP TRANSFORMER 20MBJ01 | 12/04/2023 | 12/04/2023 |  |  | 160 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20M--8-68 | TT_Task | COLD COMMISSIONING START UP TRANSFORMER 20MBJ01 | 14/03/2023 | 20/03/2023 |  |  | 168 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7-191 | TT_Task | ERECTION CABLE TRAYS ON 20UBZ03 | 27/08/2022 | 05/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA7L16 | TT_Task | CABLING INTERNAL ELECTRICAL MODULES 20UBA1110/20 - BFT | 08/12/2022 | 21/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA7-105 | TT_Task | CABLING INTERNAL ELECTRICAL MODULES 20UBA8110/20 - BFT | 08/12/2022 | 21/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA7C-32 | TT_Task | CABLING INTERNAL ELECTRICAL MODULES 01UBA9010/20 - PART OF ELECTRICAL MODULES ASSEMBLY | 26/07/2022 | 08/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD7-36 | TT_Task | E - AND IC CABLING COOLING TOWER FIRST 4 CELLS 20PAD INCL. RISER | 23/03/2023 | 19/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK7E26 | TT_Task | CABLING MODULES IN UMC BUILDING | 11/12/2022 | 07/01/2023 |  |  | 800 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAW5C24 | TT_Task | ERECTION INDOOR EARTHING 20URD | 19/06/2022 | 13/08/2022 |  |  | 2584 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BFT4-27 | TT_Mile | ERECTION MANUALS ON SITE SEE/SFC-TRANSFORMERS 20MKC / 20MBJ | 28/05/2022 | 28/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BBT2-46 | TT_Mile | ERECTION MANUALS ON SITE AUX. TRANSFORMER 20BBT | 16/07/2022 | 16/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BBT2-47 | TT_Mile | ERECTION MANUALS ON SITE SUMP PUMPS GM FOR UBF | 10/06/2022 | 10/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20CFE2-90 | TT_Mile | ERECTION MANUALS ON SITE EMISSION MONITORING SYSTEM CFE | 02/06/2022 | 02/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---3M106 | TT_FinMile | ERECTION MANUALS ON SITE MODULE 20UPY00Y | 16/07/2022 | 16/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---3M107 | TT_FinMile | ERECTION MANUALS ON SITE MODULE 20MAG50Y | 19/02/2022 | 19/02/2022 |  |  | 304 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---3M108 | TT_FinMile | ERECTION MANUALS ON SITE MODULE 20MAL00YC | 22/03/2022 | 22/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---3M109 | TT_FinMile | ERECTION MANUALS ON SITE MODULE 20MAW10Y | 25/03/2022 | 25/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---3M110 | TT_FinMile | ERECTION MANUALS ON SITE MODULE 20MAW50Y | 08/04/2022 | 08/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---3M111 | TT_FinMile | ERECTION MANUALS ON SITE MODULE 20UMCM1Y | 12/04/2022 | 12/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---3M112 | TT_FinMile | ERECTION MANUALS ON SITE MODULE 20UMCL1Y | 12/04/2022 | 12/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LDK2B91 | TT_Mile | ERECTION MANUALS ON SITE MODULE 20LDK00Y | 15/03/2022 | 15/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PGB2B92 | TT_Mile | ERECTION MANUALS ON SITE MODULE 20PGB10Y | 17/04/2022 | 17/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---3M113 | TT_FinMile | ERECTION MANUALS ON SITE MODULE 20PGB20Y | 12/04/2022 | 12/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---3M114 | TT_FinMile | ERECTION MANUALS ON SITE MODULE 20PCB10Y | 21/05/2022 | 21/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---3M115 | TT_FinMile | ERECTION MANUALS ON SITE MODULE 20LAC10Y | 10/05/2022 | 10/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---3M116 | TT_FinMile | ERECTION MANUALS ON SITE MODULE 20LAC10Y | 12/04/2022 | 12/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK7B34 | TT_Task | INSTALLATION OF IC CABINETS | 04/08/2022 | 10/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK7B35 | TT_Task | INSTALLATION OF CCR EQUIPMENT | 11/08/2022 | 17/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK7B36 | TT_Task | INSTALLATION OF NEW MIMIC PANELS | 30/07/2022 | 03/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBY5-61 | TT_Task | SUPPORT INSTALLATION IN RAISED FLOOR | 28/06/2022 | 07/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK7B37 | TT_Task | RELOCATION OF TABLES | 08/07/2022 | 17/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK7B38 | TT_Task | SHIFTING OF BOARDS AND MIMICS | 18/07/2022 | 22/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK7B39 | TT_Task | INSTALLATION OF NEW TABLES | 23/07/2022 | 29/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBY5-62 | TT_Task | CORE DRILLING WITHIN 10UCA | 18/08/2022 | 31/08/2022 |  |  | 120 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7B40 | TT_Task | INSTALLATION OF CABLE TRAYS FOR EXTERNAL CONNECTION IN CONTROL BUILDING UCA | 28/07/2022 | 17/08/2022 |  |  | 232 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK7B41 | TT_Task | CABLING FROM 00UCA TO D2 STATION | 26/10/2022 | 29/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK7B42 | TT_Task | CABLING FROM 00UCA TO 400kV SUBSTATION | 30/11/2022 | 27/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBY5-63 | TT_Task | FIRE BARRIER SEALING | 28/12/2022 | 10/01/2023 |  |  | 720 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK7B43 | TT_Task | RELOCATION C4 | 15/04/2021 | 22/04/2021 | 15/04/2021 | 22/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BZK7B44 | TT_Task | RELOCATION C1 | 06/12/2021 | 10/12/2021 | 06/12/2021 | 10/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BZK7B45 | TT_Task | RELOCATION C2 / C3 | 01/02/2022 | 10/02/2022 |  |  | 3392 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD6-30 | TT_Task | MOBILISATION / MATERIAL UNLOADING | 11/08/2022 | 24/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD6-31 | TT_Task | FILL PACK GLUEING FIRST 4 CELLS | 25/08/2022 | 12/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD6-32 | TT_Task | DISTRIBUTION LATERAL PIPES FIRST 4 CELLS | 13/10/2022 | 16/11/2022 |  |  | 168 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD6-33 | TT_Task | DRIFT ELIMINATION ASSEMBLY FIRST 4 CELLS | 13/10/2022 | 16/11/2022 |  |  | 168 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD6-34 | TT_Task | INSTALLATION FILL PACKS SUPPORT FIRST 4 CELLS | 29/09/2022 | 19/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD6-35 | TT_Task | AUXILIARY FRP STUCTURE INSTALLATION FIRST 4 CELLS | 25/08/2022 | 28/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD6-36 | TT_Task | INSTALLATION OF FILL PACKS FIRST 4 CELLS | 20/10/2022 | 07/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD6-37 | TT_Task | INSTALLATION OF DISTRIBUTION SYSTEM FIRST 4 CELLS | 08/12/2022 | 25/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD6-38 | TT_Task | INSTALLATION OF SOUND ABBATMENT SYSTEM FIRST 4 CELLS | 20/10/2022 | 23/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD6-39 | TT_Task | INSTALLATION OF SUPPORT AND DRIFT ELIMINATOR FIRST 4 CELLS | 26/01/2023 | 01/03/2023 |  |  | 616 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD6-40 | TT_Task | INSTALLATION OF AIR MIX SYSTEM FIRST 4 CELLS | 08/12/2022 | 25/01/2023 |  |  | 896 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD6-41 | TT_Task | INSTALLATION OF INTERNAL WALKWAY FIRST 4 CELLS | 08/12/2022 | 04/01/2023 |  |  | 1064 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD6-42 | TT_Task | INSTALLATION OF MECHANICAL GROUP FIRST 4 CELLS | 26/01/2023 | 22/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD6-43 | TT_Task | INSTALLATION OF FAN STACK FIRST 4 CELLS | 16/02/2023 | 22/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD6-44 | TT_Task | INSTALLATION OF COIL BUNDLES AND SEALING FIRST 4 CELLS | 24/11/2022 | 21/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD6-45 | TT_Task | INSTALLATION OF VACUUM PIPE LINE FIRST 4 CELLS | 07/01/2023 | 10/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD6-46 | TT_Task | INSTALLATION OF VACUUM SKID FIRST 4 CELLS | 26/12/2022 | 27/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD6-47 | TT_Task | INSTALLATION OF DUMPERS WITH ACTUATORS FIRST 4 CELLS | 22/12/2022 | 11/01/2023 |  |  | 1008 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD6-48 | TT_Task | INSTALLATION OF PIPING DRY AREA FIRST 4 CELLS | 11/02/2023 | 17/03/2023 |  |  | 488 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD6-51 | TT_Task | FILL PACK GLUEING LAST 4 CELLS | 25/09/2022 | 12/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD6-55 | TT_Task | DISTRIBUTION LATERAL PIPES LAST 4 CELLS | 13/11/2022 | 17/12/2022 |  |  | 168 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD6-56 | TT_Task | DRIFT ELIMINATION ASSEMBLY LAST 4 CELLS | 13/11/2022 | 17/12/2022 |  |  | 168 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD6-54 | TT_Task | INSTALLATION FILL PACKS SUPPORT LAST 4 CELLS | 30/10/2022 | 19/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD6-52 | TT_Task | AUXILIARY FRP STUCTURE INSTALLATION LAST 4 CELLS | 25/09/2022 | 29/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD6-57 | TT_Task | INSTALLATION OF FILL PACKS LAST 4 CELLS | 20/11/2022 | 07/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD6-61 | TT_Task | INSTALLATION OF DISTRIBUTION SYSTEM LAST 4 CELLS | 08/01/2023 | 25/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD6-58 | TT_Task | INSTALLATION OF SOUND ABBATMENT SYSTEM LAST 4 CELLS | 20/11/2022 | 24/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD6-67 | TT_Task | INSTALLATION OF SUPPORT AND DRIFT ELIMINATOR LAST 4 CELLS | 26/02/2023 | 01/04/2023 |  |  | 368 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD6-62 | TT_Task | INSTALLATION OF AIR MIX SYSTEM LAST 4 CELLS | 08/01/2023 | 25/02/2023 |  |  | 648 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD6-63 | TT_Task | INSTALLATION OF INTERNAL WALKWAY LAST 4 CELLS | 08/01/2023 | 04/02/2023 |  |  | 816 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD6-68 | TT_Task | INSTALLATION OF MECHANICAL GROUP LAST 4 CELLS | 26/02/2023 | 25/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD6-69 | TT_Task | INSTALLATION OF FAN STACK LAST 4 CELLS | 19/03/2023 | 22/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD6-59 | TT_Task | INSTALLATION OF COIL BUNDLES AND SEALING LAST 4 CELLS | 25/12/2022 | 21/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD6-64 | TT_Task | INSTALLATION OF VACUUM PIPE LINE LAST 4 CELLS | 22/01/2023 | 25/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD6-65 | TT_Task | INSTALLATION OF DUMPERS WITH ACTUATORS LAST 4 CELLS | 22/01/2023 | 11/02/2023 |  |  | 760 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD6-66 | TT_Task | INSTALLATION OF PIPING DRY AREA LAST 4 CELLS | 26/02/2023 | 01/04/2023 |  |  | 368 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--B--2-93 | TT_Mile | 100% CABLE PULLING DATA TRANSFER TO SITE | 31/01/2022 | 31/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---3B93 | TT_FinMile | DELIVERY OF MAW/MAL VALVES (WELDING) FOR SHIPMENT LOT 1 | 31/12/2021 | 31/12/2021 |  |  | 224 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5E48 | TT_FinMile | (RFE) ERECTION CEP AND LDK PIT PLATFORM IN 20UMC | 30/05/2022 | 30/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5E47 | TT_Task | ERECTION CEP AND LDK PIT PLATFORM IN 20UMC | 03/05/2022 | 30/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5E50 | TT_FinMile | (RFE) GENERATOR PLATFORM @5.44m IN 20UMC | 30/07/2022 | 30/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5E49 | TT_Task | ERECTION GENERATOR PLATFORM @5.44m IN 20UMC | 26/06/2022 | 30/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5E52 | TT_FinMile | (RFE) GENERATOR MISC. AND INTERMEDIATE SHAFT PLATFORM @5.87M IN 20UMC | 11/04/2022 | 11/04/2022 |  |  | 72 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5E51 | TT_Task | ERECTION GENERATOR MISC. AND INTERMEDIATE SHAFT PLATFORM @5.87M IN 20UMC | 15/03/2022 | 11/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5E54 | TT_FinMile | (RFE) GENERATOR MISC. PLATFORM 2 @6.56m IN 20UMC | 23/05/2022 | 23/05/2022 |  |  | 464 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5E53 | TT_Task | ERECTION GENERATOR MISC. PLATFORM 2 @6.56m IN 20UMC | 26/04/2022 | 23/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5E56 | TT_FinMile | (RFE) STEAM TURBINE PLATFORM @5.44m IN 20UMC(Part of Geno platform) | 13/06/2022 | 13/06/2022 |  |  | 296 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5E55 | TT_Task | ERECTION STEAM TURBINE PLATFORM @5.44m IN 20UMC(Part of Geno platform) | 10/05/2022 | 13/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5E58 | TT_FinMile | (RFE) STEAM TURBINE MISC. PLATFORM 1 @6.56m IN 20UMC(Part of Geno platform) | 18/04/2022 | 18/04/2022 |  |  | 16 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5E57 | TT_Task | ERECTION STEAM TURBINE MISC. PLATFORM 1 @6.56m IN 20UMC(Part of Geno platform) | 22/03/2022 | 18/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5E60 | TT_FinMile | (RFE) STEAM TURBINE MISC. PLATFORM 2 @8.07m IN 20UMC(Part of Geno platform) | 03/05/2022 | 03/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5E59 | TT_Task | ERECTION STEAM TURBINE MISC. PLATFORM 2 @8.07m IN 20UMC(Part of Geno platform) | 06/04/2022 | 03/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD3-81 | TT_Task | MANUFACTURING COOLING TOWER - FILL - 20PAD | 03/01/2022 | 26/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD3-82 | TT_Task | MANUFACTURING COOLING TOWER - FRP - 20PAD | 03/01/2022 | 26/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD3-83 | TT_Task | MANUFACTURING COOLING TOWER - NOISE ATT / PIPING / DRIFT ELIM - 20PAD | 04/01/2022 | 27/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD3-84 | TT_Task | MANUFACTURING COOLING TOWER - WALKWAY - 20PAD | 04/01/2022 | 26/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD3-85 | TT_Task | MANUFACTURING COOLING TOWER - DRY EQUIPMENT ELECTRICAL - 20PAD | 04/01/2022 | 26/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD3-86 | TT_Task | MANUFACTURING COOLING TOWER - MECH. EQUIPMENT FANSTACK - 20PAD | 29/03/2022 | 27/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD3-87 | TT_Task | MANUFACTURING COOLING TOWER - VACUUM SKID PIPING - 20PAD | 01/02/2022 | 26/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD4-42 | TT_FinMile | (OTD-OS) ON SITE 20PAD FILL BATCH 2 | 24/09/2022 | 24/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD3-88 | TT_FinMile | (RFS) READY FOR SHIPMENT COOLING TOWER EQUIPMENT (EU) 20PAD FILL BATCH 2 | 24/07/2022 | 24/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD4-41 | TT_Task | TRANSPORT (EU) 20PAD FILL BATCH 2 | 25/07/2022 | 24/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD4B11 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION - (EU) 20PAD FILL BATCH 2 | 27/06/2022 | 24/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD3B71 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) - (EU) 20PAD FILL BATCH 2 | 26/06/2022 | 26/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD4-44 | TT_FinMile | (OTD-OS) ON SITE 20PAD FRP BATCH 1 | 16/08/2022 | 16/08/2022 |  |  | 64 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD3-89 | TT_FinMile | (RFS) READY FOR SHIPMENT COOLING TOWER EQUIPMENT 20PAD FRP BATCH 1 | 22/07/2022 | 22/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD4-43 | TT_Task | TRANSPORT 20PAD FRP BATCH 1 | 23/07/2022 | 16/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD4B12 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION - 20PAD FRP BATCH 1 | 25/06/2022 | 22/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD3B72 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) - 20PAD FRP BATCH 1 | 25/06/2022 | 25/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD4-45 | TT_FinMile | (OTD-OS) ON SITE 20PAD FRP BATCH 2 | 24/09/2022 | 24/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD3-90 | TT_FinMile | (RFS) READY FOR SHIPMENT COOLING TOWER EQUIPMENT 20PAD FRP BATCH 2 | 23/08/2022 | 23/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD4-46 | TT_Task | TRANSPORT 20PAD FRP BATCH 2 | 24/08/2022 | 24/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD4B13 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION - 20PAD FRP BATCH 2 | 27/07/2022 | 23/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD3B73 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) - 20PAD FRP BATCH 2 | 26/07/2022 | 26/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD4-47 | TT_FinMile | (OTD-OS) ON SITE 20PAD NOISE ATT / PIPING / DRIFT ELIM BATCH 1 | 24/09/2022 | 24/09/2022 |  |  | 144 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD3-91 | TT_FinMile | (RFS) READY FOR SHIPMENT COOLING TOWER EQUIPMENT (EU) 20PAD NOISE ATT / PIPING / DRIFT ELIM BATCH 1 | 24/07/2022 | 24/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD4-48 | TT_Task | TRANSPORT (EU) 20PAD NOISE ATT / PIPING / DRIFT ELIM BATCH 1 | 25/07/2022 | 24/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD4B14 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION - (EU) 20PAD NOISE ATT / PIPING / DRIFT ELIM BATCH 1 | 27/06/2022 | 24/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD3B74 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) - (EU) 20PAD NOISE ATT / PIPING / DRIFT ELIM BATCH 1 | 27/06/2022 | 27/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD4-50 | TT_FinMile | (OTD-OS) ON SITE 20PAD NOISE ATT / PIPING / DRIFT ELIM BATCH 2 | 25/10/2022 | 25/10/2022 |  |  | 144 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD3-92 | TT_FinMile | (RFS) READY FOR SHIPMENT COOLING TOWER EQUIPMENT (EU) 20PAD NOISE ATT / PIPING / DRIFT ELIM BATCH 2 | 24/08/2022 | 24/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD4-49 | TT_Task | TRANSPORT (EU) 20PAD NOISE ATT / PIPING / DRIFT ELIM BATCH 2 | 25/08/2022 | 25/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD4B15 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION - (EU) 20PAD NOISE ATT / PIPING / DRIFT ELIM BATCH 2 | 28/07/2022 | 24/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD3B75 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) - (EU) 20PAD NOISE ATT / PIPING / DRIFT ELIM BATCH 2 | 27/07/2022 | 27/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD4-51 | TT_FinMile | (OTD-OS) ON SITE 20PAD WALKWAY BATCH 1 | 24/09/2022 | 24/09/2022 |  |  | 144 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD3-93 | TT_FinMile | (RFS) READY FOR SHIPMENT COOLING TOWER EQUIPMENT 20PAD WALKWAY BATCH 1 | 23/08/2022 | 23/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD4-52 | TT_Task | TRANSPORT 20PAD WALKWAY BATCH 1 | 24/08/2022 | 24/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD4B16 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION - 20PAD WALKWAY BATCH 1 | 27/07/2022 | 23/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD3B76 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) - 20PAD WALKWAY BATCH 1 | 27/07/2022 | 27/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD4-53 | TT_FinMile | (OTD-OS) ON SITE 20PAD WALKWAY BATCH 2 | 25/10/2022 | 25/10/2022 |  |  | 592 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD3-94 | TT_FinMile | (RFS) READY FOR SHIPMENT COOLING TOWER EQUIPMENT 20PAD WALKWAY BATCH 2 | 23/09/2022 | 23/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD4-54 | TT_Task | TRANSPORT 20PAD WALKWAY BATCH 2 | 24/09/2022 | 25/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD4B17 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION - 20PAD WALKWAY BATCH 2 | 27/08/2022 | 23/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD3B77 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) - 20PAD WALKWAY BATCH 2 | 26/08/2022 | 26/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5E62 | TT_FinMile | (RFE) STEAM TURBINE MISC. PLATFORM 3 @10.09m IN 20UMC(Part of Geno platform) | 08/06/2022 | 08/06/2022 |  |  | 336 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5E61 | TT_Task | ERECTION STEAM TURBINE MISC. PLATFORM 3 @10.09m IN 20UMC(Part of Geno platform) | 12/05/2022 | 08/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5E64 | TT_FinMile | (RFE) STEAM TURBINE MISC. PLATFORM 4 @12.75m IN 20UMC(Part of Geno platform) | 23/05/2022 | 23/05/2022 |  |  | 464 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5E63 | TT_Task | ERECTION STEAM TURBINE MISC. PLATFORM 4 @12.75m IN 20UMC(Part of Geno platform) | 26/04/2022 | 23/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5E66 | TT_FinMile | (RFE) ERECTION LP TURBINE PLATFORM @6.00m(1st Part before ST Bearing)(Main Pipe Support Struc.) | 16/05/2022 | 16/05/2022 |  |  | 136 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5E65 | TT_Task | ERECTION LP TURBINE PLATFORM @6.00m IN 20UMC (1st Part before ST Bearing)(Main Pipe Support Struc.) | 26/04/2022 | 16/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5E68 | TT_FinMile | (RFE) LP TURBINE PLATFORM @6.00m(2nd PART AFTER UPY PLACING)(Main Pipe Support Struc.) | 04/09/2022 | 04/09/2022 |  |  | 112 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5E67 | TT_Task | ERECTION LP TURBINE PLATFORM @6.00m (2nd PART AFTER UPY PLACING)(Main Pipe Support Struc.) | 15/08/2022 | 04/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5E70 | TT_FinMile | (RFE) CRANE MAINTENANCE PLATFORM @15.30m IN 20UMC(Part of Mainframe) | 15/04/2022 | 15/04/2022 |  |  | 40 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5E69 | TT_Task | ERECTION CRANE MAINTENANCE PLATFORM @15.30m IN 20UMC(Part of Mainframe) | 19/02/2022 | 15/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5E72 | TT_FinMile | (RFE) ERECTION PLATFORM ABOVE CONDENSER @15.37m IN 20UMC | 18/09/2022 | 18/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5E71 | TT_Task | ERECTION PLATFORM ABOVE CONDENSER @15.37m IN 20UMC | 15/08/2022 | 18/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5E74 | TT_FinMile | (RFE) ANNEX PLATFORM 1 @5.44m IN 20UMC | 30/06/2022 | 30/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5E73 | TT_Task | ERECTION ANNEX PLATFORM 1 @5.44m IN 20UMC | 03/06/2022 | 30/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5E76 | TT_FinMile | (RFE) ANNEX PLATFORM 2 @9.34m IN 20UMC(not existing-TBD) | 09/06/2022 | 09/06/2022 |  |  | 328 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5E75 | TT_Task | ERECTION ANNEX PLATFORM 2 @9.34m IN 20UMC(not existing-TBD) | 13/05/2022 | 09/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5E78 | TT_FinMile | (RFE) VENTILATION PLATFORM @26.47m IN UMC(Part of Mainframe) | 02/05/2022 | 02/05/2022 |  |  | 632 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5E77 | TT_Task | ERECTION VENTILATION PLATFORM @26.47m IN 20UMC(part of Mainframe) | 08/03/2022 | 02/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD4-55 | TT_FinMile | (OTD-OS) ON SITE 20PAD DRY EQUIPMENT ELECTRICAL BATCH 1 | 24/11/2022 | 24/11/2022 |  |  | 624 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD3-95 | TT_FinMile | (RFS) READY FOR SHIPMENT COOLING TOWER EQUIPMENT (EU) 20PAD DRY EQUIPMENT ELECTRICAL BATCH 1 | 23/09/2022 | 23/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD4-57 | TT_Task | TRANSPORT (EU) 20PAD DRY EQUIPMENT ELECTRICAL BATCH 1 | 24/09/2022 | 24/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD4B18 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION - (EU) 20PAD DRY EQUIPMENT ELECTRICAL BATCH 1 | 27/08/2022 | 23/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD3B78 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) - (EU) 20PAD DRY EQUIPMENT ELECTRICAL BATCH 1 | 27/08/2022 | 27/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD4-56 | TT_FinMile | (OTD-OS) ON SITE 20PAD DRY EQUIPMENT ELECTRICAL BATCH 2 | 25/12/2022 | 25/12/2022 |  |  | 496 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD3-96 | TT_FinMile | (RFS) READY FOR SHIPMENT COOLING TOWER EQUIPMENT (EU) 20PAD DRY EQUIPMENT ELECTRICAL BATCH 2 | 24/10/2022 | 24/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD4-58 | TT_Task | TRANSPORT (EU) 20PAD DRY EQUIPMENT ELECTRICAL BATCH 2 | 25/10/2022 | 25/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD4B19 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION - (EU) 20PAD DRY EQUIPMENT ELECTRICAL BATCH 2 | 27/09/2022 | 24/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD3B79 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) - (EU) 20PAD DRY EQUIPMENT ELECTRICAL BATCH 2 | 26/09/2022 | 26/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD4-61 | TT_FinMile | (OTD-OS) ON SITE 20PAD MECH. EQUIPMENT FANSTACK BATCH 1 | 24/01/2023 | 24/01/2023 |  |  | 8 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD3-97 | TT_FinMile | (RFS) READY FOR SHIPMENT COOLING TOWER EQUIPMENT (EU) 20PAD MECH. EQUIPMENT FANSTACK BATCH 1 | 23/11/2022 | 23/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD4-59 | TT_Task | TRANSPORT (EU) 20PAD MECH. EQUIPMENT FANSTACK BATCH 1 | 24/11/2022 | 24/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD4B20 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION - (EU) 20PAD MECH. EQUIPMENT FANSTACK BATCH 1 | 27/10/2022 | 23/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD3B80 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) - (EU) 20PAD MECH. EQUIPMENT FANSTACK BATCH 1 | 27/10/2022 | 27/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD4-62 | TT_FinMile | (OTD-OS) ON SITE 20PAD MECH. EQUIPMENT FANSTACK BATCH 2 | 25/02/2023 | 25/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD3-98 | TT_FinMile | (RFS) READY FOR SHIPMENT COOLING TOWER EQUIPMENT (EU) 20PAD MECH. EQUIPMENT FANSTACK BATCH 2 | 25/12/2022 | 25/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD4-60 | TT_Task | TRANSPORT (EU) 20PAD MECH. EQUIPMENT FANSTACK BATCH 2 | 26/12/2022 | 25/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD4B21 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION - (EU) 20PAD MECH. EQUIPMENT FANSTACK BATCH 2 | 28/11/2022 | 25/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD3B81 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) - (EU) 20PAD MECH. EQUIPMENT FANSTACK BATCH 2 | 27/11/2022 | 27/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD4-63 | TT_FinMile | (OTD-OS) ON SITE 20PAD VACUUM SKID PIPING | 25/12/2022 | 25/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD3-99 | TT_FinMile | (RFS) READY FOR SHIPMENT COOLING TOWER EQUIPMENT (EU) 20PAD VACUUM SKID PIPING | 24/10/2022 | 24/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD4-64 | TT_Task | TRANSPORT (EU) 20PAD VACUUM SKID PIPING | 25/10/2022 | 25/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD4B22 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION - (EU) 20PAD VACUUM SKID PIPING | 27/09/2022 | 24/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD3B82 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) - (EU) 20PAD VACUUM SKID PIPING | 26/09/2022 | 26/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMY6M75 | TT_Task | PLACING AND ALIGNMENT OF MODULE UMY00-A11/A41/D11/D41 (inside UMC building) | 22/04/2022 | 12/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--UB-2-36 | TT_FinMile | (C) BASIC DESIGN PLANT LAYOUT DWGS (UF) TRANSFORMER AREA AVAILABLE | 15/05/2021 | 15/05/2021 | 15/05/2021 | 15/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UR-2-45 | TT_FinMile | (C) BASIC DESIGN PLANT LAYOUT DWGS (UF) COOLING TOWER AVAILABLE | 15/05/2021 | 15/05/2021 | 15/05/2021 | 15/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UE-2E37 | TT_FinMile | (C) BASIC DESIGN PLANT LAYOUT DWGS (UF) FUEL GAS AREA AVAILABLE | 15/05/2021 | 15/05/2021 | 15/05/2021 | 15/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UE2-E38 | TT_FinMile | (C) BASIC DESIGN PLANT LAYOUT DWGS (UF) CLEAN DIRTY OIL TANK AREA AVAILABLE | 15/05/2021 | 15/05/2021 | 15/05/2021 | 15/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
CLP20UEZ5-84 | TT_FinMile | (RFE) FOUNDATION 20UEZ02 (CLP Scope) | 30/06/2021 | 30/06/2021 | 30/06/2021 | 30/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
CLP20UEZ5-82 | TT_Task | CONSTRUCTION FOUNDATION 20UEZ02 (CLP Scope) | 03/06/2021 | 30/06/2021 | 03/06/2021 | 30/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
CLP20UEZ5-81 | TT_Task | WORK PREPARATION, EXCAVATION 20UEZ02 (CLP Scope) | 20/05/2021 | 02/06/2021 | 20/05/2021 | 02/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
CLP20UEZ5-83 | TT_Mile | (H) START PLACING FORMWORK 20UEZ02 (CLP Scope) | 03/06/2021 | 03/06/2021 | 03/06/2021 | 03/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
CLP20UEZ2-108 | TT_Task | PREPARATION FOUNDATION GROUNDING DWGS 20UEZ02 (CLP Scope) | 07/02/2021 | 20/02/2021 | 07/02/2021 | 20/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
CLP20UEZ2-106 | TT_Task | BASIC BUILDING DESIGN INCL. 3D MODEL 20UEZ02 (CLP Scope) | 21/12/2020 | 16/01/2021 | 21/12/2020 | 16/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
CLP20UEZ2-105 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UEZ02 (CLP Scope) | 20/12/2020 | 20/12/2020 | 20/12/2020 | 20/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
CLP20UEZ2-111 | TT_FinMile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION 20UEZ02 (CLP Scope) | 19/05/2021 | 19/05/2021 | 19/05/2021 | 19/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
CLP20UEZ2-107 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE 20UEZ02 (CLP Scope) | 17/01/2021 | 20/02/2021 | 17/01/2021 | 20/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
CLP20UEZ2-109 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE - 20UEZ02 (CLP Scope) | 21/02/2021 | 21/04/2021 | 21/02/2021 | 21/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
CLP20UEZ2-110 | TT_Task | BD - CONSENT LETTER - DESIGN 20UEZ02 (CLP Scope) | 22/04/2021 | 19/05/2021 | 22/04/2021 | 19/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7-192 | TT_Task | ERECTION CABLE TRAYS ON 20UEZ02 | 03/11/2022 | 12/11/2022 |  |  | 16 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7-193 | TT_Task | ERECTION CABLE TRAYS ON 20UEY03 | 18/05/2022 | 27/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7-194 | TT_Task | ERECTION STACK CABLE TRAYS FOR EMISSION MONITORING PART 1 (parallel to Pre-assembly stack part 1) | 19/05/2022 | 22/06/2022 |  |  | 312 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7-195 | TT_Task | ERECTION STACK CABLE TRAYS FOR EMISSION MONITORING PART 2 (parallel to Pre-assembly stack part 2) | 30/05/2022 | 03/07/2022 |  |  | 224 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7-196 | TT_Task | ERECTION CABLE TRAYS ON 20UBY05 | 10/11/2022 | 14/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7-197 | TT_Task | ERECTION CABLE TRAYS ON 10UEY01 | 22/06/2022 | 19/07/2022 |  |  | 304 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7-198 | TT_Task | ERECTION CABLE TRAYS 20UMC SOUTH / WEST CORNER | 26/05/2022 | 22/06/2022 |  |  | 1368 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7-199 | TT_Task | ADAPTION CABLE TRAYS ON 10UBS04/05 /10UBA | 09/04/2022 | 06/05/2022 |  |  | 368 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7B41 | TT_Task | INSTALLATION OF CABLE TRAYS FOR D2 PLANT TO SUBSTATION BRANCH | 23/06/2022 | 20/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7B42 | TT_Task | INSTALLATION OF CABLE TRAYS C-STATION TO SUBSTATION BRANCH | 14/07/2022 | 10/08/2022 |  |  | 600 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7B43 | TT_Task | INSTALLATION OF CABLE TRAY BRANCH TO SUBSTATION | 12/05/2022 | 01/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7B44 | TT_Task | INSTALLATION OF CABLE TRAYS INSIDE SUBSTATION | 02/06/2022 | 06/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
CL20-TPE-10 | TT_Mile | RELEASE FOR INSTALLATION CABLE TRAYS FROM D2 PLANT TO SUBSTATION | 09/05/2022 | 09/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
CL20-TPE-15 | TT_Mile | RELEASE FOR INSTALLATION CABLE TRAYS FROM C-STATION TO SUBSTATION BRANCH | 09/05/2022 | 09/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
CL20-TPE-16 | TT_Mile | RELEASE FOR INSTALLATION CABLE TRAY BRANCH TO SUBSTATION | 09/05/2022 | 09/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
CL20-TPE-17 | TT_Mile | RELEASE FOR INSTALLATION CABLE TRAYS INSIDE SUBSTATION | 30/05/2022 | 30/05/2022 |  |  | 24 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK7B01 | TT_Task | INTERCONNECTING IC CABLING TO EXISTING DCS IN 00UCA (D1) -D2 TO D1 CONTROL ROOM | 15/11/2022 | 19/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK7A35 | TT_Task | CABLING GIS TO D2 | 14/12/2022 | 10/01/2023 |  |  | 720 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK7B46 | TT_Task | CABLING DEMIN. WATER AREA | 22/12/2022 | 04/01/2023 |  |  | 1056 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK7A36 | TT_Task | CABLING 20UMC TO UBA7x | 11/12/2022 | 14/01/2023 |  |  | 184 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK7E27 | TT_Task | CABLING TO OIL MODULE | 11/12/2022 | 31/12/2022 |  |  | 560 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK7A37 | TT_Task | CABLING TO GT FROM 20UBA7x | 11/12/2022 | 17/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK7-200 | TT_Task | CABLING ULA INTERNAL TO 20UBA1110/20 | 22/12/2022 | 04/01/2023 |  |  | 768 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK7B47 | TT_Task | CABLING TO / INSIDE WATER INTAKE | 23/03/2023 | 05/04/2023 |  |  | 336 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK7C34 | TT_Task | CABLING TO ST FROM 20UBA7x | 29/09/2022 | 09/11/2022 |  |  | 1272 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK7B48 | TT_Task | CABLING MV COUPLING 20BBA - 90BBA 20BBB - 90BBB | 03/11/2022 | 30/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK7F29 | TT_Task | CABLING STREET AREA | 10/05/2023 | 23/05/2023 |  |  | 304 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
CL20UBZ-10 | TT_FinMile | (RFE) HV CABLE CONDUIT BY CLP - SOUTH OF UBZ01 / CLOSE TO TP-C6 | 30/06/2021 | 30/06/2021 | 30/06/2021 | 30/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BZK7-190 | TT_Task | CABLING TO 20UBA1110/20 AND ULA FROM EXTERNAL | 22/12/2022 | 18/01/2023 |  |  | 656 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
CL20UBZ-15 | TT_FinMile | (RFE) CONTROL CABLE CONDUIT BY CLP - SOUTH OF UBZ01 / CLOSE TO TP-C6 | 30/06/2021 | 30/06/2021 | 30/06/2021 | 30/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UEY2-81 | TT_Task | BASIC DESIGN / BASIC BUILDING DESIGN INCL. 3D MODEL 20UEY02 | 12/06/2021 | 02/07/2021 | 12/06/2021 | 02/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UEY2-86 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UEY02 | 11/06/2021 | 11/06/2021 | 11/06/2021 | 11/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UEY5-104 | TT_FinMile | (RFE) FOUNDATION 20UEY02 | 12/04/2022 | 12/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY5-103 | TT_Mile | (H) START PLACING FORMWORK 20UEY02 | 04/03/2022 | 04/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY5-101 | TT_Task | WORK PREPARATION, EXCAVATION 20UEY02 | 25/02/2022 | 03/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY2-83 | TT_Task | PREPARATION FOUNDATION GROUNDING DWGS 20UEY02 | 25/08/2021 | 07/09/2021 | 25/08/2021 | 07/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UEY2-82 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE 20UEY02 | 03/07/2021 | 05/12/2021 | 03/07/2021 | 05/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UEY2-88 | TT_Mile | (F) CONCRETE STRUCTURE DWGS ON SITE RELEASED FOR EXECUTION 20UEY02 | 11/02/2022 | 11/02/2022 |  |  | 112 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY2-85 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE 20UEY02 | 13/12/2021 | 10/02/2022 | 13/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UEY2-84 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN CONCRETE 20UEY02 | 08/09/2021 | 05/12/2021 | 08/09/2021 | 05/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UEY2-87 | TT_Task | BD - CONSENT LETTER DETAIL DESIGN CONCRETE 20UEY02 | 11/02/2022 | 10/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P221-600 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE 20UEY02 | 13/12/2021 | 13/12/2021 | 13/12/2021 | 13/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y48 | TT_FinMile | (RFE) CONCRETE WORKS LDK PT+TRENCH 20UMC | 10/01/2022 | 10/01/2022 |  |  | 360 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BFT8-78 | TT_FinMile | (TOP-20BFT02) LV-TRANSFORMER 20BFT02 | 27/03/2023 | 27/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY5-108 | TT_FinMile | (RFE) FOUNDATION 20UEY01 PART 2 | 25/03/2022 | 25/03/2022 |  |  | 512 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY5-107 | TT_Mile | (H) START PLACING FORMWORK 20UEY01 PART 2 | 03/03/2022 | 03/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY5-105 | TT_Task | WORK PREPARATION / EXCAVATION / PILE TRIMMING / PLATE WELDING 20UEY01 PART 2 | 25/02/2022 | 02/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BBA8-38 | TT_FinMile | (TOP-20BBB) MV SWITCHGEAR 20BB | 28/03/2023 | 28/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20B--8-52 | TT_FinMile | MV AVAILABLE (BACK ENERGISING) VIA 90BBA | 28/03/2023 | 28/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BBA8-40 | TT_FinMile | (TOP-90BBA) MV SWITCHGEAR 90BBA | 27/02/2023 | 27/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BBA8-41 | TT_FinMile | (TOP-90BBB) MV SWITCHGEAR 90BBB | 15/05/2023 | 15/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BBA8-46 | TT_FinMile | (TOP-90B01) MV FEEDER TO SWITCHGEAR 90BBA | 04/03/2023 | 04/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BBA8-47 | TT_FinMile | (TOP-90B02) MV FEEDER TO SWITCHGEAR 90BBB | 06/06/2023 | 06/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BBA8-49 | TT_FinMile | (TOP-20BBB) MV FEEDER TO SWITCHGEAR 20BBB | 11/04/2023 | 11/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BF-8-19 | TT_FinMile | (TOP-20BFF) LV SWITCHGEAR BFF/BMF (HRSG) | 10/04/2023 | 10/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BF-8-21 | TT_Task | COMMISSIONING LV SWITCHGEAR BFF/BMF (HRSG) | 11/04/2023 | 17/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BFT8-26 | TT_FinMile | (TOP-20BFT04) TRANSFORMER 20BFT04 | 16/05/2023 | 16/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BFT8-27 | TT_Task | COMMISSIONING LV TRANSFORMER 20BFT04 | 17/05/2023 | 23/05/2023 |  |  | 24 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20ACA8-26 | TT_FinMile | (TOP-20ACA) HV SWITCHGEAR IN FRONT OF 20BAT (GIL) | 27/02/2023 | 27/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20ACA8-27 | TT_FinMile | (TOP-20AC) HV FEEDER | 27/02/2023 | 27/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BFT8-79 | TT_FinMile | (TOP-20MKC) SEE/SFC EQUIPMENT | 13/03/2023 | 13/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA8G29 | TT_Task | COMMISSIONING ELECTRICAL MODULES 20UBA7710/20 | 14/02/2023 | 20/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA8G30 | TT_Task | COMMISSIONING ELECTRICAL MODULES 20UBA7110/7210/7410 | 07/02/2023 | 13/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BB8-45 | TT_Task | COMMISSIONING ELECTRICAL INTERFACE GRID/PLANT (6.6kV MV CONNECTION) | 22/03/2023 | 28/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20CHA8-26 | TT_Task | COMMISSIONING UNIT PROTECTION FOR BBA | 08/03/2023 | 21/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BFC2-80 | TT_Task | QUOTATION STAGE LV- / DC-SWITCHGEAR 20BFC/BFD | 28/05/2021 | 08/07/2021 | 28/05/2021 | 08/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BFC2-15 | TT_Task | BASIC DESIGN / SPECIFICATION LV- / DC-SWITCHGEAR 20BFC/BFD | 02/04/2021 | 27/05/2021 | 02/04/2021 | 27/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BFC2-75 | TT_Mile | RFQ LV- / DC-SWITCHGEAR 20BFC/BFD | 28/05/2021 | 28/05/2021 | 28/05/2021 | 28/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--BZP2-93 | TT_Task | DETAIL DESIGN CABLE SUPPORT SYSTEM 20UBF AREA (FIRST SUBMISSION) | 12/08/2021 | 26/08/2021 | 12/08/2021 | 26/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--BZP2-94 | TT_Task | DETAIL DESIGN CABLE SUPPORT SYSTEM 20UBA71 (FIRST SUBMISSION) | 22/10/2021 | 05/12/2021 | 22/10/2021 | 05/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--BZP2-95 | TT_Task | DETAIL DESIGN CABLE SUPPORT SYSTEM 20UBA11 (FIRST SUBMISSION) | 23/09/2021 | 07/10/2021 | 23/09/2021 | 07/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--BZP2-96 | TT_Task | DETAIL DESIGN CABLE SUPPORT SYSTEM 20UBA81 (FIRST SUBMISSION) | 29/10/2021 | 04/12/2021 | 29/10/2021 |  | 64 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--BZP2-97 | TT_Task | DETAIL DESIGN CABLE SUPPORT SYSTEM 90UBA10 (FIRST SUBMISSION) | 08/10/2021 | 21/10/2021 | 08/10/2021 | 21/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--BZP2-98 | TT_Task | DETAIL DESIGN CABLE SUPPORT SYSTEM 20UMC (FIRST SUBMISSION) | 24/12/2021 | 07/01/2022 | 24/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--BZP2-99 | TT_Task | DETAIL DESIGN CABLE SUPPORT SYSTEM 20UMY (FIRST SUBMISSION) | 05/11/2021 | 03/12/2021 | 05/11/2021 | 03/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--BZP2-100 | TT_Task | DETAIL DESIGN CABLE SUPPORT SYSTEM 20ULA (FIRST SUBMISSION) | 05/12/2021 | 19/12/2021 | 05/12/2021 | 19/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--BZP2-101 | TT_Task | DETAIL DESIGN CABLE SUPPORT SYSTEM 20UEY/00UEN/20UMX (FIRST SUBMISSION) | 04/12/2021 | 18/12/2021 | 04/12/2021 | 18/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--BZP2-102 | TT_Task | DETAIL DESIGN CABLE SUPPORT SYSTEM 20URA/20URD AREA(FIRST SUBMISSION) | 01/01/2022 | 15/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BZL2-89 | TT_Task | CHECK OF BASIC DESIGN WITH ATKINS | 29/04/2021 | 12/05/2021 | 29/04/2021 | 12/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--CYA2-86 | TT_Mile | BASIC DESIGN HANDOVER ATKINS TO SIEMENS - EXTRA-LOW VOLTAGE SYSTEMS | 28/01/2022 | 28/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--CYA2-87 | TT_Mile | BASIC DESIGN HANDOVER ATKINS TO SIEMENS - LIGHTING SMALL POWER SYSTEM | 29/04/2021 | 29/04/2021 | 29/04/2021 | 29/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--CYA2-88 | TT_Mile | BASIC DESIGN HANDOVER ATKINS TO SIEMENS - PABX TELEPHONE SYSTEM | 28/01/2022 | 28/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--CYA2-89 | TT_Mile | BASIC DESIGN HANDOVER ATKINS TO SIEMENS - PASSIVE LAN NETWORK | 28/01/2022 | 28/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--CYA2-90 | TT_Mile | BASIC DESIGN HANDOVER ATKINS TO SIEMENS - CLOCK SYSTEM | 28/01/2022 | 28/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--CYA2-91 | TT_Mile | BASIC DESIGN HANDOVER ATKINS TO SIEMENS - RADIO COMMUNICATION | 28/01/2022 | 28/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--CYA2-92 | TT_Mile | BASIC DESIGN HANDOVER ATKINS TO SIEMENS - CCTV SYSTEM | 28/01/2022 | 28/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--CYA2-93 | TT_Mile | BASIC DESIGN HANDOVER ATKINS TO SIEMENS - ACCESS CONTROL SYSTEM | 28/01/2022 | 28/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--CYA2-94 | TT_Mile | BASIC DESIGN HANDOVER ATKINS TO SIEMENS - SIREN SYSTEM | 28/01/2022 | 28/01/2022 |  |  | 736 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-101 | TT_Mile | TP-M1B - FUEL GAS SUPPLY - YOC/CNOOC | 19/07/2022 | 19/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-117 | TT_Mile | TP-M5B - TOWNSWATER DOMESTIC SYSTEM (POTABLE WATER) | 20/11/2022 | 20/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-119 | TT_Mile | TP-M6B - TOWNSWATER SERVICE SYSTEM (SERVICE WATER) | 26/08/2022 | 26/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-121 | TT_Mile | TP-M7B - HYDROGEN SUPPLY | 07/10/2022 | 07/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-134 | TT_Mile | TP-M13B - FIRST UREA TANK 10HSJ20BB001 - LIQUID UREA RETURN | 01/07/2022 | 01/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-136 | TT_Mile | TP-M14B - SECOND UREA TANK 10HSJ22BB001 - LIQUID UREA RETURN | 01/07/2022 | 01/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20-1P343 | TT_Task | PREFABRICATION OF OFFRACK PIPING FOR SHIPMENT LOT 4 | 08/09/2021 | 02/02/2022 | 08/09/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI---1P6A6 | TT_Task | UNPACKING SORTING PIPING LOT 4 | 07/04/2022 | 27/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---3B94 | TT_Task | PREFABRICATION OF OFFRACK PIPING FOR SHIPMENT LOT 5 | 08/10/2021 | 03/03/2022 | 08/10/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI---1P6A7 | TT_Task | UNPACKING SORTING PIPING LOT 5 | 06/05/2022 | 26/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI---1P6A8 | TT_Task | UNPACKING SORTING PIPING LOT 6 | 25/09/2022 | 15/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI---1P6A9 | TT_Task | PREFABRICATION ON SITE ALL SYSTEMS - TEMP. PIPING | 16/10/2022 | 12/11/2022 |  |  | 1112 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---3B95 | TT_Task | PREFABRICATION OF OFFRACK PIPING FOR SHIPMENT LOT 6 | 10/11/2021 | 23/07/2022 | 10/11/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20TP-169 | TT_Mile | NOT APPLICABLE - TP-M19A - D1 CCGT EFFLUENT FROM UGE NEUTRALISATION BASIN - 10LDR31/32AP001 (Option) | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-184 | TT_Mile | NOT APPLICABLE - TP-M25A -EFFLUENT TRANSFER PUMPS TO D1 SEAL PIT (Option) | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-170 | TT_Mile | NOT APPLICABLE - TP-M20A - D1 CCGT EFFLUENT FROM UHW PUMPS - 10GMH11/12AP001 (Option) | 04/08/2022 | 04/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-171 | TT_Mile | NOT APPLICABLE - TP-M21A - D1 CCGT EFFLUENT FROM UVM PUMPS - 10GVM11/12AP001SCR (Option) | 04/08/2022 | 04/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-172 | TT_Mile | NOT APPLICABLE - TP-M22A - D1 CCGT EFFLUENT FROM HRSG DRAINS PUMPS - 10LCL11/12AP001 (Option) | 20/10/2022 | 20/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-173 | TT_Mile | NOT APPLICABLE - TP-M23A - UTS CHEMICAL DOSING AREA - 10GME11/12AP001 (Option) | 04/08/2022 | 04/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-191 | TT_Mile | TP-F1B - FIRE FIGHTING FRESH WATER SUPPLY | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-192 | TT_Mile | TP-F1C - FIRE FIGHTING FRESH WATER SUPPLY | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-202 | TT_Mile | TP-C2A - STORM WATER CONNECTION | 29/03/2022 | 29/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-203 | TT_Mile | TP-C3A - STORM WATER CONNECTION | 14/02/2022 | 14/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-204 | TT_Mile | TP-C4A - STORM WATER CONNECTION | 06/01/2022 | 06/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-205 | TT_Mile | TP-C5A - STORM WATER CONNECTION | 05/05/2022 | 05/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-206 | TT_Mile | TP-C6A - STORM WATER CONNECTION FROM D1 EVA EXIS. DRAIN CHANNEL TO D2 | 06/01/2022 | 06/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-207 | TT_Mile | TP-C7A - STORM WATER CONNECTION FROM PERIMETER TRENCH SUMP | 06/01/2022 | 06/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-208 | TT_Mile | TP-C8A - STORM WATER CONNECTION FROM PERIMETER TRENCH SUMP | 05/05/2022 | 05/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-209 | TT_Mile | TP-C9A - STORM WATER CONNECTION FROM PERIMETER TRENCH SUMP | 05/05/2022 | 05/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-210 | TT_Mile | TP-C10A - STORM WATER CONNECTION FROM PERIMETER TRENCH SUMP | 05/05/2022 | 05/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UVM-8E27 | TT_Task | COLD COMMISSIONING PLANT DRAINAGE SYSTEM UVM | 05/04/2023 | 11/04/2023 |  |  | 80 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UVM-8E26 | TT_FinMile | (TOP-20GU-01) PLANT DRAINAGE SYSTEM FOR SURFACE AND RAINWATER FROM UVM | 28/03/2023 | 28/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HSK-8B28 | TT_FinMile | (TOP-20HSK) HRSG SCR-CAT SYSTEM | 24/07/2023 | 24/07/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGA8B28 | TT_FinMile | (TOP-20SGA-02) FIRE FIGHTING FRESH WATER RING MAIN AND OUTDOOR HYDRANTS | 13/02/2023 | 13/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PUR8-26 | TT_FinMile | (TOP-20PUR-02) CATHODIC PROTECTION SYSTEM FOR PAC ELECTRICAL MODULES | 20/01/2023 | 20/01/2023 |  |  | 640 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PUR7J17 | TT_Task | ELECTRICAL ERECTION CATHODIC PROTECTION PAC ELECTRICAL MODULES | 23/10/2022 | 20/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PUR8-27 | TT_FinMile | (TOP-20PUR-01) CATHODIC PROTECTION SYSTEM FOR CONDENSER | 20/01/2023 | 20/01/2023 |  |  | 640 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-231 | TT_Mile | TP-I13 - UNIT D2 INTERFACE PANEL (00UCA) | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-232 | TT_Mile | TP-I1 - UNIT D2 DCIS (D2 Site) | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-233 | TT_Mile | TP-I4 - UNIT D2 INTERFACE PANEL (00UCA) | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-234 | TT_Mile | TP-I5 - UNIT D2 INTERFACE PANEL (00UCA) | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-235 | TT_Mile | TP-I6 - D2 CCTV SYSTEM (D2 SITE) | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-236 | TT_Mile | TP-I10 - 6.6kV SWITCHGEAR (UNIT D2 SITE) | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-237 | TT_Mile | TP-I17 - UNIT D2 CONTINUOUS EMISSION MONITORING SYSTEM (UNIT D2 SITE) | 28/07/2022 | 28/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-238 | TT_Mile | TP-I19i - UNIT D2 DISSOLVED GAS ANALYSIS SYSTEM | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-239 | TT_Mile | TP-I19ii - DGA NETWORK SWITCH (00UCA) | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-240 | TT_Mile | TP-I21 - UNIT D2 TELECOMMUNICATION PANEL (D2 SITE) | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-241 | TT_Mile | TP-I22 - UNIT D2 FIRE DETECTION SYSTEM (D2 SITE) | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-242 | TT_Mile | TP-I23 - D2 NETWORK PANEL (00UCA) | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-243 | TT_Mile | TP-I15 - UNIT D2 DCIS (D2 SITE) | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-244 | TT_Mile | TP-I16 - UNIT D2 DCIS (D2 SITE) | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-245 | TT_Mile | TP-I20 - UNIT D2 DCIS (D2 SITE) | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-246 | TT_Mile | TP-I13 - UNIT D2 INTERFACE PANEL (00UCA) | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-247 | TT_Mile | TP-I18 - UNIT D2 DCIS (D2 SITE) | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-248 | TT_Mile | TP-I2i - UNIT D2 INTERFACE PANEL (00UCA) | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-249 | TT_Mile | TP-I2ii - EXISTING D1 DCIS PANELS (00UCA) | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-250 | TT_Mile | TP-I2iii - EXISTING STATION DCIS PANELS (00UCA) | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-251 | TT_Mile | TP-I2iv - INTERFACE MARSHALLING BOXES (BAY 25) (400kV Substation) | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-261 | TT_Mile | TP-E5 - D2 ELECTRICAL / CI MODULES (D2 Site) | 05/12/2022 | 05/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-262 | TT_Mile | TP-E7 - D2 OUTDOOR EARTHING GRID (D2 Site) | 13/02/2023 | 13/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-263 | TT_Mile | TP-E8 - D2 OUTDOOR EARTHING GRID (D2 Site) | 27/09/2022 | 27/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-265 | TT_Mile | TP-E6 - MAIN D2 UPS (D2 Electrical Modules) | 27/12/2022 | 27/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-266 | TT_Mile | TP-E6ii - EXISTING BPPS CCR 415AV BOARDS / 415V AC STATION ESSENTIAL SERVICES BOARD | 27/12/2022 | 27/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TP-267 | TT_Mile | TP-E9 - D2 TEMPORARY CONSTRUCTION AND SITE OFFICE POWER | 01/07/2021 | 01/07/2021 | 01/07/2021 | 01/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20LCE7A15 | TT_Task | ELECTRICAL ERECTION / VALVES CONDENSATE SYSTEM 20LCE | 29/11/2022 | 05/12/2022 |  |  | 1152 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LCE6A15 | TT_Task | ERECTION, NDT, PT PIPES / VALVES 20LCE | 11/06/2022 | 14/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LCE6A45 | TT_Task | INSULATION PIPES / VALVES CONDENSATE 20LCE(Not appicable) | 25/10/2022 | 28/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PUS7A15 | TT_Task | ELECTRICAL ERECTION / VALVES BIOCIDE GENERATION 20PUS | 28/11/2022 | 04/12/2022 |  |  | 1096 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PUS6A15 | TT_Task | ERECTION, NDT, PT PIPES / VALVES 20PUS | 24/06/2022 | 29/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PUS6A45 | TT_Task | INSULATION PIPES / VALVES BIOCIDE GENERATION 20PUS(No Insulation) | 24/10/2022 | 27/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PB-7A15 | TT_Task | ELECTRICAL ERECTION / VALVES COOLING WATER MAKE-UP SYSTEM 20PBE/PBQ/PUN | 28/11/2022 | 04/12/2022 |  |  | 1048 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PB-6A15 | TT_Task | ERECTION, NDT, PT PIPES / VALVES 20PBE/PBQ/PUN | 24/06/2022 | 29/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PB-6A45 | TT_Task | INSULATION PIPES / VALVES COOLING WATER MAKE-UP SYSTEM 20PBE/PBQ/PUN(No Insulation) | 24/10/2022 | 27/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PSB7A15 | TT_Task | ELECTRICAL ERECTION / VALVES COOLING WATER 20PSB | 28/11/2022 | 04/12/2022 |  |  | 1096 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PSB6A15 | TT_Task | ERECTION, NDT, PT PIPES / VALVES 20PSB | 24/06/2022 | 29/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PSB6A45 | TT_Task | INSULATION PIPES / VALVES COOLING WATER 20PSB(No Insulation) | 24/10/2022 | 27/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SCB7A15 | TT_Task | ELECTRICAL ERECTION / VALVES COMPRESSED AIR SYSTEM 20SCB | 07/11/2022 | 13/11/2022 |  |  | 1520 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SCB6A15 | TT_Task | ERECTION, NDT, PT PIPES / VALVES 20SCB | 24/06/2022 | 29/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SCB6A45 | TT_Task | INSULATION PIPES / VALVES COMPRESSED AIR SYSTEM 20SCB (No Insulation) | 03/10/2022 | 06/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20QJA7A15 | TT_Task | ELECTRICAL ERECTION / VALVES GAS SUPPLY AND DISTRIBUTION QJA10 | 07/11/2022 | 13/11/2022 |  |  | 816 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20QJA6A15 | TT_Task | ERECTION, NDT, PT PIPES / VALVES 20QJA10 | 24/06/2022 | 29/09/2022 |  |  | 24 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20QJA6A45 | TT_Task | INSULATION PIPES / VALVES GAS SUPPLY AND DISTRIBUTION QJA10(No Insulation) | 03/10/2022 | 06/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20QJA7A16 | TT_Task | ELECTRICAL ERECTION / VALVES GAS SUPPLY AND DISTRIBUTION QJA20 | 07/11/2022 | 13/11/2022 |  |  | 1296 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20QJA6A46 | TT_Task | ERECTION, NDT, PT PIPES / VALVES 20QJA20 | 24/06/2022 | 29/09/2022 |  |  | 24 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20QJA6A47 | TT_Task | INSULATION PIPES / VALVES GAS SUPPLY AND DISTRIBUTION QJA20(No Insulation) | 03/10/2022 | 06/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAM7A15 | TT_Task | ELECTRICAL ERECTION PIPES / VALVES MAM | 03/12/2022 | 16/12/2022 |  |  | 976 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAM6A45 | TT_Task | INSULATION PIPES / VALVES FOR STEAM SYSTEM MAM | 29/10/2022 | 02/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAM6A15 | TT_Task | ERECTION, NDT, PT PIPES / VALVES MAM | 17/09/2022 | 28/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAG6A46 | TT_Task | ERECTION, NDT, PT PIPES / VALVES MAG50 | 20/05/2022 | 28/07/2022 |  |  | 528 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAG7A16 | TT_Task | ELECTRICAL ERECTION / VALVES MAG50 | 31/10/2022 | 06/11/2022 |  |  | 1296 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAG6A47 | TT_Task | INSULATION PIPES / VALVES FOR CONDENSATION SYSTEM MAG50 | 03/10/2022 | 06/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HSJ7A15 | TT_Task | ELECTRICAL ERECTION / VALVES SCR SYSTEM 20HSJ | 21/02/2023 | 27/02/2023 |  |  | 864 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HSJ6A15 | TT_Task | ERECTION, NDT, PT PIPES / VALVES 20HSJ | 11/10/2022 | 16/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HSJ6A45 | TT_Task | INSULATION PIPES / VALVES SCR SYSTEM 20HSJ | 17/01/2023 | 20/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKA7A15 | TT_Task | ELECTRICAL ERECTION / VALVES GENERATOR 20MKA | 28/01/2023 | 03/02/2023 |  |  | 640 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKA6A15 | TT_Task | ERECTION, NDT, PT PIPES / VALVES 20MKA | 10/09/2022 | 23/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKA6A45 | TT_Task | INSULATION PIPES / VALVES GENERATOR 20MKA | 24/12/2022 | 27/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5-99 | TT_FinMile | (RFE) READY FOR E-ERECTION 01UBA9010/20 | 05/06/2022 | 05/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5-100 | TT_FinMile | (RFE) READY FOR E-ERECTION 20UBA8110/20 | 28/06/2022 | 28/06/2022 |  |  | 960 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5-102 | TT_FinMile | (RFE) READY FOR E-ERECTION 20UBA7910/20 | 16/06/2022 | 16/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5-101 | TT_FinMile | (RFE) READY FOR E-ERECTION 20UBA7xxx | 13/04/2022 | 13/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5-103 | TT_FinMile | (RFE) READY FOR E-ERECTION 20UBA1110/20 | 15/05/2022 | 15/05/2022 |  |  | 1184 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-6-49 | TT_Task | ERECTION STACK HRSG20_2nd part | 18/06/2022 | 24/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-6-50 | TT_Task | ERECTION STACK HRSG20_4th part | 01/08/2022 | 07/08/2022 |  |  | 176 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM1A8-30 | TT_Task | COMMISSIONING OF TP-M1A | 26/04/2023 | 02/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM1A3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-M1A | 19/07/2022 | 19/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM1A6-25 | TT_Task | TERMINATION OF TP-M1A | 22/10/2022 | 28/10/2022 |  |  | 1432 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM1A2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-M1A | 11/04/2021 | 08/05/2021 | 11/04/2021 | 08/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPM1A2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-M1A | 26/04/2022 | 26/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM1A6-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-M1A | 19/07/2022 | 19/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM1A2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-M1A | 26/04/2022 | 02/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM1A2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-M1A | 21/10/2022 | 21/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM1A8-26 | TT_Mile | MEDIA AVAILABLE TP-M1A | 26/04/2023 | 26/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA4G61 | TT_Mile | (ET4a) LATEST DELIVERY DATE BOP IC CUBICLES FOR ASSEMBLY 20UBA7310/30 | 18/11/2021 | 18/11/2021 | 18/11/2021 | 18/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA4-70 | TT_Mile | (ET4b) ELECTRICAL MODULES AT WORKSHOP READY FOR COMPONENT INSTALLATION ELECTRICAL MODULES 20UBA8010/20 | 17/06/2022 | 17/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA3-26 | TT_Task | CLIENT - REVIEW - STEEL STRUCTURE 20URA | 04/09/2021 | 28/09/2021 | 04/09/2021 | 28/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MBL2-101 | TT_Task | DETAIL DESIGN AIR INTAKE SYSTEM 20MBL | 14/05/2021 | 28/07/2021 | 14/05/2021 | 28/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MBR3A82 | TT_FinMile | (RFS) READY FOR SHIPMENT EXPANSION JOINT 20MBR | 22/03/2022 | 22/03/2022 |  |  | 304 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBR4-41 | TT_Task | TRANSPORT EXPANSION JOINT 20MBR | 30/04/2022 | 23/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MBR4-11 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION EXPANSION JOINT 20MBR | 23/02/2022 | 22/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MBR3-71 | TT_Mile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) EXPANSION JOINT 20MBR | 23/02/2022 | 23/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBR4-42 | TT_FinMile | (OTD-OS) ON SITE EXPANSION JOINT 20MBR | 23/07/2022 | 23/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--CYA2-95 | TT_Mile | BASIC DESIGN INPUT HANDOVER SIEMENS TO ATKINS - LIGHTING SMALL POWER SYSTEM | 09/04/2021 | 09/04/2021 | 09/04/2021 | 09/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MAJ6A16 | TT_Task | INSULATION PIPES / VALVES FOR STEAM SYSTEM MAJ | 19/08/2022 | 22/09/2022 |  |  | 552 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM1B8-30 | TT_Task | COMMISSIONING OF TP-M1B | 26/04/2023 | 02/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM1B3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-M1B | 19/07/2022 | 19/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM1B6-25 | TT_Task | TERMINATION OF TP-M1B | 17/10/2022 | 30/10/2022 |  |  | 1416 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM1B2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-M1B | 11/04/2021 | 08/05/2021 | 11/04/2021 | 08/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPM1B2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-M1B | 26/04/2022 | 26/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM1B6-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-M1B | 19/07/2022 | 16/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM1B2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-M1B | 26/04/2022 | 02/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM1B2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-M1B | 17/10/2022 | 17/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM1B8-26 | TT_Mile | MEDIA AVAILABLE TP-M1B | 26/04/2023 | 26/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBY4-56 | TT_FinMile | (RFE) FOUNDATION 20UBY04 | 06/06/2022 | 06/06/2022 |  |  | 192 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBY4-53 | TT_Task | WORK PREPARATION, EXCAVATION 20UBY04 | 29/03/2022 | 11/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBY4-55 | TT_Mile | (H) START PLACING FORMWORK 20UBY04 | 12/04/2022 | 12/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM2C8-30 | TT_Task | COMMISSIONING OF TP-M2C | 20/05/2023 | 26/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM2C3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-M2C | 17/09/2022 | 17/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM2C6-25 | TT_Task | TERMINATION OF TP-M2C | 22/10/2022 | 04/11/2022 |  |  | 1568 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM2C2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-M2C | 11/04/2021 | 08/05/2021 | 11/04/2021 | 08/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPM2C2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-M2C | 25/06/2022 | 25/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM2C6-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-M2C | 17/09/2022 | 21/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM2C2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-M2C | 25/06/2022 | 01/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM2C2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-M2C | 22/10/2022 | 22/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM2C8-26 | TT_Mile | MEDIA AVAILABLE TP-M2C | 20/05/2023 | 20/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM4A8-30 | TT_Task | COMMISSIONING OF TP-M4A | 01/06/2022 | 07/06/2022 |  |  | 2488 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM4A3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-M4A | 18/05/2022 | 18/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM4A6-25 | TT_Task | TERMINATION OF TP-M4A | 25/05/2022 | 31/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM4A2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-M4A | 11/04/2021 | 08/05/2021 | 11/04/2021 | 08/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPM4A2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-M4A | 10/12/2021 | 10/12/2021 | 10/12/2021 | 10/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPM4A6-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-M4A | 18/05/2022 | 31/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM4A2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-M4A | 10/12/2021 | 16/12/2021 | 10/12/2021 | 16/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPM4A2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-M4A | 18/05/2022 | 18/05/2022 |  |  | 56 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM4A8-26 | TT_Mile | MEDIA AVAILABLE TP-M4A | 01/06/2022 | 01/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM5A8-30 | TT_Task | COMMISSIONING OF TP-M5A | 25/07/2023 | 31/07/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM5A3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-M5A | 20/11/2022 | 20/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM5A6-25 | TT_Task | TERMINATION OF TP-M5A | 22/01/2023 | 04/02/2023 |  |  | 1360 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM5A2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-M5A | 11/04/2021 | 08/05/2021 | 11/04/2021 | 08/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPM5A2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-M5A | 01/09/2022 | 01/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM5A6-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-M5A | 20/11/2022 | 21/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM5A2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-M5A | 01/09/2022 | 07/09/2022 |  |  | 584 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM5A2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-M5A | 22/01/2023 | 22/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM5A8-26 | TT_Mile | MEDIA AVAILABLE TP-M5A | 25/07/2023 | 25/07/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAA7-67 | TT_Task | PLACEMENT BAA BELOW AIR FILTER HOUSE OUTER PART 20BAA | 23/08/2022 | 29/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAA3B81 | TT_FinMile | (RFS) READY FOR SHIPMENT IPB FIRST PARTS / SADDLES 20BAA | 27/06/2022 | 27/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAA4-42 | TT_Task | TRANSPORT IPB IPB FIRST PARTS / SADDLES 20BAA | 28/06/2022 | 22/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAA4-43 | TT_FinMile | (OTD-OS) ON SITE (ET8) IPB FIRST PARTS / SADDLES 20BAA | 22/08/2022 | 22/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAA4-41 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION IPB FIRST PARTS / SADDLES 20BAA | 31/05/2022 | 27/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAA3-71 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) IPB FIRST PARTS / SADDLES 20BAA | 30/05/2022 | 30/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBD5-64 | TT_Task | CONSTRUCTION FOUNDATION PLINGTHS 20UBG01/02- Rebarwork baseslab/foundation | 20/05/2022 | 26/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBD5-65 | TT_Task | CONSTRUCTION PLINTHS 20UBD01/02 | 14/05/2022 | 27/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBX5-46 | TT_Task | CONSTRUCTION PLINTHS 20UBX/20UBG03 | 31/05/2022 | 13/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM5B8-30 | TT_Task | COMMISSIONING OF TP-M5B | 25/07/2023 | 31/07/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM5B3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-M5B | 20/11/2022 | 20/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM5B6-25 | TT_Task | TERMINATION OF TP-M5B | 22/01/2023 | 04/02/2023 |  |  | 1360 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM5B2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-M5B | 11/04/2021 | 08/05/2021 | 11/04/2021 | 08/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPM5B2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-M5B | 01/09/2022 | 01/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM5B6-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-M5B | 20/11/2022 | 21/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM5B2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-M5B | 01/09/2022 | 07/09/2022 |  |  | 584 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM5B2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-M5B | 22/01/2023 | 22/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM5B8-26 | TT_Mile | MEDIA AVAILABLE TP-M5B | 25/07/2023 | 25/07/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM6A8-30 | TT_Task | COMMISSIONING OF TP-M6A | 23/04/2023 | 29/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM6A3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-M6A | 29/08/2022 | 29/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM6A6-25 | TT_Task | TERMINATION OF TP-M6A | 31/10/2022 | 13/11/2022 |  |  | 1280 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM6A2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-M6A | 11/04/2021 | 08/05/2021 | 11/04/2021 | 08/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPM6A2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-M6A | 08/05/2022 | 08/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM6A6-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-M6A | 29/08/2022 | 30/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM6A2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-M6A | 08/05/2022 | 14/05/2022 |  |  | 848 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM6A2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-M6A | 31/10/2022 | 31/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM6A8-26 | TT_Mile | MEDIA AVAILABLE TP-M6A | 23/04/2023 | 23/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM6B8-30 | TT_Task | COMMISSIONING OF TP-M6B | 23/04/2023 | 29/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM6B3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-M6B | 26/08/2022 | 26/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM6B6-25 | TT_Task | TERMINATION OF TP-M6B | 31/10/2022 | 13/11/2022 |  |  | 1280 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM6B2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-M6B | 11/04/2021 | 08/05/2021 | 11/04/2021 | 08/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPM6B2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-M6B | 08/05/2022 | 08/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM6B6-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-M6B | 26/08/2022 | 30/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM6B2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-M6B | 08/05/2022 | 14/05/2022 |  |  | 824 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM6B2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-M6B | 31/10/2022 | 31/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM6B8-26 | TT_Mile | MEDIA AVAILABLE TP-M6B | 23/04/2023 | 23/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM7A8-30 | TT_Task | COMMISSIONING OF TP-M7A | 27/05/2023 | 02/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM7A3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-M7A | 07/10/2022 | 07/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM7A6-25 | TT_Task | TERMINATION OF TP-M7A | 23/12/2022 | 05/01/2023 |  |  | 1128 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM7A2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-M7A | 11/04/2021 | 08/05/2021 | 11/04/2021 | 08/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPM7A2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-M7A | 17/07/2022 | 17/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM7A6-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-M7A | 07/10/2022 | 22/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM7A2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-M7A | 17/07/2022 | 23/07/2022 |  |  | 600 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM7A2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-M7A | 23/12/2022 | 23/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM7A8-26 | TT_Mile | MEDIA AVAILABLE TP-M7A | 27/05/2023 | 27/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM7B8-30 | TT_Task | COMMISSIONING OF TP-M7B | 30/05/2023 | 05/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM7B3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-M7B | 07/10/2022 | 07/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM7B6-25 | TT_Task | TERMINATION OF TP-M7B | 23/12/2022 | 05/01/2023 |  |  | 1152 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM7B2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-M7B | 11/04/2021 | 08/05/2021 | 11/04/2021 | 08/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPM7B2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-M7B | 17/07/2022 | 17/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM7B6-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-M7B | 07/10/2022 | 22/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM7B2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-M7B | 17/07/2022 | 23/07/2022 |  |  | 600 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM7B2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-M7B | 23/12/2022 | 23/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM7B8-26 | TT_Mile | MEDIA AVAILABLE TP-M7B | 30/05/2023 | 30/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM8A8-30 | TT_Task | COMMISSIONING OF TP-M8A | 30/05/2023 | 05/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM8A3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-M8A | 18/06/2022 | 18/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM8A6-25 | TT_Task | TERMINATION OF TP-M8A | 24/09/2022 | 07/10/2022 |  |  | 1872 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM8A2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-M8A | 11/04/2021 | 08/05/2021 | 11/04/2021 | 08/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPM8A2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-M8A | 25/03/2022 | 25/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM8A6-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-M8A | 18/06/2022 | 23/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM8A2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-M8A | 25/03/2022 | 31/03/2022 |  |  | 624 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM8A2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-M8A | 24/09/2022 | 24/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM8A8-26 | TT_Mile | MEDIA AVAILABLE TP-M8A | 30/05/2023 | 30/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM9A8-30 | TT_Task | COMMISSIONING OF TP-M9A | 08/06/2023 | 14/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM9A3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-M9A | 18/06/2022 | 18/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM9A6-25 | TT_Task | TERMINATION OF TP-M9A | 24/09/2022 | 07/10/2022 |  |  | 1944 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM9A2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-M9A | 16/04/2021 | 13/05/2021 | 16/04/2021 | 13/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPM9A2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-M9A | 25/03/2022 | 25/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM9A6-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-M9A | 18/06/2022 | 24/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM9A2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-M9A | 25/03/2022 | 31/03/2022 |  |  | 624 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM9A2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-M9A | 24/09/2022 | 24/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM9A8-26 | TT_Mile | MEDIA AVAILABLE TP-M9A | 08/06/2023 | 08/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM9B8-30 | TT_Task | COMMISSIONING OF TP-M9B | 08/06/2023 | 14/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM9B3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-M9B | 18/05/2022 | 18/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM9B6-25 | TT_Task | TERMINATION OF TP-M9B | 24/08/2022 | 06/09/2022 |  |  | 2192 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM9B2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-M9B | 11/04/2021 | 08/05/2021 | 11/04/2021 | 08/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPM9B2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-M9B | 09/02/2022 | 09/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM9B6-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-M9B | 18/05/2022 | 23/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM9B2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-M9B | 09/02/2022 | 15/02/2022 |  |  | 112 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM9B2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-M9B | 24/08/2022 | 24/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM9B8-26 | TT_Mile | MEDIA AVAILABLE TP-M9B | 08/06/2023 | 08/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM10A8-30 | TT_Task | COMMISSIONING OF TP-M10A | 28/05/2022 | 03/06/2022 |  |  | 2488 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM10A3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-M10A | 14/05/2022 | 14/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM10A6-25 | TT_Task | TERMINATION OF TP-M10A | 21/05/2022 | 27/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM10A2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-M10A | 11/04/2021 | 08/05/2021 | 11/04/2021 | 08/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPM10A2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-M10A | 11/12/2021 | 11/12/2021 | 11/12/2021 | 11/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPM10A6-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-M10A | 14/05/2022 | 27/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM10A2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-M10A | 11/12/2021 | 17/12/2021 | 11/12/2021 | 17/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPM10A2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-M10A | 14/05/2022 | 14/05/2022 |  |  | 56 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM10A8-26 | TT_Mile | MEDIA AVAILABLE TP-M10A | 28/05/2022 | 28/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM13A8-30 | TT_Task | COMMISSIONING OF TP-M13A | 16/06/2023 | 22/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM13A3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-M13A | 01/07/2022 | 01/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM13A6-25 | TT_Task | TERMINATION OF TP-M13A | 23/09/2022 | 06/10/2022 |  |  | 2016 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM13A2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-M13A | 11/04/2021 | 08/05/2021 | 11/04/2021 | 08/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPM13A2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-M13A | 08/04/2022 | 08/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM13A6-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-M13A | 01/07/2022 | 22/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM13A2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-M13A | 08/04/2022 | 14/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM13A2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-M13A | 23/09/2022 | 23/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM13A8-26 | TT_Mile | MEDIA AVAILABLE TP-M13A | 16/06/2023 | 16/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM13B8-30 | TT_Task | COMMISSIONING OF TP-M13B | 16/06/2023 | 22/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM13B3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-M13B | 01/07/2022 | 01/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM13B6-25 | TT_Task | TERMINATION OF TP-M13B | 23/09/2022 | 06/10/2022 |  |  | 2016 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM13B2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-M13B | 11/04/2021 | 08/05/2021 | 11/04/2021 | 08/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPM13B2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-M13B | 08/04/2022 | 08/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM13B6-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-M13B | 01/07/2022 | 22/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM13B2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-M13B | 08/04/2022 | 14/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM13B2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-M13B | 23/09/2022 | 23/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM13B8-26 | TT_Mile | MEDIA AVAILABLE TP-M13B | 16/06/2023 | 16/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---3M118 | TT_FinMile | (RFS) READY FOR SHIPMENT LOOSE STEEL FOR MODULES LOT 2 (20UMCL1Y/20UMCM1Y) | 19/03/2022 | 19/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---4M29 | TT_Task | TRANSPORT LOOSE STEEL FOR MODULES LOT 2 (20UMCL1Y/20UMCM1Y) | 20/03/2022 | 12/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---4M28 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION LOOSE STEEL FOR MODULES LOT 2 (20UMCL1Y/20UMCM1Y) | 20/02/2022 | 19/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---3M117 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) LOOSE STEEL FOR MODULES LOT 2 (20UMCL1Y/20UMCM1Y) | 19/02/2022 | 19/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC4M42 | TT_FinMile | (OTD-OS) ON SITE LOOSE STEEL MODULE 20UMCM1Y | 12/04/2022 | 12/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC6M42 | TT_Task | ERECTION LOOSE STEEL FOR MODULE 20UMCM1Y | 13/04/2022 | 10/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC4M43 | TT_FinMile | (OTD-OS) ON SITE LOOSE STEEL MODULE 20UMCM1Y | 12/04/2022 | 12/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC6M43 | TT_Task | ERECTION LOOSE STEEL FOR MODULE 20UMCM1Y | 13/04/2022 | 10/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---3M120 | TT_FinMile | (RFS) READY FOR SHIPMENT LOOSE STEEL FOR MODULES LOT 1 (20UMY00Y/20ULY00Y) | 14/02/2022 | 14/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---4M31 | TT_Task | TRANSPORT LOOSE STEEL FOR MODULES LOT 1 (20UMY00Y/20ULY00Y) | 15/02/2022 | 10/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---4M30 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION LOOSE STEEL FOR MODULES LOT 1 (20UMY00Y/20ULY00Y) | 18/01/2022 | 14/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---3M119 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) LOOSE STEEL FOR MODULES LOT 1 (20UMY00Y/20ULY00Y) | 18/01/2022 | 18/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMY4M41 | TT_FinMile | (OTD-OS) ON SITE LOOSE STEEL FOR MODULE 20UMY00Y/20ULY00Y | 10/03/2022 | 10/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---3M122 | TT_FinMile | (RFS) READY FOR SHIPMENT LOOSE STEEL FOR MODULES LOT 3 (20UEY1Y/20UEY02Y) | 20/04/2022 | 20/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---4M33 | TT_Task | TRANSPORT LOOSE STEEL FOR MODULES LOT 3 (20UEY1Y/20UEY02Y) | 21/04/2022 | 14/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---4M32 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION LOOSE STEEL FOR MODULES LOT 3 (20UEY1Y/20UEY02Y) | 24/03/2022 | 20/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---3M121 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) LOOSE STEEL FOR MODULES LOT 3 (20UEY1Y/20UEY02Y) | 23/03/2022 | 23/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY4-131 | TT_FinMile | (OTD-OS) ON SITE LOOSE STEEL FOR MODULE 20UEY01Y | 14/05/2022 | 14/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY4-132 | TT_FinMile | (OTD-OS) ON SITE LOOSE STEEL FOR MODULE 20UEY02Y | 14/05/2022 | 14/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMY6M77 | TT_Task | PRE-ASSEMBLY UMY00Y-A11/A41/D11/D41 (inside UMC Building) | 25/03/2022 | 21/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC6B-5 | TT_FinMile | (OTD-OS) ON SITE PIPES CA01-UMC-WA05B (Gxx,LBA20/90,LBx,LCx,LDK,MAx,MBx,MKx,PAB,PAH,PCB,PGB,QC,QFB,SCB,SGx) | 06/04/2022 | 06/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC6B-10 | TT_Task | WORK PREPARATION PIPING CA01-UMC-WA05B | 07/04/2022 | 20/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC6B-15 | TT_Task | ERECTION,NDT LB PIPES / VALVES CA01-UMC-WA05B (Gxx,LBA20/90,LBx,LCx,LDK,MAx,MBx,MKx,PAB,PAH,PCB,PGB,QC,QFB,SCB,SGx) | 21/04/2022 | 23/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC6B-20 | TT_Task | ERECTION,NDT SB PIPES / VALVES CA01-UMC-WA05B (Gxx,LBA20/90,LBx,LCx,LDK,MAx,MBx,MKx,PAB,PAH,PCB,PGB,QC,QFB,SCB,SGx) | 27/10/2022 | 15/02/2023 |  |  | 240 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC6A-5 | TT_FinMile | (OTD-OS) ON SITE PIPES CA01-UMC-WA02A (LDK,MAG) | 06/04/2022 | 06/04/2022 |  |  | 296 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC6A-10 | TT_Task | WORK PREPARATION PIPING CA01-UMC-WA02A (LDK,MAG) | 14/05/2022 | 27/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC6A-15 | TT_Task | ERECTION,NDT LB PIPES / VALVES CA01-UMC-WA02A (LDK,MAG) | 31/05/2022 | 29/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC6A-20 | TT_Task | ERECTION,NDT SB PIPES / VALVES CA01-UMC-WA02A (LDK,MAG) | 16/08/2022 | 26/09/2022 |  |  | 1376 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC6B-25 | TT_FinMile | (OTD-OS) ON SITE PIPES CA01-UMC-WA03B (Gxx,LBA90,LBx,LCA,LDK,LDT,MAJ,MAM,MAW,PCB,PGB,QC,QFB,SBM,SCB,SGA) | 06/04/2022 | 06/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC6B-30 | TT_Task | WORK PREPARATION PIPING CA01-WA03B (Gxx,LBA90,LBx,LCA,LDK,LDT,MAJ,MAM,MAW,PCB,PGB,QC,QFB,SBM,SCB,SGA) | 28/05/2022 | 10/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC6B-35 | TT_Task | ERECTION,NDT LB PIPES / VALVES CA01-UMC-WA03B (Gxx,LBA90,LBx,LCA,LDK,LDT,MAJ,MAM,MAW,PCB,PGB,QC,QFB,SBM,SCB,SGA) | 11/06/2022 | 23/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC6B-40 | TT_Task | ERECTION,NDT SB PIPES / VALVES CA01-UMC-WA03B (Gxx,LBA90,LBx,LCA,LDK,LDT,MAJ,MAM,MAW,PCB,PGB,QC,QFB,SBM,SCB,SGA) | 10/09/2022 | 28/10/2022 |  |  | 1120 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC6B-45 | TT_FinMile | (OTD-OS) ON SITE PIPES CA01-UMC-WA04B (EGD,EKG70,Gxx,LBA90,LBx,LCA,LDK;MBA;MBH,PGB,QC,QFB,QU,SBM,SCB) | 06/04/2022 | 06/04/2022 |  |  | 72 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC6B-50 | TT_Task | WORK PREPARATION PIPING CA01-WA04B (EGD,EKG70,Gxx,LBA90,LBx,LCA,LDK;MBA;MBH,PGB,QC,QFB,QU,SBM,SCB) | 16/04/2022 | 13/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC6B-55 | TT_Task | ERECTION,NDT LB PIPES / VALVES CA01-UMC-WA04B (EGD,EKG70,Gxx,LBA90,LBx,LCA,LDK;MBA;MBH,PGB,QC,QFB,QU,SBM,SCB) | 14/05/2022 | 02/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC6B-60 | TT_Task | ERECTION,NDT SB PIPES / VALVES CA01-UMC-WA04B (EGD,EKG70,Gxx,LBA90,LBx,LCA,LDK;MBA;MBH,PGB,QC,QFB,QU,SBM,SCB) | 20/08/2022 | 14/10/2022 |  |  | 1232 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC6B-65 | TT_FinMile | (OTD-OS) ON SITE PIPES CA01-UMC-WA06B (MAV,MAX,MBA,MBH,MKx,PGB,QFB,QJA,SBM,SCB,SGA,SGC,SGE) | 06/04/2022 | 06/04/2022 |  |  | 224 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC6B-70 | TT_Task | WORK PREPARATION PIPING CA01-WA06B (MAV,MAX,MBA,MBH,MKx,PGB,QFB,QJA,SBM,SCB,SGA,SGC,SGE) | 05/05/2022 | 18/05/2022 |  |  | 48 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC6B-75 | TT_Task | ERECTION,NDT LB PIPES / VALVES CA01-UMC-WA06B (MAV,MAX,MBA,MBH,MKx,PGB,QFB,QJA,SBM,SCB,SGA,SGC,SGE) | 25/05/2022 | 11/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC6B-80 | TT_Task | ERECTION,NDT SB PIPES / VALVES CA01-UMC-WA06B (MAV,MAX,MBA,MBH,MKx,PGB,QFB,QJA,SBM,SCB,SGA,SGC,SGE) | 21/09/2022 | 22/11/2022 |  |  | 920 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMY6B-5 | TT_FinMile | (OTD-OS) ON SITE PIPES CA02-UMY-WA00B (EGD,EKx,Gxx,HSJ,LAB,LBA90,LBx,LCA,LCL,MAV,MBA,PGB,QC,QFB,QJA,QU,SCB) | 06/04/2022 | 06/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMY6B-10 | TT_Task | WORK PREPARATION PIPING CA02-UMY-WA00B (EGD,EKx,Gxx,HSJ,LAB,LBA90,LBx,LCA,LCL,MAV,MBA,PGB,QC,QFB,QJA,QU,SCB) | 17/04/2022 | 14/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMY6B-15 | TT_Task | ERECTION,NDT LB PIPES / VALVES CA02-UMY-WA00B (EGD,EKx,Gxx,HSJ,LAB,LBA90,LBx,LCA,LCL,MAV,MBA,PGB,QC,QFB,QJA,QU,SCB) | 26/05/2022 | 23/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMY6B-20 | TT_Task | ERECTION,NDT SB PIPES / VALVES CA02-UMY-WA00B (EGD,EKx,Gxx,HSJ,LAB,LBA90,LBx,LCA,LCL,MAV,MBA,PGB,QC,QFB,QJA,QU,SCB) | 07/11/2022 | 01/03/2023 |  |  | 128 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UHW6A-5 | TT_FinMile | (OTD-OS) ON SITE PIPES CA02-UHW-WA00A (LCL) | 06/04/2022 | 06/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UHW6A-10 | TT_Task | WORK PREPARATION PIPING CA02-UHW-WA00A (LCL) | 07/04/2022 | 20/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UHW6A-15 | TT_Task | ERECTION,NDT LB PIPES / VALVES CA02-UHW-WA00A (LCL) | 21/04/2022 | 19/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UHW6A-20 | TT_Task | ERECTION,NDT SB PIPES / VALVES CA02-UHW-WA00A (LCL) | 06/10/2022 | 07/12/2022 |  |  | 800 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UHA6-5 | TT_FinMile | (OTD-OS) ON SITE PIPES CA02 (EKG,EKT,GHC,GKB,PGB,QC,SCB) | 06/04/2022 | 06/04/2022 |  |  | 1960 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UHA6-10 | TT_Task | WORK PREPARATION PIPING CA02 (EKG,EKT,GHC,GKB,PGB,QC,SCB) | 08/12/2022 | 21/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UHA6-15 | TT_Task | ERECTION,NDT LB PIPES / VALVES CA02 (EKG,EKT,GHC,GKB,PGB,QC,SCB) | 22/12/2022 | 15/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UHA6-20 | TT_Task | ERECTION,NDT SB PIPES / VALVES CA02 (EKG,EKT,GHC,GKB,PGB,QC,SCB) | 02/02/2023 | 29/03/2023 |  |  | 16 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UHA6B-5 | TT_FinMile | (OTD-OS) ON SITE PIPES CA02-UHA-WA00B (EKG,GHD,GKB,GM,HAD,HSJ,LAB,LBA90,LBH,LCA,SCB) | 06/04/2022 | 06/04/2022 |  |  | 80 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UHA6B-10 | TT_Task | WORK PREPARATION PIPING CA02-UHA-WA00B (EKG,GHD,GKB,GM,HAD,HSJ,LAB,LBA90,LBH,LCA,SCB) | 17/04/2022 | 05/05/2022 |  |  | 120 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UHA6B-15 | TT_Task | ERECTION,NDT LB PIPES / VALVES CA02-UHA-WA00B (EKG,GHD,GKB,GM,LAB,LBA90,LBH,LCA,SCB) | 21/05/2022 | 02/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UHA6B-20 | TT_Task | ERECTION,NDT SB PIPES / VALVES CA02-UHA-WA00B (EKG,GHD,GKB,GM,HAD,HSJ,LAB,LBA90,LBH,LCA,SCB) | 05/08/2022 | 06/10/2022 |  |  | 1296 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA6-5 | TT_FinMile | (OTD-OS) ON SITE PIPES CA03 (PAB,PAR,PSB) | 05/05/2022 | 05/05/2022 |  |  | 424 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA6-10 | TT_Task | WORK PREPARATION PIPING CA03 (MAV, PAB,PAR,PSB,PUS) | 28/06/2022 | 11/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA6-15 | TT_Task | ERECTION,NDT LB PIPES / VALVES CA03 (MAV, PAB,PAR,PSB,PUS) | 12/07/2022 | 14/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA6-20 | TT_Task | ERECTION,NDT SB PIPES / VALVES CA03 (MAV, PAB,PAR,PSB,PUS) | 01/11/2022 | 02/01/2023 |  |  | 592 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEN65 | TT_FinMile | (OTD-OS) ON SITE PIPES CA04 (EGD,EKG,GHC,GHD,GKB,GM,HSJ,LCL,MAV,PSB,QFB,QJA,SCB) | 05/05/2022 | 05/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEN610 | TT_Task | WORK PREPARATION PIPING CA04 (EGD,EKG,GHC,GHD,GKB,GM,HSJ,LCL,MAV,PSB,QFB,QJA,SCB) | 18/05/2022 | 31/05/2022 |  |  | 48 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEN615 | TT_Task | ERECTION,NDT LB PIPES / VALVES CA04 (EGD,EKG,GHC,GHD,GKB,GM,HSJ,LCL,MAV,PSB,QFB,QJA,SCB) | 07/06/2022 | 24/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEN620 | TT_Task | ERECTION,NDT SB PIPES / VALVES CA04 (EGD,EKG,GHC,GHD,GKB,GM,HSJ,LCL,MAV,PSB,QFB,QJA,SCB) | 21/09/2022 | 15/11/2022 |  |  | 976 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBF65 | TT_FinMile | (OTD-OS) ON SITE PIPES CA05 (EGD,GHD,GKB,LDT) | 20/04/2022 | 20/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBF610 | TT_Task | WORK PREPARATION PIPING CA05 (EGD,GHD,GKB,LDT) | 21/04/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBF615 | TT_Task | ERECTION,NDT LB PIPES / VALVES CA05 (EGD,GHD,GKB,LDT) | 05/05/2022 | 22/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBF620 | TT_Task | ERECTION,NDT SB PIPES / VALVES CA05 (EGD,GHD,GKB,LDT) | 02/06/2022 | 22/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC6A-40 | TT_FinMile | (OTD-OS) ON SITE PIPES CA01-UMC-WA01A (GMM,LCA,LCE,LDK,MAG,MAW,SCB) | 06/04/2022 | 06/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC6A-25 | TT_Task | WORK PREPARATION PIPING CA01-UMC-WA01A (GMM,LCA,LCE,LDK,MAG,MAW,SCB) | 07/04/2022 | 20/04/2022 |  |  | 40 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC6A-30 | TT_Task | ERECTION,NDT LB PIPES / VALVES CA01-UMC-WA01A (GMM,LCA,LCE,LDK,MAG,MAW,SCB) | 26/04/2022 | 15/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC6A-35 | TT_Task | ERECTION,NDT SB PIPES / VALVES CA01-UMC-WA01A (GMM,LCA,LCE,LDK,MAG,MAW,SCB) | 02/08/2022 | 12/09/2022 |  |  | 1488 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC6-5 | TT_FinMile | (OTD-OS) ON SITE PIPES CA01 (GHD,GKB,LDT) | 06/04/2022 | 06/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC6-10 | TT_Task | WORK PREPARATION PIPING CA01 (GHD,GKB,LDT) | 07/04/2022 | 20/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC6-15 | TT_Task | ERECTION,NDT LB PIPES / VALVES CA01 (GHD,GKB,LDT) | 21/04/2022 | 22/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC6-20 | TT_Task | ERECTION,NDT SB PIPES / VALVES CA01 (GHD,GKB,LDT) | 09/06/2022 | 20/07/2022 |  |  | 1920 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEZ6A-20 | TT_FinMile | (OTD-OS) ON SITE PIPES CA06-UEZ-WA00A (EGD,EKG,GHC,GHD,GKB,MAV,QFB,QJA,SCB) | 06/04/2022 | 06/04/2022 |  |  | 328 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEZ6A-5 | TT_Task | WORK PREPARATION PIPING CA06-UEZ-WA00A (EGD,EKG,GHC,GHD,GKB,MAV,QFB,QJA,SCB) | 18/05/2022 | 31/05/2022 |  |  | 48 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEZ6A-10 | TT_Task | ERECTION,NDT LB PIPES / VALVES CA06-UEZ-WA00A (EGD,EKG,GHC,GHD,GKB,MAV,QFB,QJA,SCB) | 07/06/2022 | 19/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEZ6A-15 | TT_Task | ERECTION,NDT SB PIPES / VALVES CA06-UEZ-WA00A (EGD,EKG,GHC,GHD,GKB,MAV,QFB,QJA,SCB) | 17/08/2022 | 11/10/2022 |  |  | 1256 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEZ6B-20 | TT_FinMile | (OTD-OS) ON SITE PIPES CA06-UEZ-WA00B (EGD,EKG,GHC,GHD,GKB,QFB,QJA,SCB) | 06/04/2022 | 06/04/2022 |  |  | 216 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEZ6B-5 | TT_Task | WORK PREPARATION PIPING CA06-UEZ-WA00B (EGD,EKG,GHC,GHD,GKB,QFB,QJA,SCB) | 04/05/2022 | 17/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEZ6B-10 | TT_Task | ERECTION,NDT LB PIPES / VALVES CA06-UEZ-WA00B (EGD,EKG,GHC,GHD,GKB,QFB,QJA,SCB) | 18/05/2022 | 04/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEZ6B-15 | TT_Task | ERECTION,NDT SB PIPES / VALVES CA06-UEZ-WA00B (EGD,EKG,GHC,GHD,GKB,QFB,QJA,SCB) | 05/10/2022 | 20/12/2022 |  |  | 696 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UVM6B15 | TT_FinMile | (OTD-OS) ON SITE PIPES CA07-UVM-WA00B (HSJ,PSB) | 05/05/2022 | 05/05/2022 |  |  | 336 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UVM6B20 | TT_Task | WORK PREPARATION PIPING CA07-UVM-WA00B (HSJ,PSB) | 17/06/2022 | 30/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UVM6B5 | TT_Task | ERECTION,NDT LB PIPES / VALVES CA07-UVM-WA00B (HSJ,PSB) | 01/07/2022 | 20/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UVM6B10 | TT_Task | ERECTION,NDT SB PIPES / VALVES CA07-UVM-WA00B (HSJ,PSB) | 07/10/2022 | 01/12/2022 |  |  | 848 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMY6B10 | TT_FinMile | (OTD-OS) ON SITE PIPES CA07-UMY-WA00B | 06/04/2022 | 06/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMY6B15 | TT_Task | WORK PREPARATION PIPING CA07-UMY-WA00B | 07/04/2022 | 20/04/2022 |  |  | 104 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMY6B20 | TT_Task | ERECTION,NDT LB PIPES / VALVES CA07-UMY-WA00B | 04/05/2022 | 12/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMY6B5 | TT_Task | ERECTION,NDT SB PIPES / VALVES CA07-UMY-WA00B | 29/06/2022 | 09/08/2022 |  |  | 1760 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20ULD6B5 | TT_FinMile | (OTD-OS) ON SITE PIPES CA07-ULD-WA00B (LDN,LDT) | 06/04/2022 | 06/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20ULD6B10 | TT_Task | WORK PREPARATION PIPING CA07-ULD-WA00B (LDN,LDT) | 07/04/2022 | 20/04/2022 |  |  | 104 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20ULD6B15 | TT_Task | ERECTION,NDT LB PIPES / VALVES CA07-ULD-WA00B (LDN,LDT) | 04/05/2022 | 12/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20ULD6B20 | TT_Task | ERECTION,NDT SB PIPES / CA07-ULD-WA00B (LDN,LDT) | 29/06/2022 | 09/08/2022 |  |  | 1760 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UZ6A20 | TT_FinMile | (OTD-OS) ON SITE PIPES CA01-UZ-WA00A (PAB) | 07/07/2021 | 07/07/2021 | 07/07/2021 | 07/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UZ6A5 | TT_Task | WORK PREPARATION PIPING CA01-UZ-WA00A (PAB) | 08/07/2021 | 21/07/2021 | 08/07/2021 | 21/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UZ6A10 | TT_Task | ERECTION,NDT LB PIPES / VALVES CA01-UZ-WA00A (PAB) | 02/08/2021 | 29/11/2021 | 02/08/2021 | 29/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UZ6A15 | TT_Task | ERECTION,NDT SB PIPES / VALVES CA01-UZ-WA00A (PAB) | 04/10/2021 | 29/11/2021 | 04/10/2021 | 29/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UZ6A25 | TT_FinMile | (OTD-OS) ON SITE PIPES CA02-UZ-WA00A (PAB) | 21/08/2021 | 21/08/2021 | 21/08/2021 | 21/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UZ6A30 | TT_Task | WORK PREPARATION PIPING CA02-UZ-WA00A (PAB) | 22/08/2021 | 30/09/2021 | 22/08/2021 | 30/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UZ6A35 | TT_Task | ERECTION,NDT LB PIPES / VALVES CA02-UZ-WA00A (PAB) | 22/08/2021 | 29/11/2021 | 22/08/2021 | 29/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UZ6A40 | TT_Task | ERECTION,NDT SB PIPES / VALVES CA02-UZ-WA00A (PAB) | 04/10/2021 | 30/11/2021 | 04/10/2021 | 30/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--URA2-90 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN CONCRETE SUPERSTRUCTURE 20URA-To be used/cancel xx | 25/06/2021 | 19/07/2021 | 25/06/2021 | 19/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--URA2-91 | TT_FinMile | START ON SITE SUPERSTRUCTURE-20URA/URD | 03/12/2021 | 03/12/2021 | 03/12/2021 | 03/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPM14A8-30 | TT_Task | COMMISSIONING OF TP-M14A | 16/06/2023 | 22/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM14A3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-M14A | 01/07/2022 | 01/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM14A6-25 | TT_Task | TERMINATION OF TP-M14A | 23/09/2022 | 06/10/2022 |  |  | 2016 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM14A2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-M14A | 11/04/2021 | 08/05/2021 | 11/04/2021 | 08/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPM14A2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-M14A | 08/04/2022 | 08/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM14A6-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-M14A | 01/07/2022 | 22/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM14A2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-M14A | 08/04/2022 | 14/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM14A2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-M14A | 23/09/2022 | 23/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM14A8-26 | TT_Mile | MEDIA AVAILABLE TP-M14A | 16/06/2023 | 16/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM14B8-30 | TT_Task | COMMISSIONING OF TP-M14B | 16/06/2023 | 22/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM14B3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-M14B | 01/07/2022 | 01/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM14B6-25 | TT_Task | TERMINATION OF TP-M14B | 23/09/2022 | 06/10/2022 |  |  | 2016 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM14B2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-M14B | 11/04/2021 | 08/05/2021 | 11/04/2021 | 08/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPM14B2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-M14B | 08/04/2022 | 08/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM14B6-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-M14B | 01/07/2022 | 22/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM14B2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-M14B | 08/04/2022 | 14/04/2022 |  |  | 616 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM14B2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-M14B | 23/09/2022 | 23/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM14B8-26 | TT_Mile | MEDIA AVAILABLE TP-M14B | 16/06/2023 | 16/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM15A8-30 | TT_Task | COMMISSIONING OF TP-M15A | 20/05/2023 | 26/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM15A3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-M15A | 01/02/2022 | 01/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM15A6-25 | TT_Task | TERMINATION OF TP-M15A | 16/03/2022 | 29/03/2022 |  |  | 3328 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM15A2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-M15A | 11/04/2021 | 08/05/2021 | 11/04/2021 | 08/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPM15A2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-M15A | 25/01/2022 | 25/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM15A6-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-M15A | 01/02/2022 | 15/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM15A2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-M15A | 25/01/2022 | 31/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM15A2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-M15A | 16/03/2022 | 16/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM15A8-26 | TT_Mile | MEDIA AVAILABLE TP-M15A | 20/05/2023 | 20/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM16A8-30 | TT_Task | COMMISSIONING OF TP-M16A | 20/05/2023 | 26/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM16A3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-M16A | 01/02/2022 | 01/02/2022 |  |  | 584 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM16A6-25 | TT_Task | TERMINATION OF TP-M16A | 13/05/2022 | 26/05/2022 |  |  | 2864 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM16A2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-M16A | 11/04/2021 | 08/05/2021 | 11/04/2021 | 08/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPM16A2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-M16A | 08/04/2022 | 08/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM16A6-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-M16A | 15/04/2022 | 12/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM16A2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-M16A | 08/04/2022 | 14/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM16A2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-M16A | 13/05/2022 | 13/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM16A8-26 | TT_Mile | MEDIA AVAILABLE TP-M16A | 20/05/2023 | 20/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM17A8-30 | TT_Task | COMMISSIONING OF TP-M17A | 16/06/2023 | 22/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM17A3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-M17A | 29/08/2022 | 29/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM17A6-25 | TT_Task | TERMINATION OF TP-M17A | 26/09/2022 | 09/10/2022 |  |  | 1992 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM17A2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-M17A | 11/04/2021 | 08/05/2021 | 11/04/2021 | 08/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPM17A2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-M17A | 07/06/2022 | 07/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM17A6-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-M17A | 29/08/2022 | 25/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM17A2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-M17A | 07/06/2022 | 13/06/2022 |  |  | 608 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM17A2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-M17A | 26/09/2022 | 26/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM17A8-26 | TT_Mile | MEDIA AVAILABLE TP-M17A | 16/06/2023 | 16/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM18A8-30 | TT_Task | COMMISSIONING OF TP-M18A | 16/06/2023 | 22/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM18A3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-M18A | 30/08/2022 | 30/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM18A6-25 | TT_Task | TERMINATION OF TP-M18A | 27/09/2022 | 10/10/2022 |  |  | 1984 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM18A2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-M18A | 11/04/2021 | 08/05/2021 | 11/04/2021 | 08/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPM18A2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-M18A | 07/06/2022 | 07/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM18A6-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-M18A | 30/08/2022 | 26/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM18A2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-M18A | 07/06/2022 | 13/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM18A2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-M18A | 27/09/2022 | 27/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM18A8-26 | TT_Mile | MEDIA AVAILABLE TP-M18A | 16/06/2023 | 16/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM19A8-30 | TT_Task | NOT APPLICABLE - COMMISSIONING OF TP-M19A | 06/05/2023 | 12/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM19A3-15 | TT_Mile | NOT APPLICABLE - MATERIAL FOR TP INTEGRATION ON SITE TP-M19A | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM19A6-25 | TT_Task | NOT APPLICABLE - TERMINATION OF TP-M19A | 01/06/2022 | 14/06/2022 |  |  | 2600 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM19A2-5 | TT_Task | NOT APPLICABLE - TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-M19A | 11/04/2021 | 08/05/2021 | 11/04/2021 | 08/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPM19A2-10 | TT_Mile | NOT APPLICABLE - FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-M19A | 09/02/2022 | 09/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM19A6-20 | TT_Task | NOT APPLICABLE - INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-M19A | 04/05/2022 | 31/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM19A2-11 | TT_Task | NOT APPLICABLE - UPDATE OF TRANSITION PLAN TP-M19A | 09/02/2022 | 15/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM19A2-16 | TT_Mile | NOT APPLICABLE - ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-M19A | 01/06/2022 | 01/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM19A8-26 | TT_Mile | NOT APPLICABLE - MEDIA AVAILABLE TP-M19A | 06/05/2023 | 06/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM20A8-30 | TT_Task | NOT APPLICABLE - COMMISSIONING OF TP-M20A | 15/04/2023 | 21/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM20A3-15 | TT_Mile | NOT APPLICABLE - MATERIAL FOR TP INTEGRATION ON SITE TP-M20A | 04/08/2022 | 04/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM20A6-25 | TT_Task | NOT APPLICABLE - TERMINATION OF TP-M20A | 15/09/2022 | 28/09/2022 |  |  | 1584 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM20A2-5 | TT_Task | NOT APPLICABLE - TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-M20A | 11/04/2021 | 08/05/2021 | 11/04/2021 | 08/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPM20A2-10 | TT_Mile | NOT APPLICABLE - FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-M20A | 01/05/2022 | 01/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM20A6-20 | TT_Task | NOT APPLICABLE - INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-M20A | 04/08/2022 | 14/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM20A2-11 | TT_Task | NOT APPLICABLE - UPDATE OF TRANSITION PLAN TP-M20A | 01/05/2022 | 07/05/2022 |  |  | 88 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM20A2-16 | TT_Mile | NOT APPLICABLE - ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-M20A | 15/09/2022 | 15/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM20A8-26 | TT_Mile | NOT APPLICABLE - MEDIA AVAILABLE TP-M20A | 15/04/2023 | 15/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM21A8-30 | TT_Task | NOT APPLICABLE - COMMISSIONING OF TP-M21A | 15/04/2023 | 21/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM21A3-15 | TT_Mile | NOT APPLICABLE - MATERIAL FOR TP INTEGRATION ON SITE TP-M21A | 04/08/2022 | 04/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM21A6-25 | TT_Task | NOT APPLICABLE - TERMINATION OF TP-M21A | 15/09/2022 | 28/09/2022 |  |  | 1584 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM21A2-5 | TT_Task | NOT APPLICABLE - TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-M21A | 04/06/2021 | 01/07/2021 | 04/06/2021 | 01/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPM21A2-10 | TT_Mile | NOT APPLICABLE - FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-M21A | 12/05/2022 | 12/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM21A6-20 | TT_Task | NOT APPLICABLE - INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-M21A | 04/08/2022 | 14/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM21A2-11 | TT_Task | NOT APPLICABLE - UPDATE OF TRANSITION PLAN TP-M21A | 12/05/2022 | 18/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM21A2-16 | TT_Mile | NOT APPLICABLE - ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-M21A | 15/09/2022 | 15/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM21A8-26 | TT_Mile | NOT APPLICABLE - MEDIA AVAILABLE TP-M21A | 15/04/2023 | 15/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI12A8-30 | TT_Task | COMMISSIONING OF TP-I12 | 14/02/2023 | 20/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI12A3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-I12 | 30/06/2022 | 30/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI12A6-25 | TT_Task | TERMINATION OF TP-I12 | 28/07/2022 | 10/08/2022 |  |  | 1496 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI12A2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-I12 | 24/05/2021 | 18/07/2021 | 24/05/2021 | 18/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPI12A2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-I12 | 19/07/2021 | 19/07/2021 | 19/07/2021 | 19/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPI12A6-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-I12 | 30/06/2022 | 27/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI12A2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-I12 | 07/04/2022 | 13/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI12A2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-I12 | 28/07/2022 | 28/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI12A8-26 | TT_Mile | MEDIA AVAILABLE TP-I12 | 14/02/2023 | 14/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM22A8-30 | TT_Task | NOT APPLICABLE - COMMISSIONING OF TP-M22A | 15/04/2023 | 21/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM22A3-15 | TT_Mile | NOT APPLICABLE - MATERIAL FOR TP INTEGRATION ON SITE TP-M22A | 20/10/2022 | 20/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM22A6-25 | TT_Task | NOT APPLICABLE - TERMINATION OF TP-M22A | 01/12/2022 | 14/12/2022 |  |  | 968 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM22A2-5 | TT_Task | NOT APPLICABLE - TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-M22A | 04/06/2021 | 01/07/2021 | 04/06/2021 | 01/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPM22A2-10 | TT_Mile | NOT APPLICABLE - FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-M22A | 28/07/2022 | 28/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM22A6-20 | TT_Task | NOT APPLICABLE - INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-M22A | 20/10/2022 | 30/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM22A2-11 | TT_Task | NOT APPLICABLE - UPDATE OF TRANSITION PLAN TP-M22A | 28/07/2022 | 03/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM22A2-16 | TT_Mile | NOT APPLICABLE - ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-M22A | 01/12/2022 | 01/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM22A8-26 | TT_Mile | NOT APPLICABLE - MEDIA AVAILABLE TP-M22A | 15/04/2023 | 15/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM23A8-30 | TT_Task | NOT APPLICABLE - COMMISSIONING OF TP-M23A | 15/04/2023 | 21/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM23A3-15 | TT_Mile | NOT APPLICABLE - MATERIAL FOR TP INTEGRATION ON SITE TP-M23A | 04/08/2022 | 04/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM23A6-25 | TT_Task | NOT APPLICABLE - TERMINATION OF TP-M23A | 15/09/2022 | 28/09/2022 |  |  | 1584 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM23A2-5 | TT_Task | NOT APPLICABLE - TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-M23A | 04/06/2021 | 01/07/2021 | 04/06/2021 | 01/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPM23A2-10 | TT_Mile | NOT APPLICABLE - FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-M23A | 12/05/2022 | 12/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM23A6-20 | TT_Task | NOT APPLICABLE - INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-M23A | 04/08/2022 | 14/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM23A2-11 | TT_Task | NOT APPLICABLE - UPDATE OF TRANSITION PLAN TP-M23A | 12/05/2022 | 18/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM23A2-16 | TT_Mile | NOT APPLICABLE - ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-M23A | 15/09/2022 | 15/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM23A8-26 | TT_Mile | NOT APPLICABLE - MEDIA AVAILABLE TP-M23A | 15/04/2023 | 15/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM24A8-30 | TT_Task | NOT APPLICABLE - COMMISSIONING OF TP-M24A | 15/04/2023 | 21/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM24A3-15 | TT_Mile | NOT APPLICABLE - MATERIAL FOR TP INTEGRATION ON SITE TP-M24A | 12/07/2022 | 12/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM24A6-25 | TT_Task | NOT APPLICABLE - TERMINATION OF TP-M24A | 04/10/2022 | 17/10/2022 |  |  | 1432 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM24A2-5 | TT_Task | NOT APPLICABLE - TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-M24A | 04/06/2021 | 01/07/2021 | 04/06/2021 | 01/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPM24A2-10 | TT_Mile | NOT APPLICABLE - FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-M24A | 19/04/2022 | 19/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM24A6-20 | TT_Task | NOT APPLICABLE - INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-M24A | 12/07/2022 | 03/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM24A2-11 | TT_Task | NOT APPLICABLE - UPDATE OF TRANSITION PLAN TP-M24A | 19/04/2022 | 25/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM24A2-16 | TT_Mile | NOT APPLICABLE - ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-M24A | 04/10/2022 | 04/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM24A8-26 | TT_Mile | NOT APPLICABLE - MEDIA AVAILABLE TP-M24A | 15/04/2023 | 15/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM25A8-30 | TT_Task | NOT APPLICABLE - COMMISSIONING OF TP-M25A | 07/02/2023 | 13/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM25A3-15 | TT_Mile | NOT APPLICABLE - MATERIAL FOR TP INTEGRATION ON SITE TP-M25A | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM25A6-25 | TT_Task | NOT APPLICABLE - TERMINATION OF TP-M25A | 24/01/2023 | 06/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM25A2-5 | TT_Task | NOT APPLICABLE - TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-M25A | 04/02/2022 | 03/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM25A2-10 | TT_Mile | NOT APPLICABLE - FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-M25A | 04/03/2022 | 04/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM25A6-20 | TT_Task | NOT APPLICABLE - INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-M25A | 04/05/2022 | 31/05/2022 |  |  | 1896 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM25A2-11 | TT_Mile | NOT APPLICABLE - UPDATE OF TRANSITION PLAN TP-M25A | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM25A2-16 | TT_Mile | NOT APPLICABLE - ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-M25A | 24/01/2023 | 24/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM25A8-26 | TT_Mile | NOT APPLICABLE - MEDIA AVAILABLE TP-M25A | 07/02/2023 | 07/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--B--2-94 | TT_Task | BASIC DESIGN CABLE - OVERALL CABLE ROUTING DWG YD16 - FINAL SUBMISSION | 03/04/2021 | 16/04/2021 | 03/04/2021 | 16/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPM26A8-30 | TT_Task | COMMISSIONING OF TP-M26A | 25/04/2023 | 01/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM26A3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-M26A | 21/04/2022 | 21/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM26A6-25 | TT_Task | TERMINATION OF TP-M26A | 28/04/2022 | 04/05/2022 |  |  | 2840 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM26A2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-M26A | 11/04/2021 | 08/05/2021 | 11/04/2021 | 08/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPM26A2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-M26A | 09/02/2022 | 09/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM26A6-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-M26A | 21/04/2022 | 27/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM26A2-11 | TT_Mile | UPDATE OF TRANSITION PLAN TP-M26A | 09/02/2022 | 09/02/2022 |  |  | 568 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM26A2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-M26A | 28/04/2022 | 28/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM26A8-26 | TT_Mile | MEDIA AVAILABLE TP-M26A | 25/04/2023 | 25/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM28A8-30 | TT_Task | COMMISSIONING OF TP-M28A | 15/03/2023 | 21/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM28A3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-M28A | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM28A6-25 | TT_Task | TERMINATION OF TP-M28A | 29/06/2022 | 12/07/2022 |  |  | 1960 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM28A2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-M28A | 11/04/2021 | 08/05/2021 | 11/04/2021 | 08/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPM28A2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-M28A | 09/02/2022 | 09/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM28A6-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-M28A | 04/05/2022 | 28/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM28A2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-M28A | 09/02/2022 | 15/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM28A2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-M28A | 29/06/2022 | 29/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM28A8-26 | TT_Mile | MEDIA AVAILABLE TP-M28A | 15/03/2023 | 15/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM29A8-30 | TT_Task | COMMISSIONING OF TP-M29A | 15/03/2023 | 21/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM29A3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-M29A | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM29A6-25 | TT_Task | TERMINATION OF TP-M29A | 29/06/2022 | 12/07/2022 |  |  | 1960 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM29A2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-M29A | 11/04/2021 | 08/05/2021 | 11/04/2021 | 08/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPM29A2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-M29A | 09/02/2022 | 09/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM29A6-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-M29A | 04/05/2022 | 28/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM29A2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-M29A | 09/02/2022 | 15/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM29A2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-M29A | 29/06/2022 | 29/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPM29A8-26 | TT_Mile | MEDIA AVAILABLE TP-M29A | 15/03/2023 | 15/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI13A8-30 | TT_Task | COMMISSIONING OF TP-I13 | 14/02/2023 | 20/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI13A3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-I13 | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI13A6-25 | TT_Task | TERMINATION OF TP-I13 | 01/06/2022 | 14/06/2022 |  |  | 1952 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI13A2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-I13 | 24/05/2021 | 20/06/2021 | 24/05/2021 | 20/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPI13A2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-I13 | 21/06/2021 | 21/06/2021 | 21/06/2021 | 21/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPI13A6-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-I13 | 04/05/2022 | 31/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI13A2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-I13 | 09/02/2022 | 15/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI13A2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-I13 | 01/06/2022 | 01/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI13A8-26 | TT_Mile | MEDIA AVAILABLE TP-I13 | 14/02/2023 | 14/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPF1A8-30 | TT_Task | COMMISSIONING OF TP-F1A | 20/02/2023 | 26/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPF1A3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-F1A | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPF1A6-25 | TT_Task | TERMINATION OF TP-F1A | 01/06/2022 | 14/06/2022 |  |  | 1272 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPF1A2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-F1A | 11/04/2021 | 08/05/2021 | 11/04/2021 | 08/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPF1A2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-F1A | 09/02/2022 | 09/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPF1A6-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-F1A | 04/05/2022 | 31/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPF1A2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-F1A | 09/02/2022 | 15/02/2022 |  |  | 616 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPF1A2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-F1A | 01/06/2022 | 01/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPF1A8-26 | TT_Mile | MEDIA AVAILABLE TP-F1A | 20/02/2023 | 20/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI1A8-30 | TT_Task | COMMISSIONING OF TP-I1 | 14/02/2023 | 20/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI1A3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-I1 | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI1A6-25 | TT_Task | TERMINATION OF TP-I1 | 01/06/2022 | 14/06/2022 |  |  | 1952 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI1A2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-I1 | 24/05/2021 | 20/06/2021 | 24/05/2021 | 20/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPI1A2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-I1 | 21/06/2021 | 21/06/2021 | 21/06/2021 | 21/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPI1A6-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-I1 | 04/05/2022 | 31/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI1A2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-I1 | 09/02/2022 | 15/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI1A2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-I1 | 01/06/2022 | 01/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI1A8-26 | TT_Mile | MEDIA AVAILABLE TP-I1 | 14/02/2023 | 14/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPF1B8-30 | TT_Task | COMMISSIONING OF TP-F1B | 20/02/2023 | 26/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPF1B3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-F1B | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPF1B6-25 | TT_Task | TERMINATION OF TP-F1B | 01/06/2022 | 14/06/2022 |  |  | 1272 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPF1B2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-F1B | 07/05/2021 | 03/06/2021 | 07/05/2021 | 03/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPF1B2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-F1B | 09/02/2022 | 09/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPF1B6-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-F1B | 04/05/2022 | 31/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPF1B2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-F1B | 09/02/2022 | 15/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPF1B2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-F1B | 01/06/2022 | 01/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPF1B8-26 | TT_Mile | MEDIA AVAILABLE TP-F1B | 20/02/2023 | 20/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPF1C8-30 | TT_Task | COMMISSIONING OF TP-F1C | 20/02/2023 | 26/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPF1C3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-F1C | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPF1C6-25 | TT_Task | TERMINATION OF TP-F1C | 01/06/2022 | 14/06/2022 |  |  | 1272 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPF1C2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-F1C | 07/05/2021 | 03/06/2021 | 07/05/2021 | 03/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPF1C2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-F1C | 09/02/2022 | 09/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPF1C6-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-F1C | 04/05/2022 | 31/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPF1C2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-F1C | 09/02/2022 | 15/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPF1C2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-F1C | 01/06/2022 | 01/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPF1C8-26 | TT_Mile | MEDIA AVAILABLE TP-F1C | 20/02/2023 | 20/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI4A8-30 | TT_Task | COMMISSIONING OF TP-I4 | 14/02/2023 | 20/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI4A3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-I4 | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI4A7-25 | TT_Task | TERMINATION OF TP-I4 | 01/06/2022 | 14/06/2022 |  |  | 1952 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI4A2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-I4 | 24/05/2021 | 20/06/2021 | 24/05/2021 | 20/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPI4A2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-I4 | 21/06/2021 | 21/06/2021 | 21/06/2021 | 21/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPI4A7-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-I4 | 04/05/2022 | 31/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI4A2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-I4 | 09/02/2022 | 15/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI4A2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-I4 | 01/06/2022 | 01/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI4A8-26 | TT_Mile | MEDIA AVAILABLE TP-I4 | 14/02/2023 | 14/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPF2A8-30 | TT_Task | COMMISSIONING OF TP-F2A | 20/02/2023 | 26/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPF2A3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-F2A | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPF2A6-25 | TT_Task | TERMINATION OF TP-F2A | 01/06/2022 | 14/06/2022 |  |  | 2000 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPF2A2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-F2A | 07/05/2021 | 03/06/2021 | 07/05/2021 | 03/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPF2A2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-F2A | 09/02/2022 | 09/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPF2A6-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-F2A | 04/05/2022 | 31/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPF2A2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-F2A | 09/02/2022 | 15/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPF2A2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-F2A | 01/06/2022 | 01/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPF2A8-26 | TT_Mile | MEDIA AVAILABLE TP-F2A | 20/02/2023 | 20/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI5A8-30 | TT_Task | COMMISSIONING OF TP-I5 | 14/02/2023 | 20/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI5A3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-I5 | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI5A7-25 | TT_Task | TERMINATION OF TP-I5 | 01/06/2022 | 14/06/2022 |  |  | 1952 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI5A2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-I5 | 24/05/2021 | 20/06/2021 | 24/05/2021 | 20/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPI5A2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-I5 | 21/06/2021 | 21/06/2021 | 21/06/2021 | 21/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPI5A7-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-I5 | 04/05/2022 | 31/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI5A2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-I5 | 09/02/2022 | 15/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI5A2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-I5 | 01/06/2022 | 01/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI5A8-26 | TT_Mile | MEDIA AVAILABLE TP-I5 | 14/02/2023 | 14/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI6A8-30 | TT_Task | COMMISSIONING OF TP-I6 | 06/05/2023 | 12/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI6A3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-I6 | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI6A7-25 | TT_Task | TERMINATION OF TP-I6 | 23/02/2023 | 08/03/2023 |  |  | 464 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI6A2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-I6 | 24/05/2021 | 20/06/2021 | 24/05/2021 | 20/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPI6A2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-I6 | 21/06/2021 | 21/06/2021 | 21/06/2021 | 21/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPI6A7-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-I6 | 04/05/2022 | 31/05/2022 |  |  | 2136 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI6A2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-I6 | 09/02/2022 | 15/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI6A2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-I6 | 23/02/2023 | 23/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI6A8-26 | TT_Mile | MEDIA AVAILABLE TP-I6 | 06/05/2023 | 06/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI10A8-30 | TT_Task | COMMISSIONING OF TP-I10 | 14/02/2023 | 20/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI10A3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-I10 | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI10A7-25 | TT_Task | TERMINATION OF TP-I10 | 31/01/2023 | 13/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI10A2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-I10 | 24/05/2021 | 20/06/2021 | 24/05/2021 | 20/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPI10A2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-I10 | 21/06/2021 | 21/06/2021 | 21/06/2021 | 21/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPI10A7-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-I10 | 04/05/2022 | 31/05/2022 |  |  | 1952 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI10A2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-I10 | 09/02/2022 | 15/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI10A2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-I10 | 31/01/2023 | 31/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI10A8-26 | TT_Mile | MEDIA AVAILABLE TP-I10 | 14/02/2023 | 14/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI17A8-30 | TT_Task | COMMISSIONING OF TP-I17 | 09/06/2023 | 15/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI17A3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-I17 | 28/07/2022 | 28/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI17A7-25 | TT_Task | TERMINATION OF TP-I17 | 25/08/2022 | 07/09/2022 |  |  | 2192 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI17A2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-I17 | 24/05/2021 | 20/06/2021 | 24/05/2021 | 20/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPI17A2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-I17 | 21/06/2021 | 21/06/2021 | 21/06/2021 | 21/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPI17A7-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-I17 | 28/07/2022 | 24/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI17A2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-I17 | 05/05/2022 | 11/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI17A2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-I17 | 25/08/2022 | 25/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI17A8-26 | TT_Mile | MEDIA AVAILABLE TP-I17 | 09/06/2023 | 09/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI19I8-30 | TT_Task | COMMISSIONING OF TP-I19i | 09/06/2023 | 15/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI19I3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-I19i | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI19I7-25 | TT_Task | TERMINATION OF TP-I19i | 01/06/2022 | 14/06/2022 |  |  | 2872 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI19I2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-I19i | 24/05/2021 | 20/06/2021 | 24/05/2021 | 20/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPI19I2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-I19i | 21/06/2021 | 21/06/2021 | 21/06/2021 | 21/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPI19I7-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-I19i | 04/05/2022 | 31/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI19I2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-I19i | 09/02/2022 | 15/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI19I2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-I19i | 01/06/2022 | 01/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI19I8-26 | TT_Mile | MEDIA AVAILABLE TP-I19i | 09/06/2023 | 09/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI19II8-30 | TT_Task | COMMISSIONING OF TP-I19ii | 09/06/2023 | 15/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI19II3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-I19ii | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI19II7-25 | TT_Task | TERMINATION OF TP-I19ii | 01/06/2022 | 14/06/2022 |  |  | 2872 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI19II2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-I19ii | 24/05/2021 | 20/06/2021 | 24/05/2021 | 20/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPI19II2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-I19ii | 21/06/2021 | 21/06/2021 | 21/06/2021 | 21/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPI19II7-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-I19ii | 04/05/2022 | 31/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI19II2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-I19ii | 09/02/2022 | 15/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI19II2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-I19ii | 01/06/2022 | 01/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI19II8-26 | TT_Mile | MEDIA AVAILABLE TP-I19ii | 09/06/2023 | 09/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI21A8-30 | TT_Task | COMMISSIONING OF TP-I21 | 06/05/2023 | 12/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI21A3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-I21 | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI21A7-25 | TT_Task | TERMINATION OF TP-I21 | 23/02/2023 | 08/03/2023 |  |  | 464 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI21A2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-I21 | 24/05/2021 | 20/06/2021 | 24/05/2021 | 20/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPI21A2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-I21 | 21/06/2021 | 21/06/2021 | 21/06/2021 | 21/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPI21A7-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-I21 | 04/05/2022 | 31/05/2022 |  |  | 2136 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI21A2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-I21 | 09/02/2022 | 15/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI21A2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-I21 | 23/02/2023 | 23/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI21A8-26 | TT_Mile | MEDIA AVAILABLE TP-I21 | 06/05/2023 | 06/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI22A8-30 | TT_Task | COMMISSIONING OF TP-I22 | 01/06/2023 | 07/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI22A3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-I22 | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI22A7-25 | TT_Task | TERMINATION OF TP-I22 | 01/06/2022 | 14/06/2022 |  |  | 2808 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI22A2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-I22 | 24/05/2021 | 20/06/2021 | 24/05/2021 | 20/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPI22A2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-I22 | 21/06/2021 | 21/06/2021 | 21/06/2021 | 21/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPI22A7-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-I22 | 04/05/2022 | 31/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI22A2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-I22 | 09/02/2022 | 15/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI22A2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-I22 | 01/06/2022 | 01/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI22A8-26 | TT_Mile | MEDIA AVAILABLE TP-I22 | 01/06/2023 | 01/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI23A8-30 | TT_Task | COMMISSIONING OF TP-I23 | 22/02/2023 | 28/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI23A3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-I23 | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI23A7-25 | TT_Task | TERMINATION OF TP-I23 | 01/06/2022 | 14/06/2022 |  |  | 2016 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI23A2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-I23 | 24/05/2021 | 20/06/2021 | 24/05/2021 | 20/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPI23A2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-I23 | 21/06/2021 | 21/06/2021 | 21/06/2021 | 21/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPI23A7-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-I23 | 04/05/2022 | 31/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI23A2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-I23 | 09/02/2022 | 15/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI23A2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-I23 | 01/06/2022 | 01/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI23A8-26 | TT_Mile | MEDIA AVAILABLE TP-I23 | 22/02/2023 | 22/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI15A8-30 | TT_Task | COMMISSIONING OF TP-I15 | 04/04/2023 | 10/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI15A3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-I15 | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI15A7-25 | TT_Task | TERMINATION OF TP-I15 | 01/06/2022 | 14/06/2022 |  |  | 2344 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI15A2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-I15 | 24/05/2021 | 20/06/2021 | 24/05/2021 | 20/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPI15A2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-I15 | 21/06/2021 | 21/06/2021 | 21/06/2021 | 21/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPI15A7-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-I15 | 04/05/2022 | 31/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI15A2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-I15 | 09/02/2022 | 15/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI15A2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-I15 | 01/06/2022 | 01/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI15A8-26 | TT_Mile | MEDIA AVAILABLE TP-I15 | 04/04/2023 | 04/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC1A8-30 | TT_Task | COMMISSIONING OF TP-C1A | 19/03/2023 | 25/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC1A3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-C1A | 29/07/2021 | 29/07/2021 | 29/07/2021 | 29/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPC1A6-25 | TT_Task | TERMINATION OF TP-C1A | 26/08/2021 | 08/09/2021 | 26/08/2021 | 08/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPC1A2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-C1A | 08/04/2021 | 05/05/2021 | 08/04/2021 | 05/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPC1A2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-C1A | 06/05/2021 | 06/05/2021 | 06/05/2021 | 06/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPC1A6-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-C1A | 29/07/2021 | 25/08/2021 | 29/07/2021 | 25/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPC1A2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-C1A | 06/05/2021 | 12/05/2021 | 06/05/2021 | 12/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPC1A2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-C1A | 26/08/2021 | 26/08/2021 | 26/08/2021 | 26/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPC1A8-26 | TT_Mile | MEDIA AVAILABLE TP-C1A | 19/03/2023 | 19/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI16A8-30 | TT_Task | COMMISSIONING OF TP-I16 | 09/06/2023 | 15/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI16A3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-I16 | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI16A7-25 | TT_Task | TERMINATION OF TP-I16 | 01/06/2022 | 14/06/2022 |  |  | 2872 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI16A2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-I16 | 24/05/2021 | 20/06/2021 | 24/05/2021 | 20/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPI16A2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-I16 | 21/06/2021 | 21/06/2021 | 21/06/2021 | 21/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPI16A7-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-I16 | 04/05/2022 | 31/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI16A2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-I16 | 09/02/2022 | 15/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI16A2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-I16 | 01/06/2022 | 01/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI16A8-26 | TT_Mile | MEDIA AVAILABLE TP-I16 | 09/06/2023 | 09/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI20A8-30 | TT_Task | COMMISSIONING OF TP-I20 | 22/03/2023 | 28/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI20A3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-I20 | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI20A7-25 | TT_Task | TERMINATION OF TP-I20 | 01/06/2022 | 14/06/2022 |  |  | 2240 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI20A2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-I20 | 24/05/2021 | 20/06/2021 | 24/05/2021 | 20/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPI20A2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-I20 | 21/06/2021 | 21/06/2021 | 21/06/2021 | 21/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPI20A7-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-I20 | 04/05/2022 | 31/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI20A2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-I20 | 09/02/2022 | 15/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI20A2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-I20 | 01/06/2022 | 01/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI20A8-26 | TT_Mile | MEDIA AVAILABLE TP-I20 | 22/03/2023 | 22/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC2A8-30 | TT_Task | COMMISSIONING OF TP-C2A | 22/03/2023 | 28/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC2A3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-C2A | 29/03/2022 | 29/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC2A6-25 | TT_Task | TERMINATION OF TP-C2A | 26/04/2022 | 09/05/2022 |  |  | 2528 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC2A2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-C2A | 16/04/2021 | 13/05/2021 | 16/04/2021 | 13/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPC2A2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-C2A | 04/01/2022 | 04/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC2A6-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-C2A | 29/03/2022 | 25/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC2A2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-C2A | 04/01/2022 | 10/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC2A2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-C2A | 26/04/2022 | 26/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC2A8-26 | TT_Mile | MEDIA AVAILABLE TP-C2A | 22/03/2023 | 22/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC3A8-30 | TT_Task | COMMISSIONING OF TP-C3A | 22/03/2023 | 28/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC3A3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-C3A | 14/02/2022 | 14/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC3A6-25 | TT_Task | TERMINATION OF TP-C3A | 14/03/2022 | 27/03/2022 |  |  | 2872 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC3A2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-C3A | 16/04/2021 | 13/05/2021 | 16/04/2021 | 13/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPC3A2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-C3A | 15/12/2021 | 15/12/2021 | 15/12/2021 | 15/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPC3A6-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-C3A | 14/02/2022 | 13/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC3A2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-C3A | 22/11/2021 | 28/11/2021 | 22/11/2021 | 28/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPC3A2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-C3A | 14/03/2022 | 14/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC3A8-26 | TT_Mile | MEDIA AVAILABLE TP-C3A | 22/03/2023 | 22/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC4A8-30 | TT_Task | COMMISSIONING OF TP-C4A | 22/03/2023 | 28/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC4A3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-C4A | 06/01/2022 | 06/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC4A6-25 | TT_Task | TERMINATION OF TP-C4A | 03/02/2022 | 16/02/2022 |  |  | 3184 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC4A2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-C4A | 16/04/2021 | 13/05/2021 | 16/04/2021 | 13/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPC4A2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-C4A | 10/12/2021 | 10/12/2021 | 10/12/2021 | 10/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPC4A6-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-C4A | 06/01/2022 | 02/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC4A2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-C4A | 10/12/2021 | 16/12/2021 | 10/12/2021 | 16/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPC4A2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-C4A | 03/02/2022 | 03/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC4A8-26 | TT_Mile | MEDIA AVAILABLE TP-C4A | 22/03/2023 | 22/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC5A8-30 | TT_Task | COMMISSIONING OF TP-C5A | 22/03/2023 | 28/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC5A3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-C5A | 05/05/2022 | 05/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC5A6-25 | TT_Task | TERMINATION OF TP-C5A | 02/06/2022 | 15/06/2022 |  |  | 2232 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC5A2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-C5A | 16/04/2021 | 13/05/2021 | 16/04/2021 | 13/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPC5A2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-C5A | 10/02/2022 | 10/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC5A6-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-C5A | 05/05/2022 | 01/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC5A2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-C5A | 10/02/2022 | 16/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC5A2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-C5A | 02/06/2022 | 02/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC5A8-26 | TT_Mile | MEDIA AVAILABLE TP-C5A | 22/03/2023 | 22/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC6A8-30 | TT_Task | COMMISSIONING OF TP-C6A | 07/02/2023 | 13/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC6A3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-C6A | 06/01/2022 | 06/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC6A6-25 | TT_Task | TERMINATION OF TP-C6A | 03/02/2022 | 16/02/2022 |  |  | 2840 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC6A2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-C6A | 16/04/2021 | 13/05/2021 | 16/04/2021 | 13/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPC6A2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-C6A | 10/12/2021 | 10/12/2021 | 10/12/2021 | 10/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPC6A6-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-C6A | 06/01/2022 | 02/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC6A2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-C6A | 14/10/2021 | 20/10/2021 | 14/10/2021 | 20/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPC6A2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-C6A | 03/02/2022 | 03/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC6A8-26 | TT_Mile | MEDIA AVAILABLE TP-C6A | 07/02/2023 | 07/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC7A8-30 | TT_Task | COMMISSIONING OF TP-C7A | 22/03/2023 | 28/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC7A3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-C7A | 06/01/2022 | 06/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC7A6-25 | TT_Task | TERMINATION OF TP-C7A | 03/02/2022 | 16/02/2022 |  |  | 3184 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC7A2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-C7A | 16/04/2021 | 13/05/2021 | 16/04/2021 | 13/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPC7A2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-C7A | 11/12/2021 | 11/12/2021 | 11/12/2021 | 11/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPC7A6-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-C7A | 06/01/2022 | 02/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC7A2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-C7A | 14/10/2021 | 20/10/2021 | 14/10/2021 | 20/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPC7A2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-C7A | 03/02/2022 | 03/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC7A8-26 | TT_Mile | MEDIA AVAILABLE TP-C7A | 22/03/2023 | 22/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC8A8-30 | TT_Task | COMMISSIONING OF TP-C8A | 07/02/2023 | 13/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC8A3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-C8A | 05/05/2022 | 05/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC8A6-25 | TT_Task | TERMINATION OF TP-C8A | 02/06/2022 | 15/06/2022 |  |  | 1888 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC8A2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-C8A | 16/04/2021 | 13/05/2021 | 16/04/2021 | 13/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPC8A2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-C8A | 10/02/2022 | 10/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC8A6-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-C8A | 05/05/2022 | 01/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC8A2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-C8A | 10/02/2022 | 16/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC8A2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-C8A | 02/06/2022 | 02/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC8A8-26 | TT_Mile | MEDIA AVAILABLE TP-C8A | 07/02/2023 | 07/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC9A8-30 | TT_Task | COMMISSIONING OF TP-C9A | 07/02/2023 | 13/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC9A3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-C9A | 05/05/2022 | 05/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC9A6-25 | TT_Task | TERMINATION OF TP-C9A | 02/06/2022 | 15/06/2022 |  |  | 1888 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC9A2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-C9A | 16/04/2021 | 13/05/2021 | 16/04/2021 | 13/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPC9A2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-C9A | 10/02/2022 | 10/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC9A6-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-C9A | 05/05/2022 | 01/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC9A2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-C9A | 10/02/2022 | 16/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC9A2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-C9A | 02/06/2022 | 02/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC9A8-26 | TT_Mile | MEDIA AVAILABLE TP-C9A | 07/02/2023 | 07/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC10A8-30 | TT_Task | COMMISSIONING OF TP-C10A | 07/02/2023 | 13/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC10A3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-C10A | 05/05/2022 | 05/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC10A6-25 | TT_Task | TERMINATION OF TP-C10A | 02/06/2022 | 15/06/2022 |  |  | 1888 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC10A2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-C10A | 16/04/2021 | 13/05/2021 | 16/04/2021 | 13/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPC10A2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-C10A | 08/02/2022 | 08/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC10A6-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-C10A | 05/05/2022 | 01/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC10A2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-C10A | 08/02/2022 | 16/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC10A2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-C10A | 02/06/2022 | 02/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPC10A8-26 | TT_Mile | MEDIA AVAILABLE TP-C10A | 07/02/2023 | 07/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI3A8-30 | TT_Task | COMMISSIONING OF TP-I3 | 14/02/2023 | 20/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI3A3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-I3 | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI3A7-25 | TT_Task | TERMINATION OF TP-I3 | 01/06/2022 | 14/06/2022 |  |  | 1952 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI3A2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-I3 | 24/05/2021 | 20/06/2021 | 24/05/2021 | 20/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPI3A2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-I3 | 21/06/2021 | 21/06/2021 | 21/06/2021 | 21/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPI3A7-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-I3 | 04/05/2022 | 31/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI3A2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-I3 | 09/02/2022 | 15/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI3A2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-I3 | 01/06/2022 | 01/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI3A8-26 | TT_Mile | MEDIA AVAILABLE TP-I3 | 14/02/2023 | 14/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI18A8-30 | TT_Task | COMMISSIONING OF TP-I18 | 14/02/2023 | 20/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI18A3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-I18 | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI18A7-25 | TT_Task | TERMINATION OF TP-I18 | 01/06/2022 | 14/06/2022 |  |  | 1952 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI18A2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-I18 | 24/05/2021 | 20/06/2021 | 24/05/2021 | 20/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPI18A2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-I18 | 21/06/2021 | 21/06/2021 | 21/06/2021 | 21/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPI18A7-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-I18 | 04/05/2022 | 31/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI18A2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-I18 | 09/02/2022 | 15/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI18A2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-I18 | 01/06/2022 | 01/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI18A8-26 | TT_Mile | MEDIA AVAILABLE TP-I18 | 14/02/2023 | 14/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI2I8-30 | TT_Task | COMMISSIONING OF TP-I2i | 14/02/2023 | 20/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI2I3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-I2i | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI2I7-25 | TT_Task | TERMINATION OF TP-I2i | 01/06/2022 | 14/06/2022 |  |  | 1952 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI2I2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-I2i | 24/05/2021 | 20/06/2021 | 24/05/2021 | 20/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPI2I2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-I2i | 21/06/2021 | 21/06/2021 | 21/06/2021 | 21/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPI2I7-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-I2i | 04/05/2022 | 31/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI2I2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-I2i | 09/02/2022 | 15/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI2I2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-I2i | 01/06/2022 | 01/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI2I8-26 | TT_Mile | MEDIA AVAILABLE TP-I2i | 14/02/2023 | 14/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI2II8-30 | TT_Task | COMMISSIONING OF TP-I2ii | 14/02/2023 | 20/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI2II3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-I2ii | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI2II7-25 | TT_Task | TERMINATION OF TP-I2ii | 01/06/2022 | 14/06/2022 |  |  | 1952 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI2II2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-I2ii | 24/05/2021 | 20/06/2021 | 24/05/2021 | 20/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPI2II2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-I2ii | 21/06/2021 | 21/06/2021 | 21/06/2021 | 21/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPI2II7-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-I2ii | 04/05/2022 | 31/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI2II2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-I2ii | 09/02/2022 | 15/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI2II2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-I2ii | 01/06/2022 | 01/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI2II8-26 | TT_Mile | MEDIA AVAILABLE TP-I2ii | 14/02/2023 | 14/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI2III8-30 | TT_Task | COMMISSIONING OF TP-I2iii | 14/02/2023 | 20/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI2III3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-I2iii | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI2III7-25 | TT_Task | TERMINATION OF TP-I2iii | 01/06/2022 | 14/06/2022 |  |  | 1952 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI2III2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-I2iii | 24/05/2021 | 20/06/2021 | 24/05/2021 | 20/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPI2III2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-I2iii | 21/06/2021 | 21/06/2021 | 21/06/2021 | 21/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPI2III7-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-I2iii | 04/05/2022 | 31/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI2III2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-I2iii | 09/02/2022 | 15/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI2III2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-I2iii | 01/06/2022 | 01/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI2III8-26 | TT_Mile | MEDIA AVAILABLE TP-I2iii | 14/02/2023 | 14/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI2IV8-30 | TT_Task | COMMISSIONING OF TP-I2iv | 14/02/2023 | 20/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI2IV3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-I2iv | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI2IV7-25 | TT_Task | TERMINATION OF TP-I2iv | 01/06/2022 | 14/06/2022 |  |  | 1952 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI2IV2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-I2iv | 24/05/2021 | 20/06/2021 | 24/05/2021 | 20/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPI2IV2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-I2iv | 21/06/2021 | 21/06/2021 | 21/06/2021 | 21/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPI2IV7-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-I2iv | 04/05/2022 | 31/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI2IV2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-I2iv | 09/02/2022 | 15/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI2IV2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-I2iv | 01/06/2022 | 01/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPI2IV8-26 | TT_Mile | MEDIA AVAILABLE TP-I2iv | 14/02/2023 | 14/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPE4A8-30 | TT_Task | COMMISSIONING OF TP-E4 | 28/02/2023 | 06/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPE4A3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-E4 | 05/12/2022 | 05/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPE4A7-25 | TT_Task | TERMINATION OF TP-E4 (by client) | 10/02/2023 | 23/02/2023 |  |  | 32 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPE4A2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-E4 | 30/04/2021 | 27/05/2021 | 30/04/2021 | 27/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPE4A2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-E4 | 28/05/2021 | 28/05/2021 | 28/05/2021 | 28/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPE4A7-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN D2 SITE TP-E4 (by client) | 05/12/2022 | 01/01/2023 |  |  | 312 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPE4A2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-E4 | 12/09/2022 | 18/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPE4A2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-E4 | 10/02/2023 | 10/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPE4A8-26 | TT_Mile | MEDIA AVAILABLE TP-E4 | 28/02/2023 | 28/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPE5A8-30 | TT_Task | COMMISSIONING OF TP-E5 | 21/02/2023 | 27/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPE5A3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-E5 | 05/12/2022 | 05/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPE5A7-25 | TT_Task | TERMINATION OF TP-E5 | 02/01/2023 | 15/01/2023 |  |  | 288 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPE5A2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-E5 | 30/04/2021 | 27/05/2021 | 30/04/2021 | 27/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPE5A2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-E5 | 28/05/2021 | 28/05/2021 | 28/05/2021 | 28/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPE5A7-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN D2 SITE TP-E5 | 05/12/2022 | 01/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPE5A2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-E5 | 12/09/2022 | 18/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPE5A2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-E5 | 02/01/2023 | 02/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPE5A8-26 | TT_Mile | MEDIA AVAILABLE TP-E5 | 21/02/2023 | 21/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPE3A8-30 | TT_Task | COMMISSIONING OF TP-E3 | 07/03/2023 | 27/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPE3A3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-E3 | 25/12/2022 | 25/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPE3A7-25 | TT_Task | TERMINATION OF TP-E3 | 19/02/2023 | 04/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPE3A2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-E3 | 30/04/2021 | 27/05/2021 | 30/04/2021 | 27/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPE3A2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-E3 | 28/05/2021 | 28/05/2021 | 28/05/2021 | 28/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPE3A7-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-E3 | 25/12/2022 | 21/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPE3A2-11 | TT_Task | UPDATE OF TRANSITION PLAN TP-E3 | 18/12/2022 | 24/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPE3A2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-E3 | 19/02/2023 | 19/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPE3A8-26 | TT_Mile | MEDIA AVAILABLE TP-E3 | 07/03/2023 | 07/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPE2A8-30 | TT_Task | COMMISSIONING OF TP-E2 | 23/05/2023 | 12/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPE2A3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-E2 | 11/04/2023 | 11/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPE2A7-25 | TT_Task | TERMINATION OF TP-E2 | 09/05/2023 | 22/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPE2A2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-E2 | 30/04/2021 | 27/05/2021 | 30/04/2021 | 27/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPE2A2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-E2 | 28/05/2021 | 28/05/2021 | 28/05/2021 | 28/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPE2A7-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-E2 | 11/04/2023 | 08/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPE2A2-11 | TT_Mile | UPDATE OF TRANSITION PLAN TP-E2 | 11/04/2023 | 11/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPE2A2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-E2 | 09/05/2023 | 09/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPE2A8-26 | TT_Mile | MEDIA AVAILABLE TP-E2 | 23/05/2023 | 23/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPE6A8-30 | TT_Task | COMMISSIONING OF TP-E6 | 07/02/2023 | 13/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPE6A3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-E6 | 27/12/2022 | 27/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPE6A7-25 | TT_Task | TERMINATION OF TP-E6 | 24/01/2023 | 06/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPE6A2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-E6 | 30/04/2021 | 27/05/2021 | 30/04/2021 | 27/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPE6A2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-E6 | 28/05/2021 | 28/05/2021 | 28/05/2021 | 28/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPE6A7-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-E6 | 27/12/2022 | 23/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPE6A2-11 | TT_Mile | UPDATE OF TRANSITION PLAN TP-E6 | 27/12/2022 | 27/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPE6A2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-E6 | 24/01/2023 | 24/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPE6A8-26 | TT_Mile | MEDIA AVAILABLE TP-E6 | 07/02/2023 | 07/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPE6II8-30 | TT_Task | COMMISSIONING OF TP-E6ii | 07/02/2023 | 13/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPE6II3-15 | TT_Mile | MATERIAL FOR TP INTEGRATION ON SITE TP-E6ii | 27/12/2022 | 27/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPE6II7-25 | TT_Task | TERMINATION OF TP-E6ii | 24/01/2023 | 06/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPE6II2-5 | TT_Task | TECHNICAL CLARIFICATION WITH CUSTOMER / DESIGN FOR CONNECTION OF TP-E6ii | 30/04/2021 | 27/05/2021 | 30/04/2021 | 27/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPE6II2-10 | TT_Mile | FINAL AGREEMENT WITH CUSTOMER / ACCESS TIME / REQUIREMENTS TO TP ALIGNED TP-E6ii | 28/05/2021 | 28/05/2021 | 28/05/2021 | 28/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPE6II7-20 | TT_Task | INSTALLATION OF CONNECTION MATERIAL IN CUSTOMER SITE TP-E6ii | 27/12/2022 | 23/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPE6II2-11 | TT_Mile | UPDATE OF TRANSITION PLAN TP-E6ii | 27/12/2022 | 27/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPE6II2-16 | TT_Mile | ALL RELEVANT PERMITS LOTO AVAILABLE FROM CUSTOMER TP-E6ii | 24/01/2023 | 24/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPE6II8-26 | TT_Mile | MEDIA AVAILABLE TP-E6ii | 07/02/2023 | 07/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SD-310 | TT_Task | SHUTDOWN PERIOD - C4 OUTAGE | 08/01/2021 | 21/06/2021 | 08/01/2021 | 21/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20SD-315 | TT_Task | SHUTDOWN PERIOD - C1 OUTAGE | 01/12/2021 | 30/12/2021 | 01/12/2021 | 30/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20SD-325 | TT_Task | SHUTDOWN PERIOD - C3 OUTAGE | 01/02/2022 | 28/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SD-320 | TT_Task | SHUTDOWN PERIOD - C2 OUTAGE | 01/02/2022 | 28/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPE8A7-16 | TT_Mile | TERMINAL POINT READY FOR CONNECTION TP-E8 | 27/09/2022 | 27/09/2022 |  |  | 3576 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
CL20TPE8A7-26 | TT_Task | CONNECTION TO TP BY CLIENT TP-E8 | 18/12/2023 | 31/12/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20TPE7A7-17 | TT_Mile | TERMINAL POINT READY FOR CONNECTION TP-E7 | 13/02/2023 | 13/02/2023 |  |  | 2464 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
CL20TPE7A7-27 | TT_Task | CONNECTION TO TP BY CLIENT TP-E7 | 18/12/2023 | 31/12/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
CL20TPE9A7-18 | TT_Mile | TERMINAL POINT READY FOR CONNECTION TP-E9 | 01/07/2021 | 01/07/2021 | 01/07/2021 | 01/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPE9A7-28 | TT_Task | CONNECTION TO TP TP-E9 | 01/07/2021 | 14/07/2021 | 01/07/2021 | 14/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2B92 | TT_FinMile | (MS3) STEEL STRUCTURE DATA AVAILABLE 1st AMENDMENT SUBMISSION 20UMC | 31/05/2021 | 31/05/2021 | 31/05/2021 | 31/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2B93 | TT_Task | DETAIL DESIGN STEEL STRUCTURE / CRANE (AFTER RECEIVING FINAL MS3) 20UMC | 08/06/2021 | 06/08/2021 | 08/06/2021 | 06/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2B94 | TT_Task | BD - RESUBMISSION APPROVAL-1st Amendment UMC PACKAGES(topslab-trenches,CEP/LDK wall,Turbine plinght/wall) | 17/11/2021 | 12/01/2022 | 17/11/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UMC2B67 | TT_Task | BD - CONSENT LETTER DETAIL DESIGN CONCRETE BUILDING (1STPACKAGE) | 28/06/2021 | 20/07/2021 | 28/06/2021 | 21/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC2B68 | TT_FinMile | BD - BA10 COMMENCEMENT OF WORK CONCRETE 20UMC | 31/07/2021 | 31/07/2021 | 31/07/2021 | 31/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC2B70 | TT_FinMile | BD - BA10 COMMENCEMENT OF WORK CEP/LDK - PIT / TRENCH 20UMC | 31/07/2021 | 31/07/2021 | 31/07/2021 | 31/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2Y83 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE CEP/LDK PIT 20UMC | 15/05/2021 | 15/05/2021 | 15/05/2021 | 15/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2A82 | TT_Task | BD - CONSENT LETTER DETAIL DESIGN CONCRETE TURBOSET 2NDPACKAGE | 10/06/2021 | 20/07/2021 | 10/06/2021 | 21/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC2B71 | TT_FinMile | BD - BA10 COMMENCEMENT OF WORK TURBOSET FOUNDATION 20UMC | 31/07/2021 | 31/07/2021 | 31/07/2021 | 31/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2B95 | TT_Task | BASIC DESIGN / STEEL AFTER FINAL MS3 INPUT 20UMC | 18/05/2021 | 07/06/2021 | 18/05/2021 | 07/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-----2E94 | TT_Mile | CONTRACT INTO FORCE / ORDER VALVES | 19/04/2021 | 19/04/2021 | 19/04/2021 | 19/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TP-258 | TT_Mile | TP-E3 - D2 6.6kV INTERCONNECTIORS (D2 Site) | 25/12/2022 | 25/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC3E26 | TT_Task | FABRICATION DESIGN, FABRICATION, TRANSPORT STEEL PLATFORMS LOT1 20UMC (CRANE PLATFORM / MAINTENANCE PLATFORM) | 23/09/2021 | 18/02/2022 | 23/09/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2E79 | TT_FinMile | (MS3) STEEL PLATFORMS COND. PIT. FINAL DIMENSIONS, LOADS AVAILABLE LOT1 (CEP LDK) 20UMC | 29/03/2021 | 29/03/2021 | 29/03/2021 | 29/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2E80 | TT_Task | BASIC DESIGN STEEL PLATFORMS LOT1 20UMC | 30/03/2021 | 02/05/2021 | 30/03/2021 | 02/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC2B72 | TT_FinMile | BD - BA10 COMMENCEMENT OF WORK STEEL PLATFORM LOT1 20UMC | 14/03/2022 | 14/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2E84 | TT_Task | HANDRAILS AND GRATING DWGS CONNECTION FORCE REPORT LOT2 20UMC | 25/06/2021 | 15/07/2021 | 25/06/2021 | 15/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2E81 | TT_FinMile | (MS3) STEEL PLATFORMS COND. PIT. FINAL DIMENSIONS, LOADS AVAILABLE LOT2 (ST GENO,COND, BUSDUCT, MSC.) 20UMC | 27/04/2021 | 27/04/2021 | 27/04/2021 | 27/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2F76 | TT_FinMile | (F) DETAIL DESIGN STEEL PLATFORMS WITH CONTRACTOR LOT2 20UMC | 06/11/2021 | 06/11/2021 | 06/11/2021 | 06/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2E83 | TT_Task | DETAIL DESIGN STEEL PLATFORMS LOT2 20UMC | 01/06/2021 | 15/07/2021 | 01/06/2021 | 15/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC3E28 | TT_Task | FABRICATION DESIGN, FABRICATION, TRANSPORT STEEL PLATFORMS LOT2 20UMC | 07/11/2021 | 12/03/2022 | 07/11/2021 |  | 72 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2B96 | TT_Task | BD - SUBMISSION APPROVAL - STEEL PLATFORMS LOT2 20UMC | 18/08/2021 | 05/11/2021 | 18/08/2021 | 05/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2B98 | TT_Task | BD - CONSENT LETTER STEEL PLATFORMS LOT2 20UMC | 30/11/2021 | 10/01/2022 | 30/11/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2B97 | TT_Task | CLIENT - REVIEW - DETAIL DESIGN - STEEL STRUCTURE LOT2 20UMC | 16/07/2021 | 09/08/2021 | 16/07/2021 | 09/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2E82 | TT_Task | BASIC DESIGN STEEL PLATFORMS LOT2 20UMC | 28/04/2021 | 31/05/2021 | 28/04/2021 | 31/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC2B73 | TT_FinMile | BD - BA10 COMMENCEMENT OF WORK STEEL PLATFORM 20UMC | 17/01/2022 | 17/01/2022 |  |  | 432 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA2-74 | TT_FinMile | FIXING FOR CABLE TRAY ,LIGTHING (ETECH) SUBSTRUCTURE-20URA/URD | 27/07/2021 | 27/07/2021 | 27/07/2021 | 27/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHA2-75 | TT_FinMile | BD - BA10 COMMENCEMENT OF WORK CONCRETE 20UHA | 31/07/2021 | 31/07/2021 | 31/07/2021 | 31/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UHA2-82 | TT_Task | DETAIL DESIGN BARBENDING UHA (BY MCW) | 04/08/2021 | 31/08/2021 | 04/08/2021 | 31/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2A83 | TT_Task | DETAIL DESIGN BARBENDING TS FOUND. 20UMC | 10/06/2021 | 07/07/2021 | 10/06/2021 | 07/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2A84 | TT_Task | DETAIL DESIGN BARBENDING UMC BUILDING 20UMC | 22/07/2021 | 03/09/2021 | 22/07/2021 | 03/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2A85 | TT_Task | DETAIL DESIGN BARBENDING CEP/LDK 20UMC | 17/06/2021 | 30/06/2021 | 17/06/2021 | 30/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--URA2-92 | TT_Task | BARBENDING AND DRAWINGS SUBSTRUCTURE-20URA/URD | 03/09/2021 | 30/09/2021 | 03/09/2021 | 30/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UBF2-89 | TT_Task | DETAIL DESIGN BARBENDING 20UBE/UBF | 23/09/2021 | 28/10/2021 | 23/09/2021 | 28/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UBF2-90 | TT_Task | BASIC DESIGN STEEL STRUCTURE INCL. 3D MODEL 20UBE/UBF | 06/06/2021 | 21/06/2021 | 06/06/2021 | 21/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UBA2B100 | TT_Task | BASIC DESIGN STEEL STRUCTURE UBA7xxx | 28/05/2021 | 23/06/2021 | 28/05/2021 | 23/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MBL2-102 | TT_Mile | (DF) MS3 AIR INTAKE MBL | 14/05/2021 | 14/05/2021 | 14/05/2021 | 14/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URA3-27 | TT_Task | BASIC DESIGN STEEL STRUCTURE 20URA | 11/06/2021 | 01/07/2021 | 11/06/2021 | 01/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHW3-26 | TT_Task | BASIC DESIGN STEEL STRUCTURE 20UHW | 26/05/2021 | 08/06/2021 | 26/05/2021 | 08/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MBR2B66 | TT_Task | DETAIL DESIGN EXHAUST DIFFUSER FRAME 20MBR | 13/05/2021 | 13/07/2021 | 13/05/2021 | 13/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UEN2-106 | TT_Task | BASIC DESIGN STEEL STRUCTURE 20UEN | 06/09/2021 | 19/09/2021 | 06/09/2021 | 19/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MBV3-83 | TT_Task | BD - SUBMISSION APPROVAL CLEAN / DIRTY OIL TANK MBV90 | 30/09/2021 | 12/12/2021 | 30/09/2021 | 12/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URD2-75 | TT_FinMile | BD - BA10 COMMENCEMENT OF WORK CONCRETE 20URD xx | 02/07/2021 | 02/07/2021 | 02/07/2021 | 02/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--URD2-93 | TT_Task | DETAIL DESIGN BARBENDING 20URD xx | 25/08/2021 | 21/09/2021 | 25/08/2021 | 21/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2B-36 | TT_Task | BASIC DESIGN STEEL STRUCTURE 20UBA1110/20 | 22/07/2021 | 03/08/2021 | 22/07/2021 | 04/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2B-37 | TT_Task | BASIC DESIGN STEEL STRUCTURE 20UBA7910/20 | 04/09/2021 | 24/09/2021 | 04/09/2021 | 24/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2B-38 | TT_Task | BASIC DESIGN STEEL STRUCTURE 20UBA8110/20 | 31/08/2021 | 20/09/2021 | 31/08/2021 | 20/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2B-39 | TT_Task | BASIC DESIGN STEEL STRUCTURE 01UBA9010/20 | 31/10/2021 | 20/11/2021 | 31/10/2021 | 20/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--HB-2-18 | TT_Task | BD - HRSG PLATFORMS SUBMISSION APPROVAL(Lower platform, piperack, Maintenance Staircase) | 30/11/2021 | 28/01/2022 | 30/11/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--HB-2-19 | TT_Task | BD - CONSENT LETTER HRSG PLATFORMS | 29/01/2022 | 25/02/2022 |  |  | 72 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBL2C-81 | TT_Task | BASIC DESIGN STEEL STRUCTURE 20UBL | 15/09/2021 | 14/10/2021 | 15/09/2021 | 14/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBN2-106 | TT_Task | BASIC BUILDING DESIGN INCL. 3D MODEL - PRELIMINARY 20UBN | 27/10/2021 | 03/12/2021 | 27/10/2021 | 03/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBN2-107 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE PRELIMINARY 20UBN | 17/12/2021 | 30/01/2022 | 17/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UBN2-109 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE 20UBN | 28/02/2022 | 28/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBN2-110 | TT_FinMile | BD - BA10 COMMENCEMENT OF WORK CONCRETE 20UBN | 02/06/2022 | 02/06/2022 |  |  | 112 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBY2-65 | TT_Task | BASIC BUILDING DESIGN INCL. 3D MODEL- PRELIMINARY UBY02(NotExisting) | 11/06/2021 | 01/07/2021 | 11/06/2021 | 01/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBY2-66 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE - PRELIMINARY UBY02(NotExisting) | 02/07/2021 | 15/08/2021 | 02/07/2021 | 15/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBY2-67 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE - UBY02(NotExisting) | 10/09/2021 | 26/10/2021 | 10/09/2021 | 26/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UEX2-107 | TT_Task | BASIC BUILDING DESIGN INCL. 3D MODEL - PRELIMINARY 20UEX01 | 27/10/2021 | 03/12/2021 | 27/10/2021 | 03/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UEX2-108 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE - PRELIMINARY 20UEX01 | 04/12/2021 | 17/01/2022 | 04/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UEX2-109 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE 20UEX01 | 31/03/2022 | 29/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEX2D79 | TT_Task | BASIC DESIGN STEEL STRUCTURE 20UEX01 | 17/01/2022 | 06/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P221-175 | TT_Mile | BD - SUBMISSION - DETAIL DESIGN CONCRETE - AMENDMENT 20UBX/20UBG03 | 24/05/2021 | 24/05/2021 | 24/05/2021 | 24/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20USX2-41 | TT_Task | BASIC BUILDING DESIGN INCL. 3D MODEL - PRELIMINARY 20USX | 31/08/2021 | 20/09/2021 | 31/08/2021 | 20/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20USX2-42 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE - PRELIMINARY 20USX | 21/09/2021 | 21/02/2022 | 21/09/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UHX2-41 | TT_Task | BASIC BUILDING DESIGN INCL. 3D MODEL - PRELIMINARY 20UHX | 25/07/2021 | 14/08/2021 | 25/07/2021 | 14/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHX2-42 | TT_Task | DETAIL DESIGN CONCRETE STRUCTURE - PRELIMINARY 20UHX | 15/08/2021 | 28/09/2021 | 15/08/2021 | 28/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHX2-44 | TT_FinMile | BD - BA10 COMMENCEMENT OF WORK CONCRETE 20UHX | 30/11/2021 | 30/11/2021 | 30/11/2021 | 30/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P222-146 | TT_Task | CHEMICAL WASTE WATER DISCHARGE LICENSE | 13/01/2023 | 13/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAA4-41 | TT_Task | TRANSPORT COOLING TOWER COARSE SCREEN TO PORT OF EXPORT 20PAA | 29/06/2022 | 05/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--2222-135 | TT_Task | SENDING / RECEIVING / REVIEWING OFFERS ERECTION CONTRACTOR (MECHANICAL) | 19/03/2021 | 12/07/2021 | 19/03/2021 | 12/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--2222-136 | TT_Task | SENDING / RECEIVING / REVIEWING OFFERS ERECTION (E and IC) | 19/03/2021 | 12/07/2021 | 19/03/2021 | 12/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--2222-137 | TT_Task | REVISE RFQ DOCUMENTS / AUDIT / CHECK REVISED OFFERS ERECTION CONTRACTOR (MECHANICAL) | 13/07/2021 | 16/08/2021 | 13/07/2021 | 16/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--2222-138 | TT_Task | REVISE RFQ DOCUMENTS / AUDIT / CHECK REVISED OFFERS ERECTION CONTRACTOR (E and IC) | 13/07/2021 | 16/08/2021 | 13/07/2021 | 16/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--2222-139 | TT_Task | CONTRACT NEGOTIATION / AWARD ERECTION CONTRACTOR (MECHANICAL) | 03/08/2021 | 22/10/2021 | 03/08/2021 | 22/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--2222-140 | TT_Task | CONTRACT NEGOTIATION / AWARD ERECTION CONTRACTOR (E and IC) | 03/08/2021 | 02/12/2021 | 03/08/2021 | 02/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20QJ-2-17 | TT_Task | BASIC DESIGN, SPECIFICATION CENTRAL GAS SUPPLY (H2,CO2) QJ_ | 14/02/2021 | 27/03/2021 | 14/02/2021 | 27/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20QJ-2-80 | TT_Task | QUOTATION STAGE CENTRAL GAS SUPPLY (H2,CO2) QJ_ | 11/04/2021 | 22/05/2021 | 11/04/2021 | 22/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20QJ-2-86 | TT_Task | PREPARATION RFQ CENTRAL GAS SUPPLY (H2,CO2) QJ_ | 28/03/2021 | 10/04/2021 | 28/03/2021 | 10/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20QJ-2-85 | TT_Mile | CONTRACT INTO FORCE CENTRAL GAS SUPPLY (H2,CO2) QJ_ | 23/05/2021 | 23/05/2021 | 23/05/2021 | 23/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20BZK7-49 | TT_Task | 10BBA05 - FEEDER 1: MV + CONTROL CABLE CONN. C STATION / D1 STATION TO BE REMOVED FROM CABLE TRAY | 22/01/2023 | 18/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK7-50 | TT_Task | 10BBA05 - FEEDER 1: MV + CONTROL CABLE CONN. D1 STATION FROM 10BBA05 TO D2 STATION 90BBA01 INSTALLED ON CABLE TRAY | 19/02/2023 | 04/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BBA7-51 | TT_Task | COMMISSIONING MV SWITCHGEAR FEEDER 1 FOR MV + PROTECTION LINK C STATION TO D2 STATION 90BBA01 | 07/03/2023 | 21/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BBA7-52 | TT_FinMile | ENERGISATION FEEDER 20BBA00GA002 IN 20UBA7710/20 VIA 90BBA01 90BBA03 IN 01UBA9010/20 FROM C STATION | 28/03/2023 | 28/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BBA7-53 | TT_Task | COMMISSIONING MV SWITCHGEAR FEEDER 1 FOR MV + PROTECTION LINK D2 STATION 90BBA02 IN 01UBA9010/20 TO D1 STATION 10BBA05 | 29/03/2023 | 11/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BBA7-54 | TT_FinMile | ENERGISATION FEEDER 1 OF D1 STATION FROM 90BBA02 IN 01UBA9010/20 | 11/04/2023 | 11/04/2023 |  |  | 640 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK7-201 | TT_Task | 10BBA06 - FEEDER 2: MV + CONTROL CABLE CONN. C STATION / D1 STATION TO BE REMOVED FROM CABLE TRAY | 11/04/2023 | 08/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZK7-202 | TT_Task | 10BBA06 - FEEDER 2: MV + CONTROL CABLE CONN. D1 STATION FROM 10BBA06 TO D2 STATION 90BBB01 INSTALLED ON CABLE TRAY | 09/05/2023 | 22/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BBA7-55 | TT_Task | COMMISSIONING MV SWITCHGEAR FEEDER 2 FOR MV + PROTECTION LINK C STATION TO D2 STATION 90BBB01 | 23/05/2023 | 06/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BBA7-56 | TT_FinMile | ENERGISATION FEEDER 20BBB00GA002 IN 20UBA7710/20 VIA 90BBB01 90BBB03 IN 01UBA9010/20 FROM C STATION | 06/06/2023 | 06/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BBA7-57 | TT_Task | COMMISSIONING MV SWITCHGEAR FEEDER 2 FOR MV + PROTECTION LINK D2 STATION 90BBB02 IN 01UBA9010/20 TO D1 STATION 10BBA06 | 07/06/2023 | 20/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BBA7-58 | TT_FinMile | ENERGISATION FEEDER 2 OF D1 STATION FROM 90BBB02 IN 01UBA9010/20 | 20/06/2023 | 20/06/2023 |  |  | 80 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SMM3-81 | TT_Task | DETAIL AND FABRICATION DESIGN CRANE 20SMM03 FOR 20UMC | 08/08/2021 | 02/10/2021 | 08/08/2021 | 02/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--SMM2-90 | TT_Mile | CONTRACT INTO FORCE CRANES 20SMM03 FOR 20UMC | 27/04/2021 | 27/04/2021 | 27/04/2021 | 27/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--SMM2-88 | TT_Task | CONTRACT REVIEW / PREP. RFQ CRANE 20SMM03 FOR 20UMC | 30/03/2021 | 12/04/2021 | 30/03/2021 | 12/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20SMM3-82 | TT_Task | FABRICATION DESIGN/ MANUFACTURING / SHOP TEST / TRANSPORT CRANE 20SMM03 FOR 20UMC | 03/10/2021 | 12/01/2022 | 03/10/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--SMM2-89 | TT_Task | QUOTATION STAGE CRANES 20SMM03 FOR 20UMC | 13/04/2021 | 26/04/2021 | 13/04/2021 | 26/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--SMM2-91 | TT_FinMile | (DF) MS3 INPUT FOR CRANES 20SMM03 FOR 20UMC | 10/05/2021 | 10/05/2021 | 10/05/2021 | 10/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--SMM2-92 | TT_FinMile | (DF) INPUT FOR VEL CRANES 20SMM03 FOR 20UMC | 24/05/2021 | 24/05/2021 | 24/05/2021 | 24/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MAN6H16 | TT_Task | INSULATION PIPES / VALVES MAN | 03/02/2023 | 23/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAV6H16 | TT_Task | INSULATION PIPES / VALVES MAV | 19/11/2022 | 16/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAX6H17 | TT_Task | INSULATION PIPES / VALVES MAX | 10/02/2023 | 02/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MB-6A16 | TT_Task | INSULATION PIPES / VALVES 20MB (BOP) | 01/01/2023 | 28/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBA6A16 | TT_Task | INSULATION PIPES / VALVES 20MBA | 01/01/2023 | 04/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LCW6H16 | TT_Task | INSULATION PIPES / VALVES 20LCW | 18/01/2023 | 14/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20LDK6A16 | TT_Task | INSULATION PIPES / VALVES 20LDK | 29/12/2022 | 01/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20EKG6I16 | TT_Task | INSULATION PIPES 20EKG | 12/02/2023 | 04/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAH6H16 | TT_Task | INSULATION PIPES / VALVES 20PAH | 11/01/2023 | 07/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAR6A16 | TT_Task | INSULATION PIPES 20PAR MAKE UP WATER PIPES FOR COOLING TOWER | 15/08/2022 | 28/08/2022 |  |  | 624 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PCB6H16 | TT_Task | INSULATION PIPES / VALVES SERVICE COOL.WATER 20PCB | 27/11/2022 | 24/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PUR2J87 | TT_Task | CP DESIGN DRAWINGS SUBSTRUCTURE-20URA/URD | 11/06/2021 | 25/07/2021 | 11/06/2021 | 25/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PUR2J86 | TT_Task | CONCEPT REVIEW BY CLP / NEGOTIATION / AWARD CATHODIC PROTECTION 20URA xx | 02/04/2021 | 11/05/2021 | 02/04/2021 | 11/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PUR2J88 | TT_Task | COORDINATION ATKINS - CPT / INCL. EMBEDDED PARTS - SUPERSTRUCTURE 20URA/URD | 11/10/2021 | 12/11/2021 | 11/10/2021 | 12/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PUR2J89 | TT_Task | CP DESIGN DRAWINGS SUPERSTRUCTURE-20URA/URD | 03/07/2021 | 24/07/2021 | 03/07/2021 | 24/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PUR2J91 | TT_Task | CLIENT REVIEW DETAIL DESIGN SUPERSTRUCTURE AND CATHODIC PROTECTION-20URA/URD | 25/07/2021 | 18/08/2021 | 25/07/2021 | 18/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PUR2J92 | TT_Task | CLIENT - REVIEW - CONCRETE SUPERSTRUCTURE CATHODIC PROTECTION 20URA-To be used/cancel xx | 30/06/2021 | 24/07/2021 | 30/06/2021 | 24/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PUR2J93 | TT_Task | PROCUREMENT AND SHIPPING CATHODIC PROTECTION SUBSTRUCTURE-20URA/URD | 01/08/2021 | 30/09/2021 | 01/08/2021 | 30/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PUR2J94 | TT_Task | PROCUREMENT AND SHIPPING CATHODIC PROTECTION SUPERSTRUCTURE-20URA/URD | 15/06/2021 | 12/11/2021 | 15/06/2021 | 12/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI---1P2H528 | TT_Task | PIPE SUPPORTS DOCUMENTATION OFF RACK LOT4 | 06/07/2021 | 16/08/2021 | 06/07/2021 | 16/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI---1P2A518 | TT_Task | PIPE SUPPORTS DOCUMENTATION OFF RACK LOT6 | 31/08/2021 | 18/10/2021 | 31/08/2021 | 18/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI---1P2H529 | TT_Task | FABRICATION ISOMETRICS OFF RACK LOT 7 | 21/07/2021 | 30/08/2021 | 21/07/2021 | 30/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI---1P2A517 | TT_Task | PIPE SUPPORTS DOCUMENTATION OFF RACK LOT7 | 21/07/2021 | 30/08/2021 | 21/07/2021 | 30/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI---1P2A515 | TT_Task | DESIGN PHASE PIPING GRP PLASTIC MATERIAL LOT7 | 04/06/2021 | 20/07/2021 | 04/06/2021 | 20/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI---1P2H530 | TT_Task | FABRICATION ISOMETRICS OFF RACK LOT4 | 06/07/2021 | 16/08/2021 | 06/07/2021 | 16/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI---1P2A513 | TT_FinMile | (M2) LOT4-Gr.1(LAB,LBx,PAB10, PAB20)(Final PID's) | 22/04/2021 | 22/04/2021 | 22/04/2021 | 22/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI---1P2A512 | TT_Task | DESIGN PHASE PIPING LARGE BORE SUPPORTS LOT4 | 21/05/2021 | 05/07/2021 | 21/05/2021 | 05/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI---1P2H536 | TT_Task | PIPE SUPPORTS DOCUMENTATION OFF RACK LOT5 | 28/07/2021 | 14/09/2021 | 28/07/2021 | 14/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI---1P2A526 | TT_Task | DESIGN PHASE PIPING SMALL BORE SUPPORTS LOT 6 | 11/06/2021 | 27/07/2021 | 11/06/2021 | 27/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI---1P2H537 | TT_Task | FABRICATION ISOMETRICS OFF RACK LOT 6 | 28/07/2021 | 14/10/2021 | 28/07/2021 | 14/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI---1P2A525 | TT_Task | PIPE SUPPORTS DOCUMENTATION ON RACK LOT1 | 20/07/2021 | 08/09/2021 | 20/07/2021 | 08/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI---1P2A523 | TT_Task | PIPE SUPPORTS DOCUMENTATION ON RACK LOT2 | 06/08/2021 | 01/09/2021 | 06/08/2021 | 01/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI---1P2H538 | TT_Task | FABRICATION ISOMETRICS OFF RACK LOT 5 | 28/07/2021 | 14/09/2021 | 28/07/2021 | 14/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI---1P2A520 | TT_FinMile | (M2) LOT5-GR.4(GHD,GKB,GMx,QFB,SCB,SGA,MAA/B/C)(FInal Data for Piping design needed) | 03/06/2021 | 03/06/2021 | 03/06/2021 | 03/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI---1P2A521 | TT_Task | DESIGN PHASE PIPING LARGE BORE SUPPORTS LOT 5 | 11/06/2021 | 27/07/2021 | 11/06/2021 | 27/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UZx2-48 | TT_Task | REVIEW OF DETAIL DESIGN TEMPORARY BUILDINGS (by Siemens) 20UZx | 02/06/2021 | 04/06/2021 | 02/06/2021 | 04/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UZx5-51 | TT_Task | CONSTRUCTION INDUCTION-EHS / FIRST AID STATION / GATE HOUSE 20UZx | 26/07/2021 | 20/08/2021 | 26/07/2021 | 20/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UZx5-52 | TT_Task | CONSTRUCTION DAY ACCOMODATION BUILDINGS DA-1/DA-2/DA-3/DA-4/DA-5 20UZx | 01/09/2021 | 03/12/2021 | 01/09/2021 | 03/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UZx5-53 | TT_Task | CONSTRUCTION SANITARY CONTAINERS AT CONTRACTORS VILLAGE 20UZx | 10/09/2021 | 16/10/2021 | 10/09/2021 | 16/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--3335-66 | TT_Task | INSTALLATION OF POTABLE WATER AND WASTE WATER SYSTEM (TP availability needed?) | 01/07/2021 | 27/08/2021 | 01/07/2021 | 27/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--3335-67 | TT_Task | PREPARATION OF AREA AT SIEMENS INDUCTION-EHS / FIRST AID STATION / GATE HOUSE | 01/07/2021 | 22/07/2021 | 01/07/2021 | 22/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--3335-68 | TT_Task | PREPARATION OF LAYDOWN AREAS AND SIEMENS STORAGE | 01/07/2021 | 16/08/2021 | 01/07/2021 | 16/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--3335-69 | TT_Task | PREPARATION OF CONTRACTORS VILLAGE AREA | 01/07/2021 | 27/08/2021 | 01/07/2021 | 27/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--3335-70 | TT_Task | INSTALLATION OF TEMPORARY ROADS AT LAYDOWN AREA | 15/09/2021 | 02/11/2021 | 15/09/2021 | 02/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--3335-71 | TT_Task | INSTALLATION OF SIEMENS WAREHOUSE | 30/08/2021 | 03/12/2021 | 30/08/2021 | 03/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--5552-104 | TT_Task | DETAIL DESIGN SITE INFRASTRUCTURE (by subcontractor) | 14/04/2021 | 27/04/2021 | 14/04/2021 | 27/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--5552-105 | TT_Task | REVIEW OF DETAIL DESIGN SITE INFRASTRUCTURE (by Siemens) | 28/04/2021 | 04/05/2021 | 28/04/2021 | 04/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-430 | TT_Task | 20 - HOARDING PLAN AMENDMENT RENEWAL OF HOARDING PLAN | 01/04/2021 | 30/04/2021 | 01/04/2021 | 30/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-440 | TT_Task | 20(a) - HOARDING PLAN AMENDMENT RENEWAL OF HOARDING PLAN | 10/06/2021 | 09/07/2021 | 10/06/2021 | 09/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P222-147 | TT_Task | 64 - TEMPORARY EXCAVATION AND LATERAL SUPPORT (ELS) WORKS | 17/04/2021 | 16/05/2021 | 17/04/2021 | 16/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P222-148 | TT_Task | 64a - TEMPORARY EXCAVATION AND LATERAL SUPPORT (ELS) WORKS | 17/06/2021 | 16/07/2021 | 17/06/2021 | 16/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P222-149 | TT_Task | 143 - MASTER LAYOUT PLAN REVISION | 01/06/2021 | 29/08/2021 | 01/06/2021 | 29/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P222-150 | TT_Task | 143b - LANDSCAPE MASTER PLAN REVISION | 02/01/2023 | 01/04/2023 |  |  | 2192 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-8-27 | TT_Task | INSTALL BUMPERS HRSG20 | 16/02/2022 | 15/03/2022 |  |  | 56 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-6C29 | TT_Task | ERECTION STAIRCASE 2 (INLET DUCT) HRSG20 | 23/07/2022 | 05/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-6-51 | TT_Task | ERECTION STACK HRSG20_Basering | 04/06/2022 | 10/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-6-52 | TT_Task | ERECTION STACK HRSG20_Flue Gas Silencer | 11/07/2022 | 31/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-6A18 | TT_Task | FOUNDATION SURVEY HRSG20 | 21/12/2021 | 03/01/2022 | 21/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--3335-73 | TT_Task | SITE POWER - SDB1.2.1 - INSTALLATION | 01/07/2021 | 22/07/2021 | 01/07/2021 | 22/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--3335-72 | TT_Task | SITE POWER - SDB1.1 - DISMANTLE AND RELOCATE TO NEW LOCATION | 01/07/2021 | 29/07/2021 | 01/07/2021 | 29/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--3335-75 | TT_Task | SITE POWER - SDB1.5 / SDB1.6 - INSTALLATION | 01/07/2021 | 21/07/2021 | 01/07/2021 | 21/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--3335-74 | TT_Task | SITE POWER - SDB1.4 - INSTALLATION | 01/07/2021 | 29/07/2021 | 01/07/2021 | 29/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--3335-76 | TT_Task | SITE POWER - GATE HOUSE/INDUCTION ROOM/FIRST AID/LCMPTW OFFICE - INSTALLATION POWER SUPPLY | 01/07/2021 | 20/08/2021 | 01/07/2021 | 20/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--3335-77 | TT_Task | SITE POWER - WAREHOUSE/DAY ACCOMODATION BUILDINGS - INSTALLATION POWER SUPPLY | 01/07/2021 | 26/11/2021 | 01/07/2021 | 27/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--3335-78 | TT_Task | SITE POWER - ABLUTION AND SHOWR CONTAINERS - INSTALLATION POWER SUPPLY | 01/07/2021 | 22/10/2021 | 01/07/2021 | 22/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--3335-79 | TT_Task | SITE POWER - AS PER IT CONCEPT - INSTALLATION OF FIBER OPTIC/LAN CABLES | 01/07/2021 | 29/07/2021 | 01/07/2021 | 29/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UEN-2-46 | TT_Task | BASIC DESIGN PLANT LAYOUT FUEL GAS AREA | 06/03/2021 | 16/04/2021 | 06/03/2021 | 16/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UE-2-47 | TT_Task | BASIC DESIGN PLANT LAYOUT COOLING TOWER | 23/02/2021 | 16/04/2021 | 23/02/2021 | 16/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P222-151 | TT_Task | 149 - FURTHER ENVIRONMENTAL PERMIT | 15/05/2021 | 30/05/2021 | 15/05/2021 | 30/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAD8-57 | TT_Task | COMMISSIONING CATHODIC PROTECTION FOR COOLING TOWER 20PUR | 11/04/2023 | 24/04/2023 |  |  | 320 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD8-58 | TT_Task | COMMISSIONING CATHODIC PROTECTION FOR PAC ELECTRICAL MODULES | 11/04/2023 | 24/04/2023 |  |  | 320 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAD8-59 | TT_Task | COMMISSIONING CATHODIC PROTECTION FOR CONDENSER | 11/04/2023 | 24/04/2023 |  |  | 320 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---3B97 | TT_FinMile | ERECTION MANUALS ON SITE (CLOUD) FOR OFF RACK PIPING LOT 7 | 16/03/2022 | 16/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---3B98 | TT_FinMile | (RFS) READY FOR SHIPMENT OFFRACK / YARD LOT 7 | 27/04/2022 | 27/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---4B32 | TT_Task | TRANSPORT OFFRACK PIPING LOT 7 | 28/04/2022 | 01/06/2022 |  |  | 56 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---4-19 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION OFFRACK / YARD LOT 7 | 31/03/2022 | 27/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---3-78 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) FOR OFFRACK PIPING LOT 7 | 30/03/2022 | 30/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20---3B96 | TT_Task | PREFABRICATION OF OFFRACK PIPING FOR SHIPMENT LOT 7 | 05/11/2021 | 30/03/2022 | 05/11/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI-P222-152 | TT_Task | 83a - ISSUE OF LICENCES | 10/07/2023 | 07/09/2023 |  |  | 920 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P222-153 | TT_Task | 81a- ISSUE OF FIRE SAFETY REQUIREMENTS FOR STORAGE/USE OF DG UNDER DANGEROUS GOODS ORDINANCE | 09/11/2022 | 06/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HSJ3-84 | TT_Task | DETAIL DESIGN DECOMP. CHAMBER / HOT AIR BLOWER SUPPORT FRAME | 29/04/2021 | 18/07/2021 | 29/04/2021 | 18/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20HSJ3-85 | TT_Task | BD - SUBMISSION APPROVAL - DECOMP. CHAMBER / HOT AIR BLOWER SUPPORT FRAME | 19/07/2021 | 16/09/2021 | 19/07/2021 | 16/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20HSJ3-86 | TT_Task | DESIGN, MANUFACTURING, SHOP TEST SCR EQUIPMENT HSJ/HSK | 17/09/2021 | 08/12/2021 | 17/09/2021 | 08/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-396 | TT_Mile | 50 - BD - SUBMISSION - GT PLATFORM | 17/06/2021 | 17/06/2021 | 17/06/2021 | 17/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-397 | TT_Mile | 51 - BD - SUBMISSION - UMCM1Y SUPPORTING FRAME AND UMCLY PREFAB | 05/07/2021 | 05/07/2021 | 05/07/2021 | 05/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-398 | TT_Mile | 52 - BD - SUBMISSION - UPY SUPPORTING FRAME FOR CW PIPES | 03/08/2021 | 03/08/2021 | 03/08/2021 | 03/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-399 | TT_Mile | 53 - BD - SUBMISSION - UEY01/02 PIPE AND CABLE RACKS | 03/08/2021 | 03/08/2021 | 03/08/2021 | 03/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-401 | TT_Mile | 54 - BD - SUBMISSION - UMY ULY PIPE AND CABLE RACKS | 17/06/2021 | 17/06/2021 | 17/06/2021 | 17/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--2222-141 | TT_Task | 55 - BD - SUBMISSION - MiC PRE-ACCEPTANCE | 20/04/2021 | 18/06/2021 | 20/04/2021 | 18/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--2222-142 | TT_Mile | 56 - BD - SUBMISSION - UBA ACCESS PLATFORMS - 1 | 02/08/2021 | 02/08/2021 | 02/08/2021 | 02/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--2222-143 | TT_Mile | 57 - BD - SUBMISSION - UBA ACCESS PLATFORMS - 2 | 28/02/2022 | 28/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P221-211 | TT_Mile | 62 - BD - SUBMISSION - DETAIL DESIGN CONCRETE - 20UBY05 | 13/12/2021 | 13/12/2021 | 13/12/2021 | 13/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P222-154 | TT_Task | UPDATE OF PROCESS OPERATIONAL SAFETY MEASURES | 01/01/2023 | 21/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P222-155 | TT_Task | PREPARE PILOT SCHEME FOR CT | 17/04/2021 | 15/05/2021 | 17/04/2021 | 15/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P222-156 | TT_Task | CALCULATION OF OVERALL FIRE WATER DEMAND / UPDATE OF INSPECTION PROCEDURES/PREPARATION SCHEMATIC DWGS | 01/07/2022 | 11/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P222-157 | TT_Task | PREPARATION OF AS-BUILT DRAWINGS / MATERIAL TEST RECORDS FOR DG APPLICATION | 09/11/2022 | 15/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P222-158 | TT_Task | PREPARATION FOR LICENSE FOR STORAGE OF DG (CONSTRUCTION WORKS) | 19/05/2021 | 15/06/2021 | 19/05/2021 | 15/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P222-159 | TT_Task | PREPARATION DOCUMENTATION PRESSURE VESSELS (CONSTRUCTION WORKS) | 31/05/2021 | 30/06/2021 | 31/05/2021 | 30/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P222-160 | TT_Task | PREPARATION CERTIFICATIONS FOR LIFTING APPLIANCES | 19/04/2022 | 09/05/2022 |  |  | 56 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P222-161 | TT_Task | PREPARATION CERTIFICATIONS FOR PRESSURE VESSELS | 15/11/2022 | 14/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--HA-2-101 | TT_Task | HRSG ENGINEERING / PREPARATION BD SUBMISSION - STACK / MAINFRAME | 27/01/2021 | 15/05/2021 | 27/01/2021 | 15/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--HA-2-102 | TT_Task | HRSG ENGINEERING / PREPARATION BD SUBMISSION - PLATFORMS/STEELWORK | 16/05/2021 | 29/11/2021 | 16/05/2021 | 29/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P222-162 | TT_Task | PREPARATION OF FOREIGN WORKER VISA / JUSTIFICATION FOR FOREIGN EMPLOYMENT | 12/02/2021 | 31/05/2021 | 12/02/2021 | 31/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P222-163 | TT_Task | Preparation of NOTIFICATION OF CONSTRUCTION WORKS AND WORKER REGISTRATION | 14/05/2021 | 31/05/2021 | 14/05/2021 | 31/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P222-164 | TT_Task | PREPARATION OF DOCUMENTS FOR SUBMISSIONS 90/92/94/95 | 04/05/2021 | 01/06/2021 | 04/05/2021 | 01/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P222-165 | TT_Task | PREPARATION OF SUBMISSIONS TO CIC/PCFB | 14/05/2021 | 31/05/2021 | 14/05/2021 | 31/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P222-166 | TT_Task | PREPARATION OF SUBMISSIONS FOR FORM 3 - COMPLETION OF CONSTRUCTION WORKS | 17/12/2023 | 30/12/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P222-167 | TT_Task | PREPARATION OF SUBMISSION FOR FIREWALL IMPORT LICENSE | 19/11/2021 | 19/12/2021 | 19/11/2021 | 19/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P222-168 | TT_Task | PREPARATION OF SUBMISSION FOR 104/105/106 | 20/12/2021 | 19/01/2022 | 20/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI-P222-169 | TT_Task | PREPARATION OF FORM 542 SUBMISSION (TOWN WATER DOMESTIC WATER SUPPLY) | 02/06/2021 | 15/06/2021 | 02/06/2021 | 15/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P222-170 | TT_Task | PREPARATION OF FORM 542 SUBMISSION (TOWN WATER SERVICES SYSTEM) | 02/06/2021 | 15/06/2021 | 02/06/2021 | 15/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P222-171 | TT_Task | PREPARATION OF FORM 542 SUBMISSION (FRESH FIRE WATER SUPPLY) | 16/07/2021 | 17/08/2021 | 16/07/2021 | 17/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
CL-3335-80 | TT_Task | PILING/PILE TRIMMING WORKS (CLP SCOPE) | 15/01/2021 | 30/05/2021 | 15/01/2021 | 30/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P222-172 | TT_Task | DRAIN TESTS AND REPORTS | 04/12/2022 | 25/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P222-173 | TT_Task | PREPARATION OF AS-BUILT DOCUMENTATION FOR FSI/314 FSI 501 SUBMISSION | 21/11/2022 | 01/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P222-174 | TT_Task | PREPARATION OF DOCUMENTATION FOR OP SUBMISSION | 02/01/2023 | 01/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P222-175 | TT_Task | PREPARATION OF LAYOUT/LANDSCAPING PLAN | 17/04/2021 | 31/05/2021 | 17/04/2021 | 31/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P222-176 | TT_Task | PREPARATION OF LAYOUT/LANDSCAPING PLAN - REVISED/FINAL | 21/11/2022 | 01/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P222-177 | TT_Task | PREPARATION OF BPPS APCL SUBMISSION | 27/05/2022 | 07/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P222-178 | TT_Task | PREPARATION OF FINAL SUBMISSION DOCUMENTATION (TOWN WATER DOMESTIC WATER SUPPLY/TOWN WATER SERVICE) | 21/11/2022 | 14/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P222-179 | TT_Task | PREPARATION OF FINAL SUBMISSION DOCUMENTATION ( FRESH FIRE WATER) | 21/11/2022 | 29/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B96 | TT_Task | ERECTION CRANE WALKWAY 20SMM03 20UMC | 12/04/2022 | 02/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SMM6-74 | TT_Mile | (CCC) CRANE 20SMM03 IN SERVICE 20UMC | 17/05/2022 | 17/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SMM6-72 | TT_Task | PRE-ERECTION CRANE 20SMM03 FOR 20UMC / PREPARATION FOR LIFTING | 26/04/2022 | 02/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SMM6-73 | TT_Task | ERECTION / ACCEPTANCE TEST CRANE 20SMM03 FOR 20UMC | 03/05/2022 | 16/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B97 | TT_FinMile | (RFE) STEEL STRUCTURE CRANE WALKWAY RAILS 20SMM03 20UMC | 02/05/2022 | 02/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5C57 | TT_Mile | (RFE) ROOF CLOSED (ANNEX) 20UMC (single layer) | 13/05/2022 | 13/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UPY2-36 | TT_Task | DETAIL DESIGN BARBENDING STRUCTURE 20UPY | 01/09/2021 | 21/09/2021 | 01/09/2021 | 21/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UPY2-37 | TT_FinMile | BD - BA10 COMMENCEMENT OF WORK CONCRETE 20UPY | 31/07/2021 | 31/07/2021 | 31/07/2021 | 31/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-89 | TT_Task | DETAIL DESIGN BARBENDING STRUCTURE 20UTG01 | 01/04/2022 | 21/04/2022 |  |  | 88 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-90 | TT_FinMile | BD - BA10 COMMENCEMENT OF WORK CONCRETE 20UTG01 | 05/05/2022 | 05/05/2022 |  |  | 40 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-91 | TT_Task | DETAIL DESIGN BARBENDING STRUCTURE 20UTG07 | 01/04/2022 | 21/04/2022 |  |  | 32 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-92 | TT_FinMile | BD - BA10 COMMENCEMENT OF WORK CONCRETE 20UTG07 | 28/04/2022 | 28/04/2022 |  |  | 24 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--UMX2-86 | TT_Task | DETAIL DESIGN BARBENDING STRUCTURE UMX-deleted | 09/11/2021 | 29/11/2021 | 09/11/2021 | 29/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMX2-87 | TT_FinMile | BD - BA10 COMMENCEMENT OF WORK CONCRETE UMX | 15/11/2021 | 15/11/2021 | 15/11/2021 | 15/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20USX2-44 | TT_Task | DETAIL DESIGN BARBENDING STRUCTURE 20USX | 06/05/2022 | 26/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20USX2-45 | TT_FinMile | BD - BA10 COMMENCEMENT OF WORK CONCRETE 20USX | 02/06/2022 | 02/06/2022 |  |  | 104 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UHW2-51 | TT_Task | DETAIL DESIGN BARBENDING STRUCTURE UHW | 18/08/2021 | 07/09/2021 | 18/08/2021 | 07/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHW2-52 | TT_FinMile | BD - BA10 COMMENCEMENT OF WORK CONCRETE UHW | 31/07/2021 | 31/07/2021 | 31/07/2021 | 31/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2-51 | TT_Task | DETAIL DESIGN BARBENDING STRUCTURE 20UBA1110/20 | 23/10/2021 | 12/11/2021 | 23/10/2021 | 12/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2-52 | TT_FinMile | BD - BA10 COMMENCEMENT OF WORK CONCRETE 20UBA1110/20 | 05/05/2022 | 05/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-93 | TT_Task | DETAIL DESIGN BARBENDING STRUCTURE 20UTG04 | 12/02/2022 | 04/03/2022 |  |  | 216 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-94 | TT_FinMile | BD - BA10 COMMENCEMENT OF WORK CONCRETE 20UTG04 | 18/03/2022 | 18/03/2022 |  |  | 160 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEN2-107 | TT_Task | DETAIL DESIGN BARBENDING STRUCTURE 20UEN | 22/12/2021 | 11/01/2022 | 22/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--UEN2A76 | TT_FinMile | BD - BA10 COMMENCEMENT OF WORK CONCRETE 20UEN | 15/02/2022 | 15/02/2022 |  |  | 272 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--ULA2-80 | TT_Task | DETAIL DESIGN BARBENDING STRUCTURE 20ULA | 17/08/2021 | 06/09/2021 | 17/08/2021 | 06/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--ULA2-81 | TT_FinMile | BD - BA10 COMMENCEMENT OF WORK CONCRETE 20ULA | 31/07/2021 | 31/07/2021 | 31/07/2021 | 31/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBH2-96 | TT_Task | DETAIL DESIGN BARBENDING STRUCTURE 20UBH01 | 16/10/2021 | 05/11/2021 | 16/10/2021 | 05/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBH2-97 | TT_FinMile | BD - BA10 COMMENCEMENT OF WORK CONCRETE 20UBH01 | 08/01/2022 | 08/01/2022 |  |  | 440 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UHX2-45 | TT_Task | DETAIL DESIGN BARBENDING STRUCTURE 20UHX (if required) | 16/03/2022 | 05/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UVM2-86 | TT_Task | DETAIL DESIGN BARBENDING STRUCTURE 20UVM01 | 01/10/2021 | 21/10/2021 | 01/10/2021 | 21/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UVM2-87 | TT_FinMile | BD - BA10 COMMENCEMENT OF WORK CONCRETE 20UVM01 | 31/07/2021 | 31/07/2021 | 31/07/2021 | 31/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UBA2-108 | TT_Task | DETAIL DESIGN BARBENDING STRUCTURE UBA7xxx | 01/10/2021 | 21/10/2021 | 01/10/2021 | 21/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UBA2-109 | TT_FinMile | BD - BA10 COMMENCEMENT OF WORK CONCRETE UBA7xxx | 31/07/2021 | 31/07/2021 | 31/07/2021 | 31/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UBA2-110 | TT_Task | DETAIL DESIGN BARBENDING STRUCTURE UBA7910/7920 | 16/03/2022 | 05/04/2022 |  |  | 264 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--UBA2A76 | TT_FinMile | BD - BA10 COMMENCEMENT OF WORK CONCRETE UBA7910/7920 | 19/04/2022 | 19/04/2022 |  |  | 152 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-95 | TT_Task | DETAIL DESIGN BARBENDING STRUCTURE 20UTG02 | 04/02/2022 | 24/02/2022 |  |  | 384 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-96 | TT_FinMile | BD - BA10 COMMENCEMENT OF WORK CONCRETE 20UTG02 | 05/05/2022 | 05/05/2022 |  |  | 24 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UGU2-67 | TT_Task | DETAIL DESIGN BARBENDING STRUCTURE 20UGU01 | 15/01/2022 | 04/02/2022 |  |  | 488 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UGU2-68 | TT_FinMile | BD - BA10 COMMENCEMENT OF WORK CONCRETE 20UGU01 | 19/04/2022 | 19/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--UBF2A77 | TT_FinMile | BD - BA10 COMMENCEMENT OF WORK CONCRETE 20UBE/UBF | 31/07/2021 | 31/07/2021 | 31/07/2021 | 31/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ2-97 | TT_Task | DETAIL DESIGN BARBENDING STRUCTURE 20UBZ05 | 05/03/2022 | 25/03/2022 |  |  | 376 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ2-98 | TT_FinMile | BD - BA10 COMMENCEMENT OF WORK CONCRETE 20UBZ05 | 08/04/2022 | 08/04/2022 |  |  | 320 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-97 | TT_Task | DETAIL DESIGN BARBENDING STRUCTURE 20UTG03 | 31/07/2021 | 20/08/2021 | 31/07/2021 | 20/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-98 | TT_FinMile | BD - BA10 COMMENCEMENT OF WORK CONCRETE 20UTG03 | 05/05/2022 | 05/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBD2-85 | TT_Task | DETAIL DESIGN BARBENDING- 20UBD01/02 | 21/01/2022 | 10/02/2022 |  |  | 496 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBD2-86 | TT_FinMile | BD - BA10 COMMENCEMENT OF WORK CONCRETE 20UBD01/02 | 17/03/2022 | 17/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBX2-82 | TT_Task | DETAIL DESIGN BARBENDING STRUCTURE 20UBX/20UBG03 | 30/11/2021 | 20/12/2021 | 30/11/2021 | 20/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UBX2A76 | TT_FinMile | BD - BA10 COMMENCEMENT OF WORK CONCRETE 20UBX/20UBG03 | 31/07/2021 | 31/07/2021 | 31/07/2021 | 31/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBN2-111 | TT_Task | DETAIL DESIGN BARBENDING STRUCTURE 20UBN | 27/05/2022 | 16/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBY2-68 | TT_Task | DETAIL DESIGN BARBENDING STRUCTURE UBY02(NotExisting) | 01/12/2021 | 21/12/2021 | 01/12/2021 | 21/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBY2-69 | TT_FinMile | BD - BA10 COMMENCEMENT OF WORK CONCRETE UBY02(NotExisting) | 01/12/2021 | 01/12/2021 | 01/12/2021 | 01/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ2-99 | TT_Task | DETAIL DESIGN BARBENDING STRUCTURE 20UBZ04 | 07/02/2022 | 27/02/2022 |  |  | 424 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ2-100 | TT_FinMile | BD - BA10 COMMENCEMENT OF WORK CONCRETE 20UBZ04 | 17/04/2022 | 17/04/2022 |  |  | 88 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEX2-110 | TT_Task | DETAIL DESIGN BARBENDING STRUCTURE 20UEX01 | 30/05/2022 | 19/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEX2-111 | TT_FinMile | BD - BA10 COMMENCEMENT OF WORK CONCRETE 20UEX01 | 03/07/2022 | 03/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBY2-70 | TT_Task | DETAIL DESIGN BARBENDING STRUCTURE UBY01 | 29/04/2022 | 19/05/2022 |  |  | 224 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBY2-71 | TT_FinMile | BD - BA10 COMMENCEMENT OF WORK CONCRETE | 26/05/2022 | 26/05/2022 |  |  | 224 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ2-101 | TT_Task | DETAIL DESIGN BARBENDING STRUCTURE 20UBZ01 | 11/02/2022 | 03/03/2022 |  |  | 552 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ2-102 | TT_FinMile | BD - BA10 COMMENCEMENT OF WORK CONCRETE 20UBZ01 | 17/03/2022 | 17/03/2022 |  |  | 496 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20ULY2-81 | TT_Task | DETAIL DESIGN BARBENDING STRUCTURE 20ULY01 | 21/01/2022 | 10/02/2022 |  |  | 496 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20ULY2-82 | TT_FinMile | BD - BA10 COMMENCEMENT OF WORK CONCRETE 20ULY01 | 10/03/2022 | 10/03/2022 |  |  | 272 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2C79 | TT_Task | DETAIL DESIGN BARBENDING STRUCTURE 20UBA8110/20 | 11/02/2022 | 03/03/2022 |  |  | 536 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2G79 | TT_FinMile | BD - BA10 COMMENCEMENT OF WORK CONCRETE 20UBA8110/20 | 17/03/2022 | 17/03/2022 |  |  | 536 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBD2E93 | TT_Task | DETAIL DESIGN BARBENDING STRUCTURE 20UBD03/04 | 11/02/2022 | 03/03/2022 |  |  | 504 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBD2E94 | TT_FinMile | BD - BA10 COMMENCEMENT OF WORK CONCRETE 20UBD03/04 | 17/03/2022 | 17/03/2022 |  |  | 448 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBY2-72 | TT_Task | DETAIL DESIGN BARBENDING STRUCTURE UBY03 | 29/04/2022 | 19/05/2022 |  |  | 56 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBY2-73 | TT_FinMile | BD - BA10 COMMENCEMENT OF WORK CONCRETE UBY03 | 02/06/2022 | 02/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-99 | TT_Task | DETAIL DESIGN BARBENDING STRUCTURE 20UTG05 | 01/04/2022 | 21/04/2022 |  |  | 56 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-100 | TT_FinMile | BD - BA10 COMMENCEMENT OF WORK CONCRETE 20UTG05 | 05/05/2022 | 05/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ2-103 | TT_Task | DETAIL DESIGN BARBENDING STRUCTURE 20UBZ02 | 08/02/2022 | 28/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ2-104 | TT_FinMile | BD - BA10 COMMENCEMENT OF WORK CONCRETE 20UBZ02 | 07/03/2022 | 07/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UGU2-69 | TT_Task | DETAIL DESIGN BARBENDING STRUCTURE 20UGU02 | 15/01/2022 | 04/02/2022 |  |  | 352 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UGU2-70 | TT_FinMile | BD - BA10 COMMENCEMENT OF WORK CONCRETE 20UGU02 | 19/04/2022 | 19/04/2022 |  |  | 16 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBY2-74 | TT_Task | DETAIL DESIGN BARBENDING STRUCTURE UBY04/05 | 11/02/2022 | 03/03/2022 |  |  | 136 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBY2-75 | TT_FinMile | BD - BA10 COMMENCEMENT OF WORK CONCRETE UBY04/05 | 17/03/2022 | 17/03/2022 |  |  | 72 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEN2-108 | TT_Task | DETAIL DESIGN BARBENDING STRUCTURE 01UEN | 13/12/2021 | 02/01/2022 | 13/12/2021 |  | 136 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UEN2-109 | TT_FinMile | BD - BA10 COMMENCEMENT OF WORK CONCRETE 01UEN | 17/03/2022 | 17/03/2022 |  |  | 232 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY2-89 | TT_Task | DETAIL DESIGN BARBENDING STRUCTURE 20UEY03-05 | 11/02/2022 | 03/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY2-90 | TT_FinMile | BD - BA10 COMMENCEMENT OF WORK CONCRETE20UEY03-05 | 17/03/2022 | 17/03/2022 |  |  | 208 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMX2-106 | TT_Task | DETAIL DESIGN BARBENDING STRUCTURE 20UMX02 | 11/02/2022 | 03/03/2022 |  |  | 496 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMX2-107 | TT_FinMile | BD - BA10 COMMENCEMENT OF WORK CONCRETE 20UMX02 | 17/03/2022 | 17/03/2022 |  |  | 432 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY2-91 | TT_Task | DETAIL DESIGN BARBENDING STRUCTURE 20UEY02 | 04/02/2022 | 24/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY2-92 | TT_FinMile | BD - BA10 COMMENCEMENT OF WORK CONCRETE20UEY01 | 31/07/2021 | 31/07/2021 | 31/07/2021 | 31/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UEY2-93 | TT_FinMile | BD - BA10 COMMENCEMENT OF WORK CONCRETE20UEY02 | 17/03/2022 | 17/03/2022 |  |  | 160 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY2-94 | TT_Task | DETAIL DESIGN BARBENDING STRUCTURE 20UEY01 | 25/09/2021 | 15/10/2021 | 25/09/2021 | 15/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMY2-79 | TT_Task | DETAIL DESIGN BARBENDING STRUCTURE 20ULY/UMY | 16/11/2021 | 06/12/2021 | 16/11/2021 | 06/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMY2-80 | TT_FinMile | BD - BA10 COMMENCEMENT OF WORK CONCRETE 20ULY/UMY | 30/11/2021 | 30/11/2021 | 30/11/2021 | 30/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2C-81 | TT_Task | DETAIL DESIGN BARBENDING STRUCTURE 01UBA9010/20 | 05/03/2022 | 25/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2C-82 | TT_FinMile | BD - BA10 COMMENCEMENT OF WORK CONCRETE 01UBA9010/20 | 19/04/2022 | 19/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-101 | TT_Task | DETAIL DESIGN BARBENDING STRUCTURE 20UTG06 | 16/03/2022 | 05/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-102 | TT_FinMile | BD - BA10 COMMENCEMENT OF WORK CONCRETE 20UTG06 | 19/04/2022 | 19/04/2022 |  |  | 72 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
CLP20ULZ2-105 | TT_Task | DETAIL DESIGN BARBENDING STRUCTURE 20ULZ02 (CLP Scope) | 29/04/2021 | 19/05/2021 | 29/04/2021 | 19/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
CLP20ULZ2-106 | TT_FinMile | BD - BA10 COMMENCEMENT OF WORK CONCRETE 20ULZ02 (CLP Scope) | 02/06/2021 | 02/06/2021 | 02/06/2021 | 02/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBH2-98 | TT_Task | DETAIL DESIGN BARBENDING STRUCTURE 20UBH02 | 16/10/2021 | 05/11/2021 | 16/10/2021 | 05/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBH2-99 | TT_FinMile | BD - BA10 COMMENCEMENT OF WORK CONCRETE 20UBH02 | 11/12/2021 | 11/12/2021 | 11/12/2021 | 11/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
CLP20UEZ2-112 | TT_Task | DETAIL DESIGN BARBENDING STRUCTURE 20UEZ02 (CLP Scope) | 29/04/2021 | 19/05/2021 | 29/04/2021 | 19/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
CLP20UEZ2-113 | TT_FinMile | BD - BA10 COMMENCEMENT OF WORK CONCRETE 20UEZ02 (CLP Scope) | 02/06/2021 | 02/06/2021 | 02/06/2021 | 02/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UQX2-41 | TT_Task | DETAIL DESIGN BARBENDING STRUCTURE 20UQX | 16/03/2022 | 05/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQX2-42 | TT_FinMile | BD - BA10 COMMENCEMENT OF WORK CONCRETE 20UQX | 19/04/2022 | 19/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQZ2-109 | TT_Task | DETAIL DESIGN BARBENDING CIVIL ADAPTION WORKS AT SCW PUMP HOUSE 20UQB | 04/02/2022 | 24/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQZ2-110 | TT_FinMile | BD - BA10 COMMENCEMENT OF WORK CONCRETE CIVIL ADAPTION WORKS AT SCW PUMP HOUSE 20UQB | 10/03/2022 | 10/03/2022 |  |  | 11128 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY2-105 | TT_Task | DETAIL DESIGN BARBENDING STRUCTURE 20UQY01 | 16/03/2022 | 05/04/2022 |  |  | 56 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY2-106 | TT_FinMile | BD - BA10 COMMENCEMENT OF WORK CONCRETE 20UQY01 | 19/04/2022 | 19/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY2-107 | TT_Task | DETAIL DESIGN BARBENDING STRUCTURE 20UQY02 | 16/03/2022 | 05/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY2-108 | TT_FinMile | BD - BA10 COMMENCEMENT OF WORK CONCRETE 20UQY02 | 19/04/2022 | 19/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY2-109 | TT_Task | DETAIL DESIGN BARBENDING STRUCTURE 20UQY03 | 16/03/2022 | 05/04/2022 |  |  | 56 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQZ2-111 | TT_Task | DETAIL DESIGN BARBENDING STRUCTURE 20UQZ | 11/01/2022 | 31/01/2022 |  |  | 168 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BZP2-104 | TT_Task | DETAIL DESIGN CABLE SUPPORT SYSTEM 20UBY05/UBZ03/ULZ02/UBZ02 (FIRST SUBMISSION) | 08/01/2022 | 22/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--M--2D21 | TT_Task | CLIENT TERMINAL POINTS DOCUMENTS | 15/01/2021 | 10/04/2021 | 15/01/2021 | 10/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6A62 | TT_FinMile | (RFS) READY FOR SHIPMENT TO SITE ST HP/IP/LP VALVES | 29/04/2022 | 29/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-4-44 | TT_FinMile | (OTD-OS) ON SITE ST HP/IP/LP VALVES | 23/07/2022 | 23/07/2022 |  |  | 248 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-4-43 | TT_Task | TRANSPORT ST HP/IP/LP VALVES | 30/04/2022 | 23/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MA-3-85 | TT_Task | MANUFACTURING HP/IP/LP VALVES | 14/06/2021 | 01/04/2022 | 14/06/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SP20MA-3-86 | TT_Task | ENGINEERING / PROCUREMENT ST HP/IP/LP VALVES | 15/01/2021 | 13/06/2021 | 15/01/2021 | 13/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MA-4-12 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION HP/IP/LP VALVES | 02/04/2022 | 29/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MA-3-87 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) HP/IP/LP VALVES | 01/04/2022 | 01/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20--2-10 | TT_Mile | SITE WALKDOWN - GENERAL ITEMS | 08/08/2020 | 08/08/2020 | 08/08/2020 | 08/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20--2-30 | TT_Mile | SITE WALKDOWN - ELECTRICAL / IC INTERFACES | 03/02/2021 | 03/02/2021 | 03/02/2021 | 03/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20--2-40 | TT_Mile | SITE WALKDOWN - CONTROL ROOM / C4 STATION | 03/03/2021 | 03/03/2021 | 03/03/2021 | 03/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20--2-35 | TT_Mile | SITE WALKDOWN - MECHANICAL INTERFACES | 09/02/2021 | 09/02/2021 | 09/02/2021 | 09/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20--2-15 | TT_Mile | SITE WALKDOWN - SCW PUMP HOUSE 1/3 | 04/09/2020 | 04/09/2020 | 04/09/2020 | 04/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20--2-45 | TT_Mile | SITE WALKDOWN - CONTROL ROOM / C4 STATION | 19/04/2021 | 19/04/2021 | 19/04/2021 | 19/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20--2-20 | TT_Mile | SITE WALKDOWN - SCW PUMP HOUSE 2/3 | 09/09/2020 | 09/09/2020 | 09/09/2020 | 09/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20--2-25 | TT_Mile | SITE WALKDOWN - SCW PUMP HOUSE 3/3 | 12/10/2020 | 12/10/2020 | 12/10/2020 | 12/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-----2E95 | TT_Mile | ORDER MTO LONG LEAD ITEMS (80%) | 19/03/2021 | 19/03/2021 | 19/03/2021 | 19/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2A86 | TT_Mile | CONSTRUCTION DRWING TS FOUND. 20UMC READY | 15/06/2021 | 15/06/2021 | 15/06/2021 | 15/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAD3-100 | TT_Task | PROCUREMENT MATERIAL COOLING TOWER - FILL - 20PAD | 06/07/2021 | 04/10/2021 | 06/07/2021 | 04/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAD3-101 | TT_Task | PROCUREMENT MATERIAL COOLING TOWER - FRP - 20PAD | 06/07/2021 | 04/10/2021 | 06/07/2021 | 04/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAD3-102 | TT_Task | FABRICATION DESIGN COOLING TOWER - FILL - 20PAD | 05/10/2021 | 02/01/2022 | 05/10/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20PAD3-103 | TT_Task | FABRICATION DESIGN COOLING TOWER - FRP - 20PAD | 05/10/2021 | 02/01/2022 | 05/10/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20PAD3-104 | TT_Task | PROCUREMENT MATERIAL COOLING TOWER - NOISE ATT / PIPING / DRIFT ELIM - 20PAD | 06/07/2021 | 04/10/2021 | 06/07/2021 | 04/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAD3-105 | TT_Task | PROCUREMENT MATERIAL COOLING TOWER - WALKWAY - 20PAD | 06/07/2021 | 04/10/2021 | 06/07/2021 | 04/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAD3-106 | TT_Task | FABRICATION DESIGN COOLING TOWER - NOISE ATT / PIPING / DRIFT ELIM - 20PAD | 05/10/2021 | 03/01/2022 | 05/10/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20PAD3-107 | TT_Task | FABRICATION DESIGN COOLING TOWER - WALKWAY - 20PAD | 05/10/2021 | 03/01/2022 | 05/10/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20PAD3-108 | TT_Task | PROCUREMENT MATERIAL COOLING TOWER - DRY EQUIPMENT ELECTRICAL - 20PAD | 06/07/2021 | 04/10/2021 | 06/07/2021 | 04/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAD3-109 | TT_Task | FABRICATION DESIGN COOLING TOWER - DRY EQUIPMENT ELECTRICAL - 20PAD | 05/10/2021 | 03/01/2022 | 05/10/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20PAD3-110 | TT_Task | PROCUREMENT MATERIAL COOLING TOWER - MECH. EQUIPMENT FANSTACK - 20PAD | 06/07/2021 | 22/11/2021 | 06/07/2021 | 22/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAD3-111 | TT_Task | FABRICATION DESIGN COOLING TOWER - MECH. EQUIPMENT FANSTACK - 20PAD | 23/11/2021 | 28/03/2022 | 23/11/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20PAD3-112 | TT_Task | PROCUREMENT MATERIAL COOLING TOWER - VACUUM SKID PIPING - 20PAD | 06/07/2021 | 18/10/2021 | 06/07/2021 | 18/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAD3-113 | TT_Task | FABRICATION DESIGN COOLING TOWER - VACUUM SKID PIPING - 20PAD | 19/10/2021 | 31/01/2022 | 19/10/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SP20MAD3-81 | TT_Task | DETAIL DESIGN ST BEARINGS 20MAD | 12/02/2021 | 27/05/2021 | 12/02/2021 | 27/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MAD3-82 | TT_Task | PROCUREMENT MATERIAL / SUBCONTRACT ST BEARINGS 20MAD | 28/05/2021 | 09/09/2021 | 28/05/2021 | 09/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MA-3-88 | TT_Task | DETAIL DESIGN STEAM TURBINE (HI-L) | 15/01/2021 | 29/04/2021 | 15/01/2021 | 29/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MA-3-89 | TT_Task | PROCUREMENT MATERIAL / SUBCONTRACT STEAM TURBINE (HI-L) | 30/04/2021 | 12/08/2021 | 30/04/2021 | 12/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20USX2-46 | TT_FinMile | (MS2) PRELIMINARY DESIGN INPUT AVAILABLE 20USX | 31/05/2021 | 31/05/2021 | 31/05/2021 | 31/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2S-141 | TT_Task | BASIC BUILDING DESIGN INCL. 3D MODEL 20UTG04 | 31/08/2021 | 20/09/2021 | 31/08/2021 | 20/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20HB-6-53 | TT_Task | INSTALL PIPING HRSG20_External Large Bore Second Part | 24/08/2022 | 26/10/2022 |  |  | 176 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P221-3651 | TT_Mile | BD - SUBMISSION - CIVIL PART 1 | 16/03/2021 | 16/03/2021 | 16/03/2021 | 16/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20TPM1A6-26 | TT_Task | ISOLATION PCI GAS SUPPLY BY CLP | 20/10/2022 | 30/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P221-3652 | TT_Mile | BD - SUBMISSION - CIVIL PART 2 | 15/04/2021 | 15/04/2021 | 15/04/2021 | 15/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-3653 | TT_Mile | BD - SUBMISSION - CIVIL PART 3 | 31/05/2021 | 31/05/2021 | 31/05/2021 | 31/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-3654 | TT_Mile | BD - SUBMISSION - CIVIL PART 4 | 17/06/2021 | 17/06/2021 | 17/06/2021 | 17/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-3655 | TT_Mile | BD - SUBMISSION - CIVIL PART 5 | 10/05/2021 | 10/05/2021 | 10/05/2021 | 10/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-P221-3657 | TT_Mile | BD - SUBMISSION - CIVIL PART 7 | 28/02/2022 | 28/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-P221-3658 | TT_Mile | BD - SUBMISSION - CIVIL PART 7 | 31/03/2022 | 31/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--9998-105 | TT_Mile | PROVISION OF FORECAST COMMISSIONING TESTING SCHEDULE / SEQUENCING /LOADS UTILITY DEMAND NOMINATION | 08/08/2022 | 08/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--9998-100 | TT_Mile | ESTABLISH COMMISSIONING COORDINATION GROUP | 08/08/2022 | 08/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-85.00 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-SPOOL1 | 19/11/2021 | 20/11/2021 | 19/11/2021 | 20/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-85.01 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20 -SPOOL2,3,4 | 25/08/2021 | 26/08/2021 | 25/08/2021 | 26/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-85.02 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-SPOOL5 | 30/08/2021 | 25/09/2021 | 30/08/2021 | 25/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-85.03 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-SPOOL6 | 30/08/2021 | 25/09/2021 | 30/08/2021 | 25/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-85.04 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-SPOOL7,8,9 | 30/07/2021 | 31/07/2021 | 30/07/2021 | 31/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-85.05 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-SPOOL10 | 31/08/2021 | 03/09/2021 | 31/08/2021 | 03/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-85.06 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-SPOOL11 | 02/09/2021 | 04/09/2021 | 02/09/2021 | 04/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-85.07 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-SPOOL12 | 04/09/2021 | 07/09/2021 | 04/09/2021 | 07/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-85.08 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-SPOOL13 | 04/09/2021 | 24/09/2021 | 04/09/2021 | 24/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-85.09 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-SPOOL14 | 28/09/2021 | 16/10/2021 | 28/09/2021 | 16/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-85.10 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-SPOOL15 INCLD. LAMINATION | 26/10/2021 | 04/11/2021 | 26/10/2021 | 04/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-85.11 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-SPOOL16 | 21/10/2021 | 23/10/2021 | 21/10/2021 | 25/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-85.12 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-SPOOL17 | 29/09/2021 | 06/10/2021 | 29/09/2021 | 06/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-85.13 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-SPOOL18 | 09/10/2021 | 11/10/2021 | 09/10/2021 | 11/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-85.14 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-SPOOL19 | 12/10/2021 | 13/10/2021 | 12/10/2021 | 13/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-85.15 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-SPOOL20 | 14/10/2021 | 15/10/2021 | 14/10/2021 | 15/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-85.16 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-SPOOL21,22,23 | 12/11/2021 | 13/11/2021 | 12/11/2021 | 13/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-85.17 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-SPOOL24 | 26/10/2021 | 27/10/2021 | 26/10/2021 | 27/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-85.18 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-SPOOL25 INCLD. LAMINATION | 12/11/2021 | 15/11/2021 | 12/11/2021 | 15/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-85.20 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-SPOOL2931 | 29/11/2021 | 30/11/2021 | 29/11/2021 | 30/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-85.21 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-SPOOL30 | 16/12/2021 | 18/12/2021 | 16/12/2021 | 18/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-85.22 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-SPOOL32 | 29/11/2021 | 30/11/2021 | 29/11/2021 | 30/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-85.23 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-SPOOL33 | 09/12/2021 | 10/12/2021 | 09/12/2021 | 10/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-85.24 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-LAMINATION SPOOL1,2 | 19/11/2021 | 26/11/2021 | 19/11/2021 | 26/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-85.25 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-LAMINATION SPOOL 2,3 | 28/08/2021 | 27/09/2021 | 28/08/2021 | 27/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-85.26 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-LAMINATION SPOOL 3,4 | 28/08/2021 | 23/09/2021 | 28/08/2021 | 23/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-85.27 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-LAMINATION SPOOL 7,8 | 19/07/2021 | 28/08/2021 | 19/07/2021 | 30/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-85.28 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-LAMINATION SPOOL 8,9 | 24/07/2021 | 28/08/2021 | 24/07/2021 | 30/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-85.29 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-LAMINATION SPOOL 21,22 | 16/10/2021 | 19/10/2021 | 16/10/2021 | 19/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-85.30 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-LAMINATION SPOOL 22,23 | 05/11/2021 | 11/11/2021 | 05/11/2021 | 11/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-85.31 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-SPOOL26 INCLD. LAMINATION | 01/11/2021 | 02/11/2021 | 01/11/2021 | 02/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-85.33 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-LAMINATION SPOOL 29-31 | 12/11/2021 | 27/11/2021 | 12/11/2021 | 27/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-85.34 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-LAMINATION SPOOL 32-31 | 09/12/2021 | 13/12/2021 | 09/12/2021 | 13/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-85.35 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-LAMINATION SPOOL 33-31 | 11/12/2021 | 15/12/2021 | 11/12/2021 | 15/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-85.36 | TT_Task | BACKFILLING TO 0,5m BEFORE PAB INSTALLATION | 15/07/2021 | 31/07/2021 | 15/07/2021 | 31/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--SG-2-107 | TT_Task | SUPPLIER PID's PREPARATION / FRIST DESIGN DWGS (ISOMETRICS) | 24/07/2021 | 03/09/2021 | 24/07/2021 | 03/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20SCA2-89 | TT_Task | RFQ CLARIFCATION ONGOING DUE TO CLIENT REQUEST TO CHANGE AIR COMPRESSOR TYPE TO OIL FILLED | 18/07/2021 | 30/07/2021 | 18/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20SCA2-90 | TT_Task | QUOTATION STAGE AIR COMPRESSOR SYSTEM SCA - OIL FILLED COMPRESSOR | 31/07/2021 | 20/09/2021 | 31/07/2021 | 20/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-60.00 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB41-SPOOL1 | 13/11/2021 | 15/11/2021 | 13/11/2021 | 15/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-60.01 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB41-SPOOL2,3 | 27/09/2021 | 28/09/2021 | 27/09/2021 | 28/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-60.02 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB41-SPOOL4 | 23/09/2021 | 24/09/2021 | 23/09/2021 | 25/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-60.03 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB41-SPOOL5 | 23/09/2021 | 24/09/2021 | 23/09/2021 | 24/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-60.04 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB41-SPOOL6,7,8 | 07/08/2021 | 10/09/2021 | 07/08/2021 | 10/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-60.05 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB41-SPOOL9 | 27/09/2021 | 28/09/2021 | 27/09/2021 | 28/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-60.06 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB41-SPOOL10 | 29/09/2021 | 05/10/2021 | 29/09/2021 | 05/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-60.07 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB41-SPOOL11 | 02/10/2021 | 05/10/2021 | 02/10/2021 | 05/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-60.08 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB41-SPOOL12 | 30/09/2021 | 05/10/2021 | 30/09/2021 | 05/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-60.09 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB41-SPOOL13 | 27/09/2021 | 04/10/2021 | 27/09/2021 | 04/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-60.10 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB41-SPOOL14 INCLD. LAMINATION | 15/10/2021 | 20/10/2021 | 15/10/2021 | 20/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-60.12 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB41-SPOOL16 | 30/09/2021 | 07/10/2021 | 30/09/2021 | 07/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-60.13 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB41-SPOOL17 | 08/10/2021 | 09/10/2021 | 08/10/2021 | 09/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-60.14 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB41-SPOOL18 | 11/10/2021 | 12/10/2021 | 11/10/2021 | 12/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-60.15 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB41-SPOOL19 | 13/10/2021 | 14/10/2021 | 13/10/2021 | 14/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-60.16 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB41-SPOOL20,21 | 15/10/2021 | 16/10/2021 | 15/10/2021 | 16/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-60.17 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB41-SPOOL22,23 | 18/10/2021 | 19/10/2021 | 18/10/2021 | 19/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-60.18 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB41-SPOOL24 | 20/10/2021 | 21/10/2021 | 20/10/2021 | 21/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-60.19 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB41-SPOOL26 | 02/11/2021 | 03/11/2021 | 02/11/2021 | 03/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-60.20 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB41-SPOOL27,28,29 | 30/11/2021 | 01/12/2021 | 30/11/2021 | 01/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-60.22 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB41-LAMINATION SPOOL 01,02 | 03/11/2021 | 27/11/2021 | 03/11/2021 | 27/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-60.23 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB41-LAMINATION SPOOL 02,03 | 31/08/2021 | 01/09/2021 | 31/08/2021 | 01/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-60.24 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB41-LAMINATION SPOOL 06,07 | 06/08/2021 | 10/09/2021 | 06/08/2021 | 10/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-60.25 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB41-LAMINATION SPOOL 07,08 | 04/08/2021 | 10/09/2021 | 04/08/2021 | 10/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-60.26 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB41-LAMINATION SPOOL 20,21 | 29/09/2021 | 11/10/2021 | 29/09/2021 | 11/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-60.27 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB41-LAMINATION SPOOL 22,23 | 29/09/2021 | 11/10/2021 | 29/09/2021 | 11/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-60.28 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB41-LAMINATION SPOOL 25,26 | 12/10/2021 | 02/11/2021 | 12/10/2021 | 02/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-60.29 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB41-LAMINATION SPOOL 27-28 | 21/10/2021 | 27/10/2021 | 21/10/2021 | 28/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-60.30 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB41-LAMINATION SPOOL 28-29 | 21/10/2021 | 27/10/2021 | 21/10/2021 | 28/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--URA2-93 | TT_Task | ATKINS REDESIGN DD SUPERSTRUCTURE-20URA/URD | 25/08/2021 | 21/09/2021 | 25/08/2021 | 21/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--URA2-94 | TT_Task | BD - SUBMISSION APPROVAL SUPERSTRUCTURE- RESUBMISSION 20URA/URD | 15/09/2021 | 12/11/2021 | 15/09/2021 | 12/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--URA2-98 | TT_Task | BARBENDING AND DRAWINGS SUPERSTRUCTURE-20URA/URD | 14/10/2021 | 12/11/2021 | 14/10/2021 | 12/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URA2B8 | TT_Task | BD - SUBMISSION APPROVAL SUBSTRUCTURE 20URA/URD 1ST SUBMISSION (1STPACKAGE) | 16/03/2021 | 12/05/2021 | 16/03/2021 | 13/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--URA2-99 | TT_Task | ATKINS REDESIGN DD SUBSTRUCTURE-20URA/URD | 15/06/2021 | 21/07/2021 | 15/06/2021 | 22/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--URA2-100 | TT_Task | COORDINATION ATKINS - CPT / INCL. EMBEDDED PARTS - SUBSTRUCTURE 20URA/URD | 06/08/2021 | 02/09/2021 | 06/08/2021 | 02/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--3335-80 | TT_Task | SITE POWER - SDB1.7 - INSTALLATION | 01/07/2021 | 13/08/2021 | 01/07/2021 | 13/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--URA2-101 | TT_FinMile | COOLING TOWER COMPONENTS (SPIG) SUPERSTRUCTURE-20URA/URD | 08/08/2021 | 08/08/2021 | 08/08/2021 | 08/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--URA2-102 | TT_FinMile | COORDINATION OF TERMINAL POINTS SUPERSTRUCTURE-20URA/URD | 08/08/2021 | 08/08/2021 | 08/08/2021 | 08/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URA2-75 | TT_FinMile | FIXING FOR COMPONENTS(PLUS CP),PIPING(MTECH) SUPERSTRUCTURE-20URA/URD | 08/08/2021 | 08/08/2021 | 08/08/2021 | 08/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URA2-76 | TT_FinMile | FIXING FOR CABLE TRAY ,LIGTHING (ETECH) SUPERSTRUCTURE-20URA/URD | 08/08/2021 | 08/08/2021 | 08/08/2021 | 08/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--URA2-103 | TT_FinMile | (F) START ON SITE SUBSTRUCTURE-20URA/URD | 07/09/2021 | 07/09/2021 | 07/09/2021 | 07/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA3H56 | TT_Task | MANUFACTURING ELECTRICAL MODULES 20UBA7320 | 08/07/2021 | 09/12/2021 | 08/07/2021 | 09/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA4-71 | TT_Mile | (ET4b) ELECTRICAL MODULES AT WORKSHOP READY FOR COMPONENT INSTALLATION ELECTRICAL MODULES 20UBA7320 | 10/12/2021 | 10/12/2021 | 10/12/2021 | 10/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA2H2 | TT_Mile | E-AND IC- MANUALS FOR COMP.INSTALL.AVAILABLE ELECTRICAL MODULES 20UBA7320 | 30/06/2021 | 30/06/2021 | 30/06/2021 | 30/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBA4G63 | TT_Mile | (ET4a) LATEST DELIVERY DATE GT+ST+BOP IC CUBICLES FOR ASSEMBLY 20UBA7320-(10 CABINETS) | 05/01/2022 | 05/01/2022 |  |  | 408 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA4B49 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION ELECTRICAL MODULES 20UBA7320 | 03/04/2022 | 30/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA3B80 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) ELECTRICAL MODULES 20UBA7320 | 02/04/2022 | 02/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20CJ-3-55 | TT_Task | MANUFACTURING BOP IC CABINETS FOR ELECTRICAL MODULES 20UBA7320-20CJC01+20CRY02 | 16/10/2021 | 04/01/2022 | 16/10/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UBA7-107 | TT_Task | INSTALLATION ELECTRICAL MODULES 20UBA7320 | 29/07/2022 | 18/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA7-108 | TT_Task | CABLING INTERNAL 20UBA7320 - PART OF ELECTRICAL MODULES ASSEMBLY | 05/08/2022 | 18/08/2022 |  |  | 336 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA7-106 | TT_Task | PLACING 20UBA7320 | 26/06/2022 | 26/06/2022 |  |  | 256 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA4B50 | TT_FinMile | (OTD-OS) ON SITE (ET4d) ELECTRICAL MODULES 20UBA7320 | 25/06/2022 | 25/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MA-3-90 | TT_Task | MANUFACTURING MAW VALVES | 05/07/2021 | 25/03/2022 | 05/07/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20MA-6A63 | TT_FinMile | (RFS) READY FOR SHIPMENT TO SITE ST MAW VALVES | 01/04/2022 | 01/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-4-46 | TT_FinMile | (OTD-OS) ON SITE ST MAW VALVES | 06/04/2022 | 06/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MA-4-45 | TT_Task | TRANSPORT ST MAW VALVES (AIR FREIGHT) | 02/04/2022 | 06/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MA-4-13 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION MAW VALVES | 26/03/2022 | 01/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MA-3-91 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) MAW VALVES | 25/03/2022 | 25/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAW6M12 | TT_Task | INSTALLATION OF MAW VALVES IN MODULE 20MAW50Y | 07/04/2022 | 20/04/2022 |  |  | 128 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAW6M13 | TT_Task | INSTALLATION OF MAW VALVES IN MODULE 20MAW10Y | 07/04/2022 | 20/04/2022 |  |  | 16 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BZL3-81 | TT_Task | DETAIL DESIGN LIGHTING SMALL POWER BZL HIGHBAY, 20UMC | 16/12/2021 | 18/03/2022 | 16/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20BZL7E19 | TT_Task | LIGHTING AND SMALL POWER INSTALLATION 01UEN | 07/11/2022 | 20/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZL8E27 | TT_Task | COMMISSIONING LIGHTING/SMALL POWER IN 01UEN | 21/11/2022 | 27/11/2022 |  |  | 1192 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZL8E26 | TT_FinMile | (TOP-20BZL-05) LIGHTING/SMALL POWER IN 01UEN | 20/11/2022 | 20/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZL7C16 | TT_Task | LIGHTING AND SMALL POWER 20UEN | 12/03/2023 | 25/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA8-61 | TT_FinMile | (TOP-20BZL06) LIGHTING AND SMALL POWER 20UEN | 25/03/2023 | 25/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20B--8-53 | TT_Task | COMMISSIONING LIGHTING AND SMALL POWER 20UEN | 26/03/2023 | 08/04/2023 |  |  | 664 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2B99 | TT_Task | BD - SUBMISSION APPROVAL - STEEL PLATFORMS LOT1 20UMC CEP/LDK/CRANE WALKWAY STAIRCASE | 02/07/2021 | 05/11/2021 | 02/07/2021 | 05/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20---3B99 | TT_Task | PREFABRICATION OF LAST ITEMS FOR SHIPMENT LOT 3 | 19/03/2022 | 25/03/2022 |  |  | 168 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BAA3-72 | TT_Task | DETAIL DESIGN / MANUFACTURING / SHOP TEST IPB FIRST PARTS / SADDLES 20BAA | 05/10/2021 | 30/05/2022 | 05/10/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20E--7-10 | TT_FinMile | ELECTRICAL ERECTION FINISHED FOR OIL FLUSHING | 25/02/2023 | 25/02/2023 |  |  | 112 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20E--7-15 | TT_FinMile | ELECTRICAL ERECTION FINISHED FOR 6.6kV/ 400kV BACK ENERGISING | 28/12/2022 | 28/12/2022 |  |  | 720 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20E--7-25 | TT_FinMile | ELECTRICAL ERECTION FINISHED FOR 6.6kV STATION BOARD (90BBA-D1) | 04/03/2023 | 04/03/2023 |  |  | 16 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20E--7-35 | TT_FinMile | ELECTRICAL ERECTION FINISHED FOR 1ST. IGNITION GT | 22/06/2023 | 22/06/2023 |  |  | 64 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20E--7-30 | TT_FinMile | ELECTRICAL ERECTION FINISHED FOR 6.6kV STATION BOARD (90BBB-D1) | 06/06/2023 | 06/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20E--7-5 | TT_FinMile | ELECTRICAL ERECTION CONTRACTOR MOBILISATION FINISHED | 02/04/2022 | 02/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5A15.00 | TT_Task | TURBOSET FOUNDATION (SLAB +/-0.00m) 20UMC - Blinding | 14/07/2021 | 23/07/2021 | 14/07/2021 | 24/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5A15.01 | TT_Task | TURBOSET FOUNDATION (SLAB +/-0.00m) 20UMC - Rebar bending | 29/07/2021 | 14/08/2021 | 29/07/2021 | 16/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5A15.02 | TT_Task | TURBOSET FOUNDATION (SLAB +/-0.00m) 20UMC - Excavation | 07/08/2021 | 09/08/2021 | 07/08/2021 | 10/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5A15.03 | TT_Task | TURBOSET FOUNDATION (SLAB +/-0.00m) 20UMC -Bituminous Paint | 13/08/2021 | 17/08/2021 | 13/08/2021 | 18/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5A15.04 | TT_Task | TURBOSET FOUNDATION (SLAB +/-0.00m) 20UMC -Formwork Erection S1 | 14/08/2021 | 07/09/2021 | 14/08/2021 | 07/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5A15.05 | TT_Task | TURBOSET FOUNDATION (SLAB +/-0.00m) 20UMC -Rebar Fixing Bottom Layer S1 | 18/08/2021 | 10/09/2021 | 18/08/2021 | 10/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5A15.06 | TT_Task | TURBOSET FOUNDATION (SLAB +/-0.00m) 20UMC -Grounding Installation | 25/08/2021 | 17/09/2021 | 25/08/2021 | 17/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5A15.07 | TT_Task | TURBOSET FOUNDATION (SLAB +/-0.00m) 20UMC -Working Platform Erection | 04/09/2021 | 25/09/2021 | 04/09/2021 | 25/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5A15.08 | TT_Task | TURBOSET FOUNDATION (SLAB +/-0.00m) 20UMC -Installation Drain PipesConduits | 15/09/2021 | 23/09/2021 | 15/09/2021 | 23/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5A15.09 | TT_Task | TURBOSET FOUNDATION (SLAB +/-0.00m) 20UMC -Rebar Fixing Top Layer | 08/09/2021 | 25/09/2021 | 08/09/2021 | 25/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5A15.10 | TT_Task | TURBOSET FOUNDATION (SLAB +/-0.00m) 20UMC -Installation of Cast-In Items | 24/09/2021 | 04/10/2021 | 24/09/2021 | 04/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5A15.11 | TT_Task | TURBOSET FOUNDATION (SLAB +/-0.00m) 20UMC -Concrete Pour | 07/10/2021 | 07/10/2021 | 07/10/2021 | 07/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5A15.12 | TT_Task | TURBOSET FOUNDATION (SLAB +/-0.00m) 20UMC -Curing | 08/10/2021 | 20/10/2021 | 08/10/2021 | 20/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5A15.13 | TT_Task | TURBOSET FOUNDATION (SLAB +/-0.00m) 20UMC -Dismantling Formworks | 21/10/2021 | 23/10/2021 | 21/10/2021 | 23/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5A15.14 | TT_Task | TURBOSET FOUNDATION (SLAB +/-0.00m) 20UMC -Backfilling | 25/10/2021 | 29/10/2021 | 25/10/2021 | 29/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5A15.15 | TT_FinMile | TURBOSET FOUNDATION (SLAB +/-0.00m) 20UMC -Completed | 01/11/2021 | 01/11/2021 | 01/11/2021 | 01/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y46.00 | TT_Task | CONSTRUCTION CEP PIT - Vertical Blinding (Lvl +2.50m)-Formwork Erection | 29/07/2021 | 31/07/2021 | 29/07/2021 | 01/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y46.01 | TT_Task | CONSTRUCTION CEP PIT - Vertical Blinding (Lvl +2.50m)-Concrete Pour | 02/08/2021 | 02/08/2021 | 02/08/2021 | 03/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y46.02 | TT_Task | CONSTRUCTION CEP PIT - Base Slab S1(Lvl +1.80m)-Damp Proofing | 10/08/2021 | 11/08/2021 | 10/08/2021 | 12/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y47.01 | TT_Task | CONSTRUCTION LDK PIT - Vertical Blinding (Lvl +0.75m)-Concrete Pour | 03/08/2021 | 03/08/2021 | 03/08/2021 | 04/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y47.00 | TT_Task | CONSTRUCTION LDK PIT - Vertical Blinding (Lvl +0.75m)-Formwork Erection | 02/08/2021 | 02/08/2021 | 02/08/2021 | 03/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y47.02 | TT_Task | CONSTRUCTION LDK PIT - Vertical Blinding (Lvl +0.75m)-Dismantle Formworks | 04/08/2021 | 04/08/2021 | 04/08/2021 | 05/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y47.04 | TT_Task | CONSTRUCTION LDK PIT - Base Slab(Lvl +0.65m)-Rebar FixingGrounding Installattion | 09/08/2021 | 11/08/2021 | 09/08/2021 | 12/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y47.03 | TT_Task | CONSTRUCTION LDK PIT - Base Slab(Lvl +0.65m)-Damp Proofing | 06/08/2021 | 06/08/2021 | 06/08/2021 | 07/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y47.05 | TT_Task | CONSTRUCTION LDK PIT - Base Slab(Lvl +0.65m)-Formwork ErectionInstallation of cast-in elements | 12/08/2021 | 13/08/2021 | 12/08/2021 | 14/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y47.06 | TT_Task | CONSTRUCTION LDK PIT - Base Slab(Lvl +0.65m)-Concrete Pour | 14/08/2021 | 14/08/2021 | 14/08/2021 | 15/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2A87 | TT_Task | BD - SUBMISSION APPROVAL-DETAIL DESIGN CONCRETE TURBOSET RESUBMISSION 1ST AND 2ND PACKAGES | 24/05/2021 | 09/06/2021 | 24/05/2021 | 10/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UEN2-110 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 01UEN NON PILED | 06/09/2021 | 06/09/2021 | 06/09/2021 | 06/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UBA2-111 | TT_FinMile | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE UBA7910/7920 NON PILED | 10/08/2021 | 10/08/2021 | 10/08/2021 | 10/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UBA2F62 | TT_FinMile | (MS3) STEEL STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UBA7910/20 NON PILED | 15/10/2021 | 15/10/2021 | 15/10/2021 | 15/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-UZA2-96.00 | TT_Task | SUBBASE RING ROAD INCL.(U/G) SYSTEM - PART1A-20UZA03-Excavation /Stripping | 11/10/2021 | 28/11/2021 | 11/10/2021 | 28/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-UZA2-96.01 | TT_Task | SUBBASE RING ROAD INCL.(U/G) SYSTEM - PART1A-20UZA03- base course | 21/10/2021 | 02/12/2021 | 21/10/2021 | 02/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-UZA2-96.02 | TT_Task | SUBBASE RING ROAD INCL.(U/G) SYSTEM - PART1A-20UZA03- sub base | 25/10/2021 | 06/12/2021 | 25/10/2021 | 06/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-UZA2-96.03 | TT_Task | SUBBASE RING ROAD INCL.(U/G) SYSTEM - PART1A-20UZA03-Road base | 05/11/2021 | 16/12/2021 | 05/11/2021 | 16/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-UZA2-97.00 | TT_Task | SUBBASE RING ROAD INCL.(U/G) SYSTEM - PART1B-20UZA02-Excavation /Stripping | 03/05/2022 | 17/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-UZA2-97.01 | TT_Task | SUBBASE RING ROAD INCL.(U/G) SYSTEM - PART1B-20UZA02-Laying base course and compaction | 18/05/2022 | 27/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-UZA2-97.02 | TT_Task | SUBBASE RING ROAD INCL.(U/G) SYSTEM - PART1B-20UZA02-Laying sub base and compaction | 28/05/2022 | 06/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-UZA2-97.03 | TT_Task | SUBBASE RING ROAD INCL.(U/G) SYSTEM - PART1B-20UZA02-Sub Finishing | 07/06/2022 | 13/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-UZA2-98.01 | TT_Task | SUBBASE RING ROAD INCL.(U/G) SYSTEM - PART1C-20UZA04-Laying base course and compaction | 29/06/2022 | 08/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-UZA2-98.00 | TT_Task | SUBBASE RING ROAD INCL.(U/G) SYSTEM - PART1C-20UZA04-Excavation /Stripping | 14/06/2022 | 28/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-UZA2-98.02 | TT_Task | SUBBASE RING ROAD INCL.(U/G) SYSTEM - PART1C-20UZA04-Laying sub base and compaction | 09/07/2022 | 18/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-UZA2-98.03 | TT_Task | SUBBASE RING ROAD INCL.(U/G) SYSTEM - PART1C-20UZA04-Sub Finishing | 19/07/2022 | 25/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-UZA2-99.00 | TT_Task | SUBBASE RING ROAD INCL.(U/G) SYSTEM - PART 2A-20UZA01-Excavation /Stripping | 05/04/2022 | 12/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-UZA2-99.01 | TT_Task | SUBBASE RING ROAD INCL.(U/G) SYSTEM - PART 2A-20UZA01-Laying base course and compaction | 13/04/2022 | 19/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-UZA2-99.02 | TT_Task | SUBBASE RING ROAD INCL.(U/G) SYSTEM - PART 2A-20UZA01-Laying sub base and compaction | 20/04/2022 | 26/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-UZA2-99.03 | TT_Task | SUBBASE RING ROAD INCL.(U/G) SYSTEM - PART 2A-20UZA01-Sub Finishing | 27/04/2022 | 02/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UHW5-20.01 | TT_Task | WORK PREPARATION, EXCAVATION 20UHW - Formworks for vertical blinding | 02/10/2021 | 07/10/2021 | 02/10/2021 | 07/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHW5-20.00 | TT_Task | WORK PREPARATION, EXCAVATION 20UHW - Blinding work to bottom pit | 22/07/2021 | 08/08/2021 | 22/07/2021 | 09/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHW5-20.02 | TT_Task | WORK PREPARATION, EXCAVATION 20UHW - Concreting for vertical blinding | 08/10/2021 | 10/10/2021 | 08/10/2021 | 10/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHW5-20.03 | TT_Task | WORK PREPARATION, EXCAVATION 20UHW - Adjust horizontal blinding | 27/10/2021 | 07/11/2021 | 27/10/2021 | 07/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHW5-70.03 | TT_Task | CONSTRUCTION STRUCTURE HRSG BLOWDOWN PIT 20UHW - Rebar fixing and grounding installation for base slab (1st Pour) | 26/11/2021 | 10/12/2021 | 26/11/2021 | 10/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHW5-70.04 | TT_Task | CONSTRUCTION STRUCTURE HRSG BLOWDOWN PIT 20UHW - Concreting for base slab (1st Pour) | 11/12/2021 | 11/12/2021 | 11/12/2021 | 11/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHW5-70.05 | TT_Task | CONSTRUCTION STRUCTURE HRSG BLOWDOWN PIT 20UHW - Rebar fixing of wall in pit (2nd Pour) | 17/12/2021 | 26/12/2021 | 17/12/2021 | 26/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHW5-70.06 | TT_Task | CONSTRUCTION STRUCTURE HRSG BLOWDOWN PIT 20UHW - Formwork for wal in pit (2nd pour) | 27/12/2021 | 03/01/2022 | 27/12/2021 |  | 184 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UHW5-70.07 | TT_Task | CONSTRUCTION STRUCTURE HRSG BLOWDOWN PIT 20UHW - Concreting for wal in pit (2nd pour) | 31/01/2022 | 31/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UHW5-70.08 | TT_Task | CONSTRUCTION STRUCTURE HRSG BLOWDOWN PIT 20UHW - Curing and dismantling | 01/02/2022 | 06/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UHA5-15.00 | TT_Task | CONSTRUCTION FOUNDATION 20UHA - Rebar fixing and grounding installation for base slab part1- left side -15m | 24/09/2021 | 29/09/2021 | 24/09/2021 | 29/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHA5-05.00 | TT_Task | WORK PREPARATION, EXCAVATION 20UHA-Formworks for side of blinding | 13/09/2021 | 18/09/2021 | 13/09/2021 | 19/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHA5-05.01 | TT_Task | WORK PREPARATION, EXCAVATION 20UHA-Excavation to correction setting-out level | 03/09/2021 | 12/09/2021 | 03/09/2021 | 13/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHA5-05.02 | TT_Task | WORK PREPARATION, EXCAVATION 20UHA-Blinding | 20/09/2021 | 24/09/2021 | 20/09/2021 | 24/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHA5-15.01 | TT_Task | CONSTRUCTION FOUNDATION 20UHA - Formwork for base slab part1- left side -15m | 22/09/2021 | 26/09/2021 | 22/09/2021 | 27/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHA5-15.02 | TT_Task | CONSTRUCTION FOUNDATION 20UHA - Anchor bolt installation base slab part1 | 30/09/2021 | 07/11/2021 | 30/09/2021 | 07/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHA5-15.03 | TT_Task | CONSTRUCTION FOUNDATION 20UHA - Concreting base slab part1 | 10/11/2021 | 10/11/2021 | 10/11/2021 | 10/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHA5-15.04 | TT_Task | CONSTRUCTION FOUNDATION 20UHA - Rebar fixing and grounding installation for base slab part2- right side -31m | 21/10/2021 | 27/11/2021 | 21/10/2021 | 27/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHA5-15.05 | TT_Task | CONSTRUCTION FOUNDATION 20UHA - Formwork for base slab part2- right side -31m | 24/10/2021 | 02/12/2021 | 24/10/2021 | 02/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHA5-15.07 | TT_Task | CONSTRUCTION FOUNDATION 20UHA - Concreting base slab part2 | 03/12/2021 | 03/12/2021 | 03/12/2021 | 03/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHA5-15.08 | TT_Task | CONSTRUCTION FOUNDATION 20UHA - Rebar fixing and grounding installation for base slab part3- mid part -12m | 06/12/2021 | 10/12/2021 | 06/12/2021 | 10/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHA5-15.09 | TT_Task | CONSTRUCTION FOUNDATION 20UHA - Desmantling of formworks part2 | 04/12/2021 | 05/12/2021 | 04/12/2021 | 05/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHA5-15.11 | TT_Task | CONSTRUCTION FOUNDATION 20UHA - Concreting base slab part3 Includ. MBR pedestal | 11/12/2021 | 11/12/2021 | 11/12/2021 | 11/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHA5-15.12 | TT_Task | CONSTRUCTION FOUNDATION 20UHA - Formwork removal and cleanup | 12/12/2021 | 20/12/2021 | 12/12/2021 | 20/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBF5-05.00 | TT_Task | WORK PREPARATION / EXCAVATION / PILE TRIMMING / PLATE WELDING 20UBE/UBF - Preparation and excavation | 11/01/2022 | 13/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBF5-05.01 | TT_Task | WORK PREPARATION / EXCAVATION / PILE TRIMMING / PLATE WELDING 20UBE/UBF - Blinding | 14/01/2022 | 14/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBF5-05.02 | TT_Task | WORK PREPARATION / EXCAVATION / PILE TRIMMING / PLATE WELDING 20UBE/UBF - Pile trimming | 15/01/2022 | 17/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-4G41 | TT_FinMile | (OTD-OS) ON SITE HEATING SURFACES HRSG20 MODULE5 | 26/03/2022 | 26/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-4G42 | TT_FinMile | (OTD-OS) ON SITE HEATING SURFACES HRSG20 MODULE4 | 30/03/2022 | 30/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-4G43 | TT_FinMile | (OTD-OS) ON SITE HEATING SURFACES HRSG20 MODULE3 | 03/04/2022 | 03/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-4G44 | TT_FinMile | (OTD-OS) ON SITE HEATING SURFACES HRSG20 MODULE2 | 07/04/2022 | 07/04/2022 |  |  | 48 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-4G45 | TT_FinMile | (OTD-OS) ON SITE HEATING SURFACES HRSG20 MODULE1 | 24/04/2022 | 24/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-4G50 | TT_Task | TRANSPORT HEATING SURFACES HRSG20 MODULE1 | 15/04/2022 | 24/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--URA2-104 | TT_Task | BD - RESUBMISSION APPROVAL SUBSTRUCTURE 2ND AMENDMENT 20URA/URD | 22/09/2021 | 13/11/2021 | 22/09/2021 | 14/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--URA2-105 | TT_Mile | BD - SUBMISSION APPROVAL SUBSTRUCTURE AMENDMENT SUBMISSION 20URA/URD WITHDRAWN | 12/08/2021 | 12/08/2021 | 12/08/2021 | 12/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI-UZA2-96.04 | TT_Task | SUBBASE RING ROAD INCL.(U/G) SYSTEM - PART1A-20UZA03-drainage | 15/02/2022 | 04/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y46.03 | TT_Task | CONSTRUCTION CEP PIT - Base Slab S1(Lvl +1.80m)-Rebar FixingGrounding Installation | 14/08/2021 | 19/08/2021 | 14/08/2021 | 20/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y46.04 | TT_Task | CONSTRUCTION CEP PIT - Base Slab S1(Lvl +1.80m)-Formwork ErectionInstallation of cast-in elements | 14/08/2021 | 19/08/2021 | 14/08/2021 | 20/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y46.05 | TT_Task | CONSTRUCTION CEP PIT - Base Slab S1(Lvl +1.80m)-Concrete Pour | 20/08/2021 | 20/08/2021 | 20/08/2021 | 20/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y46.06 | TT_Task | CONSTRUCTION CEP PIT - Base Slab S1(Lvl +1.80m)- Dismantling wailingstruts | 21/08/2021 | 21/08/2021 | 21/08/2021 | 23/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y46.07 | TT_Task | CONSTRUCTION CEP PIT - Base Slab S2(Lvl +2.40m)-Damp Proofing | 10/08/2021 | 11/08/2021 | 10/08/2021 | 12/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y46.08 | TT_Task | CONSTRUCTION CEP PIT - Base Slab S2(Lvl +2.40m)-Rebar FixingGrounding Installattion | 12/08/2021 | 28/08/2021 | 12/08/2021 | 30/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y46.09 | TT_Task | CONSTRUCTION CEP PIT - Base Slab S2(Lvl +2.40m)-Formwork ErectionInstallation of Cast-in Elements | 19/08/2021 | 30/08/2021 | 19/08/2021 | 30/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y46.10 | TT_Task | CONSTRUCTION CEP PIT - Base Slab S2(Lvl +2.40m)-Concrete Pour | 01/09/2021 | 01/09/2021 | 01/09/2021 | 01/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y46.11 | TT_Task | CONSTRUCTION CEP PIT - Base Slab S2(Lvl +2.40m)-Curing | 02/09/2021 | 03/09/2021 | 02/09/2021 | 03/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y46.12 | TT_Task | CONSTRUCTION CEP PIT - Base Slab S2(Lvl +2.40m)-Dismantle Formworks | 04/09/2021 | 07/09/2021 | 04/09/2021 | 07/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y46.13 | TT_Task | CONSTRUCTION CEP PIT - Screen Wall 0507-Scaffold Erection | 16/09/2021 | 21/09/2021 | 16/09/2021 | 23/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y46.14 | TT_Task | CONSTRUCTION CEP PIT - Screen Wall 0507-Vertical Blinding (Lvl +5.475m)-Formwork Erection | 23/09/2021 | 30/09/2021 | 23/09/2021 | 30/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y46.15 | TT_Task | CONSTRUCTION CEP PIT - Screen Wall 0507-Vertical Blinding (Lvl +5.475m)-Concrete Pour | 12/10/2021 | 12/10/2021 | 12/10/2021 | 12/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y46.16 | TT_Task | CONSTRUCTION CEP PIT - Screen Wall 0507-Vertical Blinding (Lvl +5.475m)-Dismantling Formworks | 15/10/2021 | 15/10/2021 | 15/10/2021 | 15/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y46.17 | TT_Task | CONSTRUCTION CEP PIT - Screen Wall 0507-Vertical Blinding (Lvl +5.475m)-Damp Proofing | 16/10/2021 | 18/10/2021 | 16/10/2021 | 18/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y46.18 | TT_Task | CONSTRUCTION CEP PIT - Screen Wall 02050607-Rebar Fixing | 26/10/2021 | 11/11/2021 | 26/10/2021 | 11/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y46.19 | TT_Task | CONSTRUCTION CEP PIT - Screen Wall 02050607-Formwork Erection | 12/11/2021 | 24/11/2021 | 12/11/2021 | 24/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y46.20 | TT_Task | CONSTRUCTION CEP PIT - Screen Wall 02050607-Concrete Pour | 25/11/2021 | 25/11/2021 | 25/11/2021 | 25/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y46.21 | TT_Task | CONSTRUCTION CEP PIT - Screen Wall 02050607-Curing | 26/11/2021 | 03/12/2021 | 26/11/2021 | 03/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y46.22 | TT_Task | CONSTRUCTION CEP PIT - Screen Wall 02050607-Dismantle Formworks | 04/12/2021 | 04/12/2021 | 04/12/2021 | 04/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y46.23 | TT_Task | CONSTRUCTION CEP PIT - Top Slab(Lvl +5.15m)-ExcavationCompaction | 06/12/2021 | 06/12/2021 | 06/12/2021 | 06/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y46.24 | TT_Task | CONSTRUCTION CEP PIT - Screen Wall 05-Sheet Pile Cutting | 07/12/2021 | 07/12/2021 | 07/12/2021 | 07/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y46.25 | TT_Task | CONSTRUCTION CEP PIT - Top Slab(Lvl +5.15m)-Blinding | 08/12/2021 | 08/12/2021 | 08/12/2021 | 08/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y46.26 | TT_Task | CONSTRUCTION CEP PIT - Top Slab(Lvl +5.15m)-Damp Proofing | 09/12/2021 | 09/12/2021 | 09/12/2021 | 09/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y46.27 | TT_Task | CONSTRUCTION CEP PIT - Top Slab(Lvl +5.15m)-Formwork Erection | 28/12/2021 | 28/12/2021 | 28/12/2021 | 28/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y46.28 | TT_Task | CONSTRUCTION CEP PIT - Top Slab(Lvl +5.15m)-Rebarfixing | 29/12/2021 | 29/12/2021 | 29/12/2021 | 29/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y46.29 | TT_Task | CONSTRUCTION CEP PIT - Top Slab(Lvl +5.15m)-Concrete Pour | 30/12/2021 | 30/12/2021 | 30/12/2021 | 30/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y46.30 | TT_Task | CONSTRUCTION CEP PIT - Screen Wall 03-Rebar Fixing | 06/01/2022 | 10/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y46.31 | TT_Task | CONSTRUCTION CEP PIT - Screen Wall 03-Formwork | 11/01/2022 | 12/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y46.32 | TT_Task | CONSTRUCTION CEP PIT - Screen Wall 03-Concrete Pour | 13/01/2022 | 13/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y46.33 | TT_Task | CONSTRUCTION CEP PIT - Screen Wall 03-Curing | 14/01/2022 | 17/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y46.34 | TT_Task | CONSTRUCTION CEP PIT - Screen Wall 03-Dismantling Formworks | 18/01/2022 | 18/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y46.35 | TT_Task | CONSTRUCTION CEP PIT - Screen Wall 03-Damp Proofing | 19/01/2022 | 19/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y46.36 | TT_Task | CONSTRUCTION CEP PIT - Screen Wall 03-Backfilling | 20/01/2022 | 20/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y46.37 | TT_Task | (RFE) CONSTRUCTION CEP PIT | 21/01/2022 | 21/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y47.07 | TT_Task | CONSTRUCTION LDK PIT - Excavation around pit +350mPD | 21/08/2021 | 27/08/2021 | 21/08/2021 | 28/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y47.08 | TT_Task | CONSTRUCTION LDK PIT - Sheet Pile Cutting | 27/09/2021 | 15/10/2021 | 27/09/2021 | 15/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y47.09 | TT_Task | CONSTRUCTION LDK PIT - Scaffold Erection(Lvl +2.65m) | 23/09/2021 | 24/09/2021 | 23/09/2021 | 24/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y47.12 | TT_Task | CONSTRUCTION LDK PIT - Vertical Blinding (Lvl +2.65m)-Dismatle Works | 20/10/2021 | 20/10/2021 | 20/10/2021 | 20/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y47.10 | TT_Task | CONSTRUCTION LDK PIT - Vertical Blinding (Lvl +2.65m)-Formwork Erection | 16/10/2021 | 18/10/2021 | 16/10/2021 | 18/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y47.11 | TT_Task | CONSTRUCTION LDK PIT - Vertical Blinding (Lvl +2.65m)-Concrete Pour | 19/10/2021 | 19/10/2021 | 19/10/2021 | 19/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y47.13 | TT_Task | CONSTRUCTION LDK PIT - Screen Wall S1(Lvl +2.65m)-Damp Proofing | 21/10/2021 | 21/10/2021 | 21/10/2021 | 21/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y47.14 | TT_Task | CONSTRUCTION LDK PIT - Dismatle of WalingStruts | 27/09/2021 | 15/10/2021 | 27/09/2021 | 15/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y47.15 | TT_Task | CONSTRUCTION LDK PIT - Screen Wall S1(Lvl +2.65m)-Rebar Fixing | 25/10/2021 | 04/11/2021 | 25/10/2021 | 04/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y47.16 | TT_Task | CONSTRUCTION LDK PIT - Screen Wall S1(Lvl +2.65m)-Formworks Erection | 01/11/2021 | 06/11/2021 | 01/11/2021 | 06/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y47.17 | TT_Task | CONSTRUCTION LDK PIT - Screen Wall S1(Lvl +2.65m)-Concrete Pour | 06/11/2021 | 06/11/2021 | 06/11/2021 | 06/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y47.18 | TT_Task | CONSTRUCTION LDK PIT - Screen Wall S1(Lvl +2.65m)-Curing | 08/11/2021 | 11/11/2021 | 08/11/2021 | 11/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y47.19 | TT_Task | CONSTRUCTION LDK PIT - Screen Wall S2(Lvl +4.65m)-Rebar Fixing | 05/11/2021 | 30/11/2021 | 05/11/2021 | 30/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y47.20 | TT_Task | CONSTRUCTION LDK PIT - Screen Wall S2(Lvl +4.65m)-Formwork | 06/12/2021 | 13/12/2021 | 06/12/2021 | 13/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y47.21 | TT_Task | CONSTRUCTION LDK PIT - Screen Wall S2(Lvl +4.65m)-Concrete Pour | 14/12/2021 | 14/12/2021 | 14/12/2021 | 14/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y47.22 | TT_Task | CONSTRUCTION LDK PIT - Screen Wall S2(Lvl +4.65m)-Curing | 15/12/2021 | 22/12/2021 | 15/12/2021 | 22/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y47.23 | TT_Task | CONSTRUCTION LDK PIT - Screen Wall S2(Lvl +4.65m)-Dismatle Formwork | 22/12/2021 | 22/12/2021 | 22/12/2021 | 22/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y47.24 | TT_Task | CONSTRUCTION LDK PIT - Screen Wall S3(Lvl +4.65m)-DampProofing | 08/01/2022 | 08/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y47.25 | TT_Task | (RFE CONSTRUCTION LDK PIT | 10/01/2022 | 10/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y47.27 | TT_Task | CONSTRUCTION LDK TRENCH - LDK Trench Slab-Blinding | 10/11/2021 | 11/11/2021 | 10/11/2021 | 11/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y47.28 | TT_Task | CONSTRUCTION LDK TRENCH - LDK Trench Slab-Formwork Erection | 12/11/2021 | 13/11/2021 | 12/11/2021 | 13/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y47.29 | TT_Task | CONSTRUCTION LDK TRENCH - LDK Trench Slab-Rebarworks | 25/11/2021 | 26/11/2021 | 25/11/2021 | 26/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y47.30 | TT_Task | CONSTRUCTION LDK TRENCH - LDK Trench Slab-Concrete Pour | 14/12/2021 | 14/12/2021 | 14/12/2021 | 14/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y47.31 | TT_Task | CONSTRUCTION LDK TRENCH - LDK Trench Walls-Rebarworks | 29/11/2021 | 18/12/2021 | 29/11/2021 | 18/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y47.32 | TT_Task | CONSTRUCTION LDK TRENCH - LDK Trench Walls-Formwork | 23/12/2021 | 31/12/2021 | 23/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y47.33 | TT_Task | CONSTRUCTION LDK TRENCH - LDK Trench Walls-Concrete Pouring | 03/01/2022 | 03/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y47.34 | TT_Task | CONSTRUCTION LDK TRENCH - LDK Trench Walls-Curing | 04/01/2022 | 06/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y47.35 | TT_Task | CONSTRUCTION LDK TRENCH - LDK Trench Walls-Formwork Removal | 07/01/2022 | 07/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--URA2-107 | TT_Task | BD - CONSENT LETTER RESUBMISSION2 SUBSTRUCTURE 20URA/URD | 27/10/2021 | 08/11/2021 | 27/10/2021 | 09/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--ULA2-82 | TT_FinMile | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE - WITHDRAWAL 20ULA(2NDPACKAGES) | 13/05/2021 | 13/05/2021 | 13/05/2021 | 13/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UPY2-38 | TT_FinMile | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE - WITHDRAWN 20UPY (1STPACKAGE) | 13/05/2021 | 13/05/2021 | 13/05/2021 | 13/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UBE5-18.00 | TT_Task | CONSTRUCTION FOUNDATION 20UBE/UBF- Formwork installation part1 baseslab | 23/01/2022 | 01/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBE5-18.01 | TT_Task | CONSTRUCTION FOUNDATION 20UBE/UBF- Rebarfixing and grounding installation part1 baseslab | 02/02/2022 | 15/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBE5-18.02 | TT_Task | CONSTRUCTION FOUNDATION 20UBE/UBF- Concreting part1 baseslab | 16/02/2022 | 17/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBF5-15.01 | TT_Task | CONSTRUCTION TRANSFORMER TABLE WALLS 20UBF- Formwork installation Part2 | 18/02/2022 | 02/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBF5-15.02 | TT_Task | CONSTRUCTION TRANSFORMER TABLE WALLS 20UBF- Rebarfixing and grounding installation part2 | 03/03/2022 | 22/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBF5-15.03 | TT_Task | CONSTRUCTION TRANSFORMER TABLE WALLS 20UBF- Concreting part2 | 23/03/2022 | 24/03/2022 |  |  | 8 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBF5E15.00 | TT_Task | CONSTRUCTION WALLS 20UBF-Working platform and formwork installation stage1 Part3 | 18/02/2022 | 09/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBF5E15.01 | TT_Task | CONSTRUCTION WALLS 20UBF-Rebarfixing and grounding installation Part3 | 10/03/2022 | 29/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBF5E15.02 | TT_Task | CONSTRUCTION WALLS 20UBF-Formwork installation stage2 Part3 | 30/03/2022 | 12/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBF5E15.03 | TT_Task | CONSTRUCTION WALLS 20UBF-Concreting stage2 Part3 | 13/04/2022 | 15/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBF5E15.04 | TT_Task | CONSTRUCTION WALLS 20UBF-Remove formwork stage2 Part3 | 16/04/2022 | 20/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-17.01 | TT_Task | CONSTRUCTION FOUNDATION BAY1(BASIN)- Apply damproofing | 10/09/2021 | 17/09/2021 | 10/09/2021 | 17/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-17.02 | TT_Task | CONSTRUCTION FOUNDATION BAY1(BASIN)- Grounding installation | 02/10/2021 | 06/10/2021 | 02/10/2021 | 06/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-17.03 | TT_Task | CONSTRUCTION FOUNDATION BAY1(BASIN)- Rebar fabrication | 01/10/2021 | 28/10/2021 | 01/10/2021 | 28/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-17.04 | TT_Task | CONSTRUCTION FOUNDATION BAY1(BASIN)- Rebar fixing-Lower | 18/10/2021 | 28/10/2021 | 18/10/2021 | 28/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-17.05 | TT_Task | CONSTRUCTION FOUNDATION BAY1(BASIN)- Formwork Erection | 02/09/2021 | 28/09/2021 | 02/09/2021 | 28/09/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-17.06 | TT_Task | CONSTRUCTION FOUNDATION BAY1(BASIN)- Installation of tower crane support | 29/10/2021 | 30/10/2021 | 29/10/2021 | 30/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-17.07 | TT_Task | CONSTRUCTION FOUNDATION BAY1(BASIN)- Installation of Cathodic protection | 29/10/2021 | 02/12/2021 | 29/10/2021 | 02/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-17.08 | TT_Task | CONSTRUCTION FOUNDATION BAY1(BASIN)- Concreting | 04/12/2021 | 04/12/2021 | 04/12/2021 | 04/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-17.09 | TT_Task | CONSTRUCTION FOUNDATION BAY1(BASIN)- Curing of Concrete | 30/11/2021 | 03/12/2021 | 30/11/2021 | 03/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-17.10 | TT_Task | CONSTRUCTION FOUNDATION BAY1(BASIN)-Formwork desmantling | 30/11/2021 | 02/12/2021 | 30/11/2021 | 02/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-19.11 | TT_Task | CONSTRUCTION FOUNDATION BAY2A- Apply damproofing | 11/01/2022 | 14/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-19.12 | TT_Task | CONSTRUCTION FOUNDATION BAY2A- Grounding installation | 09/10/2021 | 11/10/2021 | 09/10/2021 | 11/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-19.13 | TT_Task | CONSTRUCTION FOUNDATION BAY2A- Rebar fabrication | 08/10/2021 | 08/10/2021 | 08/10/2021 | 08/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-19.14 | TT_Task | CONSTRUCTION FOUNDATION BAY2A- Rebar fixing-Lower | 05/10/2021 | 16/10/2021 | 05/10/2021 | 17/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-19.15 | TT_Task | CONSTRUCTION FOUNDATION BAY2A- Formwork Erection | 13/01/2022 | 15/01/2022 |  |  | 1968 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-19.16 | TT_Task | CONSTRUCTION FOUNDATION BAY2A- Installation of Cathodic protection | 28/10/2021 | 28/10/2021 | 28/10/2021 | 28/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-19.17 | TT_Task | CONSTRUCTION FOUNDATION BAY2A- Concreting | 27/11/2021 | 27/11/2021 | 27/11/2021 | 27/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-19.18 | TT_Task | CONSTRUCTION FOUNDATION BAY2A- Curing of Concrete | 28/11/2021 | 29/11/2021 | 28/11/2021 | 29/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-36.02 | TT_Task | CONSTRUCTION FOUNDATION BAY2B- Grounding installation | 21/10/2021 | 25/10/2021 | 21/10/2021 | 25/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-36.03 | TT_Task | CONSTRUCTION FOUNDATION BAY2B- Rebar fabrication | 11/10/2021 | 23/10/2021 | 11/10/2021 | 23/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-36.05 | TT_Task | CONSTRUCTION FOUNDATION BAY2B- Rebar fixing-Lower | 13/11/2021 | 29/11/2021 | 13/11/2021 | 29/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-36.04 | TT_Task | CONSTRUCTION FOUNDATION BAY2B- Formwork Erection | 30/09/2021 | 12/10/2021 | 30/09/2021 | 12/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-36.06 | TT_Task | CONSTRUCTION FOUNDATION BAY2B- Installation of Cathodic protection | 30/11/2021 | 19/12/2021 | 30/11/2021 | 19/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-36.07 | TT_Task | CONSTRUCTION FOUNDATION BAY2B- Concreting | 31/12/2021 | 31/12/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-36.08 | TT_Task | CONSTRUCTION FOUNDATION BAY2B-Curing of Concrete | 01/01/2022 | 04/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-19.19 | TT_Task | CONSTRUCTION FOUNDATION BAY2A- Formwork desmantling | 30/11/2021 | 01/12/2021 | 30/11/2021 | 01/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-19.01 | TT_Task | CONSTRUCTION FOUNDATION BAY2(BASIN)- Apply damproofing | 15/10/2021 | 22/10/2021 | 15/10/2021 | 22/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-19.02 | TT_Task | CONSTRUCTION FOUNDATION BAY2(BASIN)- Grounding installation | 19/10/2021 | 23/10/2021 | 19/10/2021 | 23/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-19.03 | TT_Task | CONSTRUCTION FOUNDATION BAY2(BASIN)- Rebar fabrication | 19/10/2021 | 26/11/2021 | 19/10/2021 | 26/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-19.05 | TT_Task | CONSTRUCTION FOUNDATION BAY2(BASIN)- Rebar fixing-Lower | 30/11/2021 | 06/12/2021 | 30/11/2021 | 06/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-19.04 | TT_Task | CONSTRUCTION FOUNDATION BAY2(BASIN)- Formwork Erection | 26/10/2021 | 10/12/2021 | 26/10/2021 | 10/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-19.06 | TT_Task | CONSTRUCTION FOUNDATION BAY2(BASIN)- Installation of tower crane support | 09/12/2021 | 10/12/2021 | 09/12/2021 | 10/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-19.07 | TT_Task | CONSTRUCTION FOUNDATION BAY2(BASIN)- Installation of Cathodic protection | 07/12/2021 | 02/01/2022 | 07/12/2021 |  | 11664 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-19.08 | TT_Task | CONSTRUCTION FOUNDATION BAY2(BASIN)- Concreting | 05/01/2022 | 05/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-19.09 | TT_Task | CONSTRUCTION FOUNDATION BAY2(BASIN)- Curing of Concrete | 06/01/2022 | 08/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-19.10 | TT_Task | CONSTRUCTION FOUNDATION BAY2(BASIN)- Formwork desmantling | 09/01/2022 | 10/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B75.01 | TT_Task | WORK PREPARATION FOUNDATION 20UMC- Part4 SW Blinding | 04/01/2022 | 13/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B75.00 | TT_Task | WORK PREPARATION FOUNDATION 20UMC- Part4 SW Excavation | 10/12/2021 | 18/12/2021 | 10/12/2021 | 18/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B75.02 | TT_Task | WORK PREPARATION FOUNDATION 20UMC- Part4 SW Pile trimming/Plate Welding/U-bar installation | 13/12/2021 | 26/12/2021 | 13/12/2021 | 26/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B90.01 | TT_Task | CONCRETE CONSTRUCTION BUILDING FOUNDATION 20UMC- Part4 SW Rebarfixing, gndg install, CJ prep.,Anchor bolt, for pile cap | 21/01/2022 | 01/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B90.00 | TT_Task | CONCRETE CONSTRUCTION BUILDING FOUNDATION 20UMC- Part4 SW Formwork for pile cap | 14/01/2022 | 20/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B90.02 | TT_Task | CONCRETE CONSTRUCTION BUILDING FOUNDATION 20UMC- Part4 SW Concrete pouring for pile cap/tiebeam/baselsab | 16/02/2022 | 16/02/2022 |  |  | 8 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B90.03 | TT_Task | CONCRETE CONSTRUCTION BUILDING FOUNDATION 20UMC- Part4 SW Formwork for tie beam | 20/01/2022 | 26/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B90.04 | TT_Task | CONCRETE CONSTRUCTION BUILDING FOUNDATION 20UMC- Part4 SW Rebarfixing for tie beam | 24/01/2022 | 31/01/2022 |  |  | 40 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B90.06 | TT_Task | CONCRETE CONSTRUCTION BUILDING FOUNDATION 20UMC- Part4 SW Formwork erection baseslab | 27/01/2022 | 05/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B90.07 | TT_Task | CONCRETE CONSTRUCTION BUILDING FOUNDATION 20UMC- Part4 SW Rebarfixing baseslab | 06/02/2022 | 15/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B75.03 | TT_Task | WORK PREPARATION FOUNDATION 20UMC- Part1 NW Excavation | 09/09/2021 | 05/11/2021 | 09/09/2021 | 05/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B75.04 | TT_Task | WORK PREPARATION FOUNDATION 20UMC- Part1 NW Blinding | 05/11/2021 | 26/11/2021 | 05/11/2021 | 26/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B75.05 | TT_Task | WORK PREPARATION FOUNDATION 20UMC- Part1 NW Pile trimming/Plate Welding/U-bar installation | 28/09/2021 | 20/10/2021 | 28/09/2021 | 20/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B90.09 | TT_Task | CONCRETE CONSTRUCTION BUILDING FOUNDATION 20UMC- Part1 NW Formwork pile cap | 18/11/2021 | 26/11/2021 | 18/11/2021 | 26/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B90.11 | TT_Task | CONCRETE CONSTRUCTION BUILDING FOUNDATION 20UMC- Part1 NW Concrete pouring for pile cap/Tie Bea/Baseslab | 21/01/2022 | 21/01/2022 |  |  | 216 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B90.10 | TT_Task | CONCRETE CONSTRUCTION BUILDING FOUNDATION 20UMC- Part1 NW Rebarfixing, gndg install, CJ prep. for pile cap | 18/12/2021 | 01/01/2022 | 18/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B90.12 | TT_Task | CONCRETE CONSTRUCTION BUILDING FOUNDATION 20UMC- Part1 NW Formwork for tie beam | 27/11/2021 | 06/12/2021 | 27/11/2021 | 06/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B90.13 | TT_Task | CONCRETE CONSTRUCTION BUILDING FOUNDATION 20UMC- Part1 NW Rebarfixing for tie beam | 22/12/2021 | 02/01/2022 | 22/12/2021 |  | 144 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B90.15 | TT_Task | CONCRETE CONSTRUCTION BUILDING FOUNDATION 20UMC- Part1 NW Formwork for baseslab | 22/12/2021 | 29/12/2021 | 22/12/2021 | 29/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B90.16 | TT_Task | CONCRETE CONSTRUCTION BUILDING FOUNDATION 20UMC- Part1 NW Rebarfixing for baseslab | 02/01/2022 | 13/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B75.06 | TT_Task | WORK PREPARATION FOUNDATION 20UMC- Part2 NE Excavation | 25/10/2021 | 28/10/2021 | 25/10/2021 | 29/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B75.07 | TT_Task | WORK PREPARATION FOUNDATION 20UMC- Part2 NE Blinding | 05/11/2021 | 26/11/2021 | 05/11/2021 | 26/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B75.08 | TT_Task | WORK PREPARATION FOUNDATION 20UMC- Part2 NE Pile trimming/Plate Welding/U-bar installation | 21/10/2021 | 04/11/2021 | 21/10/2021 | 04/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B90.18 | TT_Task | CONCRETE CONSTRUCTION BUILDING FOUNDATION 20UMC- Part2 NE Formwork pile cap | 28/11/2021 | 06/12/2021 | 28/11/2021 | 06/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B90.19 | TT_Task | CONCRETE CONSTRUCTION BUILDING FOUNDATION 20UMC- Part2 NE Rebarfixing, gndg install, CJ prep., for pile cap | 18/12/2021 | 01/01/2022 | 18/12/2021 |  | 128 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B90.20 | TT_Task | CONCRETE CONSTRUCTION BUILDING FOUNDATION 20UMC- Part2 NE Concrete pouring pile cap/Tie Beam / baseslab | 23/01/2022 | 23/01/2022 |  |  | 200 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B90.21 | TT_Task | CONCRETE CONSTRUCTION BUILDING FOUNDATION 20UMC- Part2 NE Formwork for tie beam | 30/11/2021 | 09/12/2021 | 30/11/2021 | 09/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B90.22 | TT_Task | CONCRETE CONSTRUCTION BUILDING FOUNDATION 20UMC- Part2 NE Rebarwork for tie beam | 23/12/2021 | 03/01/2022 | 23/12/2021 |  | 11656 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B90.24 | TT_Task | CONCRETE CONSTRUCTION BUILDING FOUNDATION 20UMC- Part2 NE Formwork for baseslab | 23/12/2021 | 30/12/2021 | 23/12/2021 | 30/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B90.25 | TT_Task | CONCRETE CONSTRUCTION BUILDING FOUNDATION 20UMC- Part2 NE Rebarfixing, grounding install, CJ prep. for baselslab | 30/12/2021 | 10/01/2022 | 30/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B75.09 | TT_Task | WORK PREPARATION FOUNDATION 20UMC- Part3 SE Excavation | 05/11/2021 | 07/12/2021 | 05/11/2021 | 07/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B75.11 | TT_Task | WORK PREPARATION FOUNDATION 20UMC- Part3 SE Pile trimming/Plate Welding/U-bar installation | 11/11/2021 | 24/12/2021 | 11/11/2021 | 24/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B75.10 | TT_Task | WORK PREPARATION FOUNDATION 20UMC- Part3 SE Blinding | 06/01/2022 | 15/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B90.27 | TT_Task | CONCRETE CONSTRUCTION BUILDING FOUNDATION 20UMC- Part3 SE Formwork pile cap | 16/01/2022 | 23/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B90.28 | TT_Task | CONCRETE CONSTRUCTION BUILDING FOUNDATION 20UMC- Part3 SE Rebarfixing, gndg install, CJ prep.,Anchor bolt, for pile cap | 24/01/2022 | 05/02/2022 |  |  | 32 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B90.29 | TT_Task | CONCRETE CONSTRUCTION BUILDING FOUNDATION 20UMC- Part3 SE Concrete pouring pile cap/Tie beam.Baseslab | 17/02/2022 | 17/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B90.30 | TT_Task | CONCRETE CONSTRUCTION BUILDING FOUNDATION 20UMC- Part3 SE Formwork for tie beam | 24/01/2022 | 30/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B90.31 | TT_Task | CONCRETE CONSTRUCTION BUILDING FOUNDATION 20UMC- Part3 SE Rebarwork for tie beam | 31/01/2022 | 09/02/2022 |  |  | 8 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B90.33 | TT_Task | CONCRETE CONSTRUCTION BUILDING FOUNDATION 20UMC- Part3 SE Formwork for baseslab | 31/01/2022 | 06/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B90.34 | TT_Task | CONCRETE CONSTRUCTION BUILDING FOUNDATION 20UMC- Part3 SE Rebarfixing, grounding install, CJ prep. for baselslab | 07/02/2022 | 16/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20ULA5-05.00 | TT_Task | WORK PREPARATION, EXCAVATION 20ULA- Excavation pile cap stage1 | 01/10/2021 | 09/10/2021 | 01/10/2021 | 09/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20ULA5-05.01 | TT_Task | WORK PREPARATION, EXCAVATION 20ULA- Blinding pile cap stage1 | 19/10/2021 | 26/10/2021 | 19/10/2021 | 27/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20ULA5-15.00 | TT_Task | CONSTRUCTION FOUNDATION 20ULA- Formwork for pile cap stage1 | 14/10/2021 | 23/10/2021 | 14/10/2021 | 23/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20ULA5-15.01 | TT_Task | CONSTRUCTION FOUNDATION 20ULA- Rebarfixing for pile cap stage1 | 29/10/2021 | 02/11/2021 | 29/10/2021 | 02/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20ULA5-15.02 | TT_Task | CONSTRUCTION FOUNDATION 20ULA- Concreting for pile cap stage1 | 03/11/2021 | 04/11/2021 | 03/11/2021 | 04/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20ULA5-05.1 | TT_Task | WORK PREPARATION, EXCAVATION 20ULA- Blinding other area | 12/10/2021 | 14/10/2021 | 12/10/2021 | 14/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20ULA5-15.03 | TT_Task | CONSTRUCTION FOUNDATION 20ULA- Rebarfixing slab other area stage2 | 07/12/2021 | 20/12/2021 | 07/12/2021 | 20/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20ULA5-15.04 | TT_Task | CONSTRUCTION FOUNDATION 20ULA- Formwork slab other area stage2 | 07/12/2021 | 21/12/2021 | 07/12/2021 | 21/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20ULA5-15.05 | TT_Task | CONSTRUCTION FOUNDATION 20ULA- Concreting slab other area stage2 | 10/01/2022 | 10/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20ULA5-15.06 | TT_Task | CONSTRUCTION FOUNDATION 20ULA- Curing and Remove Formwork stage2 | 11/01/2022 | 14/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBX2-83 | TT_Task | BASIC DESIGN STEEL STRUCTURE 20UBX | 27/08/2021 | 06/10/2021 | 27/08/2021 | 06/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MA-3-92 | TT_Task | MANUFACTURING ST LP OUTER CASING | 13/08/2021 | 18/02/2022 | 13/08/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SP20MA-3C82 | TT_FinMile | DELIVERY ST LP INNER CASING MA- | 21/04/2022 | 21/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MA-4C41 | TT_Task | TRANSPORT ST LP INNER CASING MA- | 06/05/2022 | 29/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MA-3C83 | TT_FinMile | (RFS) READY FOR SHIPMENT ST LP INNER CASING MA- | 05/05/2022 | 05/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MA-4-14 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION ST LP INNER CASING MA- | 22/04/2022 | 05/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MA-3-94 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) ST LP INNER CASING MA- | 21/04/2022 | 21/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MA-4C42 | TT_FinMile | (OTD-OS) ON SITE ST LP INNER CASING MA- | 29/07/2022 | 29/07/2022 |  |  | 288 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MA-3-93 | TT_Task | MANUFACTURING ST LP INNER CASING | 13/08/2021 | 21/04/2022 | 13/08/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SP20MA-3-95 | TT_Task | MANUFACTURING ST ROTOR | 17/09/2021 | 12/04/2022 | 17/09/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SP20MA-3C84 | TT_FinMile | DELIVERY ST ROTOR | 12/04/2022 | 12/04/2022 |  |  | 112 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MA-4C43 | TT_Task | TRANSPORT ST ROTOR | 30/04/2022 | 23/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MA-3C85 | TT_FinMile | (RFS) READY FOR SHIPMENT ST ROTOR | 26/04/2022 | 26/04/2022 |  |  | 24 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MA-4-15 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION ST ROTOR | 13/04/2022 | 26/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MA-3-96 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) ST ROTOR | 12/04/2022 | 12/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MA-4C44 | TT_FinMile | (OTD-OS) ON SITE ST ROTOR | 23/07/2022 | 23/07/2022 |  |  | 120 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-UZA2-100.00 | TT_Task | SUBBASE RING ROAD INCL.(U/G) SYSTEM - PART 2B-20UZA01-Excavation /Stripping | 13/01/2022 | 11/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-UZA2-100.01 | TT_Task | SUBBASE RING ROAD INCL.(U/G) SYSTEM - PART 2B-20UZA01-Laying base course and compaction | 12/02/2022 | 01/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-UZA2-100.02 | TT_Task | SUBBASE RING ROAD INCL.(U/G) SYSTEM - PART 2B-20UZA01-Laying sub base and compaction | 02/03/2022 | 19/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-UZA2-101.00 | TT_Task | SUBBASE RING ROAD INCL.(U/G) SYSTEM - PART 2C-20UZA01-Excavation /Stripping | 03/05/2022 | 01/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-UZA2-101.01 | TT_Task | SUBBASE RING ROAD INCL.(U/G) SYSTEM - PART 2C-20UZA01-Laying base course and compaction | 02/06/2022 | 21/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-UZA2-101.02 | TT_Task | SUBBASE RING ROAD INCL.(U/G) SYSTEM - PART 2C-20UZA01-Sub Finishing | 22/06/2022 | 11/07/2022 |  |  | 112 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI-UZA2-100.03 | TT_Task | SUBBASE RING ROAD INCL.(U/G) SYSTEM - PART 2B-20UZA01-Sub Finishing | 20/03/2022 | 06/04/2022 |  |  | 880 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UPY5P15.00 | TT_Task | CONSTRUCTION CONCRETE STRUCTURE 20UPY- Formworks | 01/02/2022 | 07/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UPY5P05.00 | TT_Task | WORK PREPARATION / EXCAVATION / PILE TRIMMING / PLATE WELDING 20UPY- Excavation | 16/01/2022 | 19/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UPY5P05.01 | TT_Task | WORK PREPARATION / EXCAVATION / PILE TRIMMING / PLATE WELDING 20UPY- Blinding | 20/01/2022 | 20/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UPY5P05.02 | TT_Task | WORK PREPARATION / EXCAVATION / PILE TRIMMING / PLATE WELDING 20UPY- Pile Trimming | 21/01/2022 | 31/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UPY5P15.01 | TT_Task | CONSTRUCTION CONCRETE STRUCTURE 20UPY- Rebarworks and Grounding Installation | 08/02/2022 | 19/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UPY5P15.02 | TT_Task | CONSTRUCTION CONCRETE STRUCTURE 20UPY- Concrete Pour | 20/02/2022 | 20/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UPY5P15.03 | TT_Task | CONSTRUCTION CONCRETE STRUCTURE 20UPY- Curing and Remove formwork Pour | 21/02/2022 | 26/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-70.01 | TT_Task | WORK PREPARATION, EXCAVATION 20UTG07- Blinding | 01/05/2022 | 01/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-70.00 | TT_Task | WORK PREPARATION, EXCAVATION 20UTG07- Excavation | 26/04/2022 | 30/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-72.00 | TT_Task | CONSTRUCTION FOUNDATION 20UTG07- Formwork for baseslab | 02/05/2022 | 07/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-72.01 | TT_Task | CONSTRUCTION FOUNDATION 20UTG07- Rebarwork and grounding installation for baseslab | 08/05/2022 | 17/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-72.02 | TT_Task | CONSTRUCTION FOUNDATION 20UTG07- Concreting for baseslab | 18/05/2022 | 18/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-72.03 | TT_Task | CONSTRUCTION FOUNDATION 20UTG07- Curing and Remove formwors for baseslab | 19/05/2022 | 20/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-77.00 | TT_Task | CONSTRUCTION FOUNDATION 20UTG07- Formwork for wall stage1 | 21/05/2022 | 26/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-77.01 | TT_Task | CONSTRUCTION FOUNDATION 20UTG07- Rebarwork for wall | 27/05/2022 | 05/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-77.02 | TT_Task | CONSTRUCTION FOUNDATION 20UTG07- Formwork-closed for wall stage2 | 06/06/2022 | 11/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-77.03 | TT_Task | CONSTRUCTION FOUNDATION 20UTG07- Concreting for walls | 12/06/2022 | 12/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-77.04 | TT_Task | CONSTRUCTION FOUNDATION 20UTG07- Curing and remove formwork for walls | 13/06/2022 | 15/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEN5-05.00 | TT_Task | WORK PREPARATION, EXCAVATION 20UEN- Excavation | 03/02/2022 | 09/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEN5-05.01 | TT_Task | WORK PREPARATION, EXCAVATION 20UEN- Blinding | 10/02/2022 | 17/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEN5-15.00 | TT_Task | CONSTRUCTION FOUNDATION 20UEN-Formwork for slab/foundation | 18/02/2022 | 03/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEN5-15.01 | TT_Task | CONSTRUCTION FOUNDATION 20UEN-Rebarwork. grounding installation, anchor bolt, cast-in | 04/03/2022 | 21/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEN5-15.02 | TT_Task | CONSTRUCTION FOUNDATION 20UEN-Concreting slab/foundation | 22/03/2022 | 23/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEN5-15.03 | TT_Task | CONSTRUCTION FOUNDATION 20UEN-Curing and formwork removal | 24/03/2022 | 01/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBN5-5.00 | TT_Task | WORK PREPARATION, EXCAVATION 20UBN- Excavation | 17/06/2022 | 19/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBN5-5.01 | TT_Task | WORK PREPARATION, EXCAVATION 20UBN- Blinding | 20/06/2022 | 22/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBN5-10.00 | TT_Task | CONSTRUCTION FOUNDATION 20UBN- Formwork for baseslab/foundation | 23/06/2022 | 30/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBN5-10.01 | TT_Task | CONSTRUCTION FOUNDATION 20UBN- Rebarworks,grounding installation baseslab/foundation | 01/07/2022 | 21/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBN5-10.02 | TT_Task | CONSTRUCTION FOUNDATION 20UBN- Concreting baseslab/foundation | 22/07/2022 | 23/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBN5-10.03 | TT_Task | CONSTRUCTION FOUNDATION 20UBN- Curing,remove formwork,and backfill baseslab/foundation | 24/07/2022 | 28/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEN5-19.00 | TT_Task | WORK PREPARATION, EXCAVATION 01UEN- Excavation | 20/01/2022 | 31/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEN5-19.01 | TT_Task | WORK PREPARATION, EXCAVATION 01UEN- Blinding | 01/02/2022 | 02/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEN5-17.00 | TT_Task | CONSTRUCTION FOUNDATION 01UEN- Formwork installation for baseslab/foundation | 03/02/2022 | 22/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEN5-17.01 | TT_Task | CONSTRUCTION FOUNDATION 01UEN- Rebarwork,grounding install for baseslab/foundation | 23/02/2022 | 15/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEN5-17.02 | TT_Task | CONSTRUCTION FOUNDATION 01UEN- Concreting baseslab/foundation | 16/04/2022 | 19/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEN5-17.03 | TT_Task | CONSTRUCTION FOUNDATION 01UEN- Curing,removal formwork,backfill baseslab/foundation | 20/04/2022 | 29/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20USX5-15.01 | TT_Task | CONSTRUCTION FOUNDATION 20USX- Rebarworks for baseslab/foundation | 07/06/2022 | 15/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20USX5-15.00 | TT_Task | CONSTRUCTION FOUNDATION 20USX- Formwork installation for baseslab/foundation | 01/06/2022 | 06/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20USX5-15.02 | TT_Task | CONSTRUCTION FOUNDATION 20USX- Concreting for baseslab/foundation | 16/06/2022 | 16/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20USX5-15.03 | TT_Task | CONSTRUCTION FOUNDATION 20USX- Curing, removal formwork, backfill baseslab/foundation | 17/06/2022 | 22/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5-55.01 | TT_Task | CONSTRUCTION FOUNDATION 20UBA1110/20-Rebarwork | 15/04/2022 | 22/04/2022 |  |  | 104 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5-55.00 | TT_Task | CONSTRUCTION FOUNDATION 20UBA1110/20-Formwork | 08/04/2022 | 14/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5-55.02 | TT_Task | CONSTRUCTION FOUNDATION 20UBA1110/20-Concreting | 06/05/2022 | 06/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5-55.03 | TT_Task | CONSTRUCTION FOUNDATION 20UBA1110/20-Curing and desmantling | 07/05/2022 | 11/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-44.01 | TT_Task | CONSTRUCTION FOUNDATION 20UTG04-Rebarwork for baseslab/foundation | 14/04/2022 | 23/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-44.00 | TT_Task | CONSTRUCTION FOUNDATION 20UTG04-Formwork instalation for baseslab/foundation | 08/04/2022 | 13/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-44.02 | TT_Task | CONSTRUCTION FOUNDATION 20UTG04-Concreting for baseslab/foundation | 24/04/2022 | 24/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-44.03 | TT_Task | CONSTRUCTION FOUNDATION 20UTG04-Curing,removal formwork,backfill for baseslab/foundation | 25/04/2022 | 28/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBH5-22.00 | TT_Task | CONSTRUCTION OIL COLLECTION PIT / OIL SEPARATOR 20UBH01-Rebarwork and grounding install baseslab(1st pour) | 05/03/2022 | 16/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBH5-22.01 | TT_Task | CONSTRUCTION OIL COLLECTION PIT / OIL SEPARATOR 20UBH01-Concreting of baseslab | 17/03/2022 | 17/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBH5-22.02 | TT_Task | CONSTRUCTION OIL COLLECTION PIT / OIL SEPARATOR 20UBH01-Inner formwork erection for walls Top slab(2nd pour) | 18/03/2022 | 26/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBH5-22.03 | TT_Task | CONSTRUCTION OIL COLLECTION PIT / OIL SEPARATOR 20UBH01-Rebarwork for walls Top slab(2nd pour) | 27/03/2022 | 04/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBH5-22.04 | TT_Task | CONSTRUCTION OIL COLLECTION PIT / OIL SEPARATOR 20UBH01-Close formwork for walls (2nd pour) | 05/04/2022 | 12/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBH5-22.05 | TT_Task | CONSTRUCTION OIL COLLECTION PIT / OIL SEPARATOR 20UBH01-Concreting for walls top slab (2nd pour) | 13/04/2022 | 14/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBH5-22.06 | TT_Task | CONSTRUCTION OIL COLLECTION PIT / OIL SEPARATOR 20UBH01-Curing and desmantle formwork | 15/04/2022 | 20/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBH5-22.07 | TT_Task | CONSTRUCTION OIL COLLECTION PIT / OIL SEPARATOR 20UBH01-Backfill around structure | 21/04/2022 | 24/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UHX5-15.00 | TT_Task | CONSTRUCTION FOUNDATION 20UHX-Formwork installation for baseslab/foundation | 13/04/2022 | 18/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UHX5-15.01 | TT_Task | CONSTRUCTION FOUNDATION 20UHX-Rebarwork for baseslab/foundation | 19/04/2022 | 28/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UHX5-15.02 | TT_Task | CONSTRUCTION FOUNDATION 20UHX-Concreting for baseslab/foundation | 29/04/2022 | 29/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UHX5-15.03 | TT_Task | CONSTRUCTION FOUNDATION 20UHX-Curing, removal formwork,Backfill | 30/04/2022 | 02/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UVM5-16.00 | TT_Task | CONSTRUCTION FOUNDATION 20UVM01-Rebarwork for baseslab(1st pour) | 25/05/2022 | 30/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UVM5-16.01 | TT_Task | CONSTRUCTION FOUNDATION 20UVM01-Concreting for baseslab(1st pour) | 31/05/2022 | 31/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UVM5-16.02 | TT_Task | CONSTRUCTION FOUNDATION 20UVM01-Inner formwork for baseslab(2nd pour) | 01/06/2022 | 03/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UVM5-16.03 | TT_Task | CONSTRUCTION FOUNDATION 20UVM01-Rebarwork for wall top slab(2nd pour) | 05/06/2022 | 10/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UVM5-16.04 | TT_Task | CONSTRUCTION FOUNDATION 20UVM01-Close formwork for wall(2nd pour) | 11/06/2022 | 12/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UVM5-16.05 | TT_Task | CONSTRUCTION FOUNDATION 20UVM01-Concreting for wall top slab(2nd pour) | 13/06/2022 | 13/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UVM5-16.06 | TT_Task | CONSTRUCTION FOUNDATION 20UVM01-Curing,desmantling formwork | 14/06/2022 | 15/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UVM5-16.07 | TT_Task | CONSTRUCTION FOUNDATION 20UVM01-Backfilling around structure | 16/06/2022 | 16/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5-17.01 | TT_Task | CONSTRUCTION FOUNDATION 20UBA7xxx-Formworks | 08/02/2022 | 19/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5-17.02 | TT_Task | CONSTRUCTION FOUNDATION 20UBA7xxx-Rebarfixing | 20/02/2022 | 05/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5-17.03 | TT_Task | CONSTRUCTION FOUNDATION 20UBA7xxx-Concreting | 06/03/2022 | 06/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5-17.04 | TT_Task | CONSTRUCTION FOUNDATION 20UBA7xxx-Pedestal rebars | 07/03/2022 | 16/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5-17.05 | TT_Task | CONSTRUCTION FOUNDATION 20UBA7xxx-Pedestal formworks | 17/03/2022 | 26/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5-17.06 | TT_Task | CONSTRUCTION FOUNDATION 20UBA7xxx-Pedestal concreting | 27/03/2022 | 27/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5-17.07 | TT_Task | CONSTRUCTION FOUNDATION 20UBA7xxx-Curing desmantling | 28/03/2022 | 03/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5-15.03 | TT_Task | CONSTRUCTION FOUNDATION 20UBA7910/20- Formwork | 17/05/2022 | 23/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5-15.04 | TT_Task | CONSTRUCTION FOUNDATION 20UBA7910/20- Rebar | 24/05/2022 | 02/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5-15.05 | TT_Task | CONSTRUCTION FOUNDATION 20UBA7910/20- Concreting | 03/06/2022 | 03/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5-15.06 | TT_Task | CONSTRUCTION FOUNDATION 20UBA7910/20- Pedestal rebar | 04/06/2022 | 06/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5-15.07 | TT_Task | CONSTRUCTION FOUNDATION 20UBA7910/20- Pedestal formwork | 07/06/2022 | 09/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5-15.08 | TT_Task | CONSTRUCTION FOUNDATION 20UBA7910/20- Pedestal conreting | 10/06/2022 | 10/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5-15.09 | TT_Task | CONSTRUCTION FOUNDATION 20UBA7910/20- Curing and desmantling | 11/06/2022 | 12/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBD5-61.00 | TT_Task | CONSTRUCTION FOUNDATION 20UBG01/02- Formwork installation for baseslab/foundation | 12/05/2022 | 19/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBD5-61.01 | TT_Task | CONSTRUCTION FOUNDATION 20UBG01/02- Concreting baseslab/foundation | 27/05/2022 | 28/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBD5-61.02 | TT_Task | CONSTRUCTION FOUNDATION 20UBG01/02- Curing,removal formworks, backfill baseslab/foundation | 29/05/2022 | 01/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ5-74.00 | TT_Task | CONSTRUCTION FOUNDATION 20UBZ05- Rebarwork for baseslab | 19/05/2022 | 23/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ5-74.01 | TT_Task | CONSTRUCTION FOUNDATION 20UBZ05- Formwork install for baseslab | 21/05/2022 | 24/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ5-74.02 | TT_Task | CONSTRUCTION FOUNDATION 20UBZ05- Concreting for baseslab | 25/05/2022 | 25/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ5-74.03 | TT_Task | CONSTRUCTION FOUNDATION 20UBZ05- Formwork install for walls | 26/05/2022 | 30/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ5-74.04 | TT_Task | CONSTRUCTION FOUNDATION 20UBZ05- Rebarwork for walls | 31/05/2022 | 07/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ5-74.05 | TT_Task | CONSTRUCTION FOUNDATION 20UBZ05- Formwork for walls(Closing) | 08/06/2022 | 12/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ5-74.06 | TT_Task | CONSTRUCTION FOUNDATION 20UBZ05- Concreting for walls | 13/06/2022 | 14/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ5-74.07 | TT_Task | CONSTRUCTION FOUNDATION 20UBZ05- Curing,desmantling,backfill for walls | 15/06/2022 | 19/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBD5-15.00 | TT_Task | CONSTRUCTION FOUNDATION 20UBD01/02- Formwork Install for baseslab/foundation | 21/04/2022 | 26/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBD5-15.01 | TT_Task | CONSTRUCTION FOUNDATION 20UBD01/02- Rebarwork Install for baseslab/foundation | 27/04/2022 | 09/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBD5-15.02 | TT_Task | CONSTRUCTION FOUNDATION 20UBD01/02- Concreting baseslab/foundation | 10/05/2022 | 10/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBD5-15.03 | TT_Task | CONSTRUCTION FOUNDATION 20UBD01/02- Curing,desmantling formwork,backfill baseslab/foundation | 11/05/2022 | 13/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBX5-15.00 | TT_Task | CONSTRUCTION FOUNDATION 20UBX/20UBG03- Formwork installation for baseslab/foundation | 12/05/2022 | 17/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBX5-15.01 | TT_Task | CONSTRUCTION FOUNDATION 20UBX/20UBG03- Rebarwork,grounding install for baseslab/foundation | 15/05/2022 | 25/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBX5-15.02 | TT_Task | CONSTRUCTION FOUNDATION 20UBX/20UBG03- Concreting baseslab/foundation | 26/05/2022 | 26/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBX5-15.03 | TT_Task | CONSTRUCTION FOUNDATION 20UBX/20UBG03- Curing,removal formwork,backfill baseslab/foundation | 27/05/2022 | 30/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ5-66.00 | TT_Task | CONSTRUCTION FOUNDATION 20UBZ04- Formwork installation for baseslab/foundation | 29/04/2022 | 02/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ5-66.01 | TT_Task | CONSTRUCTION FOUNDATION 20UBZ04- Rebarwork,grounding install for baseslab/foundation | 03/05/2022 | 07/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ5-66.02 | TT_Task | CONSTRUCTION FOUNDATION 20UBZ04- Concreting baseslab/foundation | 08/05/2022 | 08/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ5-66.03 | TT_Task | CONSTRUCTION FOUNDATION 20UBZ04- Formwork for walls(One side) | 09/05/2022 | 13/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ5-66.04 | TT_Task | CONSTRUCTION FOUNDATION 20UBZ04- Rebarworks for walls | 14/05/2022 | 21/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ5-66.05 | TT_Task | CONSTRUCTION FOUNDATION 20UBZ04- Formwork for walls(Closed) | 22/05/2022 | 27/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ5-66.06 | TT_Task | CONSTRUCTION FOUNDATION 20UBZ04- Concreting for walls | 28/05/2022 | 28/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ5-66.07 | TT_Task | CONSTRUCTION FOUNDATION 20UBZ04- Curing,removal formwork,backfill baseslab/foundation | 29/05/2022 | 02/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAV6-71 | TT_Task | ERECTION OF TEMPORARIES FOR LUBE OIL FLUSHING | 12/02/2023 | 25/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAV6-72 | TT_Task | FILLING LUBE OIL TANK MAV | 26/02/2023 | 04/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAV6-73 | TT_Task | TEST RUN OF LUBE OIL PUMPS | 05/03/2023 | 11/03/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20PAB5-85.37 | TT_Task | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20- SPOOL 2/3/4 CONNECTION + ALIGN | 28/09/2021 | 05/10/2021 | 28/09/2021 | 05/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--HB-2-16.01 | TT_Task | BD - HRSG PACKAGES SUBMISSION APPROVAL -RESUBMISSION/WITHDRAWN STACK | 03/11/2021 | 03/11/2021 | 03/11/2021 | 04/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20HA-4B47 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION HEATING SURFACES HRSG20 MODULE 1 | 11/03/2022 | 02/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-3B85 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) HEATING SURFACES HRSG20 MODULE1 | 10/03/2022 | 10/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-3G81 | TT_FinMile | (RFS) READY FOR SHIPMENT HEATING SURFACES HRSG20 MOD 2-6 (Incl. Hangers/Baffles/ Installation Material) | 12/03/2022 | 12/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY2-95 | TT_FinMile | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE - WITDRAWN 20UEY01 (1STPACKAGE) | 13/05/2021 | 13/05/2021 | 13/05/2021 | 13/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20EGD8-26 | TT_FinMile | (TOP-20EGD) SUPPLY OF LIQUID FUEL FOR DIESEL GENERATOR | 26/05/2023 | 26/05/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGM8-43 | TT_FinMile | (TOP-20SGM-07)FF INERTGAS SYSTEM IN 20UBA7710/7720 SGM INSIDE CONTAINERS | 29/09/2022 | 29/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGM8-44 | TT_FinMile | (TOP-20SGM-08)FF INERTGAS SYSTEM IN 20UBA7610/7620 SGM INSIDE CONTAINERS | 27/10/2022 | 27/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGM8-45 | TT_FinMile | (TOP-20SGM-09)FF INERTGAS SYSTEM IN 20UBA7310/7320/7330 SGM INSIDE CONTAINERS | 13/10/2022 | 13/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGM6-22 | TT_Task | ERECTION FF INERTGAS SYSTEM IN 20UBA7710/7720 SGM | 16/09/2022 | 29/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGM6-23 | TT_Task | ERECTION FF INERTGAS SYSTEM IN 20UBA7610/7620 SGM | 14/10/2022 | 27/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGM6-24 | TT_Task | ERECTION FF INERTGAS SYSTEM IN 20UBA7310/7320/7330 SGM | 30/09/2022 | 13/10/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGM8-46 | TT_Task | COLD COMMISSIONING FF INERTGAS SYSTEM IN 20UBA7710/7720 SGM INSIDE CONTAINERS | 30/09/2022 | 06/10/2022 |  |  | 1488 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGM8-47 | TT_Task | COLD COMMISSIONING FF INERTGAS SYSTEM IN 20UBA7610/7620 SGM INSIDE CONTAINERS | 28/10/2022 | 03/11/2022 |  |  | 1264 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SGM8-48 | TT_Task | COLD COMMISSIONING FF INERTGAS SYSTEM IN 20UBA7310/7320/7330 SGM INSIDE CONTAINERS | 14/10/2022 | 20/10/2022 |  |  | 1376 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5A15.16 | TT_Task | TURBOSET FOUNDATION (SLAB +/-0.00m) 20UMC -Damp Proofing | 25/10/2021 | 01/11/2021 | 25/10/2021 | 01/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SP20MAV3-82 | TT_FinMile | (RFS) READY FOR SHIPMENT (NORTH SEA PORT) LUBE OIL 20MAV90 TANK | 07/07/2022 | 07/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAV4-26 | TT_Task | TRANSPORT LUBE OIL 20MAV90 TANK | 16/07/2022 | 09/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MAV4-41 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION LUBE OIL 20MAV90 TANK | 10/06/2022 | 07/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MAV3-81 | TT_Mile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) LUBE OIL 20MAV90 TANK | 10/06/2022 | 10/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MAV4-42 | TT_FinMile | (OTD-OS) ON SITE LUBE OIL MODULE 20MAV90 TANK | 09/09/2022 | 09/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MAV6-74 | TT_Task | ERECTION LUBE OIL MODULE UMC 20MAV90 TANK | 10/09/2022 | 12/09/2022 |  |  | 2040 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20ULY2-83 | TT_Task | DETAIL DESIGN / DELTA ENGINEERING STEEL STRUCTURE 20ULY01 | 19/07/2021 | 21/02/2022 | 19/07/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20B--8-20 | TT_Mile | 1ST. PCC ON SITE | 23/06/2022 | 23/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BAW2-89 | TT_Task | DETAIL DESIGN INDOOR GROUNDING-SE | 27/11/2021 | 07/01/2022 | 27/11/2021 |  | 11624 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--BZL4-43 | TT_Mile | (OTD-OS) ON SITE LIGHTING SMALL POWER BZL COMPLETE PLANT | 05/08/2022 | 05/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BZL3-84 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) LIGHTING SMALL POWER BZL 20UMC, COMPLETE PLANT | 23/06/2022 | 23/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BZP4-27 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION LIGHTING SMALL POWER BZL COMPLETE PLANT | 24/06/2022 | 21/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BZL3-85 | TT_FinMile | (RFS) READY FOR SHIPMENT LIGHTING SMALL POWER BZL COMPLETE PLANT | 21/07/2022 | 21/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BZL4-44 | TT_Task | TRANSPORT LIGHTING SMALL POWER BZL COMPLETE PLANT | 22/07/2022 | 04/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MB-6-59 | TT_Task | RESTORATION PRESSURE TESTS AFTER OIL FLUSHING | 02/04/2023 | 22/04/2023 |  |  | 432 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKA8-75 | TT_Task | AIR LEAKAGE TEST GENERATOR 20MKA | 16/06/2023 | 22/06/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA3H57 | TT_Task | INSTALL. COMP., INT. CABLING, FIRE PROT., SHOP TEST ELECTRICAL MODULES 20UBA7320 | 17/12/2021 | 24/02/2022 | 17/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SP20UBA3H81 | TT_FinMile | (RFS) READY FOR SHIPMENT ELECTRICAL MODULES 20UBA7320 | 30/04/2022 | 30/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA4H26 | TT_Task | TRANSPORT ELECTRICAL MODULES 20UBA7320 | 01/05/2022 | 25/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC2B74 | TT_FinMile | BD - SUBMISSION APPROVAL - AMENDMENT BUILDING 20UMC (incl. CEP MS3 Input) WITDRAWN (1STPACKAGE) | 12/08/2021 | 12/08/2021 | 12/08/2021 | 12/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC2B75 | TT_Task | BD - SUBMISSION APPROVAL - AMENDMENT BUILDING 20UMC (incl. CEP MS3 Input) RESUBMISSION(1STPACKAGE) | 09/09/2021 | 20/10/2021 | 09/09/2021 | 20/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20ULY4-112 | TT_Mile | (HS) START ERECTION STEEL STRUCTURE 20ULY01 | 07/07/2022 | 07/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20ULY4-113 | TT_Mile | (RFE) ERECTION STEEL STRUCTURE 20ULY01 | 04/08/2022 | 04/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-168 | TT_Mile | (HS) START ERECTION STEEL STRUCTURE 2UQY01 | 20/06/2022 | 20/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-170 | TT_FinMile | (RFE) STEEL STRUCTURE 2UQY01 | 03/07/2022 | 03/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-169 | TT_Task | ERECTION STEELWORKS(For CROSSOVER PIPE) 2UQY01 | 20/06/2022 | 03/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5148 | TT_Mile | (F) DETAIL DESIGN STEEL STRUCTURE WITH CONTRACTOR 2UQY01 | 14/03/2022 | 14/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-143 | TT_Task | DETAIL DESIGN STEEL STRUCTURE 2UQY01 | 07/10/2021 | 15/12/2021 | 07/10/2021 | 15/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-142 | TT_FinMile | (MS3) STEEL STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 2UQY01 | 07/10/2021 | 07/10/2021 | 07/10/2021 | 07/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-167 | TT_Task | FABRICATION DESIGN/FABRICATION/TRANSPORT STEEL STRUC. 2UQY01 | 14/03/2022 | 19/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-144 | TT_Task | BD - SUBMISSION APPROVAL - STEEL STRUCTURE 2UQY01 | 16/12/2021 | 13/02/2022 | 16/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-145 | TT_Task | BD - CONSENT LETTER - STEEL STRUCTURE 2UQY01 | 14/02/2022 | 13/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-188 | TT_Mile | (HS) START ERECTION STEEL STRUCTURE 2UQY02 | 19/06/2022 | 19/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-190 | TT_FinMile | (RFE) STEEL STRUCTURE 2UQY02 | 02/07/2022 | 02/07/2022 |  |  | 8 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-189 | TT_Task | ERECTION STEELWORKS(For CROSSOVER PIPE) 2UQY02 | 19/06/2022 | 02/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-186 | TT_Mile | (F) DETAIL DESIGN STEEL STRUCTURE WITH CONTRACTOR 2UQY02 | 13/03/2022 | 13/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-158 | TT_Task | DETAIL DESIGN STEEL STRUCTURE 2UQY02 | 07/10/2021 | 14/12/2021 | 07/10/2021 | 14/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-159 | TT_FinMile | (MS3) STEEL STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 2UQY02 | 07/10/2021 | 07/10/2021 | 07/10/2021 | 07/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-187 | TT_Task | FABRICATION DESIGN/FABRICATION/TRANSPORT STEEL STRUC. 2UQY02 | 13/03/2022 | 18/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-160 | TT_Task | BD - SUBMISSION APPROVAL - STEEL STRUCTURE 2UQY01 | 15/12/2021 | 12/02/2022 | 15/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-161 | TT_Task | BD - CONSENT LETTER - STEEL STRUCTURE 2UQY02 | 13/02/2022 | 12/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-178 | TT_Mile | (HS) START ERECTION STEEL STRUCTURE 2UQY03 | 19/06/2022 | 19/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-180 | TT_FinMile | (RFE) STEEL STRUCTURE 2UQY03 | 02/07/2022 | 02/07/2022 |  |  | 8 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-179 | TT_Task | ERECTION STEELWORKS(For CROSSOVER PIPE) 2UQY03 | 19/06/2022 | 02/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-176 | TT_Mile | (F) DETAIL DESIGN STEEL STRUCTURE WITH CONTRACTOR 2UQY03 | 13/03/2022 | 13/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-162 | TT_Task | DETAIL DESIGN STEEL STRUCTURE 2UQY03 | 07/10/2021 | 14/12/2021 | 07/10/2021 | 14/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-163 | TT_FinMile | (MS3) STEEL STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 2UQY03 | 07/10/2021 | 07/10/2021 | 07/10/2021 | 07/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-177 | TT_Task | FABRICATION DESIGN/FABRICATION/TRANSPORT STEEL STRUC. 2UQY03 | 13/03/2022 | 18/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-164 | TT_Task | BD - CONSENT LETTER - STEEL STRUCTURE 2UQY03 | 13/02/2022 | 12/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-165 | TT_Task | BD - SUBMISSION APPROVAL - STEEL STRUCTURE 2UQY03 | 15/12/2021 | 12/02/2022 | 15/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UHX5168 | TT_Mile | (HS) START ERECTION STEEL STRUCTURE 20UHX | 27/05/2022 | 27/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UHX5-170 | TT_FinMile | (RFE) STEEL STRUCTURE 20UHX | 09/06/2022 | 09/06/2022 |  |  | 1288 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UHX5169 | TT_Task | ERECTION STEELWORKS(FOR ENCLOSURE) 20UHX | 27/05/2022 | 09/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UHX5164 | TT_Mile | (F) DETAIL DESIGN STEEL STRUCTURE WITH CONTRACTOR 20UHX | 21/01/2022 | 21/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UHX5-166 | TT_Task | DETAIL DESIGN STEEL STRUCTURE 20UHX | 12/10/2021 | 21/02/2022 | 12/10/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UHX5-167 | TT_FinMile | (MS3) STEEL STRUCTURE FINAL DIMENSIONS, LOADS AVAILABLE 20UHX | 11/10/2021 | 11/10/2021 | 11/10/2021 | 11/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHX5-165 | TT_Task | FABRICATION DESIGN/FABRICATION/TRANSPORT STEEL STRUC. 20UHX | 21/01/2022 | 28/04/2022 |  |  | 224 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UHX-168 | TT_Task | BD - SUBMISSION APPROVAL - STEEL STRUCTURE 20UHX | 28/02/2022 | 28/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UHX5-169 | TT_Task | BD - CONSENT LETTER - STEEL STRUCTURE SI20UHX5 | 29/04/2022 | 26/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZL8B28 | TT_Task | ENERGIZATION FOR LIGHTING AND SMALL POWER 20UMC HIGH BAY (FROM TEMP POWER SUPPLY) | 10/06/2022 | 16/06/2022 |  |  | 512 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZL8B29 | TT_Task | SYSTEM COMMISSIONING AND ENERGIZATION FOR LIGHTING AND SMALL POWER 20UMC (FR.TEMP POWER SUPPLY) | 04/04/2023 | 10/04/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BZL3-86 | TT_Task | DETAIL DESIGN LIGHTING SMALL POWER BZL COMPLETE PLANT | 16/12/2021 | 27/05/2022 | 16/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--BZL3-83 | TT_Task | MANUFACTURING /SHOP TEST LIGHTING SMALL POWER BZL COMPLETE PLANT | 28/05/2022 | 23/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-19.20 | TT_Task | CONSTRUCTION FOUNDATION BAY2A- Rebar fixing-Upper | 11/10/2021 | 03/11/2021 | 11/10/2021 | 03/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-36.10 | TT_Task | CONSTRUCTION FOUNDATION BAY2B- Rebar fixing-Upper | 30/11/2021 | 06/12/2021 | 30/11/2021 | 06/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-19.21 | TT_Task | CONSTRUCTION FOUNDATION BAY2(BASIN)- Rebar fixing-Upper | 14/12/2021 | 31/12/2021 | 14/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-17.11 | TT_Task | CONSTRUCTION FOUNDATION BAY1(BASIN)- Rebar fixing-Upper | 18/10/2021 | 02/12/2021 | 18/10/2021 | 02/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-48.00 | TT_Task | fwk erection for wall top slab of horizontal basin +8.75mpd part-1 20ura | 04/01/2022 | 08/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-48.01 | TT_Task | erection of column pedestal with corbel up to at +7.15mpd part-1 20ura | 27/12/2021 | 15/01/2022 | 27/12/2021 |  | 11560 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-48.02 | TT_Task | rebar fixing for wall top slab of horizontal basin +8.75mpd part-1 20ura | 04/01/2022 | 08/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-48.03 | TT_Task | cathodic protection + test for wall top slab of horizontal basin +8.75mpd part-1 20ura | 07/01/2022 | 08/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-48.04 | TT_Task | close fwk for wall top slab of horizontal basin +8.75mpd part-1 20ura | 09/01/2022 | 12/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-48.05 | TT_Task | erection of column at gridline p l from +7.15 - +13.xxmpd (1st-pour) part-1 20ura | 09/01/2022 | 16/01/2022 |  |  | 24 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-48.06 | TT_Task | concreting of wall top slab of horizontal basin +8.75mpd part-1 20ura-xx | 13/01/2022 | 13/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-52.08 | TT_Task | fwk for vertical shaft from +8.75 - +13.xxmpd (1st-pour) part-1 20ura | 14/01/2022 | 18/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-52.09 | TT_Task | erection of column at gridline m n from +7.15 - +13.xxmpd (1st-pour) part-1 20ura | 17/01/2022 | 23/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-52.10 | TT_Task | erection of wall along gridline p from +7.15 - +13.xxmpd (1st-pour) part-1 20ura | 17/01/2022 | 23/01/2022 |  |  | 8 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-52.11 | TT_Task | rebar fixing for vertical shaft from +8.75 - +13.xxmpd (1st-pour) part-1 20ura | 19/01/2022 | 24/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-52.12 | TT_Task | cathodic protection + test for vertical shaft from +8.75 - +13.xxmpd (1st-pour) part-1 20ura | 21/01/2022 | 23/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-52.13 | TT_Task | erection of column at gridline h k from +7.15 - +13.xxmpd (1st-pour) part-1 20ura | 24/01/2022 | 31/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-52.14 | TT_Task | close fwk for vertical shaft from +8.75 - +13.xxmpd (1st-pour) part-1 20ura | 25/01/2022 | 28/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-52.15 | TT_Task | erection of partition wall along gridline l from +7.15 - +13.xxmpd (1st-pour) part-1 20ura | 25/01/2022 | 01/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-52.16 | TT_Task | concreting for vertical shaft from +8.75 - +13.xxmpd (1st-pour) part-1 20ura | 29/01/2022 | 29/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-52.17 | TT_Task | rebar fixing for vertical shaft from 13.xx - +16.xxmpd (2nd-pour) part-1 20ura | 30/01/2022 | 12/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-52.18 | TT_Task | erection of column at gridline j from +7.15 - +13.xxmpd (1st-pour) part-1 20ura | 01/02/2022 | 07/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-52.19 | TT_Task | erection of partition wall along gridline h from +7.15 - +13.xxmpd (1st-pour) part-1 20ura | 02/02/2022 | 09/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-52.20 | TT_Task | formworks for vertical shaft from 13.xx - +16.xxmpd (2nd-pour) part-1 20ura | 05/02/2022 | 22/02/2022 |  |  | 8 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-52.21 | TT_Task | rebar fixing for columns from +13.xx - +16.xxmpd (2nd-pour) part-1 20ura | 06/02/2022 | 25/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-52.22 | TT_Task | cathodic protection + test for vertical shaft from 13.xx - +16.xxmpd (2nd-pour) part-1 20ura | 08/02/2022 | 13/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-52.23 | TT_Task | erection of partition wall along gridline 14 from +7.15 - +13.xxm (1st-pour) part-1 20ura | 10/02/2022 | 17/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-52.24 | TT_Task | formworks for columns from +13.xx - +16.xxmpd (2nd-pour) part-1 20ura | 10/02/2022 | 03/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-52.25 | TT_Task | rebar fixing for walls from +13.xx - +16.xxmpd (2nd-pour) part-1 20ura | 18/02/2022 | 11/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-52.26 | TT_Task | formworks for walls from +13.xx - +16.xxmpd (2nd-pour) part-1 20ura | 20/02/2022 | 13/03/2022 |  |  | 24 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-52.27 | TT_Task | cathodic protection + test for columns from +13.xx - +16.xxmpd (2nd-pour) part-1 20ura | 23/02/2022 | 01/03/2022 |  |  | 24 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-52.28 | TT_Task | falseworks soffit fwk erection for beams at +16.xxmpd part-1 20ura | 26/02/2022 | 19/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-52.29 | TT_Task | rebar fixing for beams at +16.xxmpd part-1 20ura | 28/02/2022 | 24/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-52.30 | TT_Task | cathodic protection + test for columns from +13.xx - +16.xxmpd (2nd-pour) part-1 20ura | 02/03/2022 | 08/03/2022 |  |  | 16 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-52.31 | TT_Task | side formworks for beams at +16.xxmpd part-1 20ura | 04/03/2022 | 28/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-52.32 | TT_Task | cathodic protection + test for beams at +16.xxmpd part-1 20ura | 19/03/2022 | 26/03/2022 |  |  | 16 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-52.33 | TT_Task | concreting works for wall/column (2nd-pour) and beams at +16.xxmpd part-1 20ura | 29/03/2022 | 30/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-52.34 | TT_Task | rebar fixing for vertical shaft from +16.xx - +18.90mpd part-1 20ura | 31/03/2022 | 15/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-52.35 | TT_Task | rebar fixing for columns from +16.xx - +19.xxmpd part-1 20ura | 31/03/2022 | 19/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-52.36 | TT_Task | formworks for columns from +16.xx - +19.xxmpd part-1 20ura | 04/04/2022 | 27/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-52.37 | TT_Task | formworks for vertical shaft from +16.xx - +19.xxmpd part-1 20ura | 06/04/2022 | 23/04/2022 |  |  | 16 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-52.38 | TT_Task | rebar fixing for walls from +16.xx - +19.xxmpd part-1 20ura | 08/04/2022 | 29/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-52.39 | TT_Task | cathodic protection + test for vertical shaft from +16.xx - +18.90mpd part-1 20ura | 11/04/2022 | 16/04/2022 |  |  | 8 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-52.40 | TT_Task | formworks for walls from +16.xx - +19.xxmpd part-1 20ura | 12/04/2022 | 05/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-52.41 | TT_Task | cathodic protection + test for columns from +16.xx - +19.xxmpd part-1 20ura | 16/04/2022 | 22/04/2022 |  |  | 16 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-52.42 | TT_Task | falseworks soffit fwk erection for beams at +19.xxmpd part-1 20ura | 18/04/2022 | 11/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-52.43 | TT_Task | rebar fixing for beams at +19.xxmpd part-1 20ura | 23/04/2022 | 17/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-52.44 | TT_Task | cathodic protection + test for walls from +16.xx - +19.xxmpd part-1 20ura | 25/04/2022 | 01/05/2022 |  |  | 144 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-52.45 | TT_Task | side formworks for beams at +19.xxmpd part-1 20ura | 28/04/2022 | 23/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-52.46 | TT_Task | cathodic protection + test for beams at +19.xxmpd part-1 20ura | 13/05/2022 | 20/05/2022 |  |  | 24 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-52.47 | TT_Task | concreting works for wall/column and beams at +19.xxmpd part-1 20ura | 24/05/2022 | 25/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-52.48 | TT_Task | construction of vertical shaft from +19.xx - +25.xxmpd (1st-pour) part-1 20ura | 26/05/2022 | 14/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-52.49 | TT_Task | erection of column from +19.xx - +25.xxmpd (1st-pour) part-1 20ura | 26/05/2022 | 15/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-52.50 | TT_Task | erection of wall from +19.xx - +25.xxmpd (1st-pour) part-1 20ura | 01/06/2022 | 30/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-52.51 | TT_Task | rebar fixing for vertical shaft from +25.xx - +28.xxmpd (2nd-pour) part-1 20ura | 15/06/2022 | 04/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-52.52 | TT_Task | formworks for vertical shaft from +25.xx - +28.xxmpd (2nd-pour) part-1 20ura | 21/06/2022 | 11/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-52.53 | TT_Task | rebar fixing for columns from +25.xx - +28.xxmpd (2nd-pour) part-1 20ura | 21/06/2022 | 10/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-52.54 | TT_Task | formworks for columns from +25.xx - +28.xxmpd (2nd-pour) part-1 20ura | 26/06/2022 | 17/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-52.55 | TT_Task | cathodic protection + test for vertical shaft from +25.xx - +28.xxmpd (2nd-pour) part-1 20ura | 01/07/2022 | 06/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-52.56 | TT_Task | rebar fixing for walls from +25.xx - +28.xxmpd (2nd-pour) part-1 20ura | 01/07/2022 | 24/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-52.57 | TT_Task | formworks for walls from +25.xx - +28.xxmpd (2nd-pour) part-1 20ur | 05/07/2022 | 30/07/2022 |  |  | 8 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-52.58 | TT_Task | cathodic protection + test for columns from +25.xx - +28.xxmpd (2nd-pour) part-1 20ura | 09/07/2022 | 15/07/2022 |  |  | 40 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-52.59 | TT_Task | falseworks soffit fwk erection for beams/slab at +28.xxmpd part-1 20ura | 14/07/2022 | 02/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-52.60 | TT_Task | rebar fixing for beams/slab at +28.xxmpd part-1 20ura | 20/07/2022 | 10/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-52.61 | TT_Task | cathodic protection + test for walls from +25.xx - +28.xxmpd (2nd-pour) part-1 20ura | 21/07/2022 | 28/07/2022 |  |  | 72 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-52.63 | TT_Task | side formworks for beams/slab at +28.xxmpd part-1 20ura | 24/07/2022 | 06/08/2022 |  |  | 48 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-52.64 | TT_Task | cathodic protection + test for beams/slab at +28.xxmpd part-1 20ura | 05/08/2022 | 12/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-52.65 | TT_Task | concreting works for wall/column (2nd-pour) and beams at +28.xxmpd part-1 20ura | 13/08/2022 | 14/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-52.66 | TT_Task | erection of upstand wall/column at roof +30.35m part-1 20ura | 15/08/2022 | 24/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--HB-2-16.10 | TT_Task | BD - HRSG PACKAGES SUBMISSION APPROVAL -RESUBMISSION2 MAIN FRAME | 08/11/2021 | 09/12/2021 | 08/11/2021 | 09/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-49.00 | TT_Task | fwk erection for wall top slab of horizontal basin +8.75mpd part-2 20ura | 06/01/2022 | 10/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-49.01 | TT_Task | rebar fixing for wall top slab of horizontal basin +8.75mpd part-2 20ura | 11/01/2022 | 15/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-49.02 | TT_Task | close fwk for wall top slab of horizontal basin +8.75mpd part-2 20ura | 16/01/2022 | 19/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-49.03 | TT_Task | concreting of wall top slab of horizontal basin +8.75mpd part-2 20ura | 20/01/2022 | 20/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.00 | TT_Task | erection of column at gridline a d from +7.15 - +13.xxmpd (1st-pour) part-2 20ura | 19/01/2022 | 29/01/2022 |  |  | 8 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.01 | TT_Task | formwork for vertical shaft from +8.75 - +13.xxmpd (1st-pour) part-2 20ura | 20/01/2022 | 24/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.02 | TT_Task | rebar fixing for vertical shaft from +8.75 - +13.xxmpd (1st-pour) part-2 20ura | 25/01/2022 | 31/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.04 | TT_Task | erection of column at gridline b c from +7.15 - +13.xxmpd (1st-pour) part-2 20ura | 01/02/2022 | 07/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.05 | TT_Task | erection of wall along gridline a from +7.15 - +13.xxmpd (1st-pour) part-2 20ura | 08/02/2022 | 14/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.06 | TT_Task | cathodic protection + test for vertical shaft from +8.75 - +13.xxmpd (1st-pour) part-2 20ura | 15/02/2022 | 17/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.07 | TT_Task | close formworks for vertical shaft from +8.75 - +13.xxmpd (1st-pour) part-2 20ura | 15/02/2022 | 20/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.08 | TT_Task | erection of column at gridline g f from +7.15 - +13.xxmpd (1st-pour) part-2 20ura | 15/02/2022 | 24/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.09 | TT_Task | erection of partition wall along gridline d from +7.15 - +13.xxmpd (1st-pour) part-2 20ura | 15/02/2022 | 24/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.10 | TT_Task | concreting for vertical shaft from +8.75 - +13.xxmpd (1st-pour) part-2 20ura | 25/02/2022 | 25/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.11 | TT_Task | rebar fixing for vertical shaft from 13.xx - +16.xxmpd (2nd-pour) part-2 20ura | 26/02/2022 | 11/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.12 | TT_Task | erection of column at gridline e from +7.15 - +13.xxmpd (1st-pour) part-2 20ura | 26/02/2022 | 05/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.13 | TT_Task | erection of partition wall along gridline g from +7.15 - +13.xxmpd (1st-pour) part-2 20ura | 26/02/2022 | 07/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.14 | TT_Task | formworks for vertical shaft from 13.xx - +16.xxmpd (2nd-pour) part-2 20ura | 26/02/2022 | 09/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.15 | TT_Task | rebar fixing for columns from +13.xx - +16.xxmpd (2nd-pour) part-2 20ura | 10/03/2022 | 16/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.16 | TT_Task | erection of partition wall along gridline 14 from +7.15 - +13.xxm (1st-pour) part-2 20ura | 10/03/2022 | 19/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.17 | TT_Task | formworks for columns from +13.xx - +16.xxmpd (2nd-pour) part-2 20ura | 20/03/2022 | 02/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.18 | TT_Task | cathodic protection + test for vertical shaft from 13.xx - +16.xxmpd (2nd-pour) part-2 20ura | 20/03/2022 | 25/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.19 | TT_Task | rebar fixing for walls from +13.xx - +16.xxmpd (2nd-pour) part-2 20ura | 26/03/2022 | 04/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.20 | TT_Task | formworks for walls from +13.xx - +16.xxmpd (2nd-pour) part-2 20ura | 26/03/2022 | 08/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.21 | TT_Task | cathodic protection + test for columns from +13.xx - +16.xxmpd (2nd-pour) part-2 20ura | 09/04/2022 | 15/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.22 | TT_Task | falseworks soffit fwk erection for beams at +16.xxmpd part-2 20urara | 09/04/2022 | 20/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.23 | TT_Task | cathodic protection + test for walls from +13.xx - +16.xxmpd (2nd-pour) part-2 20ura | 21/04/2022 | 27/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.24 | TT_Task | rebar fixing for beams at +16.xxmpd part-2 20ura | 28/04/2022 | 11/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.25 | TT_Task | side formworks for beams at +16.xxmpd part-2 20ura | 28/04/2022 | 07/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.26 | TT_Task | cathodic protection + test for beams at +16.xxmpd part-2 20ura | 08/05/2022 | 15/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.27 | TT_Task | concreting works for wall/column (2nd-pour) and beams at +16.xxmpd part-2 20ura | 16/05/2022 | 17/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.28 | TT_Task | rebar fixing for vertical shaft from +16.xx - +19.xxmpd part-2 20ura | 18/05/2022 | 31/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.29 | TT_Task | rebar fixing for columns from +16.xx - +19.xxmpd part-2 20ura | 18/05/2022 | 06/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.30 | TT_Task | formworks for columns from +16.xx - +19.xxmpd part-2 20ura | 07/06/2022 | 07/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.31 | TT_Task | formworks for vertical shaft from +16.xx - +19.xxmpd part-2 20ura | 07/06/2022 | 23/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.32 | TT_Task | rebar fixing for walls from +16.xx - +19.xxmpd part-2 20ura | 24/06/2022 | 10/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.33 | TT_Task | formworks for walls from +16.xx - +19.xxmpd part-2 20ura | 24/06/2022 | 07/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.34 | TT_Task | cathodic protection + test for vertical shaft from +16.xx - +19.xxmpd part-2 20ura | 24/06/2022 | 29/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.35 | TT_Task | cathodic protection + test for columns from +16.xx - +19.xxmpd part-2 20ura | 30/06/2022 | 06/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.36 | TT_Task | falseworks soffit fwk erection for beams at +19.xxmpd part-2 20ura | 30/06/2022 | 13/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.37 | TT_Task | rebar fixing for beams at +19.xxmpd part-2 20ura | 30/06/2022 | 13/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.38 | TT_Task | cathodic protection + test for walls from +16.xx - +19.xxmpd part-2 20ura | 30/06/2022 | 05/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.39 | TT_Task | side formworks for beams at +19.xxmpd part-2 20ura | 06/07/2022 | 20/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.40 | TT_Task | cathodic protection + test for beams at +19.xxmpd part-2 20ura | 06/07/2022 | 11/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.41 | TT_Task | concreting works for wall/column and beams at +19.xxmpd part-2 20ura | 12/07/2022 | 13/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.42 | TT_Task | construction of vertical shaft from +19.xx - +25.xxmpd (1st-pour) part-2 20ura | 14/07/2022 | 20/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.43 | TT_Task | erection of column from +19.xx - +25.xxmpd (1st-pour) part-2 20ura | 14/07/2022 | 25/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.44 | TT_Task | erection of wall from +19.xx - +25.xxmpd (1st-pour) part-2 20ura | 26/07/2022 | 01/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.45 | TT_Task | rebar fixing for vertical shaft from +25.xx - +28.xxmpd (2nd-pour) part-2 20ura | 26/07/2022 | 08/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.46 | TT_Task | formworks for vertical shaft from +25.xx - +28.xxmpd (2nd-pour) part-2 20ura | 09/08/2022 | 15/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.47 | TT_Task | rebar fixing for columns from +25.xx - +28.xxmpd (2nd-pour) part-2 20ura | 16/08/2022 | 27/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.48 | TT_Task | cathodic protection + test for vertical shaft from +25.xx - +28.xxmpd (2nd-pour) part-2 20ura | 16/08/2022 | 21/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.49 | TT_Task | formworks for columns from +25.xx - +28.xxmpd (2nd-pour) part-2 20ura | 22/08/2022 | 02/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.50 | TT_Task | rebar fixing for walls from +25.xx - +28.xxmpd (2nd-pour) part-2 20ura | 22/08/2022 | 28/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.51 | TT_Task | formworks for walls from +25.xx - +28.xxmpd (2nd-pour) part-2 20ura | 29/08/2022 | 04/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.52 | TT_Task | cathodic protection + test for columns from +25.xx - +28.xxmpd (2nd-pour) part-2 20ura | 29/08/2022 | 03/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.53 | TT_Task | falseworks soffit fwk erection for beams/slab at +28.xxmpd part-2 20ura | 04/09/2022 | 10/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.54 | TT_Task | cathodic protection + test for walls from +25.xx - +28.xxmpd (2nd-pour) part-2 20ura | 04/09/2022 | 17/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.55 | TT_Task | rebar fixing for beams/slab at +28.xxmpd part-2 20ura | 04/09/2022 | 17/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.56 | TT_Task | side formworks and rebar fixing for beams/slab at +28.xxmpd part-2 20ura | 04/09/2022 | 10/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.57 | TT_Task | cathodic protection + test for beams/slab at +28.xxmpd part-2 20ura | 04/09/2022 | 09/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.58 | TT_Task | concreting works for wall/column (2nd-pour) and beams at +28.xxmpd part-2 20ura | 10/09/2022 | 10/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-54.59 | TT_Task | erection of upstand wall/column at roof +30.35m part-2 20ura | 10/09/2022 | 18/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-49.04 | TT_Task | erection of column pedestal with corbel up to at +7.15mpd part-2 20ura | 11/01/2022 | 28/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-4A42 | TT_Mile | TRANSPORT LOT1 NON PRESSURE PARTS VIETNAM | 30/12/2021 | 30/12/2021 | 30/12/2021 | 30/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20HB-4A43 | TT_Mile | TRANSPORT LOT2 NON PRESSURE PARTS VIETNAM | 15/02/2022 | 15/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-4A44 | TT_Mile | TRANSPORT LOT3 NON PRESSURE PARTS VIETNAM | 31/03/2022 | 31/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-4A45 | TT_Mile | TRANSPORT LOT1 PRESSURE PARTS KOREA | 11/03/2022 | 11/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-4A46 | TT_Mile | TRANSPORT LOT2 PRESSURE PARTS KOREA | 15/04/2022 | 15/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--HA-3E28 | TT_Task | BASIC / DETAIL DESIGN / ORDERING / DELIVERY / MANUFACTURING PIPING HRSG20 INTERNALPIPING | 28/01/2021 | 24/02/2022 | 28/01/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20HA-3B90 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) PIPING HRSG20_INTERNALPIPING | 10/02/2022 | 10/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-4B52 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION PIPING HRSG20 INTERNALPIPING | 10/02/2022 | 09/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-3B91 | TT_FinMile | (RFS) READY FOR SHIPMENT PIPING HRSG20_INTERNAL PIPING | 09/03/2022 | 09/03/2022 |  |  | 8 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-4B53 | TT_Task | TRANSPORT PIPING HRSG20_INTERNAL PIPING | 11/03/2022 | 30/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HA-4B54 | TT_FinMile | (OTD-OS) ON SITE PIPING HRSG20_INTERNAL PIPING | 30/03/2022 | 30/03/2022 |  |  | 128 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MB-4G41 | TT_FinMile | (OTD-OS) ONSITE GT SUPPORTS 20MB- | 24/06/2022 | 24/06/2022 |  |  | 56 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MBL4-26 | TT_Task | TRANSPORT AIR INTAKE SYSTEM AIR INTAKE SYSTEM 20MBL- Others | 02/08/2022 | 29/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKA4-41 | TT_Task | TRANSPORT GENERATOR FOUNDATION PLATES 20MKA | 30/04/2022 | 24/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MKA4-42 | TT_FinMile | (OTD-OS) ON SITE GENERATOR FOUNDATION PLATES 20MKA | 24/06/2022 | 24/06/2022 |  |  | 8 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY5-106.00 | TT_Task | CONSTRUCTION FOUNDATION 20UEY01 PART 2 - Formwork | 03/03/2022 | 10/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY5-106.01 | TT_Task | CONSTRUCTION FOUNDATION 20UEY01 PART 2 - Rebarfixing | 11/03/2022 | 22/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY5-106.02 | TT_Task | CONSTRUCTION FOUNDATION 20UEY01 PART 2 - Concreting | 23/03/2022 | 23/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY5-106.03 | TT_Task | CONSTRUCTION FOUNDATION 20UEY01 PART 2 - Curing and removal of Formworks | 24/03/2022 | 25/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY5-90.00 | TT_Task | CONSTRUCTION FOUNDATION 20UEY01 PART 1 - Formwork | 26/12/2021 | 30/12/2021 | 26/12/2021 | 30/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UEY5-90.01 | TT_Task | CONSTRUCTION FOUNDATION 20UEY01 PART 1 - Rebarfixing | 31/12/2021 | 11/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY5-90.02 | TT_Task | CONSTRUCTION FOUNDATION 20UEY01 PART 1 - Concreting | 12/01/2022 | 12/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY5-90.03 | TT_Task | CONSTRUCTION FOUNDATION 20UEY01 PART 1 - Curing and removal of formworks | 13/01/2022 | 14/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY5-102.01 | TT_Task | CONSTRUCTION FOUNDATION 20UEY02 -Rebarfixing | 18/03/2022 | 06/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY5-102.00 | TT_Task | CONSTRUCTION FOUNDATION 20UEY02 -Formwork | 04/03/2022 | 17/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY5-102.02 | TT_Task | CONSTRUCTION FOUNDATION 20UEY02 -Concreting | 07/04/2022 | 07/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY5-102.03 | TT_Task | CONSTRUCTION FOUNDATION 20UEY02 -Curing and desmatling of formwork | 08/04/2022 | 12/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMY5-15.00 | TT_Task | CONSTRUCTION FOUNDATION PIPE BRIDGE 20ULY/UMY- Formwork | 27/01/2022 | 28/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMY5-15.01 | TT_Task | CONSTRUCTION FOUNDATION PIPE BRIDGE 20ULY/UMY- Rebarfixing + Anchor Bolt installation | 01/02/2022 | 05/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMY5-15.02 | TT_Task | CONSTRUCTION FOUNDATION PIPE BRIDGE 20ULY/UMY- Concreting | 06/02/2022 | 06/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMY5-15.03 | TT_Task | CONSTRUCTION FOUNDATION PIPE BRIDGE 20ULY/UMY- Curing and desmantling of formwork | 07/02/2022 | 08/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5C-10.01 | TT_Task | CONSTRUCTION FOUNDATION 01UBA9010/20- Formwork | 03/04/2022 | 09/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5C-10.02 | TT_Task | CONSTRUCTION FOUNDATION 01UBA9010/20- Rebar | 10/04/2022 | 19/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5C-10.03 | TT_Task | CONSTRUCTION FOUNDATION 01UBA9010/20- Concreting | 20/04/2022 | 20/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5C-10.04 | TT_Task | CONSTRUCTION FOUNDATION 01UBA9010/20- Pedestal rebar | 21/04/2022 | 25/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5C-10.05 | TT_Task | CONSTRUCTION FOUNDATION 01UBA9010/20- Pedestal formwork | 26/04/2022 | 02/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5C-10.06 | TT_Task | CONSTRUCTION FOUNDATION 01UBA9010/20- Concreting | 03/05/2022 | 03/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5C-10.07 | TT_Task | CONSTRUCTION FOUNDATION 01UBA9010/20- Curing and desmnatling | 04/05/2022 | 08/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBH5-24.00 | TT_Task | CONSTRUCTION OIL COLLECTION PIT / OIL SEPARATOR 20UBH02- Formworks(1st Pour) | 15/05/2022 | 19/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBH5-24.01 | TT_Task | CONSTRUCTION OIL COLLECTION PIT / OIL SEPARATOR 20UBH02- Rebarfixing(1st Pour) | 20/05/2022 | 27/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBH5-24.02 | TT_Task | CONSTRUCTION OIL COLLECTION PIT / OIL SEPARATOR 20UBH02- Concreting(1st Pour) | 28/05/2022 | 28/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBH5-24.03 | TT_Task | CONSTRUCTION OIL COLLECTION PIT / OIL SEPARATOR 20UBH02- Inner formworks for Wall Top Slab | 29/05/2022 | 04/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBH5-24.04 | TT_Task | CONSTRUCTION OIL COLLECTION PIT / OIL SEPARATOR 20UBH02- Rebarfixing for Wall Top Slab | 05/06/2022 | 16/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBH5-24.05 | TT_Task | CONSTRUCTION OIL COLLECTION PIT / OIL SEPARATOR 20UBH02- Close formworks Wall Top Slab | 17/06/2022 | 23/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBH5-24.06 | TT_Task | CONSTRUCTION OIL COLLECTION PIT / OIL SEPARATOR 20UBH02- Concreting Wall Top Slab | 24/06/2022 | 25/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBH5-24.07 | TT_Task | CONSTRUCTION OIL COLLECTION PIT / OIL SEPARATOR 20UBH02- Curing and desmatling formworks Wall Top Slab | 26/06/2022 | 01/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBH5-24.08 | TT_Task | CONSTRUCTION OIL COLLECTION PIT / OIL SEPARATOR 20UBH02- Backfilling around the structure | 02/07/2022 | 05/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY5-15.00 | TT_Task | CONSTRUCTION FOUNDATION 20UEY03-05- Formwork slab/foundation | 13/04/2022 | 22/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY5-15.01 | TT_Task | CONSTRUCTION FOUNDATION 20UEY03-05- Rebarfixing slab/foundation | 23/04/2022 | 10/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY5-15.02 | TT_Task | CONSTRUCTION FOUNDATION 20UEY03-05- Concreting slab/foundation | 11/05/2022 | 12/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY5-15.03 | TT_Task | CONSTRUCTION FOUNDATION 20UEY03-05- Curing Remove formwork backfilling around | 13/05/2022 | 17/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQZ5-156.00 | TT_Task | CONSTRUCTION FOUNDATION PIPE CABLE TRENCH 20UQZ-Formwork baseslab pipe cable trench | 15/02/2022 | 19/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQZ5-156.01 | TT_Task | CONSTRUCTION FOUNDATION PIPE CABLE TRENCH 20UQZ-Rebarfixing baseslab pipe cable trench | 20/02/2022 | 26/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQZ5-156.02 | TT_Task | CONSTRUCTION FOUNDATION PIPE CABLE TRENCH 20UQZ-Concreting baseslab pipe cable trench | 27/02/2022 | 28/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQZ5-156.03 | TT_Task | CONSTRUCTION FOUNDATION PIPE CABLE TRENCH 20UQZ-One side formwork wall pipe cable trench | 01/03/2022 | 07/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQZ5-156.04 | TT_Task | CONSTRUCTION FOUNDATION PIPE CABLE TRENCH 20UQZ-Rebarfixing wall pipe cable trench | 08/03/2022 | 17/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQZ5-156.05 | TT_Task | CONSTRUCTION FOUNDATION PIPE CABLE TRENCH 20UQZ-Closed formwork wall pipe cable trench | 18/03/2022 | 24/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQZ5-156.06 | TT_Task | CONSTRUCTION FOUNDATION PIPE CABLE TRENCH 20UQZ-Concreting wall pipe cable trench | 25/03/2022 | 26/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQZ5-156.07 | TT_Task | CONSTRUCTION FOUNDATION PIPE CABLE TRENCH 20UQZ-Curing desmantling form Backfilling around struct. | 27/03/2022 | 01/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBY4-54.00 | TT_Task | CONSTRUCTION FOUNDATION 20UBY04 PART 1- Formworks | 12/04/2022 | 18/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBY4-54.01 | TT_Task | CONSTRUCTION FOUNDATION 20UBY04 PART 1- Rebarfixing | 19/04/2022 | 30/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBY4-54.02 | TT_Task | CONSTRUCTION FOUNDATION 20UBY04 PART 1- Concreting | 01/05/2022 | 01/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBY4-54.03 | TT_Task | CONSTRUCTION FOUNDATION 20UBY04 PART 1- Curing and desmantling formwork and backfilling | 02/05/2022 | 05/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBY4-57.00 | TT_Task | CONSTRUCTION FOUNDATION 20UBY04 PART 2- Formworks | 06/05/2022 | 13/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBY4-57.01 | TT_Task | CONSTRUCTION FOUNDATION 20UBY04 PART 2- Rebarfixing | 14/05/2022 | 31/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBY4-57.02 | TT_Task | CONSTRUCTION FOUNDATION 20UBY04 PART 2- Concreting | 01/06/2022 | 01/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBY4-57.03 | TT_Task | CONSTRUCTION FOUNDATION 20UBY04 PART 2- Curing and desmantling formwork and backfilling | 02/06/2022 | 06/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBY5-54.00 | TT_Task | CONSTRUCTION FOUNDATION 20UBY05- Formwork | 27/03/2022 | 02/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBY5-54.01 | TT_Task | CONSTRUCTION FOUNDATION 20UBY05- Rebarwork | 03/04/2022 | 13/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBY5-54.02 | TT_Task | CONSTRUCTION FOUNDATION 20UBY05- Concreting | 14/04/2022 | 14/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBY5-54.03 | TT_Task | CONSTRUCTION FOUNDATION 20UBY05- Curing and desmantling formwork and backfilling | 15/04/2022 | 17/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBY5-47.00 | TT_Task | CONSTRUCTION FOUNDATION 20UBY01- Formwork | 24/06/2022 | 30/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBY5-47.01 | TT_Task | CONSTRUCTION FOUNDATION 20UBY01- Rebarwork | 01/07/2022 | 11/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBY5-47.02 | TT_Task | CONSTRUCTION FOUNDATION 20UBY01- Concreting | 12/07/2022 | 12/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBY5-47.03 | TT_Task | CONSTRUCTION FOUNDATION 20UBY01- Curing and remove formwork | 13/07/2022 | 14/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ5-62.00 | TT_Task | CONSTRUCTION FOUNDATION 20UBZ01- Formwork baseslab | 19/05/2022 | 22/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ5-62.01 | TT_Task | CONSTRUCTION FOUNDATION 20UBZ01- Rebarwork baseslab | 23/05/2022 | 27/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ5-62.02 | TT_Task | CONSTRUCTION FOUNDATION 20UBZ01- Concreting baseslab | 28/05/2022 | 28/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ5-62.03 | TT_Task | CONSTRUCTION FOUNDATION 20UBZ01- One side formwork wall | 29/05/2022 | 02/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ5-62.04 | TT_Task | CONSTRUCTION FOUNDATION 20UBZ01- Rebarfxing for wall | 03/06/2022 | 10/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ5-62.05 | TT_Task | CONSTRUCTION FOUNDATION 20UBZ01- Closing formwork for wall | 05/06/2022 | 10/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ5-62.06 | TT_Task | CONSTRUCTION FOUNDATION 20UBZ01- Concreting for wall | 11/06/2022 | 11/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ5-62.6 | TT_Task | CONSTRUCTION FOUNDATION 20UBZ01- Curing and desmantling formwork and backfilling | 12/06/2022 | 16/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20ULY5-55.00 | TT_Task | CONSTRUCTION FOUNDATION PIPE BRIDGE 20ULY01- Formwork | 21/04/2022 | 29/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20ULY5-55.01 | TT_Task | CONSTRUCTION FOUNDATION PIPE BRIDGE 20ULY01- Rebarfixing | 30/04/2022 | 11/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20ULY5-55.02 | TT_Task | CONSTRUCTION FOUNDATION PIPE BRIDGE 20ULY01- Concreting | 12/05/2022 | 12/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20ULY5-55.03 | TT_Task | CONSTRUCTION FOUNDATION PIPE BRIDGE 20ULY01- Curing and desmantling formwork and backfill | 13/05/2022 | 18/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5-52.01 | TT_Task | CONSTRUCTION FOUNDATION 20UBA8110/20- Formwork | 24/05/2022 | 30/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5-52.02 | TT_Task | CONSTRUCTION FOUNDATION 20UBA8110/20- Rebar | 31/05/2022 | 07/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5-52.03 | TT_Task | CONSTRUCTION FOUNDATION 20UBA8110/20- Concreting | 08/06/2022 | 08/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5-52.04 | TT_Task | CONSTRUCTION FOUNDATION 20UBA8110/20- Pedestal rebar | 09/06/2022 | 15/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5-52.05 | TT_Task | CONSTRUCTION FOUNDATION 20UBA8110/20- Pedestal formwork | 12/06/2022 | 18/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5-52.06 | TT_Task | CONSTRUCTION FOUNDATION 20UBA8110/20- Pedestal concreting | 19/06/2022 | 19/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5-52.07 | TT_Task | CONSTRUCTION FOUNDATION 20UBA8110/20- Curing and desmantling | 20/06/2022 | 24/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBD5-57.00 | TT_Task | CONSTRUCTION FOUNDATION 20UBD03/04- Formwork baseslab/foundation | 13/05/2022 | 21/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBD5-57.01 | TT_Task | CONSTRUCTION FOUNDATION 20UBD03/04- Rebarwork baseslab/foundation | 22/05/2022 | 02/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBD5-57.02 | TT_Task | CONSTRUCTION FOUNDATION 20UBD03/04- Concreting baseslab/foundation | 03/06/2022 | 03/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBD5-57.03 | TT_Task | CONSTRUCTION FOUNDATION 20UBD03/04- Curing and desmantling formwork and backfilling | 04/06/2022 | 09/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBY5-58.00 | TT_Task | CONSTRUCTION FOUNDATION 20UBY03-Formwork slab/foundation | 03/06/2022 | 09/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBY5-58.01 | TT_Task | CONSTRUCTION FOUNDATION 20UBY03-Rebarfixing slab/foundation | 07/06/2022 | 13/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBY5-58.02 | TT_Task | CONSTRUCTION FOUNDATION 20UBY03-Concreting slab/foundation | 14/06/2022 | 14/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBY5-58.03 | TT_Task | CONSTRUCTION FOUNDATION 20UBY03-Curing and desmantling and backfill | 15/06/2022 | 17/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEX2-80.00 | TT_Task | CONSTRUCTION FOUNDATION 20UEX01- Rebarfixing baseslab | 04/07/2022 | 16/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEX2-80.01 | TT_Task | CONSTRUCTION FOUNDATION 20UEX01- Concreting baseslab | 17/07/2022 | 17/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEX2-90.00 | TT_Task | CONSTRUCTION WALLS 20UEX01- Inner formwork for walls | 17/07/2022 | 22/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEX2-90.01 | TT_Task | CONSTRUCTION WALLS 20UEX01- Rebarfixing for walls | 20/07/2022 | 27/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEX2-90.02 | TT_Task | CONSTRUCTION WALLS 20UEX01- Close Formwork for walls | 23/07/2022 | 28/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEX2-95.00 | TT_Task | CONSTRUCTION ROOF 20UEX01- Rebarfixing for top slab | 30/07/2022 | 09/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEX2-95.01 | TT_Task | CONSTRUCTION ROOF 20UEX01- Concreting for top slab | 10/08/2022 | 10/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEX2-95.02 | TT_Task | CONSTRUCTION ROOF 20UEX01- Curing and desmantling formwork | 11/08/2022 | 15/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEX2-90.03 | TT_Task | CONSTRUCTION WALLS 20UEX01- Concreting for walls | 29/07/2022 | 29/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEX2-95.03 | TT_Task | CONSTRUCTION ROOF 20UEX01- Backfilling | 16/08/2022 | 20/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-54.00 | TT_Task | CONSTRUCTION FOUNDATION 20UTG05- Formwork for baseslab/foundation | 06/05/2022 | 11/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-54.01 | TT_Task | CONSTRUCTION FOUNDATION 20UTG05- Rebarfixing for baseslab/foundation | 12/05/2022 | 21/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-54.02 | TT_Task | CONSTRUCTION FOUNDATION 20UTG05- Concreting for baseslab/foundation | 22/05/2022 | 22/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-54.03 | TT_Task | CONSTRUCTION FOUNDATION 20UTG05- Curing and desmantling formwork and backfill | 23/05/2022 | 26/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMX5-18.00 | TT_Task | CONSTRUCTION FOUNDATION 20UMX02- Formwork for baseslab | 11/05/2022 | 17/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMX5-18.01 | TT_Task | CONSTRUCTION FOUNDATION 20UMX02- Rebarfixing for baseslab | 14/05/2022 | 25/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMX5-18.02 | TT_Task | CONSTRUCTION FOUNDATION 20UMX02- Concreting for baseslab | 26/05/2022 | 26/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMX5-18.03 | TT_Task | CONSTRUCTION FOUNDATION 20UMX02- Inner Formworks for walls and topslab | 27/05/2022 | 05/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMX5-18.04 | TT_Task | CONSTRUCTION FOUNDATION 20UMX02- Rebarworks for walls and topslab | 03/06/2022 | 17/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMX5-18.05 | TT_Task | CONSTRUCTION FOUNDATION 20UMX02- Close formwork walls | 18/06/2022 | 25/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMX5-18.06 | TT_Task | CONSTRUCTION FOUNDATION 20UMX02- Concreting for walls and top slab | 26/06/2022 | 26/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMX5-18.07 | TT_Task | CONSTRUCTION FOUNDATION 20UMX02- Curing and desmantling | 27/06/2022 | 30/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMX5-18.08 | TT_Task | CONSTRUCTION FOUNDATION 20UMX02- Backfilling | 01/07/2022 | 03/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQX5-55.00 | TT_Task | CONSTRUCTION FOUNDATION 20UQX- Formworks baseslab | 11/04/2022 | 12/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQX5-55.01 | TT_Task | CONSTRUCTION FOUNDATION 20UQX- Rebarfixing baseslab | 13/04/2022 | 15/04/2022 |  |  | 32 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQX5-55.02 | TT_Task | CONSTRUCTION FOUNDATION 20UQX- Concreting baseslab | 20/04/2022 | 20/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQX5-55.03 | TT_Task | CONSTRUCTION FOUNDATION 20UQX- One side formwork for walls | 21/04/2022 | 24/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQX5-55.04 | TT_Task | CONSTRUCTION FOUNDATION 20UQX- Rebarfixing for walls | 25/04/2022 | 29/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQX5-55.05 | TT_Task | CONSTRUCTION FOUNDATION 20UQX- Close formwork for walls | 30/04/2022 | 03/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQX5-55.06 | TT_Task | CONSTRUCTION FOUNDATION 20UQX- Concreting for walls | 04/05/2022 | 04/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQX5-55.07 | TT_Task | CONSTRUCTION FOUNDATION 20UQX- Curing and desmantling forms and backfill | 05/05/2022 | 07/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-148.00 | TT_Task | CONSTRUCTION FOUNDATION PIPE / CABLE TRENCH 20UQY01-Formworks baseslab cable trench | 20/04/2022 | 22/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-148.01 | TT_Task | CONSTRUCTION FOUNDATION PIPE / CABLE TRENCH 20UQY01-Rebarfixing baseslab cable trench | 23/04/2022 | 26/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-148.02 | TT_Task | CONSTRUCTION FOUNDATION PIPE / CABLE TRENCH 20UQY01-Concreting baseslab cable trench | 27/04/2022 | 27/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-148.03 | TT_Task | CONSTRUCTION FOUNDATION PIPE / CABLE TRENCH 20UQY01-One side formwork for walls cable trench | 28/04/2022 | 02/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-148.04 | TT_Task | CONSTRUCTION FOUNDATION PIPE / CABLE TRENCH 20UQY01-Rebarwork for walls cable trench | 03/05/2022 | 09/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-148.05 | TT_Task | CONSTRUCTION FOUNDATION PIPE / CABLE TRENCH 20UQY01-Close formwork for walls cable trench | 10/05/2022 | 14/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-148.06 | TT_Task | CONSTRUCTION FOUNDATION PIPE / CABLE TRENCH 20UQY01-Concreting for walls cable trench | 15/05/2022 | 15/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-148.07 | TT_Task | CONSTRUCTION FOUNDATION PIPE / CABLE TRENCH 20UQY01-Curing and desmantling formwork and backfill | 16/05/2022 | 18/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-152.00 | TT_Task | CONSTRUCTION FOUNDATION PIPE / CABLE TRENCH 20UQY02- Formworks baseslab cable trench | 13/04/2022 | 15/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-152.01 | TT_Task | CONSTRUCTION FOUNDATION PIPE / CABLE TRENCH 20UQY02- Rebarfixing baseslab cable trench | 16/04/2022 | 19/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-152.02 | TT_Task | CONSTRUCTION FOUNDATION PIPE / CABLE TRENCH 20UQY02- Concreting baseslab cable trench | 20/04/2022 | 20/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-152.03 | TT_Task | CONSTRUCTION FOUNDATION PIPE / CABLE TRENCH 20UQY02- One side formwork for walls cable trench | 21/04/2022 | 25/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-152.04 | TT_Task | CONSTRUCTION FOUNDATION PIPE / CABLE TRENCH 20UQY02- Rebarwork for walls cable trench | 26/04/2022 | 02/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-152.05 | TT_Task | CONSTRUCTION FOUNDATION PIPE / CABLE TRENCH 20UQY02- Close formwork for walls cable trench | 03/05/2022 | 07/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-152.06 | TT_Task | CONSTRUCTION FOUNDATION PIPE / CABLE TRENCH 20UQY02- Concreting for walls cable trench | 08/05/2022 | 08/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-152.07 | TT_Task | CONSTRUCTION FOUNDATION PIPE / CABLE TRENCH 20UQY02- Curing and desmantling for walls cable trench | 09/05/2022 | 11/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-156.00 | TT_Task | CONSTRUCTION FOUNDATION PIPE / CABLE TRENCH 20UQY03- Formworks baseslab cable trench | 20/04/2022 | 22/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-156.01 | TT_Task | CONSTRUCTION FOUNDATION PIPE / CABLE TRENCH 20UQY03- Rebarfixing baseslab cable trench | 23/04/2022 | 26/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-156.02 | TT_Task | CONSTRUCTION FOUNDATION PIPE / CABLE TRENCH 20UQY03- Concreting baseslab cable trench | 27/04/2022 | 27/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-156.03 | TT_Task | CONSTRUCTION FOUNDATION PIPE / CABLE TRENCH 20UQY03- One side formwork for walls cable trench | 28/04/2022 | 02/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-156.04 | TT_Task | CONSTRUCTION FOUNDATION PIPE / CABLE TRENCH 20UQY03- Rebarwork for walls cable trench | 03/05/2022 | 09/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-156.05 | TT_Task | CONSTRUCTION FOUNDATION PIPE / CABLE TRENCH 20UQY03- Close formwork for walls cable trench | 10/05/2022 | 14/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-156.06 | TT_Task | CONSTRUCTION FOUNDATION PIPE / CABLE TRENCH 20UQY03- Concreting for walls cable trench | 15/05/2022 | 15/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQY5-156.07 | TT_Task | CONSTRUCTION FOUNDATION PIPE / CABLE TRENCH 20UQY03- Curing and desmantling for walls cable trench | 16/05/2022 | 18/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5-7.00 | TT_Task | WORK PREPARATION 7xxx- Excavation | 25/01/2022 | 31/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5-7.01 | TT_Task | WORK PREPARATION 7xxx- Blinding | 01/02/2022 | 07/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5-05.00 | TT_Task | WORK PREPARATION FOUNDATION 20UBA7910/20- Excavation | 09/05/2022 | 11/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5-05.01 | TT_Task | WORK PREPARATION FOUNDATION 20UBA7910/20- Blinding | 12/05/2022 | 16/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5-59.00 | TT_Task | WORK PREPARATION / EXCAVATION FOUNDATION 20UBA8110/20- Excavation | 10/05/2022 | 16/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5-59.01 | TT_Task | WORK PREPARATION / EXCAVATION FOUNDATION 20UBA8110/20- Blinding | 17/05/2022 | 23/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5C-5.00 | TT_Task | WORK PREPARATION 01UBA9010/20 - Excavation | 26/03/2022 | 28/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5C-5.01 | TT_Task | WORK PREPARATION 01UBA9010/20 - Blinding | 29/03/2022 | 02/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5-45.00 | TT_Task | WORK PREPARATION 20UBA1110/20- Excavation | 01/04/2022 | 03/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5-45.01 | TT_Task | WORK PREPARATION 20UBA1110/20- Blinding | 04/04/2022 | 07/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UPY6M10.00 | TT_Task | MECHANICAL ERECTION MODULE 20UPY00Y- A10 | 14/08/2022 | 16/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UPY6M10.01 | TT_Task | MECHANICAL ERECTION MODULE 20UPY00Y- A11 | 17/08/2022 | 20/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC6M16.00 | TT_Task | MECHANICAL ERECTION MODULE PxB 20UMCL1Y-D1-A11 | 11/05/2022 | 24/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC6M16.01 | TT_Task | MECHANICAL ERECTION MODULE PxB 20UMCL1Y-D1-G10 | 11/05/2022 | 24/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC6M16.02 | TT_Task | MECHANICAL ERECTION MODULE PxB 20UMCL1Y-D1-D10 | 11/05/2022 | 24/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC6M15.00 | TT_Task | MECHANICAL ERECTION MODULE 20UMCM1Y- A20 | 11/05/2022 | 24/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC6M15.01 | TT_Task | MECHANICAL ERECTION MODULE 20UMCM1Y-C20 | 11/05/2022 | 24/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC6M15.02 | TT_Task | MECHANICAL ERECTION MODULE 20UMCM1Y-D50 | 11/05/2022 | 24/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC6M15.03 | TT_Task | MECHANICAL ERECTION MODULE 20UMCM1Y-F10 | 11/05/2022 | 24/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC6M15.04 | TT_Task | MECHANICAL ERECTION MODULE 20UMCM1Y-H10 | 11/05/2022 | 24/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC6M15.05 | TT_Task | MECHANICAL ERECTION MODULE 20UMCM1Y-K30 | 11/05/2022 | 24/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMY6M18.00 | TT_Task | ERECTION RACK TOWER UMY00YE12 | 12/04/2022 | 17/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMY6M18.01 | TT_Task | ERECTION RACK TOWER UMY00YE43 | 12/04/2022 | 17/04/2022 |  |  | 272 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMY6M17.00 | TT_Task | ERECTION RACK TOWER UMY00Y-A11 | 24/04/2022 | 29/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMY6M17.01 | TT_Task | ERECTION RACK TOWER UMY00Y-A41 | 24/04/2022 | 29/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMY6M17.02 | TT_Task | ERECTION RACK TOWER UMY00Y-D11 | 24/04/2022 | 29/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMY6M17.03 | TT_Task | ERECTION RACK TOWER UMY00Y-D41 | 24/04/2022 | 29/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMY6M17.04 | TT_Task | ERECTION RACK TOWER UMY00YK16 | 24/04/2022 | 29/04/2022 |  |  | 176 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMY6M16.00 | TT_Task | ERECTION RACK TOWER UMY00YG12 | 18/04/2022 | 23/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMY6M16.01 | TT_Task | ERECTION RACK TOWER UMY00YG43 | 18/04/2022 | 23/04/2022 |  |  | 224 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--CKA4-26 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION THERMODYN. DIAGNOSIS SERVER | 08/01/2023 | 04/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20EK-3-83 | TT_FinMile | (RFS) READY FOR SHIPMENT CONDENSATE TANK 01EK | 29/06/2022 | 29/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20EK-4-43 | TT_FinMile | (OTD-OS) ON SITE CONDENSATE TANK 01EK | 31/08/2022 | 31/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20EK-4-42 | TT_Task | TRANSPORT (FROM AUSTRIA) CONDENSATE TANK 01EK | 30/06/2022 | 31/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20EK-4B11 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION CONDENSATE TANK 01EK | 02/06/2022 | 29/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20EK-3B71 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) CONDENSATE TANK 01EK | 01/06/2022 | 01/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20EK-6-19.00 | TT_Task | MECHANICAL ERECTION CONDENSATE TANK 01EK | 01/09/2022 | 07/09/2022 |  |  | 2000 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--HB-2-16.00 | TT_FinMile | BD - HRSG PACKAGES SUBMISSION APPROVAL-WITHDRAWN STACK + MAIN FRAME | 03/08/2021 | 03/08/2021 | 03/08/2021 | 03/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--HB-2-16.03 | TT_Task | BD - HRSG PACKAGES SUBMISSION APPROVAL -RESUBMISSION 2 STACK | 12/11/2021 | 10/01/2022 | 12/11/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--HB-2-16.04 | TT_Task | BD - CONSENT LETTER STACK | 11/01/2022 | 09/02/2022 |  |  | 632 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--HB-2-18.00 | TT_Task | BD - HRSG PLATFORMS SUBMISSION APPROVAL(Side platforms and roof canopy) | 14/12/2021 | 11/02/2022 | 14/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--HB-2-18.01 | TT_Task | BD - CONSENT LETTER HRSG PLATFORMS(Side platforms and roof canopy) | 12/02/2022 | 11/03/2022 |  |  | 1160 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2B79.00 | TT_FinMile | BD - SUBMISSION APPROVAL - STEEL STRUCTURE 20UMC (Incl. Crane Walkawy) WITHDRAWN | 12/07/2021 | 12/07/2021 | 12/07/2021 | 12/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2B79.01 | TT_Task | BD - RESUBMISSION APPROVAL - UMC PACKAGES(Steel,topslab,CEP/LDK screen wall,turbine plinth/wall) | 12/07/2021 | 26/08/2021 | 12/07/2021 | 27/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5A25.00 | TT_Task | TURBOSET FOUNDATION (PLINTHS / WALLS) 20UMC- Preparation Works | 25/10/2021 | 06/11/2021 | 25/10/2021 | 06/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5A25.01 | TT_Task | TURBOSET FOUNDATION (PLINTHS / WALLS) 20UMC- Rebarfixing | 07/11/2021 | 27/11/2021 | 07/11/2021 | 27/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5A25.02 | TT_Task | TURBOSET FOUNDATION (PLINTHS / WALLS) 20UMC- Formworks | 13/11/2021 | 02/12/2021 | 13/11/2021 | 02/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5A25.03 | TT_Task | TURBOSET FOUNDATION (PLINTHS / WALLS) 20UMC- Installation of cast in items | 30/11/2021 | 06/12/2021 | 30/11/2021 | 06/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5A25.04 | TT_Task | TURBOSET FOUNDATION (PLINTHS / WALLS) 20UMC- Concrete pouring | 07/12/2021 | 15/01/2022 | 07/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5A25.05 | TT_Task | TURBOSET FOUNDATION (PLINTHS / WALLS) 20UMC- Curing and desmantling | 16/01/2022 | 20/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5B59.00 | TT_Task | ERECTION STEEL STRUCTURE FOR ELECTRICAL MODULES 20UBA7xxx - Platforms | 03/06/2022 | 16/06/2022 |  |  | 48 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5B59.01 | TT_Task | ERECTION STEEL STRUCTURE FOR ELECTRICAL MODULES 20UBA7xxx - Frame | 19/08/2022 | 01/09/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5B17.00 | TT_Task | ERECTION STEEL STRUCTURE 20UBA8110/20-Platforms | 11/11/2022 | 17/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5B17.01 | TT_Task | ERECTION STEEL STRUCTURE 20UBA8110/20-Frame | 01/12/2022 | 07/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5C-35.00 | TT_Task | ERECTION STEEL PLATFORMS 01UBA9010/20-Platforms | 29/06/2022 | 05/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5C-35.01 | TT_Task | ERECTION STEEL PLATFORMS 01UBA9010/20-Frame | 19/07/2022 | 25/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5B-45.00 | TT_Task | ERECTION STEEL STRUCTURE 20UBA1110/20-Platforms | 11/11/2022 | 17/11/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBA5B-45.01 | TT_Task | ERECTION STEEL STRUCTURE 20UBA1110/20-Frame | 01/12/2022 | 07/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MA-4C45 | TT_Task | TRANSPORT TURBINE EXHAUST MANIFOLD | 23/03/2022 | 21/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MA-3C86 | TT_FinMile | (RFS) READY FOR SHIPMENT TURBINE EXHAUST MANIFOLD | 22/03/2022 | 22/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MA-3-97 | TT_Task | DESIGN / MANUFACTURING TURBINE EXHAUST MANIFOLD | 13/09/2021 | 22/02/2022 | 13/09/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SP20MA-4C46 | TT_FinMile | (OTD-OS) ON SITE TURBINE EXHAUST MANIFOLD | 21/04/2022 | 21/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MA-4-16 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION TURBINE EXHAUST MANIFOLD | 23/02/2022 | 22/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MA-3-98 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) TURBINE EXHAUST MANIFOLD | 22/02/2022 | 22/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MA-3C87 | TT_FinMile | (RFS) READY FOR SHIPMENT ST CROSS OVER PIPE MA- | 20/03/2022 | 20/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MA-4C47 | TT_Task | TRANSPORT ST CROSS OVER PIPE MA- | 21/03/2022 | 19/04/2022 |  |  | 1368 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--HB-2-16.08 | TT_Task | BD - HRSG PACKAGES SUBMISSION APPROVAL -RESUBMISSION1 MAIN FRAME+ STACK | 14/09/2021 | 02/11/2021 | 14/09/2021 | 03/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--HB-2-16.09 | TT_FinMile | BD - HRSG PACKAGES SUBMISSION APPROVAL -WITDRAWN MAIN STACK + MAIN FRAME | 03/11/2021 | 03/11/2021 | 03/11/2021 | 03/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2A94 | TT_FinMile | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE - WITHDRAWN CEP/LDK - PIT - (1STPACKAGE) | 13/05/2021 | 13/05/2021 | 13/05/2021 | 13/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2A95 | TT_FinMile | BD - SUBMISSION APPROVAL-DETAIL DESIGN-TURBOSET WITHDRAWN (2NDPACKAGE) | 13/05/2021 | 13/05/2021 | 13/05/2021 | 13/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC2B77 | TT_FinMile | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE - WITHDRAWN BUILDING (1STPACKAGE) | 13/05/2021 | 13/05/2021 | 13/05/2021 | 13/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2A96 | TT_FinMile | BD - CONSENT LETTER TURBOSET DETAIL DESIGN CONCRETE 20UMC - WITHDRAWN | 30/06/2021 | 30/06/2021 | 30/06/2021 | 30/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2A97 | TT_Task | BD - CONSENT LETTER DETAIL DESIGN CONCRETE TURBOSET 20UMC PACKAGE 12 - RESUBMISSION | 30/06/2021 | 22/07/2021 | 30/06/2021 | 23/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2A98 | TT_Task | BD - SUBMISSION APPROVAL - TURBOSET DETAIL DESIGN CONCRET - 2ND AMMENDMENT (PILE CAP) | 23/07/2021 | 01/08/2021 | 23/07/2021 | 02/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2A99 | TT_FinMile | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE - 2ND AMMENDMENT (PILE CAP) WITHDRAWN | 02/08/2021 | 02/08/2021 | 02/08/2021 | 02/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2A100 | TT_Task | BD - RESUBMISSION APPROVAL - DETAIL DESIGN CONCRETE - 2ND AMMENDMENT (PILE CAP) | 09/09/2021 | 07/10/2021 | 09/09/2021 | 08/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2A101 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE - RESUBMISSION CEP/LDK - PIT(1STPACKAGE) | 24/05/2021 | 09/06/2021 | 24/05/2021 | 10/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC2B78 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE - RESUBMISSION BUILDING (1STPACKAGE) | 24/05/2021 | 09/06/2021 | 24/05/2021 | 10/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URA2B9 | TT_FinMile | BD - SUBMISSION APPROVAL SUBSTRUCTURE 20URA/URD WITDRAWN (1STPACKAGE) | 13/05/2021 | 13/05/2021 | 13/05/2021 | 13/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URA2B10 | TT_Task | BD - SUBMISSION APPROVAL SUBSTRUCTURE 20URA/URD RESUBMISSION (1STPACKAGE) | 24/05/2021 | 09/06/2021 | 24/05/2021 | 10/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHA2B4 | TT_FinMile | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE - WITDRAWN 20UHA(2NDPACKAGE) | 13/05/2021 | 13/05/2021 | 13/05/2021 | 13/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UHW2B4 | TT_FinMile | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE - WITHDRAWN 20UHW(2NDPACKAGE) | 13/05/2021 | 13/05/2021 | 13/05/2021 | 13/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC3B25.00 | TT_Mile | (OTD-OS) ONSITE STEEL STRUCTURE 20UMC 1ST DELIVERY | 29/01/2022 | 29/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC3B25.0 | TT_FinMile | (OTD-OS) ONSITE STEEL STRUCTURE 20UMC 2ND DELIVERY | 23/03/2022 | 23/03/2022 |  |  | 264 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--URA2-108 | TT_FinMile | BD - CONSENT LETTER RESUBMISSION2 SUBSTRUCTURE 20URA/URD -WITHDRAWN | 09/11/2021 | 09/11/2021 | 09/11/2021 | 09/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--URA2-109 | TT_Task | BD - CONSENT LETTER RESUBMISSION3 SUBSTRUCTURE 20URA/URD | 15/11/2021 | 18/11/2021 | 15/11/2021 | 19/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20URA2B11 | TT_FinMile | BD - SUBMISSION APPROVAL SUPERSTRUCTURE- 1ST SUBMISSION 20URA/URD- WITDRAWN | 20/08/2021 | 20/08/2021 | 20/08/2021 | 20/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2B100 | TT_FinMile | BD - SUBMISSION APPROVAL - STANDING SEAM ROOF/WALL/PANELS - CLADDING 20UMC | 26/11/2021 | 26/11/2021 | 26/11/2021 | 26/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2B101 | TT_Task | BD - RESUBMISSION APPROVAL - STANDING SEAM ROOF/WALL/PANELS - CLADDING 20UMC | 24/12/2021 | 21/02/2022 | 24/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20URA5-36.11 | TT_Task | CONSTRUCTION FOUNDATION BAY2B- Formwork | 10/12/2021 | 23/12/2021 | 10/12/2021 | 23/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-14.00 | TT_Task | CONSTRUCTION FOUNDATION 20UTG01-Rebarfxing | 11/05/2022 | 14/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-14.01 | TT_Task | CONSTRUCTION FOUNDATION 20UTG01-Formwork | 15/05/2022 | 17/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-14.02 | TT_Task | CONSTRUCTION FOUNDATION 20UTG01-Concreting | 18/05/2022 | 18/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-10.00 | TT_Task | WORK PREPARATION, EXCAVATION 20UTG01-Excavation | 03/05/2022 | 08/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-10.01 | TT_Task | WORK PREPARATION, EXCAVATION 20UTG01-Blinding | 09/05/2022 | 10/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-20.00 | TT_Task | WORK PREPARATION, EXCAVATION 20UTG02- Excavation | 14/04/2022 | 19/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-20.01 | TT_Task | WORK PREPARATION, EXCAVATION 20UTG02- Blinding | 20/04/2022 | 21/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-24.00 | TT_Task | CONSTRUCTION FOUNDATION 20UTG02-Formwork | 22/04/2022 | 27/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-24.01 | TT_Task | CONSTRUCTION FOUNDATION 20UTG02-Rebarfixing | 28/04/2022 | 08/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-24.02 | TT_Task | CONSTRUCTION FOUNDATION 20UTG02-Concreting | 09/05/2022 | 09/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-24.03 | TT_Task | CONSTRUCTION FOUNDATION 20UTG02-Curing and removal form and backfill | 10/05/2022 | 13/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-30.00 | TT_Task | WORK PREPARATION, EXCAVATION 20UTG03- Excavation | 28/04/2022 | 03/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-30.01 | TT_Task | WORK PREPARATION, EXCAVATION 20UTG03- Blinding | 04/05/2022 | 04/05/2022 |  |  | 8 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-34.00 | TT_Task | CONSTRUCTION FOUNDATION 20UTG03- Rebarfxing | 06/05/2022 | 11/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-40.00 | TT_Task | WORK PREPARATION, EXCAVATION 20UTG04- Excavation | 01/04/2022 | 06/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-40.01 | TT_Task | WORK PREPARATION, EXCAVATION 20UTG04- Blinding | 07/04/2022 | 07/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-34.01 | TT_Task | CONSTRUCTION FOUNDATION 20UTG03- Formworks | 12/05/2022 | 21/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-34.02 | TT_Task | CONSTRUCTION FOUNDATION 20UTG03- Concreting | 22/05/2022 | 22/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-34.03 | TT_Task | CONSTRUCTION FOUNDATION 20UTG03- Curing desmanlting forms and backfill | 23/05/2022 | 26/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ5-69.01 | TT_Task | WORK PREPARATION, EXCAVATION 20UBZ02 - Blinding | 14/02/2022 | 14/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ5-69.00 | TT_Task | WORK PREPARATION, EXCAVATION 20UBZ02 - Excavation | 08/02/2022 | 13/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URD5-37.00 | TT_Task | CONSTRUCTION OF WALLS 20URD- Working platform/formwork installation | 05/01/2022 | 22/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URD5-37.01 | TT_Task | CONSTRUCTION OF WALLS 20URD- Rebarfixing | 23/01/2022 | 07/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URD5-37.02 | TT_Task | CONSTRUCTION OF WALLS 20URD- Close formwork | 08/02/2022 | 21/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20URD5-37.03 | TT_Task | CONSTRUCTION OF WALLS 20URD- Concreting of Wall | 22/02/2022 | 24/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UGU5-82.00 | TT_Task | WORK PREPARATION / EXCAVATION 20UGU02-Excavation | 21/03/2022 | 26/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UGU5-82.01 | TT_Task | WORK PREPARATION / EXCAVATION 20UGU02-Blinding | 27/03/2022 | 27/03/2022 |  |  | 128 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UGU5-85.00 | TT_Task | CONSTRUCTION BASE PLATE DRAINAGE PIT 20UGU02- Formwork | 13/04/2022 | 16/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UGU5-85.01 | TT_Task | CONSTRUCTION BASE PLATE DRAINAGE PIT 20UGU02- Rebarfixing | 17/04/2022 | 21/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UGU5-85.02 | TT_Task | CONSTRUCTION BASE PLATE DRAINAGE PIT 20UGU02- Concreting | 22/04/2022 | 22/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UGU5-86.00 | TT_Task | CONSTRUCTION WALLS DRAINAGE PIT 20UGU02- Formwork | 23/04/2022 | 30/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UGU5-86.01 | TT_Task | CONSTRUCTION WALLS DRAINAGE PIT 20UGU02- Rebarfixing | 01/05/2022 | 06/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UGU5-86.02 | TT_Task | CONSTRUCTION WALLS DRAINAGE PIT 20UGU02- Concreting | 07/05/2022 | 07/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-60.00 | TT_Task | WORK PREPARATION, EXCAVATION 20UTG06-Excavation | 06/04/2022 | 11/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-60.01 | TT_Task | WORK PREPARATION, EXCAVATION 20UTG06-Blinding | 12/04/2022 | 12/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-64.00 | TT_Task | CONSTRUCTION FOUNDATION 20UTG06-Formwork | 13/04/2022 | 18/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-64.01 | TT_Task | CONSTRUCTION FOUNDATION 20UTG06-Rebarfixing | 19/04/2022 | 28/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-64.02 | TT_Task | CONSTRUCTION FOUNDATION 20UTG06-Concreting | 29/04/2022 | 29/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG5-64.03 | TT_Task | CONSTRUCTION FOUNDATION 20UTG06-Curing, desmantling forms and backfill | 30/04/2022 | 03/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UZJ5-64.00 | TT_Task | CONSTRUCTION FOUNDATION FENCESGATES- Part1 | 10/11/2022 | 14/12/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UZJ5-64.01 | TT_Task | CONSTRUCTION FOUNDATION FENCESGATES- Part2 | 15/12/2022 | 18/01/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UZJ5-64.02 | TT_Task | CONSTRUCTION FOUNDATION FENCESGATES- Part3 | 19/01/2023 | 22/02/2023 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B15-01 | TT_Task | ERECTION STEEL STRUCTURE MAIN BUILDING / CRANE RAILS 20UMC-Column and bracing Erection (Grid T3-T2) 2 nos. | 05/02/2022 | 09/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B15-00 | TT_Task | ERECTION STEEL STRUCTURE MAIN BUILDING / CRANE RAILS 20UMC-Truss Pre assembly 8 nos. | 25/01/2022 | 21/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B15-02 | TT_Task | ERECTION STEEL STRUCTURE MAIN BUILDING / CRANE RAILS 20UMC-Truss and bracing Erection (Grid T3-T2) 2 nos. | 10/02/2022 | 14/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B15-03 | TT_Task | ERECTION STEEL STRUCTURE MAIN BUILDING / CRANE RAILS 20UMC-Column and bracing Erection (Grid T2-T1) 6 nos. | 15/02/2022 | 21/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B15-04 | TT_Task | ERECTION STEEL STRUCTURE MAIN BUILDING / CRANE RAILS 20UMC-Arc beam and bracing Erection (Grid T1) 8 nos. | 22/02/2022 | 28/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B15-05 | TT_Task | ERECTION STEEL STRUCTURE MAIN BUILDING / CRANE RAILS 20UMC-Column and bracing Erection (Grid T3-T8) 7 nos. | 01/03/2022 | 07/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B15-06 | TT_Task | ERECTION STEEL STRUCTURE MAIN BUILDING / CRANE RAILS 20UMC-Truss and bracing Erection (Grid T3-T8) 4 nos. | 08/03/2022 | 12/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B15-07 | TT_Task | ERECTION STEEL STRUCTURE MAIN BUILDING / CRANE RAILS 20UMC-Column and bracing Erection (Grid T8-T9) 4 nos. | 13/03/2022 | 17/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B15-08 | TT_Task | ERECTION STEEL STRUCTURE MAIN BUILDING / CRANE RAILS 20UMC-Truss and bracing Erection (Grid T8-T9) 2 nos. | 18/03/2022 | 22/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B15-09 | TT_Task | ERECTION STEEL STRUCTURE MAIN BUILDING / CRANE RAILS 20UMC-Column and bracing Erection (Grid T9-T10) 8 nos. | 23/03/2022 | 29/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B15-10 | TT_Task | ERECTION STEEL STRUCTURE MAIN BUILDING / CRANE RAILS 20UMC-Arc beam and bracing Erection (Grid T10) 8 nos. | 30/03/2022 | 05/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B15-11 | TT_Task | ERECTION STEEL STRUCTURE MAIN BUILDING / CRANE RAILS 20UMC-Crane Girder Installation | 06/04/2022 | 15/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ5-70.00 | TT_Task | CONSTRUCTION FOUNDATION 20UBZ02- Forworks for baseslab | 15/02/2022 | 18/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ5-70.01 | TT_Task | CONSTRUCTION FOUNDATION 20UBZ02- Rebarfixing for baseslab | 19/02/2022 | 23/02/2022 |  |  | 96 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ5-70.02 | TT_Task | CONSTRUCTION FOUNDATION 20UBZ02- Concreting for baseslab | 08/03/2022 | 08/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ5-70.03 | TT_Task | CONSTRUCTION FOUNDATION 20UBZ02- Formwork for wall | 09/03/2022 | 13/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ5-70.04 | TT_Task | CONSTRUCTION FOUNDATION 20UBZ02- Rebarfixing for wall | 14/03/2022 | 21/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ5-70.05 | TT_Task | CONSTRUCTION FOUNDATION 20UBZ02- Close formwork for wall | 22/03/2022 | 27/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ5-70.06 | TT_Task | CONSTRUCTION FOUNDATION 20UBZ02- Concreting for wall | 28/03/2022 | 28/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UBZ5-70.07 | TT_Task | CONSTRUCTION FOUNDATION 20UBZ02- Curing, desmantling forms and backfill | 29/03/2022 | 02/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B90.36 | TT_Task | CONCRETE CONSTRUCTION BUILDING FOUNDATION 20UMC- Part1 NW Adjust blinding | 08/12/2021 | 24/12/2021 | 08/12/2021 | 24/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B90.37 | TT_Task | CONCRETE CONSTRUCTION BUILDING FOUNDATION 20UMC- Part2 NE Adjust blinding | 08/12/2021 | 19/12/2021 | 08/12/2021 | 19/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UGU5-76.01 | TT_Task | WORK PREPARATION / EXCAVATION 20UGU01-Excavation | 07/04/2022 | 11/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UGU5-76.02 | TT_Task | WORK PREPARATION / EXCAVATION 20UGU01-Blinding | 12/04/2022 | 12/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UGU5-79.00 | TT_Task | CONSTRUCTION BASE PLATE PUMP PIT 20UGU01-Sum pit rebarfixing | 13/04/2022 | 16/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UGU5-79.01 | TT_Task | CONSTRUCTION BASE PLATE PUMP PIT 20UGU01-Sum pit formwork | 17/04/2022 | 19/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UGU5-79.02 | TT_Task | CONSTRUCTION BASE PLATE PUMP PIT 20UGU01-Sum pit concreting | 20/04/2022 | 20/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UGU5-79.03 | TT_Task | CONSTRUCTION BASE PLATE PUMP PIT 20UGU01-Baseslab rebarfixing | 21/04/2022 | 24/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UGU5-79.04 | TT_Task | CONSTRUCTION BASE PLATE PUMP PIT 20UGU01-Baseslab formwork | 25/04/2022 | 29/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UGU5-79.05 | TT_Task | CONSTRUCTION BASE PLATE PUMP PIT 20UGU01-Baseslab concreting | 30/04/2022 | 30/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UGU5-80.00 | TT_Task | CONSTRUCTION WALLS PUMP PIT 20UGU01-Rebarworks | 01/05/2022 | 08/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UGU5-80.01 | TT_Task | CONSTRUCTION WALLS PUMP PIT 20UGU01-Formworks | 09/05/2022 | 14/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UGU5-80.02 | TT_Task | CONSTRUCTION WALLS PUMP PIT 20UGU01-Concreting | 15/05/2022 | 15/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UGU5-80.03 | TT_Task | CONSTRUCTION WALLS PUMP PIT 20UGU01-Curing and desmantling of forms | 16/05/2022 | 19/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQZ5-160.01 | TT_Task | CONCRETE WORKS - CIVIL ADAPTION WORKS AT SCW PUMP HOUSE 20UQB-Formworks | 12/03/2022 | 19/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQZ5-160.00 | TT_Task | CONCRETE WORKS - CIVIL ADAPTION WORKS AT SCW PUMP HOUSE 20UQB-Rebarfixing | 04/03/2022 | 11/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UQZ5-160.02 | TT_Task | CONCRETE WORKS - CIVIL ADAPTION WORKS AT SCW PUMP HOUSE 20UQB-Concreting | 20/03/2022 | 20/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI----P3I37 | TT_FinMile | (RFS) READY FOR SHIPMENT CONTROL VALVE | 22/10/2021 | 22/10/2021 | 22/10/2021 | 22/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI----P3I38 | TT_Task | TRANSPORT CONTROL VALVE | 25/10/2021 | 01/11/2021 | 25/10/2021 | 01/11/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI----P3I36 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION CONTROL VALVE | 09/10/2021 | 22/10/2021 | 09/10/2021 | 22/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI----P3I35 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) FOR CONTROL VALVE | 08/10/2021 | 08/10/2021 | 08/10/2021 | 08/10/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y47.37 | TT_Task | CONSTRUCTION LDK PIT - Screen Wall S3(Lvl +4.65m)-Formwork | 15/12/2021 | 21/12/2021 | 15/12/2021 | 21/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y47.36 | TT_Task | CONSTRUCTION LDK PIT - Screen Wall S3(Lvl +4.65m)-Concrete Pour | 03/01/2022 | 03/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y47.38 | TT_Task | CONSTRUCTION LDK PIT - Screen Wall S3(Lvl +4.65m)-Curing | 04/01/2022 | 06/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5Y47.39 | TT_Task | CONSTRUCTION LDK PIT - Screen Wall S3(Lvl +4.65m)-Dismatle Formwork | 07/01/2022 | 07/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-6A19 | TT_Task | PREPARATION WORKS HRSG STRUCTURE ERECTION HRSG20 | 04/01/2022 | 14/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20HB-6A20 | TT_Mile | START ERECTION HRSG MAIN STRUCTURE | 15/01/2022 | 15/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SCA2-92 | TT_Mile | ERECTION MANUALS ON SITE AIR COMPRESSOR SYSTEM SCA | 26/02/2022 | 26/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SCA3-81 | TT_Task | DETAIL DESIGN / CLARIFICATION LD PLANT AIR RECEIVER 20QFB02BB001 | 21/09/2021 | 01/12/2021 | 21/09/2021 | 01/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20SCA6-41 | TT_Task | PLACING LD PLANT AIR RECEIVER 20QFB02BB001 | 09/05/2022 | 11/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SCA3-83 | TT_FinMile | (RFS) READY FOR SHIPMENT LD PLANT AIR RECEIVER 20QFB02BB001 | 08/04/2022 | 08/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SCA3-82 | TT_Task | MANUFACTURING / SHOP TEST LD PLANT AIR RECEIVER 20QFB02BB001 | 02/12/2021 | 11/03/2022 | 02/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20SCA4-42 | TT_FinMile | (OTD-OS) ON SITE LD PLANT AIR RECEIVER 20QFB02BB001 | 08/05/2022 | 08/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SCA4-41 | TT_Task | TRANSPORT LD PLANT AIR RECEIVER 20QFB02BB001 | 09/04/2022 | 08/05/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SCA4B11 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION LD PLANT AIR RECEIVER 20QFB02BB001 | 12/03/2022 | 08/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SCA3B71 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) LD PLANT AIR RECEIVER 20QFB02BB001 | 11/03/2022 | 11/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SCA3-84 | TT_Task | DETAIL DESIGN / CLARIFICATION SCA SKID AIR RECEIVERS 20SCA10BB001/2 | 21/09/2021 | 17/12/2021 | 21/09/2021 | 17/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20SCA6-42 | TT_Task | PLACING SCA SKID AIR RECEIVERS 20SCA10BB001/2 | 11/08/2022 | 13/08/2022 |  |  | 520 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SCA3-86 | TT_FinMile | (RFS) READY FOR SHIPMENT SCA SKID AIR RECEIVERS 20SCA10BB001/2 | 11/07/2022 | 11/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SCA3-85 | TT_Task | MANUFACTURING / SHOP TEST SCA SKID AIR RECEIVERS 20SCA10BB001/2 | 18/12/2021 | 13/06/2022 | 18/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20SCA4-44 | TT_FinMile | (OTD-OS) ON SITE SCA SKID AIR RECEIVERS 20SCA10BB001/2 | 10/08/2022 | 10/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SCA4-43 | TT_Task | TRANSPORT SCA SKID AIR RECEIVERS 20SCA10BB001/2 | 12/07/2022 | 10/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SCA4B12 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION SCA SKID AIR RECEIVERS 20SCA10BB001/2 | 14/06/2022 | 11/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20SCA3B72 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) SCA SKID AIR RECEIVERS 20SCA10BB001/2 | 13/06/2022 | 13/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--2M-34 | TT_Task | BD - REJECTION REWORK- SUPPORTING FRAME FOR MODULES LOT 1 | 30/11/2021 | 19/12/2021 | 30/11/2021 | 19/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI--2M-35 | TT_Task | BD - RESUBMISSION - SUPPORTING FRAME FOR MODULES LOT 1 | 20/12/2021 | 17/02/2022 | 20/12/2021 |  | 11296 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--2M-36 | TT_Task | BD - CONSENT LETTER - SUPPORTING FRAME FOR MODULES LOT 2 | 13/01/2022 | 13/03/2022 |  |  | 11104 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2B102 | TT_Task | BD - WITHDRAWAL REWORK STEEL PLATFORMS LOT1 20UMC | 24/12/2021 | 13/01/2022 | 24/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2B103 | TT_Task | BD - RESUBMISSION APPROVAL STEEL PLATFORMS LOT1 20UMC | 14/01/2022 | 14/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY2-96 | TT_Task | DETAIL DESIGN STEELWORK 10UEY01 | 10/01/2022 | 20/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY3-113 | TT_Task | FABRICATION DESIGN/FABRICATION/TRANSPORT STEEL STRUC 10UEY01 | 28/02/2022 | 05/06/2022 |  |  | 16 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20BZP7-200 | TT_Task | ERECTION LOOSE STEEL SUPPORTS FOR CABLE TRAYS BEFORE LIFTING OF MODULE 20UEY01 | 30/11/2021 | 13/12/2021 | 30/11/2021 | 13/12/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
SI20UEY2-97 | TT_Task | BD - SUBMISSION APPROVAL - STEEL STRUCTURE 10UEY01 | 28/02/2022 | 28/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY2-98 | TT_Task | BD - CONSENT LETTER - STEEL STRUCTURE 10UEY01 | 29/04/2022 | 26/05/2022 |  |  | 96 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY6-96 | TT_Task | MODIFY STEELWORK ON 10UEY01 | 08/06/2022 | 21/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--UBA2-112 | TT_Task | BD - AMENDMENT SUBMISSION - DETAIL DESIGN CONCRETE - UBA7xxx | 13/12/2021 | 10/01/2022 | 13/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--UBA2-113 | TT_Task | BD - AMENDMENT SUBMISSION - STEEL STRUCTURE 20UBA7xxx | 06/12/2021 | 03/02/2022 | 06/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--UBA2-114 | TT_Task | BD - CONSENT LETTER AMENDMENT - STEEL STRUCTURE 20UBA7xxx | 04/02/2022 | 03/03/2022 |  |  | 728 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--UBF2-91 | TT_Task | BD - AMENDMENT SUBMISSION - DETAIL DESIGN CONCRETE | 13/12/2021 | 09/01/2022 | 13/12/2021 |  | 184 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SP20MPB3A95 | TT_FinMile | (RFS) READY FOR SHIPMENT STEEL WORK ENCLOSURE 20MPB | 06/07/2022 | 06/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MPB4-44 | TT_Task | LOGISTICS AND CUSTOMS PREPARATION STEEL WORK ENCLOSURE 20MPB | 09/06/2022 | 06/07/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MPB3-84 | TT_FinMile | TIMES OF COMPLETION (FINAL DATA IN KANLOG) STEEL WORK ENCLOSURE 20MPB | 08/06/2022 | 08/06/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SP20MPB4A44 | TT_FinMile | (OTD-OS) ON SITE STEEL WORK ENCLOSURE 20MPB | 31/08/2022 | 31/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20MPB4-27 | TT_Task | TRANSPORT STEEL WORK ENCLOSURE 20MPB | 07/07/2022 | 31/08/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UEY2-99 | TT_Task | BD - AMENDMENT SUBMISSION - DETAIL DESIGN CONCRETE 20UEY01 | 13/01/2022 | 09/02/2022 |  |  | 328 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UHW2-53 | TT_Task | BD - RESUBMISSION APPROVAL - DETAIL DESIGN CONCRETE - 20UHW (RC PIT WALLS) | 05/11/2021 | 03/01/2022 | 05/11/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UHW2-54 | TT_Task | BD - CONSENT LETTER - DETAIL DESIGN CONCRETE - 20UHW (RC PIT WALLS) | 04/01/2022 | 30/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--ULA2-83 | TT_Task | BD - AMENDMENT SUBMISSION - DETAIL DESIGN CONCRETE RESUBMISSION 20ULA /20UHW / 20UMY (left side) | 13/12/2021 | 09/01/2022 | 13/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2A102 | TT_Task | BD - AMENDMENT SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE - TURBOSET PLINTHS | 17/12/2021 | 13/01/2022 | 17/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UMC2B79 | TT_Task | BD - AMENDMENT SUBMISSION APPROVAL - RC SUP (GROUNDSLAB / BEAM) | 17/12/2021 | 13/01/2022 | 17/12/2021 |  | 56 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2B104 | TT_Task | BD - AMENDMENT SUBMISSION - UMC MAIN FRAME incl. CRANE WALKWAY HVAC PLATFORM | 17/12/2021 | 13/01/2022 | 17/12/2021 |  | 88 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--UMC2A103 | TT_Task | BD - AMENDMENT - DETAIL DESIGN CONCRETE CEP/LDK PIT (SCREEN WALL) | 13/12/2021 | 02/01/2022 | 13/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UMY2-86 | TT_Task | BD - AMENDMENT SUBMISSION - DETAIL DESIGN CONCRETE - 20UMY (right side) | 13/12/2021 | 09/01/2022 | 13/12/2021 |  | 216 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI--URA2-110 | TT_Task | BD - AMENDMENT SUBMISSION - CAPS 20URA/URD | 13/12/2021 | 09/01/2022 | 13/12/2021 |  | 11608 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-103 | TT_Task | BD - SUBMISSION APPROVAL - DETAIL DESIGN CONCRETE WALLS 20UTG07 | 28/02/2022 | 28/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UTG2-104 | TT_Task | BD - CONSENT LETTER - DETAIL DESIGN CONCRETE WALLS 20UTG07 | 29/04/2022 | 26/05/2022 |  |  | 128 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BZP2-105 | TT_Task | DETAIL DESIGN CABLE SUPPORT SYSTEM 20UEZ02/20UQY0102/03/20UQX/20UQZ (FIRST SUBMISSION) | 15/01/2022 | 29/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI--BZP2-106 | TT_Task | DETAIL DESIGN CABLE SUPPORT SYSTEM 20UBN (FIRST SUBMISSION) | 29/01/2022 | 12/02/2022 |  |  | 11336 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B90.38 | TT_Task | CONCRETE CONSTRUCTION BUILDING FOUNDATION 20UMC- Part2 NE Anchor Bolt installation | 16/01/2022 | 22/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20UMC5B90.39 | TT_Task | CONCRETE CONSTRUCTION BUILDING FOUNDATION 20UMC- Part1 NW Anchor Bolt installation | 14/01/2022 | 20/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20ULA5-15.61 | TT_Task | CONSTRUCTION FOUNDATION 20ULA- Anchor Bolt Installation | 04/01/2022 | 08/01/2022 |  |  | 8 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
SI20ULA5-15.6 | TT_Task | CONSTRUCTION FOUNDATION 20ULA- Covid Delay of Anchor Bolt Delivery Stage 2 | 04/01/2022 | 08/01/2022 | 16/12/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml