## Sheet1
ID | TaskType | Label | PlannedStart | PlannedEnd | ActualStart | ActualEnd | Float | Status | File
MWH.06.M1010 | TT_FinMile | MWH06 Admin/COLO1 - LV3 Cx Complete (CO-66: 20-Aug-21) | 02/10/2021 | 02/10/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH.06.M1000 | TT_Mile | Project Start | 27/04/2020 | 27/04/2020 | 24/02/2020 | 24/02/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1000 | TT_Task | Mobilization | 27/04/2020 | 20/05/2020 | 06/04/2020 | 02/05/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1010 | TT_Task | Establish Access Roads / Laydown / Craft Parking / Temp Utilities | 14/05/2020 | 19/06/2020 | 24/04/2020 | 23/05/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1160 | TT_Task | Telecom-Communications Site Loop/Ductbank | 29/06/2020 | 01/10/2020 | 25/06/2020 | 08/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-P1050 | TT_FinMile | Grant County Permanent Power Required for CX | 08/01/2021 | 08/01/2021 | 08/01/2021 | 08/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1120 | TT_Task | Site Water / Fire Loop | 24/07/2020 | 07/10/2020 | 22/06/2020 | 24/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1130 | TT_Task | Site Storm | 29/06/2020 | 07/10/2020 | 15/06/2020 | 24/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1030 | TT_Task | Site Sanitary | 11/05/2020 | 24/07/2020 | 05/05/2020 | 10/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1040 | TT_Task | IWW System | 26/05/2020 | 08/08/2020 | 18/05/2020 | 10/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1880 | TT_Task | Pave HMA | 05/04/2021 | 28/04/2021 | 07/11/2020 | 09/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1890 | TT_Task | Landscape and Site Specialties | 17/05/2021 | 13/07/2021 | 03/05/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1900 | TT_Task | Site Lighting | 03/05/2021 | 02/07/2021 | 15/03/2021 |  | 120 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1300 | TT_Task | Aggregate Road Base | 19/10/2020 | 24/11/2020 | 05/10/2020 | 14/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.AD.CS1020 | TT_Task | Interior Footings - Excavate/FRP/Backfill | 05/06/2020 | 16/06/2020 | 02/06/2020 | 12/06/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.AD.CS1080 | TT_Task | MEP Undeground Rough-In (Interior) | 18/08/2020 | 04/09/2020 | 22/07/2020 | 22/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.AD.CS1000 | TT_Task | Perimeter Foundations - Excavate/FRP | 27/04/2020 | 14/05/2020 | 22/04/2020 | 20/05/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.AD.CS1090 | TT_Task | Aggregate Base Course | 31/08/2020 | 04/09/2020 | 24/08/2020 | 02/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.AD.CS1100 | TT_Task | Slab on Grade | 14/09/2020 | 24/09/2020 | 08/09/2020 | 22/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.AD.CS1030 | TT_Task | Erect PEMB Steel | 29/06/2020 | 09/07/2020 | 22/06/2020 | 01/07/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.AD.CS1050 | TT_Task | Exterior Insulated Metal Panels Installation | 18/08/2020 | 28/08/2020 | 09/07/2020 | 21/07/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.AD.CS1060 | TT_Task | Roof Panels Installation | 10/08/2020 | 17/08/2020 | 14/07/2020 | 21/07/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06AD-1016 | TT_Task | Hang Wall Partitions- Early Walls | 02/11/2020 | 23/11/2020 | 28/10/2020 | 06/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06AD-1018 | TT_Task | Early Room - Finishes | 16/11/2020 | 17/12/2020 | 09/11/2020 | 10/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06AD-1017 | TT_Task | MEP Rough-In / Wall Ceiling | 19/10/2020 | 02/11/2020 | 01/10/2020 | 17/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06AD-1024 | TT_Task | MEP Overhead | 19/10/2020 | 17/11/2020 | 28/09/2020 | 14/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06AD-1025 | TT_Task | Ceilings / Ligthing / FA Devices | 01/03/2021 | 13/04/2021 | 01/02/2021 | 30/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06AD-1019 | TT_Task | Set Electrical Equipment incl. OH raceways | 23/11/2020 | 13/01/2021 | 16/11/2020 | 29/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06AD-1020 | TT_Task | Domestic Water Piping | 23/11/2020 | 17/12/2020 | 16/11/2020 | 31/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06AD-1010 | TT_Task | Loading Dock Equipment Dock Doors | 05/05/2021 | 28/05/2021 | 26/04/2021 | 15/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06AD-1029 | TT_Task | Concrete Floor Sealing/Epoxy | 17/05/2021 | 24/05/2021 | 10/05/2021 | 15/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06AD-1027 | TT_Task | Electrical Devices Trim | 01/02/2021 | 22/02/2021 | 28/01/2021 | 30/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06AD-1022 | TT_Task | Plumbing Devices Trim | 26/07/2021 | 17/08/2021 | 28/06/2021 | 13/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06AD-1026 | TT_Task | Security Devices Trim | 01/02/2021 | 22/02/2021 | 26/01/2021 | 29/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06AD-1021 | TT_Task | Mechanical Ductwork Installation | 21/12/2020 | 15/01/2021 | 14/12/2020 | 31/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06AD-1023 | TT_Task | Mechanical Devices Trim | 01/02/2021 | 22/02/2021 | 18/01/2021 | 27/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.AD.Cx2000 | TT_Task | Electrical Equipment Yellow Tagging | 26/04/2021 | 10/05/2021 | 28/04/2021 | 14/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.CS1010 | TT_Task | Interior Footings - Excavate/FRP/Backfill | 13/06/2020 | 25/06/2020 | 02/06/2020 | 12/06/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.CS1090 | TT_Task | MEP Undeground Rough-In (Interior) | 14/08/2020 | 01/09/2020 | 03/08/2020 | 22/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.CS1000 | TT_Task | Perimeter Foundations - Excavate/FRP | 15/05/2020 | 03/06/2020 | 04/05/2020 | 15/05/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.CS1100 | TT_Task | Aggregate Base Course | 05/09/2020 | 11/09/2020 | 26/08/2020 | 02/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.CS1110 | TT_Task | Slab on Grade | 14/09/2020 | 24/09/2020 | 08/09/2020 | 22/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.CS1030 | TT_Task | Erect PEMB Steel | 29/06/2020 | 09/07/2020 | 26/06/2020 | 06/07/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.CS1050 | TT_Task | Exterior Insulated Metal Panels Installation - East Elevation | 18/08/2020 | 25/08/2020 | 13/07/2020 | 18/07/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.CS1080 | TT_Task | Downspouts Gutters | 18/08/2020 | 04/09/2020 | 27/07/2020 | 12/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.CS1070 | TT_Task | Roof Panels Installation | 10/08/2020 | 17/08/2020 | 18/07/2020 | 25/07/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.CS1060 | TT_Task | Exterior Insulated Metal Panels Installation - West Elevation | 18/08/2020 | 25/08/2020 | 13/07/2020 | 18/07/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.AD.CS1070 | TT_Task | Downspouts Gutters | 18/08/2020 | 29/08/2020 | 22/07/2020 | 03/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C1100 | TT_Task | Early Topout | 16/11/2020 | 18/11/2020 | 02/11/2020 | 09/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C1140 | TT_Task | Datahall Finishes- Ceiling Grid | 30/11/2020 | 10/12/2020 | 23/11/2020 | 07/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C1310 | TT_Task | Mechanical Corridor Finishes | 16/11/2020 | 10/12/2020 | 12/11/2020 | 20/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C1120 | TT_Task | Frame Top out | 02/11/2020 | 16/11/2020 | 26/10/2020 | 06/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C1050 | TT_Task | Exterior Equipment Pads - Electrical | 03/09/2020 | 18/09/2020 | 19/09/2020 | 10/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C1060 | TT_Task | Exterior Equipment Pads - Mechanical | 28/09/2020 | 12/10/2020 | 19/09/2020 | 13/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C1090 | TT_Task | Set Exterior Electrical OFCI Equipment - GEN | 12/10/2020 | 26/10/2020 | 12/10/2020 | 15/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C1110 | TT_Task | Set Exterior Mechanical OFCI Equipment (FC) | 30/11/2020 | 14/12/2020 | 23/11/2020 | 08/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C1030 | TT_Task | Frame wall MEPFP In wall roughin | 02/11/2020 | 06/11/2020 | 26/10/2020 | 31/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C1080 | TT_Task | Overhead MEPFP Rough-In | 31/10/2020 | 11/11/2020 | 14/10/2020 | 17/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C1170 | TT_Task | OverHead MEPFP Rough-In ( Add TCM Cross over piping HRA Level-3) | 17/11/2020 | 03/12/2020 | 19/10/2020 | 23/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C1210 | TT_Task | Electrical surface mounted Rough-in Above AHU | 07/11/2020 | 12/11/2020 | 26/10/2020 | 06/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C1220 | TT_Task | VFD'S Installation wirepull | 02/01/2021 | 15/01/2021 | 03/12/2020 | 03/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C1000 | TT_Task | Electrical Underground Rough-In | 31/08/2020 | 15/09/2020 | 14/08/2020 | 19/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C1280 | TT_Task | Steel Support for OH Conductors Cable Tray Installation | 02/01/2021 | 07/01/2021 | 18/12/2020 | 24/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C1420 | TT_Task | Generator Utility Power Pull | 01/02/2021 | 04/02/2021 | 08/01/2021 | 20/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C1410 | TT_Task | Electrical Feeders to Mechanical Equipment Pull-Test-Term | 22/03/2021 | 14/04/2021 | 01/03/2021 | 18/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C1460 | TT_Task | Pull/term/Test PDU to Power bus | 01/03/2021 | 24/03/2021 | 18/03/2021 | 17/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C1070 | TT_Task | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel Pipe Steel Supports) | 30/11/2020 | 03/12/2020 | 09/11/2020 | 12/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C1130 | TT_Task | Mechanical Equipment Piping Connections | 01/02/2021 | 15/02/2021 | 13/01/2021 | 29/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C1020 | TT_Task | Mechanical/Plumbing Underground Rough-In | 31/08/2020 | 15/09/2020 | 21/08/2020 | 08/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C1160 | TT_Task | Fire Alarm Installation | 11/01/2021 | 25/01/2021 | 04/01/2021 | 29/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C1440 | TT_Task | Controls Installation | 05/03/2021 | 24/03/2021 | 04/01/2021 | 30/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C1470 | TT_Task | Ligthing Installation | 01/06/2021 | 15/06/2021 | 04/05/2021 | 07/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C1230 | TT_Task | AHU/DOAS Equipment Setting | 02/01/2021 | 07/01/2021 | 26/11/2020 | 04/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C1290 | TT_Task | Hydronic Piping Installation | 01/03/2021 | 13/03/2021 | 19/02/2021 | 20/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C1370 | TT_Task | Floor Drain System Installation | 30/06/2021 | 15/07/2021 | 21/06/2021 | 26/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C1380 | TT_Task | Toilet Piping Installation / DW | 30/06/2021 | 15/07/2021 | 01/06/2021 | 01/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C1320 | TT_Task | Controls Installation | 26/03/2021 | 16/04/2021 | 10/03/2021 | 26/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C1180 | TT_Task | Fire Riser Installation | 01/03/2021 | 13/03/2021 | 08/02/2021 | 20/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C1190 | TT_Task | Fire Alarm System | 30/04/2021 | 14/05/2021 | 01/04/2021 | 16/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C1270 | TT_Task | PDU's Installation | 01/03/2021 | 03/03/2021 | 04/02/2021 | 06/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C1200 | TT_Task | Cable Tray Installation | 02/01/2021 | 15/01/2021 | 28/12/2020 | 18/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C1400 | TT_Task | Pull / Term / Test Conductors ( MER to PDU) | 05/04/2021 | 29/04/2021 | 26/03/2021 | 29/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C1330 | TT_Task | EPMS Pull Wire / Term / Test | 01/04/2021 | 15/04/2021 | 11/03/2021 | 03/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C1390 | TT_Task | BMS Pull Wire / Term / Test | 01/04/2021 | 15/04/2021 | 11/03/2021 | 03/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C1450 | TT_Task | Light Fixtures Installation | 05/05/2021 | 11/05/2021 | 26/04/2021 | 28/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C1340 | TT_Task | Controls Installation | 26/03/2021 | 03/04/2021 | 08/03/2021 | 07/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C1350 | TT_Task | Fire Alarm System | 30/04/2021 | 12/05/2021 | 01/04/2021 | 14/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.Cx2020 | TT_Task | Network Startup | 01/06/2021 | 11/06/2021 | 30/04/2021 | 12/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.Cx2060 | TT_Task | EPMS Checkout / Point to Point | 06/07/2021 | 16/07/2021 | 30/06/2021 | 06/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.Cx2000 | TT_Task | Electrical Equipment Yellow Tagging (Field Terminated equipment) | 01/06/2021 | 14/06/2021 | 11/05/2021 | 30/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C1300 | TT_Task | Assemble MER Complete Shipping Split (SE) | 02/01/2021 | 13/01/2021 | 17/12/2020 | 07/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.AD.Cx2010 | TT_Task | Admin/Colo-1 Network Startup | 17/05/2021 | 24/05/2021 | 30/04/2021 | 07/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.AD.Cx2020 | TT_Task | EPMS Checkout / Point to Point | 30/06/2021 | 13/07/2021 | 30/06/2021 | 13/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.CS1010 | TT_Task | Interior Footings - Excavate/FRP/Backfill | 08/07/2020 | 20/07/2020 | 09/06/2020 | 20/06/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.CS1070 | TT_Task | MEP Undeground Rough-In (Interior) | 31/08/2020 | 18/09/2020 | 19/08/2020 | 21/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.CS1000 | TT_Task | Perimeter Foundations - Excavate/FRP/Backfill | 22/06/2020 | 09/07/2020 | 11/05/2020 | 16/06/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.CS1080 | TT_Task | Aggregate Base Course | 19/10/2020 | 26/10/2020 | 01/10/2020 | 07/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.CS1090 | TT_Task | Slab on Grade | 19/10/2020 | 30/10/2020 | 05/10/2020 | 07/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.CS1020 | TT_Task | Erect PEMB Steel | 10/08/2020 | 25/08/2020 | 07/07/2020 | 22/07/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.CS1040 | TT_Task | Exterior Insulated Metal Panels Installation | 18/08/2020 | 01/09/2020 | 31/07/2020 | 13/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.CS1060 | TT_Task | Downspouts Gutters | 05/09/2020 | 24/09/2020 | 10/08/2020 | 17/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.CS1050 | TT_Task | Roof Panels Installation | 10/08/2020 | 26/08/2020 | 31/07/2020 | 14/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.CS1000 | TT_Task | Interior Footings - Excavate/FRP/Backfill | 08/07/2020 | 20/07/2020 | 24/06/2020 | 09/07/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.CS1070 | TT_Task | MEP Undeground Rough-In (Interior) | 19/10/2020 | 05/11/2020 | 05/10/2020 | 15/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.CS1010 | TT_Task | Perimeter Foundations - Excavate/FRP/Backfill | 22/06/2020 | 09/07/2020 | 16/06/2020 | 18/07/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.CS1080 | TT_Task | Aggregate Base Course | 06/11/2020 | 12/11/2020 | 15/10/2020 | 22/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.CS1090 | TT_Task | Slab on Grade | 02/11/2020 | 12/11/2020 | 23/10/2020 | 28/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.CS1020 | TT_Task | Erect PEMB Steel | 10/08/2020 | 25/08/2020 | 23/07/2020 | 06/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.CS1040 | TT_Task | Exterior Insulated Metal Panels Installation | 08/09/2020 | 22/09/2020 | 15/08/2020 | 22/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.CS1060 | TT_Task | Downspouts Gutters | 16/09/2020 | 22/09/2020 | 02/09/2020 | 12/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.CS1050 | TT_Task | Roof Panels Installation | 08/09/2020 | 24/09/2020 | 18/08/2020 | 01/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.CS1010 | TT_Task | Interior Footings - Excavate/FRP/Backfill | 29/08/2020 | 10/09/2020 | 25/07/2020 | 06/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.CS1070 | TT_Task | MEP Undeground Rough-In (Interior) | 31/10/2020 | 18/11/2020 | 05/10/2020 | 15/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.CS1000 | TT_Task | Perimeter Foundations - Excavate/FRP/Backfill | 06/07/2020 | 23/07/2020 | 23/06/2020 | 30/07/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.CS1080 | TT_Task | Aggregate Base Course | 11/11/2020 | 18/11/2020 | 15/10/2020 | 29/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.CS1090 | TT_Task | Slab on Grade | 02/11/2020 | 12/11/2020 | 28/10/2020 | 04/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.CS1020 | TT_Task | Erect PEMB Steel | 10/08/2020 | 25/08/2020 | 08/08/2020 | 24/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.CS1040 | TT_Task | Exterior Insulated Metal Panels Installation | 31/08/2020 | 15/09/2020 | 24/08/2020 | 30/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.CS1060 | TT_Task | Downspouts Gutters | 31/10/2020 | 18/11/2020 | 07/09/2020 | 15/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.CS1050 | TT_Task | Roof Panels Installation | 03/09/2020 | 21/09/2020 | 27/08/2020 | 13/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
A1170 | TT_Mile | Phase 1A - Funding Release | 24/02/2020 | 24/02/2020 | 24/02/2020 | 24/02/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C3090 | TT_Task | Early Topout | 19/11/2020 | 21/11/2020 | 10/11/2020 | 12/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C3120 | TT_Task | Datahall Finishes- Ceiling Grid | 30/11/2020 | 11/12/2020 | 25/11/2020 | 10/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C3370 | TT_Task | Mechanical Corridor Finishes | 24/11/2020 | 18/12/2020 | 17/11/2020 | 30/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C3110 | TT_Task | Frame Top out | 02/11/2020 | 16/11/2020 | 26/10/2020 | 11/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C3050 | TT_Task | Exterior Equipment Pads - Electrical | 28/09/2020 | 12/10/2020 | 19/09/2020 | 14/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C3060 | TT_Task | Exterior Equipment Pads - Mechanical | 16/10/2020 | 30/10/2020 | 19/09/2020 | 14/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C3080 | TT_Task | Set Exterior Electrical OFCI Equipment - GEN | 30/11/2020 | 14/12/2020 | 13/11/2020 | 13/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C3130 | TT_Task | Set Exterior Mechanical OFCI Equipment (FC) | 02/01/2021 | 15/01/2021 | 30/11/2020 | 09/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C3010 | TT_Task | Frame wall MEPFP In wall roughin | 07/11/2020 | 12/11/2020 | 26/10/2020 | 04/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C3070 | TT_Task | Overhead MEPFP Rough-In | 02/11/2020 | 12/11/2020 | 20/10/2020 | 31/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C3200 | TT_Task | OverHead MEPFP Rough-In | 02/11/2020 | 16/11/2020 | 20/10/2020 | 31/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C3270 | TT_Task | Electrical surface mounted Rough-in Above AHU | 16/11/2020 | 20/11/2020 | 02/11/2020 | 16/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C3280 | TT_Task | VFD'S Installation Wiring | 26/04/2021 | 10/05/2021 | 12/04/2021 | 24/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C3000 | TT_Task | Electrical Underground Rough-In | 03/09/2020 | 18/09/2020 | 29/08/2020 | 19/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C3250 | TT_Task | Steel Support for OH Conductors Cable Tray Installation | 18/01/2021 | 22/01/2021 | 07/01/2021 | 13/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C3410 | TT_Task | Generator Utility Power Pull | 02/03/2021 | 05/03/2021 | 08/02/2021 | 26/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C3390 | TT_Task | Electrical Feeders to Mechanical Equipment Pull-Test-Term | 22/03/2021 | 14/04/2021 | 04/03/2021 | 31/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C3470 | TT_Task | Pull/term/Test PDU to Power bus | 26/04/2021 | 19/05/2021 | 31/03/2021 | 04/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C3100 | TT_Task | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel Pipe Steel Supports) | 30/11/2020 | 03/12/2020 | 09/11/2020 | 12/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C3150 | TT_Task | Mechanical Equipment Piping Connections | 15/03/2021 | 22/03/2021 | 17/02/2021 | 24/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C3030 | TT_Task | Mechanical/Plumbing Underground Rough-In | 28/09/2020 | 12/10/2020 | 21/08/2020 | 08/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C3180 | TT_Task | Fire Alarm Installation | 01/02/2021 | 15/02/2021 | 18/01/2021 | 30/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C3450 | TT_Task | Controls Installation | 09/03/2021 | 27/03/2021 | 18/01/2021 | 07/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C3420 | TT_Task | Ligthing Installation | 01/06/2021 | 15/06/2021 | 04/05/2021 | 15/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C3290 | TT_Task | AHU/DOAS Equipment Setting | 02/01/2021 | 07/01/2021 | 07/12/2020 | 17/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C3340 | TT_Task | Hydronic Piping Installation | 01/03/2021 | 13/03/2021 | 22/02/2021 | 23/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C3430 | TT_Task | Floor Drain System Installation | 22/09/2021 | 06/10/2021 | 21/06/2021 | 26/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C3440 | TT_Task | Toilet Piping Installation / DW | 30/06/2021 | 15/07/2021 | 01/06/2021 | 01/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C3230 | TT_Task | Controls Installation | 15/04/2021 | 06/05/2021 | 01/03/2021 | 26/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C3160 | TT_Task | Fire Riser Installation | 30/11/2020 | 30/11/2020 | 28/11/2020 | 28/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C3170 | TT_Task | Fire Alarm System | 15/05/2021 | 29/05/2021 | 01/04/2021 | 16/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C3240 | TT_Task | PDU's Installation | 08/03/2021 | 10/03/2021 | 26/02/2021 | 09/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C3190 | TT_Task | Cable Tray Installation | 01/02/2021 | 16/02/2021 | 19/01/2021 | 04/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C3360 | TT_Task | Pull / Term / Test Conductors ( MER to PDU) | 26/04/2021 | 19/05/2021 | 16/04/2021 | 14/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C3330 | TT_Task | EPMS Pull Wire / Term / Test | 01/04/2021 | 15/04/2021 | 13/03/2021 | 03/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C3380 | TT_Task | BMS Pull Wire / Term / Test | 01/04/2021 | 15/04/2021 | 13/03/2021 | 03/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C3400 | TT_Task | Light Fixtures Installation | 12/05/2021 | 18/05/2021 | 26/04/2021 | 29/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C3310 | TT_Task | Controls Installation | 06/04/2021 | 15/04/2021 | 01/03/2021 | 07/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C3320 | TT_Task | Fire Alarm System | 04/05/2021 | 14/05/2021 | 01/04/2021 | 14/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.Cx2070 | TT_Task | Network Startup | 01/06/2021 | 11/06/2021 | 01/06/2021 | 11/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.Cx2150 | TT_Task | EPMS Checkout / Point to Point | 30/06/2021 | 13/07/2021 | 06/07/2021 | 06/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.Cx2030 | TT_Task | Electrical Equipment Yellow Tagging (Field Terminated equipment) | 10/06/2021 | 22/06/2021 | 29/05/2021 | 30/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C3300 | TT_Task | Assemble MER Complete Shipping Split (SE) | 11/01/2021 | 23/01/2021 | 07/01/2021 | 21/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C2100 | TT_Task | Early Topout | 16/11/2020 | 18/11/2020 | 02/11/2020 | 09/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C2130 | TT_Task | Datahall Finishes- Ceiling Grid | 03/12/2020 | 15/12/2020 | 23/11/2020 | 07/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C2290 | TT_Task | Mechanical Corridor Finishes | 24/11/2020 | 18/12/2020 | 20/11/2020 | 20/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C2110 | TT_Task | Frame Top out | 02/11/2020 | 16/11/2020 | 26/10/2020 | 06/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C2050 | TT_Task | Exterior Equipment Pads - Electrical | 05/09/2020 | 21/09/2020 | 21/09/2020 | 02/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C2060 | TT_Task | Exterior Equipment Pads - Mechanical | 05/10/2020 | 17/10/2020 | 21/09/2020 | 19/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C2090 | TT_Task | Set Exterior Electrical OFCI Equipment - GEN | 26/10/2020 | 07/11/2020 | 12/10/2020 | 13/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C2120 | TT_Task | Set Exterior Mechanical OFCI Equipment (FC) | 30/11/2020 | 14/12/2020 | 30/11/2020 | 09/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C2030 | TT_Task | Frame wall MEPFP In wall roughin | 02/11/2020 | 06/11/2020 | 26/10/2020 | 02/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C2080 | TT_Task | Overhead MEPFP Rough-In | 31/10/2020 | 11/11/2020 | 12/10/2020 | 16/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C2160 | TT_Task | OverHead MEPFP Rough-In | 17/11/2020 | 03/12/2020 | 19/10/2020 | 23/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C2190 | TT_Task | Electrical surface mounted Rough-in Above AHU | 16/11/2020 | 20/11/2020 | 02/11/2020 | 16/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C2200 | TT_Task | VFD'S Installation Wiring | 02/01/2021 | 15/01/2021 | 28/12/2020 | 12/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C2000 | TT_Task | Electrical Underground Rough-In | 14/08/2020 | 28/08/2020 | 06/08/2020 | 08/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C2280 | TT_Task | Steel Support for OH Conductors Cable Tray Installation | 11/01/2021 | 15/01/2021 | 04/01/2021 | 07/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C2430 | TT_Task | Generator Utility Power Test-Term | 01/03/2021 | 09/03/2021 | 27/02/2021 | 08/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C2420 | TT_Task | Electrical Feeders to Mechanical Equipment Pull-Test-Term | 22/03/2021 | 14/04/2021 | 01/03/2021 | 18/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C2460 | TT_Task | Pull/term/Test PDU to Power bus | 31/03/2021 | 23/04/2021 | 20/03/2021 | 17/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C2070 | TT_Task | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel Pipe Steel Supports) | 30/11/2020 | 03/12/2020 | 09/11/2020 | 13/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C2140 | TT_Task | Mechanical Equipment Piping Connections | 08/03/2021 | 13/03/2021 | 09/02/2021 | 20/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C2020 | TT_Task | Mechanical/Plumbing Underground Rough-In | 31/08/2020 | 15/09/2020 | 21/08/2020 | 08/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C2410 | TT_Task | Fire Alarm Installation | 18/02/2021 | 04/03/2021 | 04/01/2021 | 01/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C2450 | TT_Task | Controls Installation | 06/03/2021 | 25/03/2021 | 04/01/2021 | 10/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C2470 | TT_Task | Ligthing Installation | 16/06/2021 | 29/06/2021 | 24/05/2021 | 21/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C2210 | TT_Task | AHU/DOAS Equipment Setting | 02/01/2021 | 07/01/2021 | 23/11/2020 | 04/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C2260 | TT_Task | Hydronic Piping Installation | 01/03/2021 | 13/03/2021 | 19/02/2021 | 20/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C2350 | TT_Task | Floor Drain System Installation | 22/09/2021 | 06/10/2021 | 21/06/2021 | 26/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C2360 | TT_Task | Toilet Piping Installation / DW | 30/06/2021 | 15/07/2021 | 01/06/2021 | 01/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C2300 | TT_Task | Controls Installation | 13/04/2021 | 04/05/2021 | 01/03/2021 | 26/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C2170 | TT_Task | Fire Riser Installation | 30/11/2020 | 30/11/2020 | 28/11/2020 | 28/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C2220 | TT_Task | Fire Alarm System | 30/04/2021 | 14/05/2021 | 01/04/2021 | 16/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C2250 | TT_Task | PDU's Installation | 01/03/2021 | 03/03/2021 | 04/02/2021 | 06/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C2180 | TT_Task | Cable Tray Installation | 02/01/2021 | 15/01/2021 | 23/12/2020 | 18/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C2380 | TT_Task | Pull / Term / Test Conductors ( MER to PDU) | 01/04/2021 | 26/04/2021 | 29/03/2021 | 05/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C2310 | TT_Task | EPMS Pull Wire / Term / Test | 01/04/2021 | 15/04/2021 | 15/03/2021 | 03/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C2370 | TT_Task | BMS Pull Wire / Term / Test | 01/04/2021 | 15/04/2021 | 15/03/2021 | 03/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C2400 | TT_Task | Light Fixtures Installation | 11/05/2021 | 17/05/2021 | 26/04/2021 | 28/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C2320 | TT_Task | Controls Installation | 06/04/2021 | 15/04/2021 | 01/03/2021 | 07/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C2330 | TT_Task | Fire Alarm System | 06/05/2021 | 17/05/2021 | 01/04/2021 | 14/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.Cx2040 | TT_Task | Network Startup | 30/06/2021 | 13/07/2021 | 01/06/2021 | 13/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.Cx2090 | TT_Task | EPMS Checkout / Point to Point | 06/07/2021 | 16/07/2021 | 30/06/2021 | 06/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.Cx2010 | TT_Task | Electrical Equipment Yellow Tagging (Field Terminated equipment) | 01/06/2021 | 11/06/2021 | 19/05/2021 | 30/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C2340 | TT_Task | Assemble MER Complete Shipping Split (SE) | 11/01/2021 | 23/01/2021 | 23/12/2020 | 09/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C4100 | TT_Task | Early Topout | 19/11/2020 | 21/11/2020 | 10/11/2020 | 12/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C4130 | TT_Task | Datahall Finishes- Ceiling Grid | 21/12/2020 | 06/01/2021 | 25/11/2020 | 10/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C4350 | TT_Task | Mechanical Corridor Finishes | 02/01/2021 | 07/01/2021 | 17/11/2020 | 30/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C4110 | TT_Task | Frame Top out | 02/11/2020 | 16/11/2020 | 26/10/2020 | 11/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C4050 | TT_Task | Exterior Equipment Pads - Electrical | 28/09/2020 | 12/10/2020 | 21/09/2020 | 21/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C4060 | TT_Task | Exterior Equipment Pads - Mechanical | 28/09/2020 | 12/10/2020 | 22/09/2020 | 21/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C4090 | TT_Task | Set Exterior Electrical OFCI Equipment - GEN | 02/11/2020 | 16/11/2020 | 19/10/2020 | 22/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C4120 | TT_Task | Set Exterior Mechanical OFCI Equipment (FC) | 02/01/2021 | 15/01/2021 | 07/12/2020 | 09/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C4010 | TT_Task | Frame wall MEPFP In wall roughin | 07/11/2020 | 12/11/2020 | 26/10/2020 | 07/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C4070 | TT_Task | Overhead MEPFP Rough-In | 02/11/2020 | 12/11/2020 | 20/10/2020 | 31/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C4190 | TT_Task | OverHead MEPFP Rough-In | 02/11/2020 | 16/11/2020 | 20/10/2020 | 31/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C4230 | TT_Task | Electrical surface mounted Rough-in Above AHU | 16/11/2020 | 20/11/2020 | 02/11/2020 | 16/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C4240 | TT_Task | VFD'S Installation Wiring | 26/04/2021 | 10/05/2021 | 12/04/2021 | 24/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C4000 | TT_Task | Electrical Underground Rough-In | 05/09/2020 | 21/09/2020 | 29/08/2020 | 19/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C4280 | TT_Task | Steel Support for OH Conductors Cable Tray Installation | 11/01/2021 | 15/01/2021 | 11/01/2021 | 14/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C4440 | TT_Task | Generator Utility Power Test-Term | 15/03/2021 | 17/03/2021 | 01/03/2021 | 03/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C4410 | TT_Task | Electrical Feeders to Mechanical Equipment Pull-Test-Term | 07/04/2021 | 30/04/2021 | 24/03/2021 | 13/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C4470 | TT_Task | Pull/term/Test PDU to Power bus | 03/05/2021 | 26/05/2021 | 14/04/2021 | 04/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C4080 | TT_Task | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel Pipe Steel Supports) | 30/11/2020 | 03/12/2020 | 09/11/2020 | 12/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C4150 | TT_Task | Mechanical Equipment Piping Connections | 01/03/2021 | 06/03/2021 | 04/02/2021 | 16/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C4030 | TT_Task | Mechanical/Plumbing Underground Rough-In | 14/09/2020 | 26/09/2020 | 14/09/2020 | 22/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C4170 | TT_Task | Fire Alarm Installation | 30/04/2021 | 14/05/2021 | 01/04/2021 | 16/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C4450 | TT_Task | Controls Installation | 15/04/2021 | 04/05/2021 | 01/03/2021 | 07/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C4480 | TT_Task | Ligthing Installation | 16/06/2021 | 29/06/2021 | 24/05/2021 | 29/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C4250 | TT_Task | AHU/DOAS Equipment Setting | 02/01/2021 | 07/01/2021 | 07/12/2020 | 17/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C4320 | TT_Task | Hydronic Piping Installation | 01/03/2021 | 13/03/2021 | 22/02/2021 | 23/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C4420 | TT_Task | Floor Drain System Installation | 22/09/2021 | 06/10/2021 | 21/06/2021 | 26/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C4430 | TT_Task | Toilet Piping Installation / DW | 30/06/2021 | 15/07/2021 | 01/06/2021 | 01/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C4290 | TT_Task | Controls Installation | 06/04/2021 | 27/04/2021 | 01/03/2021 | 07/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C4160 | TT_Task | Fire Riser Installation | 30/11/2020 | 30/11/2020 | 28/11/2020 | 28/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C4200 | TT_Task | Fire Alarm System | 15/05/2021 | 29/05/2021 | 01/04/2021 | 16/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C4220 | TT_Task | PDU's Installation | 08/03/2021 | 10/03/2021 | 26/02/2021 | 01/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C4180 | TT_Task | Cable Tray Installation | 01/02/2021 | 15/02/2021 | 20/01/2021 | 04/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C4360 | TT_Task | Pull / Term / Test Conductors ( MER to PDU) | 03/05/2021 | 27/05/2021 | 15/04/2021 | 20/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C4330 | TT_Task | EPMS Pull Wire / Term / Test | 01/04/2021 | 15/04/2021 | 13/03/2021 | 03/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C4380 | TT_Task | BMS Pull Wire / Term / Test | 01/04/2021 | 15/04/2021 | 13/03/2021 | 03/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C4390 | TT_Task | Light Fixtures Installation | 21/05/2021 | 28/05/2021 | 26/04/2021 | 29/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C4300 | TT_Task | Controls Installation | 06/04/2021 | 15/04/2021 | 25/01/2021 | 07/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C4310 | TT_Task | Fire Alarm System | 21/05/2021 | 03/06/2021 | 01/04/2021 | 14/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.Cx2100 | TT_Task | Network Startup | 30/06/2021 | 13/07/2021 | 01/06/2021 | 13/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.Cx2190 | TT_Task | EPMS Checkout / Point to Point | 06/07/2021 | 16/07/2021 | 30/06/2021 | 06/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.Cx2050 | TT_Task | Electrical Equipment Yellow Tagging (Field Terminated equipment) | 07/07/2021 | 17/07/2021 | 21/06/2021 | 30/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.Cx3040 | TT_Task | Level 3 Cx - ADMIN AND COLO1 | 17/09/2021 | 01/10/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.Cx3030 | TT_Task | Load Bank IR Scan | 15/09/2021 | 06/10/2021 | 13/08/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C4340 | TT_Task | Assemble MER Complete Shipping Split (SE) | 11/01/2021 | 23/01/2021 | 09/01/2021 | 22/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.Cx4000 | TT_Task | COLO 1 Level 4 Level 5 IST | 02/10/2021 | 29/10/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-1383 | TT_Task | Lead Time for PEMB | 19/02/2020 | 18/06/2020 | 24/02/2020 | 18/06/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C1110 | TT_Task | Hang drywall / Mud / Tape | 02/01/2021 | 11/01/2021 | 01/12/2020 | 09/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C1140 | TT_Task | Datahall Finishes - Ceiling Grid | 02/01/2021 | 11/01/2021 | 18/12/2020 | 31/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C1310 | TT_Task | Mechanical Corridor Finishes | 11/01/2021 | 12/01/2021 | 28/12/2020 | 04/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C1100 | TT_Task | Frame Top out | 23/11/2020 | 04/12/2020 | 17/11/2020 | 17/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C1040 | TT_Task | Exterior Equipment Pads - Electrical | 14/12/2020 | 30/12/2020 | 14/11/2020 | 17/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C1060 | TT_Task | Exterior Equipment Pads - Mechanical | 21/12/2020 | 08/01/2021 | 02/11/2020 | 06/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C1080 | TT_Task | Set Exterior Electrical OFCI Equipment - GEN | 09/01/2021 | 23/01/2021 | 28/12/2020 | 29/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C1120 | TT_Task | Set Exterior Mechanical OFCI Equipment (FC) | 11/01/2021 | 25/01/2021 | 07/12/2020 | 18/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C1050 | TT_Task | Frame wall MEPFP In wall roughin | 16/11/2020 | 20/11/2020 | 16/11/2020 | 19/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C1090 | TT_Task | Overhead MEPFP Rough-In | 02/11/2020 | 12/11/2020 | 26/10/2020 | 14/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C1160 | TT_Task | OverHead MEPFP Rough-In | 19/11/2020 | 07/12/2020 | 26/10/2020 | 19/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C1200 | TT_Task | Electrical surface mounted Rough-in Above AHU | 12/12/2020 | 17/12/2020 | 16/11/2020 | 25/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C1150 | TT_Task | VFD'S Installation Wiring | 01/06/2021 | 15/06/2021 | 24/05/2021 | 07/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C1010 | TT_Task | Electrical Underground Rough-In | 02/11/2020 | 16/11/2020 | 28/09/2020 | 07/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C1290 | TT_Task | Steel Support for OH Conductors Cable Tray Installation | 01/03/2021 | 05/03/2021 | 05/02/2021 | 12/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C1410 | TT_Task | Generator Utility Power Test-Term | 30/04/2021 | 10/05/2021 | 31/03/2021 | 16/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C1430 | TT_Task | Electrical Feeders to Mechanical Equipment Pull-Test-Term | 30/04/2021 | 25/05/2021 | 16/04/2021 | 10/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C1460 | TT_Task | Pull/term/Test PDU to Power bus | 02/06/2021 | 23/06/2021 | 11/05/2021 | 02/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C1070 | TT_Task | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel Pipe Steel Supports) | 11/01/2021 | 14/01/2021 | 04/01/2021 | 06/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C1130 | TT_Task | Mechanical Equipment Piping Connections | 22/03/2021 | 27/03/2021 | 03/03/2021 | 10/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C1000 | TT_Task | Mechanical/Plumbing Underground Rough-In | 02/11/2020 | 16/11/2020 | 28/09/2020 | 07/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C1190 | TT_Task | Fire Alarm Installation | 11/05/2021 | 25/05/2021 | 01/04/2021 | 16/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C1450 | TT_Task | Controls Installation | 28/06/2021 | 13/07/2021 | 01/06/2021 | 15/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C1350 | TT_Task | Ligthing Installation | 23/07/2021 | 06/08/2021 | 01/06/2021 | 16/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C1210 | TT_Task | AHU/DOAS Equipment Setting | 01/03/2021 | 05/03/2021 | 01/02/2021 | 05/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C1260 | TT_Task | Hydronic Piping Installation | 03/05/2021 | 03/05/2021 | 03/05/2021 | 14/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C1360 | TT_Task | Floor Drain System Installation | 30/06/2021 | 15/07/2021 | 01/06/2021 | 15/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C1370 | TT_Task | Toilet Piping Installation / DW | 01/06/2021 | 15/06/2021 | 01/05/2021 | 15/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C1320 | TT_Task | Controls Installation | 08/06/2021 | 29/06/2021 | 08/06/2021 | 22/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C1170 | TT_Task | Fire Riser Installation | 01/06/2021 | 15/06/2021 | 01/05/2021 | 15/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C1220 | TT_Task | Fire Alarm System | 15/05/2021 | 29/05/2021 | 01/04/2021 | 16/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C1300 | TT_Task | PDU's Installation | 26/03/2021 | 29/03/2021 | 19/03/2021 | 22/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C1230 | TT_Task | Cable Tray Installation | 01/03/2021 | 13/03/2021 | 05/02/2021 | 22/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C1390 | TT_Task | Pull / Term / Test Conductors ( MER to PDU) | 03/06/2021 | 28/06/2021 | 12/05/2021 | 16/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C1280 | TT_Task | EPMS Pull Wire / Term / Test | 10/06/2021 | 24/06/2021 | 20/05/2021 | 24/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C1340 | TT_Task | BMS Pull Wire / Term / Test | 10/06/2021 | 24/06/2021 | 20/05/2021 | 24/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C1420 | TT_Task | Light Fixtures Installation | 01/06/2021 | 15/06/2021 | 30/04/2021 | 15/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C1400 | TT_Task | Controls Installation | 01/06/2021 | 15/06/2021 | 01/06/2021 | 15/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C1240 | TT_Task | Fire Alarm System | 04/05/2021 | 20/05/2021 | 01/04/2021 | 16/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.Cx2040 | TT_Task | Network Startup | 31/08/2021 | 13/09/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.Cx2090 | TT_Task | EPMS Checkout / Point to Point | 31/08/2021 | 13/09/2021 |  |  | 200 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.Cx2010 | TT_Task | Electrical Equipment Yellow Tagging (Field Terminated equipment) | 04/08/2021 | 16/08/2021 | 21/07/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C1330 | TT_Task | Assemble MER Complete Shipping Split (SE) | 01/03/2021 | 11/03/2021 | 05/02/2021 | 10/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C3110 | TT_Task | Hang drywall / Mud / Tape | 06/01/2021 | 11/01/2021 | 10/12/2020 | 31/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C3130 | TT_Task | Datahall Finishes - Ceiling Grid | 02/01/2021 | 11/01/2021 | 31/12/2020 | 07/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C3350 | TT_Task | Mechanical Corridor Finishes | 28/12/2020 | 04/01/2021 | 28/12/2020 | 04/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C3100 | TT_Task | Frame Top out | 02/01/2021 | 12/01/2021 | 07/12/2020 | 17/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C3050 | TT_Task | Exterior Equipment Pads - Electrical | 14/12/2020 | 30/12/2020 | 14/11/2020 | 19/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C3060 | TT_Task | Exterior Equipment Pads - Mechanical | 21/12/2020 | 08/01/2021 | 16/11/2020 | 19/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C3080 | TT_Task | Set Exterior Electrical OFCI Equipment - GEN | 01/02/2021 | 05/02/2021 | 19/01/2021 | 19/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C3120 | TT_Task | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | 11/01/2021 | 25/01/2021 | 04/01/2021 | 08/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C3030 | TT_Task | Frame wall MEPFP In wall roughin | 23/11/2020 | 01/12/2020 | 19/11/2020 | 09/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C3090 | TT_Task | Overhead MEPFP Rough-In | 06/11/2020 | 18/11/2020 | 28/10/2020 | 06/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C3190 | TT_Task | OverHead MEPFP Rough-In | 08/12/2020 | 21/12/2020 | 28/10/2020 | 19/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C3240 | TT_Task | Electrical surface mounted Rough-in Above AHU | 14/12/2020 | 18/12/2020 | 20/11/2020 | 25/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C3140 | TT_Task | VFD'S Installation Wiring | 01/06/2021 | 15/06/2021 | 01/05/2021 | 15/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C3010 | TT_Task | Electrical Underground Rough-In | 02/11/2020 | 16/11/2020 | 21/09/2020 | 06/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C3270 | TT_Task | Steel Support for OH Conductors Cable Tray Installation | 29/03/2021 | 02/04/2021 | 03/03/2021 | 17/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C3380 | TT_Task | Generator Utility Power Test-Term | 06/05/2021 | 14/05/2021 | 13/04/2021 | 24/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C3430 | TT_Task | Electrical Feeders to Mechanical Equipment Pull-Test-Term | 30/04/2021 | 26/05/2021 | 29/04/2021 | 25/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C3450 | TT_Task | Pull/term/Test PDU to Power bus | 08/06/2021 | 29/06/2021 | 26/05/2021 | 17/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C3070 | TT_Task | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel Pipe Steel Supports) | 11/01/2021 | 14/01/2021 | 04/01/2021 | 06/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C3150 | TT_Task | Mechanical Equipment Piping Connections | 22/03/2021 | 27/03/2021 | 09/03/2021 | 16/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C3000 | TT_Task | Mechanical/Plumbing Underground Rough-In | 02/11/2020 | 16/11/2020 | 28/09/2020 | 06/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C3180 | TT_Task | Fire Alarm Installation | 26/05/2021 | 09/06/2021 | 01/04/2021 | 16/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C3440 | TT_Task | Controls Installation | 28/06/2021 | 13/07/2021 | 01/06/2021 | 15/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C3390 | TT_Task | Ligthing Installation | 07/08/2021 | 21/08/2021 | 17/06/2021 | 29/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C3250 | TT_Task | AHU/DOAS Equipment Setting | 01/03/2021 | 05/03/2021 | 23/02/2021 | 26/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C3320 | TT_Task | Hydronic Piping Installation | 01/06/2021 | 15/06/2021 | 01/05/2021 | 15/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C3400 | TT_Task | Floor Drain System Installation | 30/06/2021 | 15/07/2021 | 01/06/2021 | 15/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C3410 | TT_Task | Toilet Piping Installation / DW | 30/06/2021 | 15/07/2021 | 17/05/2021 | 01/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C3300 | TT_Task | Controls Installation | 16/06/2021 | 08/07/2021 | 16/05/2021 | 08/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C3160 | TT_Task | Fire Riser Installation | 30/11/2020 | 30/11/2020 | 28/11/2020 | 28/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C3200 | TT_Task | Fire Alarm System | 30/04/2021 | 14/05/2021 | 01/04/2021 | 16/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C3290 | TT_Task | PDU's Installation | 01/06/2021 | 03/06/2021 | 03/05/2021 | 05/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C3210 | TT_Task | Cable Tray Installation | 01/03/2021 | 13/03/2021 | 23/02/2021 | 08/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C3360 | TT_Task | Pull / Term / Test Conductors ( MER to PDU) | 08/06/2021 | 02/07/2021 | 27/05/2021 | 22/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C3280 | TT_Task | EPMS Pull Wire / Term / Test | 28/06/2021 | 13/07/2021 | 05/06/2021 | 19/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C3330 | TT_Task | BMS Pull Wire / Term / Test | 28/06/2021 | 13/07/2021 | 05/06/2021 | 19/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C3420 | TT_Task | Light Fixtures Installation | 23/06/2021 | 08/07/2021 | 23/06/2021 | 26/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C3370 | TT_Task | Controls Installation | 01/06/2021 | 15/06/2021 | 01/06/2021 | 15/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C3220 | TT_Task | Fire Alarm System | 21/05/2021 | 03/06/2021 | 01/04/2021 | 16/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.Cx2100 | TT_Task | Network Startup | 31/08/2021 | 13/09/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.Cx2160 | TT_Task | EPMS Checkout / Point to Point | 14/09/2021 | 24/09/2021 |  |  | 100 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.Cx2050 | TT_Task | Electrical Equipment Yellow Tagging (Field Terminated equipment) | 07/09/2021 | 17/09/2021 | 05/08/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C3310 | TT_Task | Assemble MER Complete Shipping Split (SE) | 29/03/2021 | 08/04/2021 | 03/03/2021 | 17/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C2100 | TT_Task | Hang drywall / Mud / Tape | 02/01/2021 | 11/01/2021 | 01/12/2020 | 09/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C2120 | TT_Task | Datahall Finishes - Ceiling Grid | 12/01/2021 | 21/01/2021 | 18/12/2020 | 31/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C2300 | TT_Task | Mechanical Corridor Finishes | 28/12/2020 | 04/01/2021 | 28/12/2020 | 04/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C2080 | TT_Task | Frame Top out | 30/11/2020 | 09/12/2020 | 17/11/2020 | 17/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C2030 | TT_Task | Exterior Equipment Pads - Electrical | 02/11/2020 | 16/11/2020 | 26/10/2020 | 03/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C2090 | TT_Task | Exterior Equipment Pads - Mechanical | 02/11/2020 | 16/11/2020 | 30/10/2020 | 13/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C2060 | TT_Task | Set Exterior Electrical OFCI Equipment - GEN | 01/02/2021 | 05/02/2021 | 09/01/2021 | 09/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C2170 | TT_Task | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | 15/01/2021 | 29/01/2021 | 08/01/2021 | 11/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C2040 | TT_Task | Frame wall MEPFP In wall roughin | 23/11/2020 | 01/12/2020 | 16/11/2020 | 19/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C2070 | TT_Task | Overhead MEPFP Rough-In | 02/11/2020 | 12/11/2020 | 26/10/2020 | 14/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C2140 | TT_Task | OverHead MEPFP Rough-In | 19/12/2020 | 07/01/2021 | 26/10/2020 | 19/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C2190 | TT_Task | Electrical surface mounted Rough-in Above AHU | 12/12/2020 | 17/12/2020 | 16/11/2020 | 25/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C2130 | TT_Task | VFD'S Installation Wiring | 01/06/2021 | 15/06/2021 | 15/05/2021 | 29/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C2000 | TT_Task | Electrical Underground Rough-In | 02/11/2020 | 16/11/2020 | 28/09/2020 | 06/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C2330 | TT_Task | Steel Support for OH Conductors Cable Tray Installation | 27/03/2021 | 31/03/2021 | 03/03/2021 | 17/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C2420 | TT_Task | Generator Utility Power Test-Term | 06/04/2021 | 15/04/2021 | 06/04/2021 | 16/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C2410 | TT_Task | Electrical Feeders to Mechanical Equipment Pull-Test-Term | 30/04/2021 | 25/05/2021 | 16/04/2021 | 10/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C2460 | TT_Task | Pull/term/Test PDU to Power bus | 02/06/2021 | 25/06/2021 | 17/05/2021 | 02/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C2110 | TT_Task | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel Pipe Steel Supports) | 11/01/2021 | 14/01/2021 | 04/01/2021 | 06/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C2180 | TT_Task | Mechanical Equipment Piping Connections | 22/03/2021 | 27/03/2021 | 15/03/2021 | 23/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C2050 | TT_Task | Mechanical/Plumbing Underground Rough-In | 17/11/2020 | 03/12/2020 | 28/09/2020 | 06/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C2230 | TT_Task | Fire Alarm Installation | 11/05/2021 | 25/05/2021 | 01/04/2021 | 16/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C2430 | TT_Task | Controls Installation | 28/06/2021 | 13/07/2021 | 01/06/2021 | 15/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C2440 | TT_Task | Ligthing Installation | 20/07/2021 | 03/08/2021 | 01/06/2021 | 16/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C2200 | TT_Task | AHU/DOAS Equipment Setting | 01/03/2021 | 05/03/2021 | 08/02/2021 | 18/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C2250 | TT_Task | Hydronic Piping Installation | 01/06/2021 | 15/06/2021 | 01/05/2021 | 15/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C2360 | TT_Task | Floor Drain System Installation | 30/06/2021 | 15/07/2021 | 01/06/2021 | 15/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C2310 | TT_Task | Toilet Piping Installation / DW | 03/05/2021 | 15/05/2021 | 01/05/2021 | 15/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C2320 | TT_Task | Controls Installation | 30/06/2021 | 22/07/2021 | 24/05/2021 | 09/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C2150 | TT_Task | Fire Riser Installation | 30/11/2020 | 30/11/2020 | 28/11/2020 | 28/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C2210 | TT_Task | Fire Alarm System | 30/04/2021 | 14/05/2021 | 01/04/2021 | 16/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C2280 | TT_Task | PDU's Installation | 22/03/2021 | 24/03/2021 | 19/03/2021 | 20/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C2220 | TT_Task | Cable Tray Installation | 01/03/2021 | 13/03/2021 | 08/02/2021 | 23/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C2380 | TT_Task | Pull / Term / Test Conductors ( MER to PDU) | 03/06/2021 | 28/06/2021 | 21/05/2021 | 17/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C2270 | TT_Task | EPMS Pull Wire / Term / Test | 28/06/2021 | 13/07/2021 | 01/06/2021 | 15/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C2350 | TT_Task | BMS Pull Wire / Term / Test | 28/06/2021 | 13/07/2021 | 01/06/2021 | 15/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C2400 | TT_Task | Light Fixtures Installation | 18/06/2021 | 01/07/2021 | 18/06/2021 | 01/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C2390 | TT_Task | Controls Installation | 01/06/2021 | 15/06/2021 | 01/06/2021 | 15/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C2240 | TT_Task | Fire Alarm System | 10/05/2021 | 20/05/2021 | 10/05/2021 | 20/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.Cx2020 | TT_Task | Network Startup | 31/08/2021 | 13/09/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.Cx2060 | TT_Task | EPMS Checkout / Point to Point | 14/09/2021 | 24/09/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.Cx2000 | TT_Task | Electrical Equipment Yellow Tagging (Field Terminated equipment) | 13/07/2021 | 23/07/2021 | 26/07/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C2340 | TT_Task | Assemble MER Complete Shipping Split (SE) | 27/03/2021 | 07/04/2021 | 02/03/2021 | 18/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C4090 | TT_Task | Hang drywall / Mud / Tape | 06/01/2021 | 11/01/2021 | 10/12/2020 | 31/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C4110 | TT_Task | Datahall Finishes - Ceiling Grid | 11/01/2021 | 20/01/2021 | 31/12/2020 | 07/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C4300 | TT_Task | Mechanical Corridor Finishes | 28/12/2020 | 04/01/2021 | 28/12/2020 | 04/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C4080 | TT_Task | Frame Top out | 02/01/2021 | 12/01/2021 | 07/12/2020 | 17/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C4040 | TT_Task | Exterior Equipment Pads - Electrical | 02/11/2020 | 16/11/2020 | 30/10/2020 | 05/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C4060 | TT_Task | Set Exterior Electrical OFCI Equipment - GEN | 01/02/2021 | 05/02/2021 | 22/01/2021 | 22/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C4020 | TT_Task | Frame wall MEPFP In wall roughin | 23/11/2020 | 01/12/2020 | 19/11/2020 | 09/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C4070 | TT_Task | Overhead MEPFP Rough-In | 06/11/2020 | 18/11/2020 | 28/10/2020 | 06/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C4150 | TT_Task | OverHead MEPFP Rough-In | 30/11/2020 | 14/12/2020 | 28/10/2020 | 19/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C4180 | TT_Task | Electrical surface mounted Rough-in Above AHU | 30/11/2020 | 04/12/2020 | 20/11/2020 | 23/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C4120 | TT_Task | VFD'S Installation Wiring | 01/06/2021 | 15/06/2021 | 01/05/2021 | 14/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C4000 | TT_Task | Electrical Underground Rough-In | 02/11/2020 | 16/11/2020 | 28/09/2020 | 06/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C4250 | TT_Task | Steel Support for OH Conductors Cable Tray Installation | 27/03/2021 | 31/03/2021 | 09/03/2021 | 17/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C4370 | TT_Task | Generator Utility Power Test-Term | 18/05/2021 | 27/05/2021 | 19/04/2021 | 29/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C4380 | TT_Task | Electrical Feeders to Mechanical Equipment Pull-Test-Term | 30/04/2021 | 25/05/2021 | 29/04/2021 | 24/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C4390 | TT_Task | Pull/term/Test PDU to Power bus | 08/06/2021 | 29/06/2021 | 25/05/2021 | 16/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C4050 | TT_Task | Mechanical/Plumbing Underground Rough-In | 02/11/2020 | 16/11/2020 | 28/09/2020 | 06/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C4100 | TT_Task | Fire Alarm Installation | 12/05/2021 | 26/05/2021 | 01/04/2021 | 16/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C4400 | TT_Task | Controls Installation | 01/06/2021 | 15/06/2021 | 01/06/2021 | 15/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C4410 | TT_Task | Ligthing Installation | 04/08/2021 | 18/08/2021 | 17/06/2021 | 29/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C4190 | TT_Task | AHU/DOAS Equipment Setting | 01/03/2021 | 05/03/2021 | 19/02/2021 | 22/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C4270 | TT_Task | Hydronic Piping Installation | 01/06/2021 | 15/06/2021 | 01/05/2021 | 15/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C4340 | TT_Task | Floor Drain System Installation | 30/06/2021 | 15/07/2021 | 01/06/2021 | 15/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C4350 | TT_Task | Toilet Piping Installation / DW | 30/06/2021 | 15/07/2021 | 17/05/2021 | 01/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C4260 | TT_Task | Controls Installation | 01/06/2021 | 22/06/2021 | 30/04/2021 | 22/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C4130 | TT_Task | Fire Riser Installation | 30/11/2020 | 30/11/2020 | 28/11/2020 | 28/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C4160 | TT_Task | Fire Alarm System | 15/05/2021 | 29/05/2021 | 01/04/2021 | 16/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C4240 | TT_Task | PDU's Installation | 30/04/2021 | 04/05/2021 | 12/04/2021 | 24/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C4170 | TT_Task | Cable Tray Installation | 01/03/2021 | 13/03/2021 | 24/02/2021 | 10/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C4320 | TT_Task | Pull / Term / Test Conductors ( MER to PDU) | 09/06/2021 | 06/07/2021 | 26/05/2021 | 24/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C4230 | TT_Task | EPMS Pull Wire / Term / Test | 29/06/2021 | 14/07/2021 | 01/06/2021 | 15/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C4290 | TT_Task | BMS Pull Wire / Term / Test | 29/06/2021 | 14/07/2021 | 01/06/2021 | 15/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C4360 | TT_Task | Light Fixtures Installation | 23/06/2021 | 08/07/2021 | 23/06/2021 | 19/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C4330 | TT_Task | Controls Installation | 01/06/2021 | 15/06/2021 | 24/05/2021 | 15/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C4200 | TT_Task | Fire Alarm System | 21/05/2021 | 03/06/2021 | 01/04/2021 | 16/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.Cx2070 | TT_Task | Network Startup | 31/08/2021 | 13/09/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.Cx2140 | TT_Task | EPMS Checkout / Point to Point | 27/09/2021 | 07/10/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.Cx2030 | TT_Task | Electrical Equipment Yellow Tagging (Field Terminated equipment) | 18/08/2021 | 28/08/2021 | 26/07/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.Cx3040 | TT_Task | Level 3 Cx- COLO-2 | 17/11/2021 | 03/12/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.Cx3030 | TT_Task | Load Bank IR Scan | 26/10/2021 | 16/11/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C4280 | TT_Task | Assemble MER Complete Shipping Split (SE) | 27/03/2021 | 07/04/2021 | 09/03/2021 | 29/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.Cx4010 | TT_Task | COLO 2 Level 4 Level 5 IST | 04/12/2021 | 24/12/2021 |  |  | 16 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C1220 | TT_Task | Hang drywall / Mud / Tape | 02/01/2021 | 11/01/2021 | 22/12/2020 | 31/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C1260 | TT_Task | Datahall Finishes | 11/01/2021 | 25/01/2021 | 06/01/2021 | 21/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C1250 | TT_Task | Mechanical Corridor Finishes | 05/03/2021 | 26/03/2021 | 28/12/2020 | 04/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C1030 | TT_Task | Frame Top out | 02/01/2021 | 11/01/2021 | 03/12/2020 | 12/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C1050 | TT_Task | Exterior Equipment Pads - Electrical | 02/01/2021 | 02/01/2021 | 30/11/2020 | 30/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C1060 | TT_Task | Exterior Equipment Pads - Mechanical | 02/01/2021 | 15/01/2021 | 30/11/2020 | 02/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C1110 | TT_Task | Set Exterior Electrical OFCI Equipment - GEN | 01/03/2021 | 05/03/2021 | 18/03/2021 | 18/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C1160 | TT_Task | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | 01/02/2021 | 15/02/2021 | 15/01/2021 | 15/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C1090 | TT_Task | Frame wall MEPFP In wall roughin | 02/01/2021 | 07/01/2021 | 11/12/2020 | 18/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C1210 | TT_Task | Overhead MEPFP Rough-In | 16/11/2020 | 30/11/2020 | 28/10/2020 | 26/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C1070 | TT_Task | OverHead MEPFP Rough-In | 30/11/2020 | 14/12/2020 | 23/11/2020 | 28/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C1120 | TT_Task | Electrical surface mounted Rough-in Above AHU | 21/01/2021 | 26/01/2021 | 21/01/2021 | 26/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C1130 | TT_Task | VFD'S Installation Wiring | 01/06/2021 | 15/06/2021 | 30/04/2021 | 30/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C1010 | TT_Task | Electrical Underground Rough-In | 02/11/2020 | 16/11/2020 | 12/10/2020 | 21/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C1240 | TT_Task | Steel Support for OH Conductors Cable Tray Installation | 26/04/2021 | 29/04/2021 | 05/04/2021 | 09/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C1380 | TT_Task | Generator Utility Power Test-Term | 02/06/2021 | 10/06/2021 | 20/05/2021 | 31/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C1360 | TT_Task | Electrical Feeders to Mechanical Equipment Pull-Test-Term | 01/06/2021 | 24/06/2021 | 25/05/2021 | 18/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C1420 | TT_Task | Pull/term/Test PDU to Power bus | 19/06/2021 | 14/07/2021 | 19/06/2021 | 14/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C1100 | TT_Task | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel Pipe Steel Supports) | 11/01/2021 | 14/01/2021 | 21/12/2020 | 30/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C1170 | TT_Task | Mechanical Equipment Piping Connections | 30/04/2021 | 07/05/2021 | 19/04/2021 | 24/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C1000 | TT_Task | Mechanical/Plumbing Underground Rough-In | 02/11/2020 | 16/11/2020 | 19/10/2020 | 21/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C1200 | TT_Task | Fire Alarm Installation | 30/06/2021 | 15/07/2021 | 19/06/2021 | 02/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C1400 | TT_Task | Controls Installation | 06/07/2021 | 19/07/2021 | 06/07/2021 | 19/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C1330 | TT_Task | Ligthing Installation | 31/07/2021 | 13/08/2021 | 01/07/2021 | 16/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C1140 | TT_Task | AHU/DOAS Equipment Setting | 31/03/2021 | 05/04/2021 | 10/03/2021 | 15/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C1180 | TT_Task | Hydronic Piping Installation | 30/04/2021 | 14/05/2021 | 23/04/2021 | 29/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C1290 | TT_Task | Floor Drain System Installation | 31/07/2021 | 13/08/2021 | 30/06/2021 | 15/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C1300 | TT_Task | Toilet Piping Installation / DW | 30/06/2021 | 15/07/2021 | 01/06/2021 | 16/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C1190 | TT_Task | Controls Installation | 16/06/2021 | 08/07/2021 | 25/05/2021 | 22/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C1080 | TT_Task | Fire Riser Installation | 30/04/2021 | 14/05/2021 | 31/03/2021 | 14/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C1150 | TT_Task | Fire Alarm System | 15/05/2021 | 29/05/2021 | 15/04/2021 | 29/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C1390 | TT_Task | PDU's Installation | 07/05/2021 | 10/05/2021 | 12/04/2021 | 24/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C1310 | TT_Task | Cable Tray Installation | 03/04/2021 | 17/04/2021 | 10/03/2021 | 22/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C1430 | TT_Task | Pull / Term / Test Conductors ( MER to PDU) | 30/06/2021 | 27/07/2021 | 21/06/2021 | 20/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C1370 | TT_Task | EPMS Pull Wire / Term / Test | 30/06/2021 | 15/07/2021 | 21/06/2021 | 06/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C1410 | TT_Task | BMS Pull Wire / Term / Test | 30/06/2021 | 15/07/2021 | 21/06/2021 | 06/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C1450 | TT_Task | Light Fixtures Installation | 31/07/2021 | 06/08/2021 | 29/07/2021 | 04/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C1440 | TT_Task | Controls Installation | 14/06/2021 | 26/06/2021 | 13/05/2021 | 28/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C1340 | TT_Task | Fire Alarm System | 31/07/2021 | 11/08/2021 | 30/06/2021 | 13/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.Cx2020 | TT_Task | Network Startup | 14/09/2021 | 24/09/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.Cx2060 | TT_Task | EPMS Checkout / Point to Point | 27/09/2021 | 07/10/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.Cx2000 | TT_Task | Electrical Equipment Yellow Tagging (Field Terminated equipment) | 31/08/2021 | 13/09/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C1280 | TT_Task | Assemble MER Complete Shipping Split (SE) | 03/05/2021 | 13/05/2021 | 05/04/2021 | 12/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C3190 | TT_Task | Hang drywall / Mud / Tape | 14/01/2021 | 23/01/2021 | 28/12/2020 | 11/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C3240 | TT_Task | Datahall Finishes | 11/01/2021 | 25/01/2021 | 08/01/2021 | 28/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C3160 | TT_Task | Mechanical Corridor Finishes | 03/02/2021 | 24/02/2021 | 28/12/2020 | 04/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C3030 | TT_Task | Frame Top out | 12/01/2021 | 21/01/2021 | 14/12/2020 | 19/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C3050 | TT_Task | Exterior Equipment Pads - Electrical | 02/01/2021 | 15/01/2021 | 02/12/2020 | 04/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C3080 | TT_Task | Set Exterior Electrical OFCI Equipment - GEN | 15/03/2021 | 22/03/2021 | 05/03/2021 | 10/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C3060 | TT_Task | Frame wall MEPFP In wall roughin | 02/01/2021 | 07/01/2021 | 19/12/2020 | 24/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C3180 | TT_Task | Overhead MEPFP Rough-In | 21/12/2020 | 06/01/2021 | 21/12/2020 | 06/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C3090 | TT_Task | OverHead MEPFP Rough-In | 13/01/2021 | 27/01/2021 | 14/12/2020 | 28/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C3120 | TT_Task | Electrical surface mounted Rough-in Above AHU | 01/03/2021 | 05/03/2021 | 04/02/2021 | 11/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C3130 | TT_Task | VFD'S Installation Wiring | 31/07/2021 | 13/08/2021 | 30/06/2021 | 15/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C3010 | TT_Task | Electrical Underground Rough-In | 02/11/2020 | 16/11/2020 | 12/10/2020 | 24/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C3230 | TT_Task | Steel Support for OH Conductors Cable Tray Installation | 17/05/2021 | 20/05/2021 | 30/04/2021 | 05/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C3330 | TT_Task | Generator Utility Power Test-Term | 05/06/2021 | 15/06/2021 | 30/06/2021 | 16/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C3350 | TT_Task | Electrical Feeders to Mechanical Equipment Pull-Test-Term | 08/06/2021 | 01/07/2021 | 08/06/2021 | 13/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C3380 | TT_Task | Pull/term/Test PDU to Power bus | 02/07/2021 | 28/07/2021 | 02/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C3000 | TT_Task | Mechanical/Plumbing Underground Rough-In | 02/11/2020 | 16/11/2020 | 19/10/2020 | 24/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C3110 | TT_Task | Fire Alarm Installation | 28/06/2021 | 13/07/2021 | 28/06/2021 | 15/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C3370 | TT_Task | Controls Installation | 29/06/2021 | 14/07/2021 | 29/06/2021 | 20/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C3290 | TT_Task | Ligthing Installation | 16/08/2021 | 28/08/2021 | 17/07/2021 | 31/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C3140 | TT_Task | AHU/DOAS Equipment Setting | 31/03/2021 | 05/04/2021 | 16/03/2021 | 23/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C3150 | TT_Task | Hydronic Piping Installation | 30/04/2021 | 14/05/2021 | 23/04/2021 | 29/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C3210 | TT_Task | Floor Drain System Installation | 31/07/2021 | 13/08/2021 | 30/06/2021 | 15/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C3220 | TT_Task | Toilet Piping Installation / DW | 30/06/2021 | 15/07/2021 | 01/06/2021 | 16/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C3170 | TT_Task | Controls Installation | 30/06/2021 | 22/07/2021 | 30/06/2021 | 22/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C3070 | TT_Task | Fire Riser Installation | 30/11/2020 | 30/11/2020 | 28/11/2020 | 28/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C3100 | TT_Task | Fire Alarm System | 31/07/2021 | 13/08/2021 | 30/06/2021 | 15/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C3340 | TT_Task | PDU's Installation | 07/06/2021 | 09/06/2021 | 29/04/2021 | 01/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C3270 | TT_Task | Cable Tray Installation | 31/03/2021 | 14/04/2021 | 23/03/2021 | 24/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C3390 | TT_Task | Pull / Term / Test Conductors ( MER to PDU) | 16/08/2021 | 10/09/2021 | 08/07/2021 | 26/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C3320 | TT_Task | EPMS Pull Wire / Term / Test | 31/07/2021 | 13/08/2021 | 01/07/2021 | 16/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C3360 | TT_Task | BMS Pull Wire / Term / Test | 31/07/2021 | 13/08/2021 | 01/07/2021 | 16/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C3410 | TT_Task | Light Fixtures Installation | 31/07/2021 | 06/08/2021 | 01/07/2021 | 09/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C3400 | TT_Task | Controls Installation | 14/06/2021 | 26/06/2021 | 14/06/2021 | 26/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C3300 | TT_Task | Fire Alarm System | 31/07/2021 | 11/08/2021 | 01/07/2021 | 14/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.Cx2080 | TT_Task | Network Startup | 27/09/2021 | 07/10/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.Cx2140 | TT_Task | EPMS Checkout / Point to Point | 08/10/2021 | 20/10/2021 |  |  | 60 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.Cx2030 | TT_Task | Electrical Equipment Yellow Tagging (Field Terminated equipment) | 14/09/2021 | 24/09/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C3260 | TT_Task | Assemble MER Complete Shipping Split (SE) | 07/05/2021 | 18/05/2021 | 16/04/2021 | 03/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C2250 | TT_Task | Hang drywall / Mud / Tape | 08/01/2021 | 18/01/2021 | 22/12/2020 | 31/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C2270 | TT_Task | Datahall Finishes | 11/01/2021 | 25/01/2021 | 06/01/2021 | 21/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C2200 | TT_Task | Mechanical Corridor Finishes | 02/02/2021 | 23/02/2021 | 28/12/2020 | 04/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C2030 | TT_Task | Frame Top out | 02/01/2021 | 11/01/2021 | 03/12/2020 | 12/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C2050 | TT_Task | Exterior Equipment Pads - Electrical | 02/01/2021 | 15/01/2021 | 27/11/2020 | 11/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C2060 | TT_Task | Exterior Equipment Pads - Mechanical | 09/01/2021 | 23/01/2021 | 30/11/2020 | 02/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C2110 | TT_Task | Set Exterior Electrical OFCI Equipment - GEN | 01/03/2021 | 05/03/2021 | 19/02/2021 | 19/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C2160 | TT_Task | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | 26/04/2021 | 10/05/2021 | 08/04/2021 | 22/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C2090 | TT_Task | Frame wall MEPFP In wall roughin | 02/01/2021 | 07/01/2021 | 11/12/2020 | 18/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C2240 | TT_Task | Overhead MEPFP Rough-In | 16/11/2020 | 30/11/2020 | 28/10/2020 | 14/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C2070 | TT_Task | OverHead MEPFP Rough-In | 12/01/2021 | 26/01/2021 | 23/11/2020 | 28/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C2120 | TT_Task | Electrical surface mounted Rough-in Above AHU | 01/02/2021 | 05/02/2021 | 25/01/2021 | 28/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C2130 | TT_Task | VFD'S Installation Wiring | 01/06/2021 | 15/06/2021 | 30/04/2021 | 15/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C2000 | TT_Task | Electrical Underground Rough-In | 02/11/2020 | 16/11/2020 | 19/10/2020 | 31/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C2290 | TT_Task | Steel Support for OH Conductors Cable Tray Installation | 30/04/2021 | 05/05/2021 | 12/04/2021 | 14/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C2380 | TT_Task | Generator Utility Power Test-Term | 03/06/2021 | 11/06/2021 | 29/05/2021 | 09/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C2350 | TT_Task | Electrical Feeders to Mechanical Equipment Pull-Test-Term | 10/06/2021 | 06/07/2021 | 29/05/2021 | 22/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C2440 | TT_Task | Pull/term/Test PDU to Power bus | 23/06/2021 | 16/07/2021 | 23/06/2021 | 14/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C2100 | TT_Task | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel Pipe Steel Supports) | 01/02/2021 | 04/02/2021 | 11/01/2021 | 15/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C2170 | TT_Task | Mechanical Equipment Piping Connections | 03/05/2021 | 08/05/2021 | 15/04/2021 | 21/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C2020 | TT_Task | Mechanical/Plumbing Underground Rough-In | 17/11/2020 | 03/12/2020 | 19/10/2020 | 31/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C2190 | TT_Task | Fire Alarm Installation | 28/06/2021 | 13/07/2021 | 10/06/2021 | 24/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C2390 | TT_Task | Controls Installation | 25/06/2021 | 10/07/2021 | 25/06/2021 | 15/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C2410 | TT_Task | Ligthing Installation | 16/07/2021 | 30/07/2021 | 16/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C2140 | TT_Task | AHU/DOAS Equipment Setting | 31/03/2021 | 05/04/2021 | 10/03/2021 | 15/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C2180 | TT_Task | Hydronic Piping Installation | 30/04/2021 | 14/05/2021 | 23/04/2021 | 29/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C2220 | TT_Task | Floor Drain System Installation | 31/07/2021 | 13/08/2021 | 30/06/2021 | 15/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C2230 | TT_Task | Toilet Piping Installation / DW | 30/06/2021 | 15/07/2021 | 01/06/2021 | 16/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C2210 | TT_Task | Controls Installation | 16/06/2021 | 08/07/2021 | 16/06/2021 | 08/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C2080 | TT_Task | Fire Riser Installation | 30/11/2020 | 30/11/2020 | 28/11/2020 | 28/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C2150 | TT_Task | Fire Alarm System | 31/07/2021 | 13/08/2021 | 30/06/2021 | 15/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C2370 | TT_Task | PDU's Installation | 07/05/2021 | 10/05/2021 | 12/04/2021 | 24/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C2310 | TT_Task | Cable Tray Installation | 07/04/2021 | 21/04/2021 | 11/03/2021 | 24/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C2420 | TT_Task | Pull / Term / Test Conductors ( MER to PDU) | 01/07/2021 | 28/07/2021 | 24/06/2021 | 24/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C2360 | TT_Task | EPMS Pull Wire / Term / Test | 01/07/2021 | 16/07/2021 | 01/07/2021 | 16/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C2400 | TT_Task | BMS Pull Wire / Term / Test | 01/07/2021 | 16/07/2021 | 01/07/2021 | 16/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C2450 | TT_Task | Light Fixtures Installation | 21/07/2021 | 28/07/2021 | 21/07/2021 | 06/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C2430 | TT_Task | Controls Installation | 14/06/2021 | 26/06/2021 | 14/06/2021 | 26/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C2320 | TT_Task | Fire Alarm System | 30/06/2021 | 13/07/2021 | 01/06/2021 | 30/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.Cx2040 | TT_Task | Network Startup | 14/09/2021 | 24/09/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.Cx2090 | TT_Task | EPMS Checkout / Point to Point | 27/09/2021 | 07/10/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.Cx2010 | TT_Task | Electrical Equipment Yellow Tagging (Field Terminated equipment) | 13/08/2021 | 25/08/2021 | 13/08/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C2300 | TT_Task | Assemble MER Complete Shipping Split (SE) | 03/05/2021 | 13/05/2021 | 10/04/2021 | 20/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C4230 | TT_Task | Hang drywall / Mud / Tape | 14/01/2021 | 23/01/2021 | 28/12/2020 | 11/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C4260 | TT_Task | Datahall Finishes | 11/01/2021 | 25/01/2021 | 08/01/2021 | 28/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C4200 | TT_Task | Mechanical Corridor Finishes | 23/02/2021 | 16/03/2021 | 28/12/2020 | 04/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C4030 | TT_Task | Frame Top out | 12/01/2021 | 21/01/2021 | 14/12/2020 | 19/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C4050 | TT_Task | Exterior Equipment Pads - Electrical | 02/01/2021 | 15/01/2021 | 02/12/2020 | 11/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C4070 | TT_Task | Exterior Equipment Pads - Mechanical | 02/01/2021 | 15/01/2021 | 03/12/2020 | 11/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C4100 | TT_Task | Set Exterior Electrical OFCI Equipment - GEN | 01/03/2021 | 05/03/2021 | 26/02/2021 | 26/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C4130 | TT_Task | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | 30/04/2021 | 14/05/2021 | 12/04/2021 | 12/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C4060 | TT_Task | Frame wall MEPFP In wall roughin | 02/01/2021 | 07/01/2021 | 19/12/2020 | 24/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C4220 | TT_Task | Overhead MEPFP Rough-In | 15/01/2021 | 27/01/2021 | 21/12/2020 | 07/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C4110 | TT_Task | OverHead MEPFP Rough-In | 08/01/2021 | 22/01/2021 | 14/12/2020 | 28/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C4150 | TT_Task | Electrical surface mounted Rough-in Above AHU | 01/02/2021 | 05/02/2021 | 25/01/2021 | 29/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C4160 | TT_Task | VFD'S Installation Wiring | 16/06/2021 | 29/06/2021 | 16/06/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C4000 | TT_Task | Electrical Underground Rough-In | 17/11/2020 | 03/12/2020 | 19/10/2020 | 31/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C4290 | TT_Task | Steel Support for OH Conductors Cable Tray Installation | 30/04/2021 | 05/05/2021 | 26/04/2021 | 29/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C4370 | TT_Task | Generator Utility Power Test-Term | 06/07/2021 | 14/07/2021 | 29/06/2021 | 15/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C4380 | TT_Task | Electrical Feeders to Mechanical Equipment Pull-Test-Term | 05/06/2021 | 29/06/2021 | 05/06/2021 | 29/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C4430 | TT_Task | Pull/term/Test PDU to Power bus | 30/06/2021 | 22/07/2021 | 30/06/2021 | 22/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C4090 | TT_Task | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel Pipe Steel Supports) | 01/02/2021 | 04/02/2021 | 11/01/2021 | 15/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C4140 | TT_Task | Mechanical Equipment Piping Connections | 17/05/2021 | 24/05/2021 | 30/04/2021 | 07/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C4020 | TT_Task | Mechanical/Plumbing Underground Rough-In | 04/12/2020 | 18/12/2020 | 23/10/2020 | 31/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C4180 | TT_Task | Fire Alarm Installation | 31/07/2021 | 13/08/2021 | 07/07/2021 | 20/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C4410 | TT_Task | Controls Installation | 16/08/2021 | 28/08/2021 | 21/07/2021 | 04/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C4400 | TT_Task | Ligthing Installation | 30/08/2021 | 14/09/2021 | 31/07/2021 | 13/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C4170 | TT_Task | AHU/DOAS Equipment Setting | 31/03/2021 | 05/04/2021 | 16/03/2021 | 30/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C4190 | TT_Task | Hydronic Piping Installation | 30/04/2021 | 14/05/2021 | 23/04/2021 | 29/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C4240 | TT_Task | Floor Drain System Installation | 31/08/2021 | 15/09/2021 | 31/07/2021 | 13/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C4250 | TT_Task | Toilet Piping Installation / DW | 30/06/2021 | 15/07/2021 | 01/06/2021 | 16/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C4210 | TT_Task | Controls Installation | 30/06/2021 | 22/07/2021 | 30/06/2021 | 22/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C4080 | TT_Task | Fire Riser Installation | 30/11/2020 | 30/11/2020 | 28/11/2020 | 28/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C4120 | TT_Task | Fire Alarm System | 31/07/2021 | 13/08/2021 | 01/07/2021 | 16/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C4360 | TT_Task | PDU's Installation | 14/06/2021 | 16/06/2021 | 29/04/2021 | 01/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C4310 | TT_Task | Cable Tray Installation | 31/03/2021 | 14/04/2021 | 25/03/2021 | 24/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C4420 | TT_Task | Pull / Term / Test Conductors ( MER to PDU) | 31/07/2021 | 25/08/2021 | 12/07/2021 | 05/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C4350 | TT_Task | EPMS Pull Wire / Term / Test | 31/07/2021 | 13/08/2021 | 01/07/2021 | 16/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C4390 | TT_Task | BMS Pull Wire / Term / Test | 31/07/2021 | 13/08/2021 | 01/07/2021 | 16/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C4450 | TT_Task | Light Fixtures Installation | 31/08/2021 | 08/09/2021 | 06/08/2021 | 12/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C4440 | TT_Task | Controls Installation | 14/06/2021 | 26/06/2021 | 14/06/2021 | 26/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C4330 | TT_Task | Fire Alarm System | 31/07/2021 | 11/08/2021 | 01/07/2021 | 14/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.Cx2100 | TT_Task | Network Startup | 27/09/2021 | 07/10/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.Cx2150 | TT_Task | EPMS Checkout / Point to Point | 08/10/2021 | 20/10/2021 |  |  | 60 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.Cx2050 | TT_Task | Electrical Equipment Yellow Tagging (Field Terminated equipment) | 14/09/2021 | 24/09/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.Cx3040 | TT_Task | Level 3 Cx- COLO-3 | 04/01/2022 | 18/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.Cx3030 | TT_Task | Load Bank IR Scan | 08/12/2021 | 03/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C4300 | TT_Task | Assemble MER Complete Shipping Split (SE) | 30/04/2021 | 12/05/2021 | 26/04/2021 | 07/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.Cx4000 | TT_Task | COLO 3 Level 4 Level 5 IST | 19/01/2022 | 08/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH.06.M2010 | TT_FinMile | MWH06 COLO2 - LV3 Cx Complete (CO-66: 01-Oct-21) | 04/12/2021 | 04/12/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH.06.M3010 | TT_FinMile | MWH06 COLO3 - LV3 Cx Complete(CO-66: 12-Nov-21) | 19/01/2022 | 19/01/2022 |  |  | 1 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH.06.M4010 | TT_FinMile | MWH06 COLO4 - LV3 Cx Complete (CO-66: 28-Dec-21) | 28/02/2022 | 28/02/2022 |  |  | 1 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C1220 | TT_Task | Early Topout | 01/02/2021 | 03/02/2021 | 11/01/2021 | 14/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C1260 | TT_Task | Datahall Finishes | 31/03/2021 | 14/04/2021 | 15/02/2021 | 27/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C1200 | TT_Task | Mechanical Corridor Finishes | 15/04/2021 | 06/05/2021 | 09/01/2021 | 01/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C1010 | TT_Task | Frame Top out | 02/01/2021 | 11/01/2021 | 28/12/2020 | 08/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C1060 | TT_Task | Exterior Equipment Pads - Electrical | 02/01/2021 | 15/01/2021 | 07/12/2020 | 10/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C1070 | TT_Task | Exterior Equipment Pads - Mechanical | 09/01/2021 | 23/01/2021 | 07/12/2020 | 10/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C1100 | TT_Task | Set Exterior Electrical OFCI Equipment - GEN | 26/04/2021 | 03/05/2021 | 12/04/2021 | 24/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C1110 | TT_Task | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | 06/05/2021 | 19/05/2021 | 15/02/2021 | 03/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C1140 | TT_Task | Frame wall MEPFP In wall roughin | 02/01/2021 | 07/01/2021 | 28/12/2020 | 08/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C1190 | TT_Task | Overhead MEPFP Rough-In | 01/02/2021 | 12/02/2021 | 07/01/2021 | 21/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C1130 | TT_Task | OverHead MEPFP Rough-In | 30/04/2021 | 14/05/2021 | 19/02/2021 | 06/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C1150 | TT_Task | Electrical surface mounted Rough-in Above AHU | 15/03/2021 | 19/03/2021 | 16/02/2021 | 18/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C1160 | TT_Task | VFD'S Installation Wiring | 30/06/2021 | 15/07/2021 | 30/04/2021 | 14/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C1020 | TT_Task | Electrical Underground Rough-In | 02/11/2020 | 16/11/2020 | 12/10/2020 | 23/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C1280 | TT_Task | Steel Support for OH Conductors Cable Tray Installation | 07/06/2021 | 10/06/2021 | 28/04/2021 | 06/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C1380 | TT_Task | Generator Utility Power Test-Term | 06/08/2021 | 16/08/2021 | 20/07/2021 | 28/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C1340 | TT_Task | Electrical Feeders to Mechanical Equipment Pull-Test-Term | 06/08/2021 | 30/08/2021 | 20/07/2021 | 24/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C1440 | TT_Task | Pull/term/Test PDU to Power bus | 25/08/2021 | 18/09/2021 | 29/07/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C1080 | TT_Task | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel Pipe Steel Supports) | 30/04/2021 | 05/05/2021 | 01/02/2021 | 05/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C1120 | TT_Task | Mechanical Equipment Piping Connections | 30/06/2021 | 08/07/2021 | 30/04/2021 | 07/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C1000 | TT_Task | Mechanical/Plumbing Underground Rough-In | 02/11/2020 | 16/11/2020 | 12/10/2020 | 23/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C1390 | TT_Task | Fire Alarm Installation | 31/07/2021 | 13/08/2021 | 20/07/2021 | 03/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C1410 | TT_Task | Controls Installation | 31/07/2021 | 13/08/2021 | 27/07/2021 | 09/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C1300 | TT_Task | Ligthing Installation | 31/08/2021 | 15/09/2021 | 31/07/2021 | 13/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C1170 | TT_Task | AHU/DOAS Equipment Setting | 15/05/2021 | 20/05/2021 | 10/03/2021 | 10/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C1180 | TT_Task | Hydronic Piping Installation | 30/06/2021 | 15/07/2021 | 30/04/2021 | 14/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C1240 | TT_Task | Floor Drain System Installation | 30/06/2021 | 15/07/2021 | 30/04/2021 | 14/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C1250 | TT_Task | Toilet Piping Installation / DW | 30/06/2021 | 15/07/2021 | 01/06/2021 | 15/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C1210 | TT_Task | Controls Installation | 31/07/2021 | 21/08/2021 | 20/07/2021 | 09/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C1050 | TT_Task | Fire Riser Installation | 31/07/2021 | 13/08/2021 | 19/05/2021 | 03/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C1090 | TT_Task | Fire Alarm System | 31/07/2021 | 13/08/2021 | 01/07/2021 | 16/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C1370 | TT_Task | PDU's Installation | 01/06/2021 | 03/06/2021 | 01/06/2021 | 03/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C1310 | TT_Task | Cable Tray Installation | 04/05/2021 | 17/05/2021 | 12/04/2021 | 24/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C1420 | TT_Task | Pull / Term / Test Conductors ( MER to PDU) | 31/08/2021 | 27/09/2021 | 25/08/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C1360 | TT_Task | EPMS Pull Wire / Term / Test | 02/09/2021 | 17/09/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C1400 | TT_Task | BMS Pull Wire / Term / Test | 02/09/2021 | 17/09/2021 |  |  | 60 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C1450 | TT_Task | Light Fixtures Installation | 21/08/2021 | 27/08/2021 | 27/07/2021 | 21/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C1430 | TT_Task | Controls Installation | 14/06/2021 | 26/06/2021 | 20/07/2021 | 13/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C1330 | TT_Task | Fire Alarm System | 31/07/2021 | 11/08/2021 | 01/07/2021 | 16/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.Cx2020 | TT_Task | Network Startup | 26/10/2021 | 05/11/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.Cx2060 | TT_Task | EPMS Checkout / Point to Point | 02/11/2021 | 13/11/2021 |  |  | 40 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.Cx2000 | TT_Task | Electrical Equipment Yellow Tagging (Field Terminated equipment) | 13/10/2021 | 25/10/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C1290 | TT_Task | Assemble MER Complete Shipping Split (SE) | 07/06/2021 | 18/06/2021 | 27/04/2021 | 13/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C3190 | TT_Task | Early Topout | 01/02/2021 | 03/02/2021 | 18/01/2021 | 20/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C3220 | TT_Task | Datahall Finishes | 15/04/2021 | 28/04/2021 | 22/02/2021 | 01/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C3240 | TT_Task | Mechanical Corridor Finishes | 29/04/2021 | 20/05/2021 | 21/01/2021 | 13/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C3010 | TT_Task | Frame Top out | 31/03/2021 | 08/04/2021 | 09/01/2021 | 20/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C3060 | TT_Task | Exterior Equipment Pads - Electrical | 02/01/2021 | 15/01/2021 | 07/12/2020 | 10/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C3070 | TT_Task | Exterior Equipment Pads - Mechanical | 09/01/2021 | 23/01/2021 | 14/12/2020 | 16/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C3100 | TT_Task | Set Exterior Electrical OFCI Equipment - GEN | 26/04/2021 | 03/05/2021 | 12/04/2021 | 24/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C3110 | TT_Task | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | 06/05/2021 | 19/05/2021 | 01/04/2021 | 14/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C3130 | TT_Task | Frame wall MEPFP In wall roughin | 18/01/2021 | 22/01/2021 | 11/01/2021 | 15/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C3180 | TT_Task | Overhead MEPFP Rough-In | 01/02/2021 | 12/02/2021 | 07/01/2021 | 21/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C3140 | TT_Task | OverHead MEPFP Rough-In | 15/05/2021 | 29/05/2021 | 22/02/2021 | 09/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C3150 | TT_Task | Electrical surface mounted Rough-in Above AHU | 30/03/2021 | 03/04/2021 | 18/02/2021 | 20/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C3160 | TT_Task | VFD'S Installation Wiring | 30/06/2021 | 15/07/2021 | 01/06/2021 | 15/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C3020 | TT_Task | Electrical Underground Rough-In | 02/11/2020 | 16/11/2020 | 26/10/2020 | 07/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C3260 | TT_Task | Steel Support for OH Conductors Cable Tray Installation | 07/06/2021 | 10/06/2021 | 03/05/2021 | 06/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C3380 | TT_Task | Generator Utility Power Test-Term | 16/07/2021 | 16/07/2021 | 28/07/2021 | 07/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C3390 | TT_Task | Electrical Feeders to Mechanical Equipment Pull-Test-Term | 31/08/2021 | 24/09/2021 | 10/08/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C3440 | TT_Task | Pull/term/Test PDU to Power bus | 03/09/2021 | 29/09/2021 |  |  | 210 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C3080 | TT_Task | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel Pipe Steel Supports) | 30/04/2021 | 05/05/2021 | 01/02/2021 | 05/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C3120 | TT_Task | Mechanical Equipment Piping Connections | 02/07/2021 | 10/07/2021 | 04/05/2021 | 10/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C3000 | TT_Task | Mechanical/Plumbing Underground Rough-In | 02/11/2020 | 16/11/2020 | 19/10/2020 | 23/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C3370 | TT_Task | Fire Alarm Installation | 31/08/2021 | 15/09/2021 | 17/08/2021 | 30/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C3410 | TT_Task | Controls Installation | 31/08/2021 | 15/09/2021 | 17/08/2021 | 30/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C3280 | TT_Task | Ligthing Installation | 16/09/2021 | 30/09/2021 | 16/08/2021 | 28/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C3170 | TT_Task | AHU/DOAS Equipment Setting | 01/06/2021 | 05/06/2021 | 18/03/2021 | 18/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C3200 | TT_Task | Hydronic Piping Installation | 30/06/2021 | 15/07/2021 | 30/04/2021 | 14/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C3290 | TT_Task | Floor Drain System Installation | 30/06/2021 | 15/07/2021 | 30/04/2021 | 14/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C3300 | TT_Task | Toilet Piping Installation / DW | 30/06/2021 | 15/07/2021 | 30/04/2021 | 14/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C3250 | TT_Task | Controls Installation | 23/08/2021 | 14/09/2021 | 20/07/2021 | 12/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C3050 | TT_Task | Fire Riser Installation | 30/11/2020 | 30/11/2020 | 28/11/2020 | 28/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C3090 | TT_Task | Fire Alarm System | 30/06/2021 | 15/07/2021 | 15/05/2021 | 29/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C3360 | TT_Task | PDU's Installation | 07/06/2021 | 09/06/2021 | 25/06/2021 | 30/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C3310 | TT_Task | Cable Tray Installation | 01/06/2021 | 15/06/2021 | 21/04/2021 | 04/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C3420 | TT_Task | Pull / Term / Test Conductors ( MER to PDU) | 03/09/2021 | 30/09/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C3350 | TT_Task | EPMS Pull Wire / Term / Test | 14/09/2021 | 28/09/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C3400 | TT_Task | BMS Pull Wire / Term / Test | 14/09/2021 | 28/09/2021 |  |  | 180 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C3450 | TT_Task | Light Fixtures Installation | 01/10/2021 | 07/10/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C3430 | TT_Task | Controls Installation | 14/09/2021 | 28/09/2021 | 12/08/2021 | 26/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C3330 | TT_Task | Fire Alarm System | 31/08/2021 | 13/09/2021 | 31/07/2021 | 11/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.Cx2080 | TT_Task | Network Startup | 08/11/2021 | 18/11/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.Cx2140 | TT_Task | EPMS Checkout / Point to Point | 19/11/2021 | 03/12/2021 |  |  | 360 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.Cx2030 | TT_Task | Electrical Equipment Yellow Tagging (Field Terminated equipment) | 26/10/2021 | 05/11/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C3270 | TT_Task | Assemble MER Complete Shipping Split (SE) | 07/06/2021 | 18/06/2021 | 03/05/2021 | 18/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C2220 | TT_Task | Early Topout | 09/02/2021 | 11/02/2021 | 11/01/2021 | 14/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C2250 | TT_Task | Datahall Finishes | 31/03/2021 | 14/04/2021 | 15/02/2021 | 27/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C2200 | TT_Task | Mechanical Corridor Finishes | 15/04/2021 | 06/05/2021 | 03/02/2021 | 25/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C2010 | TT_Task | Frame Top out | 02/01/2021 | 11/01/2021 | 28/12/2020 | 02/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C2060 | TT_Task | Exterior Equipment Pads - Electrical | 02/01/2021 | 15/01/2021 | 14/12/2020 | 16/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C2070 | TT_Task | Exterior Equipment Pads - Mechanical | 02/01/2021 | 15/01/2021 | 14/12/2020 | 16/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C2100 | TT_Task | Set Exterior Electrical OFCI Equipment - GEN | 31/03/2021 | 05/04/2021 | 17/03/2021 | 17/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C2110 | TT_Task | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | 06/05/2021 | 19/05/2021 | 12/04/2021 | 21/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C2140 | TT_Task | Frame wall MEPFP In wall roughin | 02/01/2021 | 07/01/2021 | 28/12/2020 | 08/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C2190 | TT_Task | Overhead MEPFP Rough-In | 01/02/2021 | 12/02/2021 | 07/01/2021 | 21/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C2130 | TT_Task | OverHead MEPFP Rough-In | 30/04/2021 | 14/05/2021 | 05/02/2021 | 20/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C2150 | TT_Task | Electrical surface mounted Rough-in Above AHU | 15/03/2021 | 19/03/2021 | 29/01/2021 | 04/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C2160 | TT_Task | VFD'S Installation Wiring | 31/07/2021 | 13/08/2021 | 27/07/2021 | 09/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C2020 | TT_Task | Electrical Underground Rough-In | 02/11/2020 | 16/11/2020 | 26/10/2020 | 07/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C2280 | TT_Task | Steel Support for OH Conductors Cable Tray Installation | 07/06/2021 | 10/06/2021 | 03/05/2021 | 06/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C2380 | TT_Task | Generator Utility Power Test-Term | 03/09/2021 | 14/09/2021 | 06/08/2021 | 16/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C2360 | TT_Task | Electrical Feeders to Mechanical Equipment Pull-Test-Term | 31/08/2021 | 24/09/2021 | 31/07/2021 | 24/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C2440 | TT_Task | Pull/term/Test PDU to Power bus | 25/08/2021 | 17/09/2021 | 29/07/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C2080 | TT_Task | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel Pipe Steel Supports) | 30/04/2021 | 05/05/2021 | 01/02/2021 | 05/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C2120 | TT_Task | Mechanical Equipment Piping Connections | 02/07/2021 | 10/07/2021 | 04/05/2021 | 10/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C2000 | TT_Task | Mechanical/Plumbing Underground Rough-In | 09/11/2020 | 23/11/2020 | 26/10/2020 | 07/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C2400 | TT_Task | Fire Alarm Installation | 31/08/2021 | 15/09/2021 | 31/07/2021 | 13/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C2430 | TT_Task | Controls Installation | 01/09/2021 | 16/09/2021 | 26/08/2021 |  | 1210 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C2370 | TT_Task | Lighting Installation | 11/09/2021 | 24/09/2021 | 16/08/2021 | 28/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C2170 | TT_Task | AHU/DOAS Equipment Setting | 15/05/2021 | 20/05/2021 | 17/03/2021 | 17/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C2180 | TT_Task | Hydronic Piping Installation | 30/06/2021 | 15/07/2021 | 01/06/2021 | 15/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C2230 | TT_Task | Floor Drain System Installation | 31/08/2021 | 15/09/2021 | 31/07/2021 | 13/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C2240 | TT_Task | Toilet Piping Installation / DW | 30/06/2021 | 15/07/2021 | 01/06/2021 | 15/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C2210 | TT_Task | Controls Installation | 16/08/2021 | 07/09/2021 | 27/07/2021 | 17/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C2050 | TT_Task | Fire Riser Installation | 30/11/2020 | 30/11/2020 | 28/11/2020 | 28/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C2090 | TT_Task | Fire Alarm System | 31/07/2021 | 13/08/2021 | 01/07/2021 | 16/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C2350 | TT_Task | PDU's Installation | 01/06/2021 | 03/06/2021 | 01/06/2021 | 03/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C2290 | TT_Task | Cable Tray Installation | 06/05/2021 | 19/05/2021 | 12/04/2021 | 24/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C2410 | TT_Task | Pull / Term / Test Conductors ( MER to PDU) | 01/09/2021 | 28/09/2021 | 25/08/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C2340 | TT_Task | EPMS Pull Wire / Term / Test | 02/09/2021 | 17/09/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C2390 | TT_Task | BMS Pull Wire / Term / Test | 02/09/2021 | 17/09/2021 |  |  | 170 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C2450 | TT_Task | Light Fixtures Installation | 30/08/2021 | 07/09/2021 | 30/08/2021 |  | 89 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C2420 | TT_Task | Controls Installation | 14/06/2021 | 26/06/2021 | 14/06/2021 | 26/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C2310 | TT_Task | Fire Alarm System | 31/08/2021 | 13/09/2021 | 31/07/2021 | 11/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.Cx2040 | TT_Task | Network Startup | 26/10/2021 | 05/11/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.Cx2100 | TT_Task | EPMS Checkout / Point to Point | 08/11/2021 | 18/11/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.Cx2010 | TT_Task | Electrical Equipment Yellow Tagging (Field Terminated equipment) | 13/10/2021 | 25/10/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C2300 | TT_Task | Assemble MER Complete Shipping Split (SE) | 07/06/2021 | 18/06/2021 | 04/05/2021 | 07/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C4190 | TT_Task | Early Topout | 08/02/2021 | 10/02/2021 | 18/01/2021 | 21/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C4210 | TT_Task | Datahall Finishes | 15/04/2021 | 28/04/2021 | 22/02/2021 | 01/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C4230 | TT_Task | Mechanical Corridor Finishes | 29/04/2021 | 20/05/2021 | 15/02/2021 | 10/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C4010 | TT_Task | Frame Top out | 31/03/2021 | 08/04/2021 | 03/02/2021 | 13/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C4060 | TT_Task | Exterior Equipment Pads - Electrical | 18/01/2021 | 30/01/2021 | 14/12/2020 | 16/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C4070 | TT_Task | Exterior Equipment Pads - Mechanical | 02/01/2021 | 15/01/2021 | 14/12/2020 | 16/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C4100 | TT_Task | Set Exterior Electrical OFCI Equipment - GEN | 31/03/2021 | 05/04/2021 | 31/03/2021 | 24/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C4110 | TT_Task | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | 06/05/2021 | 19/05/2021 | 12/04/2021 | 21/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C4130 | TT_Task | Frame wall MEPFP In wall roughin | 18/01/2021 | 22/01/2021 | 11/01/2021 | 15/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C4180 | TT_Task | Overhead MEPFP Rough-In | 01/02/2021 | 12/02/2021 | 15/01/2021 | 21/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C4140 | TT_Task | OverHead MEPFP Rough-In | 15/05/2021 | 29/05/2021 | 22/02/2021 | 09/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C4150 | TT_Task | Electrical surface mounted Rough-in Above AHU | 30/03/2021 | 03/04/2021 | 12/02/2021 | 19/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C4160 | TT_Task | VFD'S Installation Wiring | 31/08/2021 | 15/09/2021 | 31/07/2021 | 13/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C4020 | TT_Task | Electrical Underground Rough-In | 07/11/2020 | 21/11/2020 | 26/10/2020 | 07/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C4260 | TT_Task | Steel Support for OH Conductors Cable Tray Installation | 07/06/2021 | 10/06/2021 | 10/05/2021 | 14/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C4370 | TT_Task | Generator Utility Power Test-Term | 31/08/2021 | 10/09/2021 | 13/08/2021 | 24/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C4390 | TT_Task | Electrical Feeders to Mechanical Equipment Pull-Test-Term | 31/08/2021 | 24/09/2021 | 31/07/2021 | 24/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C4440 | TT_Task | Pull/term/Test PDU to Power bus | 31/08/2021 | 22/09/2021 | 25/08/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C4080 | TT_Task | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel Pipe Steel Supports) | 30/04/2021 | 05/05/2021 | 01/02/2021 | 05/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C4120 | TT_Task | Mechanical Equipment Piping Connections | 02/07/2021 | 10/07/2021 | 04/05/2021 | 10/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C4000 | TT_Task | Mechanical/Plumbing Underground Rough-In | 24/11/2020 | 11/12/2020 | 26/10/2020 | 07/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C4360 | TT_Task | Fire Alarm Installation | 31/08/2021 | 15/09/2021 | 06/08/2021 | 20/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C4410 | TT_Task | Controls Installation | 31/08/2021 | 15/09/2021 | 06/08/2021 | 20/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C4380 | TT_Task | Ligthing Installation | 31/08/2021 | 15/09/2021 |  |  | 180 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C4170 | TT_Task | AHU/DOAS Equipment Setting | 01/06/2021 | 05/06/2021 | 20/03/2021 | 20/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C4200 | TT_Task | Hydronic Piping Installation | 30/06/2021 | 15/07/2021 | 01/06/2021 | 15/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C4270 | TT_Task | Floor Drain System Installation | 31/08/2021 | 15/09/2021 | 31/07/2021 | 13/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C4330 | TT_Task | Toilet Piping Installation / DW | 01/06/2021 | 15/06/2021 | 01/06/2021 | 15/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C4240 | TT_Task | Controls Installation | 08/09/2021 | 29/09/2021 | 27/07/2021 | 31/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C4050 | TT_Task | Fire Riser Installation | 30/11/2020 | 30/11/2020 | 28/11/2020 | 28/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C4090 | TT_Task | Fire Alarm System | 31/08/2021 | 15/09/2021 | 31/07/2021 | 13/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C4350 | TT_Task | PDU's Installation | 07/06/2021 | 09/06/2021 | 14/07/2021 | 16/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C4280 | TT_Task | Cable Tray Installation | 01/06/2021 | 15/06/2021 | 05/05/2021 | 24/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C4420 | TT_Task | Pull / Term / Test Conductors ( MER to PDU) | 01/09/2021 | 28/09/2021 | 25/08/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C4340 | TT_Task | EPMS Pull Wire / Term / Test | 02/09/2021 | 17/09/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C4400 | TT_Task | BMS Pull Wire / Term / Test | 02/09/2021 | 17/09/2021 |  |  | 300 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C4450 | TT_Task | Light Fixtures Installation | 31/08/2021 | 08/09/2021 | 24/08/2021 | 31/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C4430 | TT_Task | Controls Installation | 28/06/2021 | 13/07/2021 | 27/07/2021 | 24/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C4300 | TT_Task | Fire Alarm System | 31/08/2021 | 13/09/2021 | 31/07/2021 | 11/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.Cx2110 | TT_Task | Network Startup | 08/11/2021 | 18/11/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.Cx2170 | TT_Task | EPMS Checkout / Point to Point | 19/11/2021 | 03/12/2021 |  |  | 360 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.Cx2050 | TT_Task | Electrical Equipment Yellow Tagging (Field Terminated equipment) | 26/10/2021 | 05/11/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.Cx3040 | TT_Task | Level 3 Cx - COLO-4 | 14/02/2022 | 26/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.Cx3030 | TT_Task | Load Bank IR Scan | 22/01/2022 | 12/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C4290 | TT_Task | Assemble MER Complete Shipping Split (SE) | 07/06/2021 | 18/06/2021 | 11/05/2021 | 28/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.Cx4000 | TT_Task | COLO 4 Level 4 Level 5 IST | 28/02/2022 | 20/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.E1320 | TT_Mile | MSFT Delivery -MER ROJ COLO 1 CELL 1 (11/6/20) | 21/12/2020 | 21/12/2020 | 16/12/2020 | 16/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-1961 | TT_Task | Exterior Equipment Pads - Electrical | 31/08/2020 | 15/09/2020 | 26/08/2020 | 25/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-1962 | TT_Task | Exterior Equipment Pads - Mechanical | 19/10/2020 | 02/11/2020 | 09/10/2020 | 13/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-1963 | TT_Task | Set Exterior Electrical OFCI Equipment | 02/11/2020 | 16/11/2020 | 19/10/2020 | 23/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-1964 | TT_Task | Set Exterior Mechanical CFCI Equipment (remaning mini splits) | 06/11/2020 | 20/11/2020 | 28/10/2020 | 22/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-1965 | TT_Task | Admin -Electrical Underground Rough-In | 10/08/2020 | 31/08/2020 | 07/08/2020 | 29/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-1967 | TT_Task | Generator Utility Power Pull-Test | 11/01/2021 | 25/01/2021 | 04/01/2021 | 09/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-1968 | TT_Task | Electrical Feeders to Mechanical Equipment Pull-Test-Term | 18/01/2021 | 10/02/2021 | 04/01/2021 | 20/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-1969 | TT_Task | Pull/term/Test PDU to Power bus | 11/01/2021 | 11/01/2021 | 30/01/2021 | 30/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-1970 | TT_Task | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel Pipe Steel Supports) | 02/11/2020 | 05/11/2020 | 30/10/2020 | 31/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-1971 | TT_Task | Mechanical Equipment Piping Connections | 03/11/2020 | 17/11/2020 | 31/10/2020 | 31/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-1972 | TT_Task | Mechanical Underground Rough-In | 10/08/2020 | 31/08/2020 | 08/08/2020 | 25/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-1975 | TT_Task | Fire Alarm Installation | 01/02/2021 | 15/02/2021 | 11/01/2021 | 15/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-1976 | TT_Task | Controls Installation | 16/02/2021 | 02/03/2021 | 20/01/2021 | 31/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-1977 | TT_Task | Lead Time for Rebar (Footings Walls) | 27/04/2020 | 31/05/2020 | 30/03/2020 | 21/04/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH.06.P1010 | TT_Mile | Mobilize on Site | 27/04/2020 | 27/04/2020 | 06/04/2020 | 06/04/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-P1020 | TT_Mile | Break Ground | 27/04/2020 | 27/04/2020 | 22/04/2020 | 22/04/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-C1.P1000 | TT_Mile | Foundation Start - Admin/COLO 1 | 27/04/2020 | 27/04/2020 | 22/04/2020 | 22/04/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-C1.P1100 | TT_Mile | Steel Erection - Admin/COLO 1 | 27/07/2020 | 27/07/2020 | 22/06/2020 | 22/06/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-C1.P1500 | TT_Mile | Fit out Start - Admin/COLO 1 | 02/11/2020 | 02/11/2020 | 19/10/2020 | 19/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-C1.P1400 | TT_Mile | SOG- ADMIN/ COLO1 Start | 31/08/2020 | 31/08/2020 | 10/08/2020 | 10/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-C2.P1000 | TT_Mile | Foundation Start - COLO 2 | 12/06/2020 | 12/06/2020 | 04/05/2020 | 04/05/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-C2.P1100 | TT_Mile | Steel Erection - COLO 2 | 10/08/2020 | 10/08/2020 | 07/07/2020 | 07/07/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-C2.P1500 | TT_Mile | Fit out Start - COLO 2 | 02/11/2020 | 02/11/2020 | 20/10/2020 | 20/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-C2.P1400 | TT_Mile | SOG- COLO 2 Start | 02/11/2020 | 02/11/2020 | 28/10/2020 | 28/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-C3.P1000 | TT_Mile | Foundation Start - COLO 3 | 22/06/2020 | 22/06/2020 | 29/05/2020 | 29/05/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-C3.P1100 | TT_Mile | Steel Erection -COLO 3 | 10/08/2020 | 10/08/2020 | 23/07/2020 | 23/07/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-C3.P1500 | TT_Mile | Fit out Start - COLO 3 | 02/11/2020 | 02/11/2020 | 26/10/2020 | 26/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-C3.P1400 | TT_Mile | SOG- COLO 3 Start | 02/11/2020 | 02/11/2020 | 05/10/2020 | 05/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-C4.P1000 | TT_Mile | Foundation Start - COLO 4 | 29/08/2020 | 29/08/2020 | 18/07/2020 | 18/07/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-C4.P1100 | TT_Mile | Steel Erection - COLO 4 | 31/08/2020 | 31/08/2020 | 08/08/2020 | 08/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-C4.P1500 | TT_Mile | Fit out Start - COLO 4 | 30/11/2020 | 30/11/2020 | 05/11/2020 | 05/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-C4.P1400 | TT_Mile | SOG- COLO 4 Start | 02/11/2020 | 02/11/2020 | 16/10/2020 | 16/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-C1.P1200 | TT_Mile | Insulated Metal Panel Start- Admin/COLO 1 | 10/08/2020 | 10/08/2020 | 07/07/2020 | 07/07/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-C1.P1300 | TT_Mile | Roof Panel Start -Admin/COLO 1 | 10/08/2020 | 10/08/2020 | 15/07/2020 | 15/07/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-C2.P1200 | TT_Mile | Insulated Metal Panel Start- COLO 2 | 10/08/2020 | 10/08/2020 | 20/07/2020 | 20/07/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-C2.P1300 | TT_Mile | Roof Panel Start -COLO 2 | 18/08/2020 | 18/08/2020 | 27/07/2020 | 27/07/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-C3.P1200 | TT_Mile | Insulated Metal Panel Start- COLO 3 | 31/08/2020 | 31/08/2020 | 15/08/2020 | 15/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-C3.P1300 | TT_Mile | Roof Panel Start -COLO 3 | 31/08/2020 | 31/08/2020 | 18/08/2020 | 18/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-C4.P1200 | TT_Mile | Insulated Metal Panel Start- COLO 4 | 31/08/2020 | 31/08/2020 | 22/08/2020 | 22/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-C4.P1300 | TT_Mile | Roof Panel Start - COLO 4 | 02/11/2020 | 02/11/2020 | 28/08/2020 | 28/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-C1.P1800 | TT_FinMile | Cx - Level 2 Start COLO 1 | 01/06/2021 | 01/06/2021 | 07/05/2021 | 07/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-C2.P1900 | TT_Mile | Cx - Level 2 Start COLO 2 | 02/09/2021 | 02/09/2021 | 21/08/2021 | 21/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-C3.P1800 | TT_Mile | Cx - Level 2 Start COLO 3 | 31/08/2021 | 31/08/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-C4.P1800 | TT_Mile | Cx - Level 2 Start COLO 4 | 13/10/2021 | 13/10/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-C1.P1600 | TT_Mile | Ready to Set Exterior MER | 02/11/2020 | 02/11/2020 | 12/10/2020 | 12/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-C1.P1700 | TT_Mile | Ready to Set Exterior Mechanical Equipment | 02/11/2020 | 02/11/2020 | 14/10/2020 | 14/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-C2.P1600 | TT_Mile | Ready to Set MER | 30/11/2020 | 30/11/2020 | 03/11/2020 | 03/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-C2.P1700 | TT_Mile | Ready to Set Exterior Mechanical Equipment | 30/11/2020 | 30/11/2020 | 13/11/2020 | 13/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-C3.P1600 | TT_Mile | Ready to Set Exterior MER | 02/01/2021 | 02/01/2021 | 30/11/2020 | 30/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-C3.P1700 | TT_Mile | Ready to Set Exterior Mechanical Equipment | 02/01/2021 | 02/01/2021 | 02/12/2020 | 02/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-C4.P1600 | TT_Mile | Ready to Set Exterior MER | 02/01/2021 | 02/01/2021 | 10/12/2020 | 10/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-C4.P1700 | TT_Mile | Ready to Set Exterior Mechanical Equipment | 02/01/2021 | 02/01/2021 | 10/12/2020 | 10/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.E1380 | TT_Mile | MSFT Delivery -MER ROJ COLO 1 CELL 3 (11/20/20) | 11/01/2021 | 11/01/2021 | 06/01/2021 | 06/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.E1330 | TT_Mile | MSFT Delivery -MER ROJ COLO 1 CELL 2 (11/13/20) | 02/01/2021 | 02/01/2021 | 22/12/2020 | 22/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.E1470 | TT_Mile | MSFT Delivery -MER ROJ COLO 1 CELL 4 (11/30/20) | 11/01/2021 | 11/01/2021 | 08/01/2021 | 08/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.E1300 | TT_Mile | MSFT Delivery -MER ROJ COLO 2 CELL 1 (12/15/20) | 01/03/2021 | 01/03/2021 | 04/02/2021 | 04/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.E1310 | TT_Mile | MSFT Delivery -MER ROJ COLO 2 CELL 2 (12/22/20) | 01/03/2021 | 01/03/2021 | 18/02/2021 | 18/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.E1360 | TT_Mile | MSFT Delivery -MER ROJ COLO 2 CELL 3 (12/28/20) | 01/03/2021 | 01/03/2021 | 23/02/2021 | 23/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.E1410 | TT_Mile | MSFT Delivery -MER ROJ COLO 2 CELL 4 (1/5/20) | 22/03/2021 | 22/03/2021 | 08/03/2021 | 08/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.E1340 | TT_Mile | MSFT Delivery -MER ROJ COLO 3 CELL 1 (1/29/21) | 26/04/2021 | 26/04/2021 | 03/04/2021 | 03/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.E1360 | TT_Mile | MSFT Delivery -MER ROJ COLO 3 CELL 3 (2/12/21) | 26/04/2021 | 26/04/2021 | 15/04/2021 | 15/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.E1350 | TT_Mile | MSFT Delivery -MER ROJ COLO 3 CELL 2 (2/5/21) | 26/04/2021 | 26/04/2021 | 09/04/2021 | 09/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.E1370 | TT_Mile | MSFT Delivery -MER ROJ COLO 3 CELL 4 (2/19/21) | 26/04/2021 | 26/04/2021 | 23/04/2021 | 23/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.E1360 | TT_Mile | MSFT Delivery -MER ROJ COLO 4 CELL 1 (3/12/21) | 28/04/2021 | 28/04/2021 | 27/04/2021 | 27/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.E1380 | TT_Mile | MSFT Delivery -MER ROJ COLO 4 CELL 3 (3/26/21) | 30/04/2021 | 30/04/2021 | 29/04/2021 | 29/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.E1370 | TT_Mile | MSFT Delivery -MER ROJ COLO 4 CELL 2 (3/19/21) | 17/05/2021 | 17/05/2021 | 03/05/2021 | 03/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.E1390 | TT_Mile | MSFT Delivery -MER ROJ COLO 4 CELL 4 (4/2/21) | 17/05/2021 | 17/05/2021 | 10/05/2021 | 10/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-1993 | TT_Task | MV Ductbanks Procurement | 12/08/2020 | 20/08/2020 | 27/07/2020 | 03/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-1994 | TT_Task | Telecom DuctBank / Vaults Procurement | 14/05/2020 | 18/05/2020 | 06/05/2020 | 20/06/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-1995 | TT_Task | Site Temp Power Procurement Infrastructure | 29/06/2020 | 31/08/2020 | 15/06/2020 | 31/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-1996 | TT_Task | MV Wire Procurement | 12/08/2020 | 03/11/2020 | 21/07/2020 | 12/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-1997 | TT_Task | Off-Site BIM Modeling Coordination | 27/04/2020 | 24/05/2020 | 14/04/2020 | 05/05/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-1998 | TT_Task | Underground Grounding Procurement | 27/04/2020 | 17/05/2020 | 07/04/2020 | 28/04/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-1999 | TT_Task | BIM Modeling (Under ground) | 05/05/2020 | 08/06/2020 | 05/05/2020 | 08/06/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2000 | TT_Task | Electrical Long Lead Equipment Procurement (Cablebus, Panel Boards) | 27/04/2020 | 21/06/2020 | 27/04/2020 | 31/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2001 | TT_Mile | PEMB Release | 24/02/2020 | 24/02/2020 | 24/02/2020 | 24/02/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2002 | TT_Mile | Phase 1B - Funding Release | 30/03/2020 | 30/03/2020 | 30/03/2020 | 30/03/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2003 | TT_Mile | Phase 1C - Funding Release | 10/08/2020 | 10/08/2020 | 30/06/2020 | 30/06/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2004 | TT_Task | URS Vault Procurement | 28/09/2020 | 11/11/2020 | 26/09/2020 | 29/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2008 | TT_Task | BIM Modeling (Above ground) | 02/08/2020 | 30/09/2020 | 15/06/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2010 | TT_Task | Lead Time for COLO 1 Structural Interior Steel | 10/08/2020 | 31/10/2020 | 30/06/2020 | 12/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2011 | TT_Task | Lead Time for Wall Roof Metal Panels | 27/04/2020 | 21/06/2020 | 07/04/2020 | 29/06/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2012 | TT_Task | Lead Time for Admin/COLO 1 Yard Steel | 31/08/2020 | 18/10/2020 | 30/06/2020 | 18/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2013 | TT_Task | Lead Time for HM Ext. frames | 27/04/2020 | 21/06/2020 | 07/04/2020 | 10/07/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.CS1120 | TT_Task | Erect Interior Structural Steel | 02/11/2020 | 06/11/2020 | 12/10/2020 | 24/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2016 | TT_Task | Water treatment Skids Procurement ( sourcing materials and Materail approval only) | 27/04/2020 | 06/11/2020 | 07/04/2020 | 06/07/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.Cx3050 | TT_Task | Weather (5 Days) - 3 remaining Check Delay #14 for updates | 02/10/2021 | 02/10/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-1997.1 | TT_Task | Neher Mcgrath Study | 02/07/2020 | 06/08/2020 | 22/06/2020 | 24/07/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.Cx2120 | TT_Task | OFCI Lvl 3 Testing Start up (Electrical Equipment) | 10/07/2021 | 26/07/2021 | 10/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.Cx2170 | TT_Task | OFCI Lvl 3 Testing Start up (Mechanical Equipment) | 10/07/2021 | 23/07/2021 | 10/07/2021 | 23/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.Cx3000 | TT_Task | Hydronic Pipe Flush (Open and closed Loop) | 13/07/2021 | 28/07/2021 | 13/07/2021 | 28/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.Cx3010 | TT_Task | Cooling Automation | 31/07/2021 | 13/08/2021 | 31/07/2021 | 12/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.Cx2130 | TT_Task | OFCI Lvl 3 Testing Start up (Electrical Equipment) | 06/07/2021 | 20/07/2021 | 06/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.Cx2110 | TT_Task | OFCI Lvl 3 Testing Start up (Mechanical Equipment) | 06/07/2021 | 19/07/2021 | 06/07/2021 | 19/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.Cx2160 | TT_Task | OFCI Lvl 3 Testing Start up (Electrical Equipment) | 10/07/2021 | 26/07/2021 | 10/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.Cx2180 | TT_Task | OFCI Lvl 3 Testing Start up (Mechanical Equipment) | 10/07/2021 | 23/07/2021 | 10/07/2021 | 23/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.Cx2140 | TT_Task | OFCI Lvl 3 Testing Start up (Electrical Equipment) | 10/07/2021 | 26/07/2021 | 10/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.Cx2080 | TT_Task | OFCI Lvl 3 Testing Start up (Mechanical Equipment) | 10/07/2021 | 23/07/2021 | 10/07/2021 | 23/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.Cx3020 | TT_Task | BAS Prefunctional Testing on Construction Server | 31/07/2021 | 24/08/2021 | 26/07/2021 | 28/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2029 | TT_Mile | Schneider Electric ROJ Received from MSFT | 27/04/2020 | 27/04/2020 | 13/04/2020 | 13/04/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.Cx3050 | TT_Task | Weather (5 Days) - 3 remaining Check Delay #14 for updates | 28/02/2022 | 28/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.Cx3000 | TT_Task | Hydronic Pipe Flush (Open and closed Loop) | 27/09/2021 | 09/10/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.Cx3010 | TT_Task | Cooling Automation | 11/10/2021 | 25/10/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.Cx3020 | TT_Task | BAS Prefunctional Testing on Construction Server | 07/10/2021 | 30/10/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.Cx3000 | TT_Task | Hydronic Pipe Flush (Open and closed Loop) | 22/10/2021 | 04/11/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.Cx3010 | TT_Task | Cooling Automation | 05/11/2021 | 19/11/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.Cx3020 | TT_Task | BAS Prefunctional Testing on Construction Server | 01/11/2021 | 24/11/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.Cx3000 | TT_Task | Hydronic Pipe Flush (Open and closed Loop) | 30/11/2021 | 13/12/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.Cx3010 | TT_Task | Cooling Automation | 14/12/2021 | 30/12/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.Cx3020 | TT_Task | BAS Prefunctional Testing on Construction Server | 07/12/2021 | 04/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.Cx2110 | TT_Task | OFCI Lvl 3 Testing Start up (Electrical Equipment) | 16/09/2021 | 05/10/2021 |  |  | 20 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.Cx2130 | TT_Task | OFCI Lvl 3 Testing Start up (Mechanical Equipment) | 16/09/2021 | 30/09/2021 |  |  | 50 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.Cx2170 | TT_Task | OFCI Lvl 3 Testing Start up (Electrical Equipment) | 18/09/2021 | 07/10/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.Cx2190 | TT_Task | OFCI Lvl 3 Testing Start up (Mechanical Equipment) | 22/09/2021 | 06/10/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.Cx2080 | TT_Task | OFCI Lvl 3 Testing Start up (Electrical Equipment) | 18/09/2021 | 07/10/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.Cx2120 | TT_Task | OFCI Lvl 3 Testing Start up (Mechanical Equipment) | 22/09/2021 | 06/10/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.Cx2150 | TT_Task | OFCI Lvl 3 Testing Start up (Electrical Equipment) | 18/09/2021 | 07/10/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.Cx2180 | TT_Task | OFCI Lvl 3 Testing Start up (Mechanical Equipment) | 18/09/2021 | 02/10/2021 |  |  | 30 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.Cx2070 | TT_Task | OFCI Lvl 3 Testing Start up (Electrical Equipment) | 27/09/2021 | 14/10/2021 |  |  | 100 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.Cx2110 | TT_Task | OFCI Lvl 3 Testing Start up (Mechanical Equipment) | 05/10/2021 | 19/10/2021 |  |  | 100 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.Cx2160 | TT_Task | OFCI Lvl 3 Testing Start up (Electrical Equipment) | 08/10/2021 | 27/10/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.Cx2180 | TT_Task | OFCI Lvl 3 Testing Start up (Mechanical Equipment) | 18/10/2021 | 30/10/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.Cx2120 | TT_Task | OFCI Lvl 3 Testing Start up (Electrical Equipment) | 27/09/2021 | 14/10/2021 |  |  | 100 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.Cx2130 | TT_Task | OFCI Lvl 3 Testing Start up (Mechanical Equipment) | 27/09/2021 | 09/10/2021 |  |  | 170 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.Cx2170 | TT_Task | OFCI Lvl 3 Testing Start up (Electrical Equipment) | 08/10/2021 | 27/10/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.Cx2190 | TT_Task | OFCI Lvl 3 Testing Start up (Mechanical Equipment) | 08/10/2021 | 22/10/2021 |  |  | 70 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.Cx2070 | TT_Task | OFCI Lvl 3 Testing Start up (Electrical Equipment) | 08/11/2021 | 29/11/2021 |  |  | 100 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.Cx2090 | TT_Task | OFCI Lvl 3 Testing Start up (Mechanical Equipment) | 08/11/2021 | 20/11/2021 |  |  | 100 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.Cx2150 | TT_Task | OFCI Lvl 3 Testing Start up (Electrical Equipment) | 19/11/2021 | 10/12/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.Cx2160 | TT_Task | OFCI Lvl 3 Testing Start up (Mechanical Equipment) | 19/11/2021 | 06/12/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.Cx2120 | TT_Task | OFCI Lvl 3 Testing Start up (Electrical Equipment) | 08/11/2021 | 29/11/2021 |  |  | 100 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.Cx2130 | TT_Task | OFCI Lvl 3 Testing Start up (Mechanical Equipment) | 08/11/2021 | 20/11/2021 |  |  | 100 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.Cx2180 | TT_Task | OFCI Lvl 3 Testing Start up (Electrical Equipment) | 19/11/2021 | 10/12/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.Cx2190 | TT_Task | OFCI Lvl 3 Testing Start up (Mechanical Equipment) | 19/11/2021 | 06/12/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.Cx3050 | TT_Task | Weather (5 Days) - 3 remaining Check Delay #14 for updates | 19/01/2022 | 19/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.Cx3050 | TT_Task | Weather (5 Days) - 0 remaining Check Delay #14 for updates | 04/12/2021 | 04/12/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C1010 | TT_Task | Exterior Equipment Pads - for UPM's | 28/09/2020 | 01/10/2020 | 21/09/2020 | 24/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C1040 | TT_Task | Set Electrical Equipment-UPM | 02/01/2021 | 06/01/2021 | 08/12/2020 | 08/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C3020 | TT_Task | Exterior Equipment Pads - for UPM's | 28/09/2020 | 01/10/2020 | 21/09/2020 | 24/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C3040 | TT_Task | Set Electrical Equipment-UPM Cell -3 | 11/12/2020 | 15/12/2020 | 24/11/2020 | 24/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C2010 | TT_Task | Exterior Equipment Pads - for UPM's | 02/11/2020 | 05/11/2020 | 19/10/2020 | 22/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C2040 | TT_Task | Set Electrical Equipment-UPM | 30/11/2020 | 03/12/2020 | 24/11/2020 | 24/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C4020 | TT_Task | Exterior Equipment Pads - for UPM's | 28/09/2020 | 01/10/2020 | 21/09/2020 | 24/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C4040 | TT_Task | Set Electrical Equipment-UPM | 30/11/2020 | 03/12/2020 | 24/11/2020 | 24/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C1020 | TT_Task | Exterior Equipment Pads - for UPM's | 30/11/2020 | 03/12/2020 | 09/11/2020 | 13/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C1030 | TT_Task | Set Electrical Equipment-UPM | 02/01/2021 | 06/01/2021 | 08/12/2020 | 08/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C3020 | TT_Task | Exterior Equipment Pads - for UPM's | 30/11/2020 | 03/12/2020 | 09/11/2020 | 13/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C3040 | TT_Task | Set Electrical Equipment-UPM | 02/01/2021 | 06/01/2021 | 16/12/2020 | 17/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C2010 | TT_Task | Exterior Equipment Pads - for UPM's | 30/11/2020 | 03/12/2020 | 02/11/2020 | 04/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C2020 | TT_Task | Set Electrical Equipment-UPM | 02/01/2021 | 06/01/2021 | 04/11/2020 | 05/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C4010 | TT_Task | Exterior Equipment Pads - for UPM's | 30/11/2020 | 03/12/2020 | 02/11/2020 | 05/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C4030 | TT_Task | Set Electrical Equipment-UPM | 02/01/2021 | 06/01/2021 | 10/12/2020 | 11/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C1020 | TT_Task | Exterior Equipment Pads - for UPM's | 02/01/2021 | 06/01/2021 | 30/11/2020 | 02/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C1040 | TT_Task | Set Electrical Equipment-UPM | 07/01/2021 | 11/01/2021 | 29/12/2020 | 30/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C3020 | TT_Task | Exterior Equipment Pads - for UPM's | 02/01/2021 | 06/01/2021 | 07/12/2020 | 09/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C3040 | TT_Task | Set Electrical Equipment-UPM | 11/01/2021 | 14/01/2021 | 04/01/2021 | 04/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C2010 | TT_Task | Exterior Equipment Pads - for UPM's | 02/01/2021 | 06/01/2021 | 01/12/2020 | 02/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C2040 | TT_Task | Set Electrical Equipment-UPM | 07/01/2021 | 12/01/2021 | 18/12/2020 | 19/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C4010 | TT_Task | Exterior Equipment Pads - for UPM's | 02/01/2021 | 06/01/2021 | 04/12/2020 | 09/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C4040 | TT_Task | Set Electrical Equipment-UPM | 11/01/2021 | 14/01/2021 | 04/01/2021 | 04/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C1030 | TT_Task | Exterior Equipment Pads - for UPM's | 02/01/2021 | 06/01/2021 | 01/12/2020 | 04/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C1040 | TT_Task | Set Electrical Equipment-UPM | 07/01/2021 | 11/01/2021 | 30/12/2020 | 31/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C3030 | TT_Task | Exterior Equipment Pads - for UPM's | 07/01/2021 | 11/01/2021 | 01/12/2020 | 04/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C3040 | TT_Task | Set Electrical Equipment-UPM | 11/01/2021 | 14/01/2021 | 04/01/2021 | 04/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C2030 | TT_Task | Exterior Equipment Pads - for UPM's | 02/01/2021 | 06/01/2021 | 14/12/2020 | 16/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C2040 | TT_Task | Set Electrical Equipment-UPM | 11/01/2021 | 14/01/2021 | 04/01/2021 | 04/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C4030 | TT_Task | Exterior Equipment Pads - for UPM's | 07/01/2021 | 11/01/2021 | 14/12/2020 | 16/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C4040 | TT_Task | Set Electrical Equipment-UPM | 01/03/2021 | 04/03/2021 | 04/01/2021 | 07/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1910 | TT_FinMile | Site Work Complete | 28/09/2021 | 28/09/2021 |  |  | 1180 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-C1.P1900 | TT_FinMile | Admin / COLO 1 CSA complete | 03/09/2021 | 03/09/2021 | 13/07/2021 | 13/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C4490 | TT_FinMile | Mechanical Corridor complete | 03/09/2021 | 03/09/2021 | 29/07/2021 | 29/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C4400 | TT_FinMile | Data Hall complete | 30/06/2021 | 30/06/2021 | 23/06/2021 | 23/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-C2.P1800 | TT_FinMile | COLO 2 CSA complete | 31/08/2021 | 31/08/2021 | 19/07/2021 | 19/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-C3.P1900 | TT_FinMile | COLO 3 CSA complete | 31/08/2021 | 31/08/2021 | 13/08/2021 | 13/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-C4.P1900 | TT_FinMile | COLO 4 CSA complete | 07/10/2021 | 07/10/2021 |  |  | 1100 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.Cx4020 | TT_Task | Punch List - Admin/COLO 1 | 30/10/2021 | 12/11/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06AD-1021.1 | TT_Task | Set Mechanical Equipment | 23/11/2020 | 14/12/2020 | 16/11/2020 | 18/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2101 | TT_Task | Lead time for Drywall/Framing | 10/08/2020 | 05/09/2020 | 10/08/2020 | 12/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2102 | TT_Task | Design / Lead Time for MP overhead | 29/06/2020 | 28/07/2020 | 22/06/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2103 | TT_Task | Design / Lead Time for Fire Protection | 31/08/2020 | 29/09/2020 | 27/07/2020 | 28/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2104 | TT_Task | Design / Lead Time for Fire Alarm | 29/06/2020 | 27/08/2020 | 22/06/2020 | 28/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2105 | TT_Task | Design / Lead Time for Electrical/Telecom (OFCI Telecom BOM Materials) | 10/08/2020 | 07/11/2020 | 01/07/2020 | 12/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2106 | TT_Task | Design / Lead Time for Busway (OFCI Starline BOM Materials) | 26/11/2020 | 14/01/2021 | 21/09/2020 | 19/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2109 | TT_FinMile | Admin/COLO-1 BIM Signoff | 06/10/2020 | 06/10/2020 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2111 | TT_FinMile | Phase 1C1- MSFT Commitment for steel crew | 29/06/2020 | 29/06/2020 | 11/06/2020 | 11/06/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.CS1020 | TT_Task | Perimeter Foundations - Waterproof Backfill | 26/05/2020 | 06/06/2020 | 26/05/2020 | 17/06/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.AD.CS1010 | TT_Task | Perimeter Foundations - Waterproof/Backfill | 01/06/2020 | 04/06/2020 | 27/05/2020 | 05/06/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.E1120 | TT_FinMile | Pad Ready for MER COLO-2 Cell-1 | 30/11/2020 | 30/11/2020 | 17/11/2020 | 17/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.E1210 | TT_FinMile | Pad Ready for MER COLO-2 Cell-3 | 30/11/2020 | 30/11/2020 | 19/11/2020 | 19/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.E1130 | TT_FinMile | Pad Ready for MER COLO-2 Cell-2 | 30/11/2020 | 30/11/2020 | 03/11/2020 | 03/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.E1200 | TT_FinMile | Pad Ready for MER COLO-2 Cell-4 | 30/11/2020 | 30/11/2020 | 05/11/2020 | 05/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.E1120 | TT_FinMile | Pad Ready for MER COLO-3 Cell-1 | 02/01/2021 | 02/01/2021 | 30/11/2020 | 30/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.E1260 | TT_FinMile | Pad Ready for MER COLO-3 Cell-3 | 02/01/2021 | 02/01/2021 | 04/12/2020 | 04/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.E1130 | TT_FinMile | Pad Ready for MER COLO-3 Cell-2 | 02/01/2021 | 02/01/2021 | 11/12/2020 | 11/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.E1270 | TT_FinMile | Pad Ready for MER COLO-3 Cell-4 | 02/01/2021 | 02/01/2021 | 11/12/2020 | 11/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.E1120 | TT_FinMile | Pad Ready for MER COLO-4 Cell-1 | 02/01/2021 | 02/01/2021 | 10/12/2020 | 10/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.E1220 | TT_FinMile | Pad Ready for MER COLO-4 Cell-3 | 02/01/2021 | 02/01/2021 | 10/12/2020 | 10/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.E1130 | TT_FinMile | Pad Ready for MER COLO-4 Cell-2 | 02/01/2021 | 02/01/2021 | 16/12/2020 | 16/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.E1230 | TT_FinMile | Pad Ready for MER COLO-4 Cell-4 | 02/01/2021 | 02/01/2021 | 16/12/2020 | 16/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.E1140 | TT_FinMile | Pad Ready for MER COLO-1 Cell-1 | 02/11/2020 | 02/11/2020 | 10/10/2020 | 10/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.E1220 | TT_FinMile | Pad Ready for MER COLO-1 Cell-3 | 02/11/2020 | 02/11/2020 | 09/10/2020 | 09/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.E1150 | TT_FinMile | Pad Ready for MER COLO-1 Cell-2 | 02/11/2020 | 02/11/2020 | 19/10/2020 | 19/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.E1230 | TT_FinMile | Pad Ready for MER COLO-1 Cell-4 | 02/11/2020 | 02/11/2020 | 19/10/2020 | 19/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2131 | TT_Task | MV Ductbanks Procurement DRB#1 JAZ to UMS/URS UPM to UMS | 14/09/2020 | 20/09/2020 | 31/08/2020 | 06/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2132 | TT_Task | MV Wire Procurement DRB#1 JAZ to UMS/URS UPM to UMS | 12/08/2020 | 03/11/2020 | 04/08/2020 | 26/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2133 | TT_Task | UMS Vault Procurement DRB#1 | 28/09/2020 | 07/11/2020 | 26/09/2020 | 29/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2134 | TT_Task | DRB#1 BIM Modeling Coordination DRB#1 JAZ to UMS/URS UPM to UMS | 10/08/2020 | 23/08/2020 | 21/07/2020 | 03/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2135 | TT_Task | Site- Neher Mcgrath Study DRB#1 JAZ to UMS/URS UPM to UMS | 11/08/2020 | 24/08/2020 | 04/08/2020 | 26/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2140.2 | TT_FinMile | CO- DRB# 1 - Approved | 29/08/2020 | 29/08/2020 | 20/07/2020 | 20/07/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2140.1 | TT_Task | MSFT Issue DRB #1 for Review | 26/05/2020 | 01/06/2020 | 19/05/2020 | 20/07/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1840 | TT_Task | Yellow Tagging for URS | 01/02/2021 | 24/02/2021 | 13/02/2021 | 16/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1570 | TT_Task | Set MV Gear (UMS) | 21/12/2020 | 28/12/2020 | 11/12/2020 | 16/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C1250 | TT_Task | Lift Set MER in Place | 02/01/2021 | 07/01/2021 | 16/12/2020 | 16/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C3210 | TT_Task | Lift Set MER in Place | 11/01/2021 | 18/01/2021 | 06/01/2021 | 07/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C4270 | TT_Task | Lift Set MER in Place | 11/01/2021 | 18/01/2021 | 08/01/2021 | 09/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C1250 | TT_Task | Lift Set MER in Place | 01/03/2021 | 05/03/2021 | 04/02/2021 | 04/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C3230 | TT_Task | Lift Set MER in Place | 23/03/2021 | 27/03/2021 | 01/03/2021 | 02/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C2290 | TT_Task | Lift Set MER in Place | 22/03/2021 | 26/03/2021 | 01/03/2021 | 01/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C4220 | TT_Task | Lift Set MER in Place | 22/03/2021 | 26/03/2021 | 08/03/2021 | 08/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C1230 | TT_Task | Lift Set MER in Place | 26/04/2021 | 30/04/2021 | 03/04/2021 | 03/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C3200 | TT_Task | Lift Set MER in Place | 30/04/2021 | 06/05/2021 | 15/04/2021 | 15/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C2260 | TT_Task | Lift Set MER in Place | 26/04/2021 | 30/04/2021 | 09/04/2021 | 09/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C4270 | TT_Task | Lift Set MER in Place | 07/05/2021 | 12/05/2021 | 24/04/2021 | 24/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C1230 | TT_Task | Lift Set MER in Place | 01/06/2021 | 05/06/2021 | 27/04/2021 | 27/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C3210 | TT_Task | Lift Set MER in Place | 01/06/2021 | 05/06/2021 | 30/04/2021 | 03/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C2270 | TT_Task | Lift Set MER in Place | 01/06/2021 | 05/06/2021 | 03/05/2021 | 04/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C4250 | TT_Task | Lift Set MER in Place | 01/06/2021 | 05/06/2021 | 10/05/2021 | 10/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C2270 | TT_Task | Lift Set MER in Place | 02/01/2021 | 07/01/2021 | 22/12/2020 | 23/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.AD.CS1040 | TT_Task | Secondary Steel | 10/08/2020 | 17/08/2020 | 02/07/2020 | 10/07/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.CS1040 | TT_Task | Secondary Steel | 10/08/2020 | 17/08/2020 | 01/07/2020 | 09/07/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.CS1030 | TT_Task | Secondary Steel | 10/08/2020 | 17/08/2020 | 23/07/2020 | 04/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.CS1030 | TT_Task | Secondary Steel | 31/08/2020 | 05/09/2020 | 06/08/2020 | 15/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.CS1030 | TT_Task | Secondary Steel | 31/08/2020 | 08/09/2020 | 21/08/2020 | 26/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1310 | TT_Task | Set MV Gear (URS) | 23/11/2020 | 30/11/2020 | 16/11/2020 | 20/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2189 | TT_Task | JAZ Riser Support DRB#1 Procurement/ Jaz Foundations/Construction | 10/08/2020 | 18/10/2020 | 21/07/2020 | 06/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2190 | TT_Task | UPM to UMS Vaults Procurement DRB#1 | 08/09/2020 | 12/10/2020 | 03/08/2020 | 24/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1370 | TT_Task | Set UMS vault | 25/11/2020 | 08/12/2020 | 30/10/2020 | 07/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1850 | TT_Task | Yellow Tagging for UMS (includes GC, vendor Lvl-2) | 01/02/2021 | 24/02/2021 | 13/02/2021 | 16/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C1360 | TT_Task | GEN UPM to MER Cable Bus Install | 11/01/2021 | 22/01/2021 | 05/01/2021 | 16/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C3350 | TT_Task | GEN UPM to MER Cable Bus Install | 01/02/2021 | 12/02/2021 | 18/01/2021 | 25/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C2390 | TT_Task | GEN UPM to MER Cable Bus Install | 20/01/2021 | 30/01/2021 | 06/01/2021 | 20/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C4370 | TT_Task | GEN UPM to MER Cable Bus Install | 04/02/2021 | 13/02/2021 | 25/01/2021 | 05/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C1380 | TT_Task | GEN UPM to MER Cable Bus Install | 22/03/2021 | 01/04/2021 | 05/03/2021 | 13/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C3340 | TT_Task | GEN UPM to MER Cable Bus Instal | 16/04/2021 | 27/04/2021 | 18/03/2021 | 25/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C2370 | TT_Task | GEN UPM to MER Cable Bus Instal | 25/03/2021 | 05/04/2021 | 16/03/2021 | 31/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C4310 | TT_Task | GEN UPM to MER Cable Bus Instal | 15/04/2021 | 26/04/2021 | 18/03/2021 | 08/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C1320 | TT_Task | GEN UPM to MER Cable Bus Install | 30/04/2021 | 12/05/2021 | 24/04/2021 | 07/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C3280 | TT_Task | GEN UPM to MER Cable Bus Instal | 01/06/2021 | 11/06/2021 | 05/06/2021 | 18/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C2330 | TT_Task | GEN UPM to MER Cable Bus Instal | 17/05/2021 | 28/05/2021 | 05/05/2021 | 17/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C4320 | TT_Task | GEN UPM to MER Cable Bus Instal | 07/06/2021 | 18/06/2021 | 14/06/2021 | 22/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C1320 | TT_Task | GEN UPM to MER Cable Bus Instal | 14/07/2021 | 26/07/2021 | 14/06/2021 | 25/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C3320 | TT_Task | GEN UPM to MER Cable Bus Instal | 30/06/2021 | 13/07/2021 | 10/07/2021 | 16/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C2330 | TT_Task | GEN UPM to MER Cable Bus Instal | 30/06/2021 | 13/07/2021 | 15/07/2021 | 27/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C4310 | TT_Task | GEN UPM to MER Cable Bus Instal | 31/07/2021 | 11/08/2021 | 16/07/2021 | 27/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C1150 | TT_Task | HAC Installation | 02/01/2021 | 06/01/2021 | 19/12/2020 | 22/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C1260 | TT_Task | Power Bus Installation | 01/03/2021 | 11/03/2021 | 11/02/2021 | 23/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C3140 | TT_Task | HAC Installation | 04/01/2021 | 07/01/2021 | 04/01/2021 | 07/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C3220 | TT_Task | Power Bus Installation | 02/03/2021 | 12/03/2021 | 24/02/2021 | 08/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C2150 | TT_Task | HAC Installation | 04/01/2021 | 07/01/2021 | 23/12/2020 | 31/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C2240 | TT_Task | Power Bus Installation | 01/03/2021 | 11/03/2021 | 11/02/2021 | 23/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C4140 | TT_Task | HAC Installation | 11/01/2021 | 14/01/2021 | 04/01/2021 | 07/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C4210 | TT_Task | Power Bus Installation | 12/03/2021 | 24/03/2021 | 24/02/2021 | 10/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C1180 | TT_Task | HAC Installation | 01/02/2021 | 15/02/2021 | 18/01/2021 | 29/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C1270 | TT_Task | Power Bus Installation | 26/03/2021 | 06/04/2021 | 10/03/2021 | 19/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C3170 | TT_Task | HAC Installation | 03/02/2021 | 17/02/2021 | 25/01/2021 | 03/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C3260 | TT_Task | Power Bus Installation | 22/03/2021 | 01/04/2021 | 20/03/2021 | 24/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C2160 | TT_Task | HAC Installation | 01/02/2021 | 15/02/2021 | 18/01/2021 | 29/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C2260 | TT_Task | Power Bus Installation | 26/03/2021 | 06/04/2021 | 11/03/2021 | 20/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C4140 | TT_Task | HAC Installation | 01/02/2021 | 15/02/2021 | 25/01/2021 | 02/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C4210 | TT_Task | Power Bus Installation | 31/03/2021 | 12/04/2021 | 20/03/2021 | 24/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C1270 | TT_Task | HAC Installation | 31/03/2021 | 02/04/2021 | 03/02/2021 | 20/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C1350 | TT_Task | Power Bus Installation | 30/04/2021 | 06/05/2021 | 12/04/2021 | 24/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C3250 | TT_Task | HAC Installation | 07/04/2021 | 09/04/2021 | 03/02/2021 | 20/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C3310 | TT_Task | Power Bus Installation | 01/06/2021 | 05/06/2021 | 19/04/2021 | 30/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C2280 | TT_Task | HAC Installation | 03/04/2021 | 06/04/2021 | 03/02/2021 | 20/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C2340 | TT_Task | Power Bus Installation | 01/06/2021 | 05/06/2021 | 08/05/2021 | 16/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C4280 | TT_Task | HAC Installation | 12/04/2021 | 14/04/2021 | 03/02/2021 | 20/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C4340 | TT_Task | Power Bus Installation | 07/06/2021 | 11/06/2021 | 19/04/2021 | 30/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C1270 | TT_Task | HAC Installation | 15/04/2021 | 28/04/2021 | 09/03/2021 | 26/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C1350 | TT_Task | Power Bus Installation | 07/06/2021 | 11/06/2021 | 07/05/2021 | 15/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C3230 | TT_Task | HAC Installation | 29/04/2021 | 13/05/2021 | 09/03/2021 | 26/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C3340 | TT_Task | Power Bus Installation | 01/06/2021 | 05/06/2021 | 01/06/2021 | 23/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C2260 | TT_Task | HAC Installation | 29/04/2021 | 13/05/2021 | 09/03/2021 | 26/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C2320 | TT_Task | Power Bus Installation | 14/06/2021 | 18/06/2021 | 01/05/2021 | 13/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C4220 | TT_Task | HAC Installation | 07/05/2021 | 20/05/2021 | 09/03/2021 | 26/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C4320 | TT_Task | Power Bus Installation | 31/07/2021 | 05/08/2021 | 24/06/2021 | 13/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1060 | TT_Task | Vault- set 1st Vault Along UMS Duct bank run | 03/09/2020 | 05/09/2020 | 24/08/2020 | 26/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1080 | TT_Task | Duct bank- COLO-1 UPM to north vault | 19/10/2020 | 20/10/2020 | 02/10/2020 | 05/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1090 | TT_Task | Duct bank- COLO-2 UPM to north Valut | 19/10/2020 | 22/10/2020 | 05/10/2020 | 07/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1250 | TT_Task | Set URS Vault | 16/11/2020 | 25/11/2020 | 30/10/2020 | 06/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1140 | TT_Task | Duct Bank- Building to URS - 1st Half | 26/09/2020 | 05/10/2020 | 26/09/2020 | 06/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1180 | TT_Task | Duct Bank- Building to URS(upto horse shoe) - 2nd Half | 30/09/2020 | 08/10/2020 | 21/09/2020 | 06/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1070 | TT_Task | Vault- Set 2nd vault Along UMS Duct Run near COLO-2 | 08/09/2020 | 10/09/2020 | 24/08/2020 | 26/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1230 | TT_Task | Duct Bank - Vault to Vault along UMS duct Run - horseshoe | 26/10/2020 | 07/11/2020 | 12/10/2020 | 17/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1270 | TT_Task | Duct Bank - COLO-3 UPM to Vault UMS Run | 19/10/2020 | 22/10/2020 | 16/10/2020 | 21/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1150 | TT_Task | Vault- Set vault along URS to JAZ run | 16/11/2020 | 18/11/2020 | 02/11/2020 | 04/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1320 | TT_Task | Duct Bank - URS to vault - URS to JAZ run | 16/11/2020 | 23/11/2020 | 02/11/2020 | 09/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1410 | TT_Task | Duct Bank - Vault To JAZ - URS to JAZ run | 02/11/2020 | 09/11/2020 | 26/10/2020 | 04/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1170 | TT_Task | Vault- Set vault along UMS to JAZ run | 19/11/2020 | 21/11/2020 | 05/11/2020 | 07/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1210 | TT_Task | Duct Bank - JAZ to vault- UMS to JAZ run | 16/11/2020 | 23/11/2020 | 29/10/2020 | 04/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1470 | TT_Task | Duct Bank - Vault to UMS- UMS to JAZ run | 16/11/2020 | 23/11/2020 | 13/11/2020 | 20/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1550 | TT_Task | Duct Bank - south vault (along UMS duct run) to UMS | 21/11/2020 | 07/12/2020 | 12/11/2020 | 20/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1590 | TT_Task | Duct Bank - COLO-4 UPM to UMS | 23/11/2020 | 30/11/2020 | 09/11/2020 | 14/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1260 | TT_Task | Duct Back- Admin UPM to Vault | 23/10/2020 | 30/10/2020 | 24/08/2020 | 28/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1100 | TT_Task | Duct Bank Admin UPM to COLO-1 UPM | 24/09/2020 | 28/09/2020 | 17/08/2020 | 19/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1020 | TT_Task | Duct Bank - COLO1- UPM to UPM | 10/08/2020 | 13/08/2020 | 06/08/2020 | 22/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1190 | TT_Task | Vault- Set North vault- Along UPM to Vault | 09/10/2020 | 12/10/2020 | 17/08/2020 | 19/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1280 | TT_Task | Duct Bank COLO-2 UPM to Vault | 19/10/2020 | 22/10/2020 | 28/09/2020 | 01/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1240 | TT_Task | Vault - Set North Vault Along Vault to URS run | 23/10/2020 | 27/10/2020 | 20/08/2020 | 22/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1340 | TT_Task | Vault - Set South Vault Along Vault to URS run | 07/11/2020 | 10/11/2020 | 17/08/2020 | 19/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1580 | TT_Task | Vault - Set South Vault along UPM to Vault | 23/11/2020 | 25/11/2020 | 20/08/2020 | 22/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1390 | TT_Task | Duct Bank - Building to North Vault URS run | 23/10/2020 | 31/10/2020 | 02/10/2020 | 10/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1460 | TT_Task | Duct Bank - Builing to South Vault- URS Run | 02/11/2020 | 09/11/2020 | 02/10/2020 | 10/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1620 | TT_Task | Duct Bank - Vault to COLO-3 UPM | 10/11/2020 | 13/11/2020 | 12/10/2020 | 15/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1670 | TT_Task | Duct Bank - Vault to COLO-4 UPM | 16/11/2020 | 21/11/2020 | 12/10/2020 | 15/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1110 | TT_Task | Duct Bank - North Crossover (URS to west Vault Run) | 14/09/2020 | 26/09/2020 | 02/09/2020 | 09/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1200 | TT_Task | Duct Bank - South Cross over (URS to west Vault Run) | 28/09/2020 | 12/10/2020 | 02/09/2020 | 09/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1220 | TT_Task | Duct Bank - COLO-3 UPM to UPM | 06/11/2020 | 10/11/2020 | 10/10/2020 | 15/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1050 | TT_Task | Duct Bank - COLO2- UPM to UPM | 31/08/2020 | 03/09/2020 | 24/08/2020 | 29/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1350 | TT_Task | Duct Bank - COLO-4 UPM to UPM | 25/11/2020 | 02/12/2020 | 10/10/2020 | 15/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1290 | TT_Task | Pull Cross Overs- COLO-1 CELL-3 to CELL-4 | 02/01/2021 | 04/01/2021 | 28/12/2020 | 31/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1420 | TT_Task | Pull Cross Overs- COLO-2 CELL-3 to CELL-4 | 05/02/2021 | 08/02/2021 | 14/01/2021 | 15/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1520 | TT_Task | Pull Cross Overs- COLO-3 CELL-3 to CELL-4 | 09/02/2021 | 10/02/2021 | 12/01/2021 | 13/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1710 | TT_Task | Pull Cross Overs- COLO-4 CELL-3 to CELL-4 | 13/02/2021 | 15/02/2021 | 16/01/2021 | 16/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1380 | TT_Task | Pull UPM to UPM COLO-1 - CELL-1 to Cell-3 | 05/01/2021 | 06/01/2021 | 28/12/2020 | 31/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1400 | TT_Task | Pul UPM to UPM COLO-2- CELL-1 to Cell-3 | 11/01/2021 | 12/01/2021 | 02/01/2021 | 04/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1510 | TT_Task | Pull UPM to UPM COLO-3 - CELL-1 to Cell-3 | 15/01/2021 | 18/01/2021 | 09/01/2021 | 13/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1720 | TT_Task | Pull UPM to UPM COLO-4 - CELL-1 to Cell-3 | 03/02/2021 | 04/02/2021 | 08/01/2021 | 08/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1330 | TT_Task | Pull UPM to UPM Admin to COLO-1 Cell -2 | 02/01/2021 | 04/01/2021 | 28/12/2020 | 31/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1360 | TT_Task | Pull UPM to UPM COLO-1 Cell 2- Cell - 4 | 07/01/2021 | 08/01/2021 | 28/12/2020 | 31/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1440 | TT_Task | Pull UPM to UPM COLO-2 Cell 2- Cell - 4 | 03/02/2021 | 04/02/2021 | 14/01/2021 | 15/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1560 | TT_Task | Pull UPM to UPM COLO-3 Cell 2- Cell - 4 | 05/02/2021 | 08/02/2021 | 13/01/2021 | 14/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1750 | TT_Task | Pull UPM to UPM COLO-4 Cell 2- Cell - 4 | 11/02/2021 | 12/02/2021 | 15/01/2021 | 16/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1480 | TT_Task | PULL- URS to Admin | 02/01/2021 | 06/01/2021 | 01/12/2020 | 05/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1500 | TT_Task | PULL- URS to COLO-2 | 07/01/2021 | 11/01/2021 | 21/12/2020 | 23/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1640 | TT_Task | PULL- URS to COLO-3 | 12/01/2021 | 15/01/2021 | 28/12/2020 | 31/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1770 | TT_Task | PULL- URS to COLO-4 | 18/01/2021 | 21/01/2021 | 28/12/2020 | 31/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1730 | TT_Task | Pull- UMS to COLO-1,2,3 | 12/01/2021 | 04/02/2021 | 11/12/2020 | 11/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1740 | TT_Task | Pull- UMS to COLO-4 | 11/01/2021 | 12/01/2021 | 11/01/2021 | 12/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1600 | TT_Task | Pull - JAZ to URS | 30/11/2020 | 03/12/2020 | 23/11/2020 | 02/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1680 | TT_Task | Pull - JAZ to UMS | 07/01/2021 | 11/01/2021 | 07/12/2020 | 10/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1450 | TT_Task | Term COLO -1 Cell-1 UPM | 10/02/2021 | 12/02/2021 | 26/01/2021 | 05/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1430 | TT_Task | Term COLO -1 Cell-2 UPM | 01/02/2021 | 03/02/2021 | 25/01/2021 | 26/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1490 | TT_Task | Term COLO -2 Cell-1 UPM | 13/02/2021 | 16/02/2021 | 25/01/2021 | 05/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1530 | TT_Task | Term COLO -2 Cell-2 UPM | 05/02/2021 | 09/02/2021 | 21/01/2021 | 22/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1610 | TT_Task | Term COLO -3 Cell-1 UPM | 08/03/2021 | 10/03/2021 | 08/02/2021 | 10/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1660 | TT_Task | Term COLO -3 Cell-2 UPM | 01/03/2021 | 03/03/2021 | 11/02/2021 | 17/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1780 | TT_Task | Term COLO -4 Cell-1 UPM | 11/03/2021 | 13/03/2021 | 06/02/2021 | 10/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1810 | TT_Task | Term COLO -4 Cell-2 UPM | 05/03/2021 | 08/03/2021 | 18/02/2021 | 20/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1790 | TT_Task | TERM- URS- Load Side | 01/02/2021 | 15/02/2021 | 04/01/2021 | 13/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1700 | TT_Task | Term URS- Line Side | 01/02/2021 | 08/02/2021 | 31/12/2020 | 04/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1820 | TT_Task | Term- UMS- Load side | 10/02/2021 | 23/02/2021 | 13/01/2021 | 18/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1690 | TT_Task | Term- UMS- Line Side | 01/02/2021 | 08/02/2021 | 06/01/2021 | 13/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1800 | TT_Task | Term- JAZ to Structure- (Incl Stress Cones) from ums | 02/01/2021 | 12/01/2021 | 28/12/2020 | 31/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1870 | TT_Task | Curb Gutter | 30/11/2020 | 09/01/2021 | 02/11/2020 | 06/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1760 | TT_Task | Term- JAS to URS- (Incl Stress Cones) | 03/02/2021 | 13/02/2021 | 28/12/2020 | 31/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C1430 | TT_Task | Install/Dress/Test Production Fiber (Includes MOR rack set Fiber runner) | 17/05/2021 | 10/06/2021 | 30/04/2021 | 30/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C3460 | TT_Task | Install/Dress/Test Production Fiber (Includes MOR rack set Fiber runner) | 01/07/2021 | 27/07/2021 | 01/05/2021 | 30/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C2440 | TT_Task | Install/Dress/Test Production Fiber (Includes MOR rack set Fiber runner) | 19/05/2021 | 14/06/2021 | 04/05/2021 | 30/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C4460 | TT_Task | Install/Dress/Test Production Fiber (Includes MOR rack set Fiber runner) | 19/05/2021 | 14/06/2021 | 04/05/2021 | 30/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C1440 | TT_Task | Install/Dress/Test Production Fiber (Includes MOR rack set Fiber runner) | 23/07/2021 | 17/08/2021 | 21/06/2021 | 19/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C3460 | TT_Task | Install/Dress/Test Production Fiber (Includes MOR rack set Fiber runner) | 09/08/2021 | 01/09/2021 | 21/06/2021 | 19/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C2450 | TT_Task | Install/Dress/Test Production Fiber (Includes MOR rack set Fiber runner) | 30/07/2021 | 23/08/2021 | 21/06/2021 | 19/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C4420 | TT_Task | ` | 24/08/2021 | 17/09/2021 | 21/06/2021 | 19/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C1460 | TT_Task | Install/Dress/Test Production Fiber (Includes MOR rack set Fiber runner) | 20/08/2021 | 14/09/2021 | 07/07/2021 | 31/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C3420 | TT_Task | Install/Dress/Test Production Fiber (Includes MOR rack set Fiber runner) | 31/08/2021 | 24/09/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C2460 | TT_Task | Install/Dress/Test Production Fiber (Includes MOR rack set Fiber runner) | 20/08/2021 | 14/09/2021 | 17/07/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C4460 | TT_Task | Install/Dress/Test Production Fiber (Includes MOR rack set Fiber runner) | 15/09/2021 | 08/10/2021 | 17/07/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C1460 | TT_Task | Install/Dress/Test Production Fiber (Includes MOR rack set Fiber runner) | 27/09/2021 | 20/10/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C3460 | TT_Task | Install/Dress/Test Production Fiber (Includes MOR rack set Fiber runner) | 21/10/2021 | 13/11/2021 |  |  | 801 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C2460 | TT_Task | Install/Dress/Test Production Fiber (Includes MOR rack set Fiber runner) | 09/10/2021 | 02/11/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C4460 | TT_Task | Install/Dress/Test Production Fiber (Includes MOR rack set Fiber runner) | 03/11/2021 | 30/11/2021 |  |  | 691 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1540 | TT_Task | Telecom-RNG Fiber Underground installation | 01/02/2021 | 02/04/2021 | 26/01/2021 | 19/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C1240 | TT_Task | IDF Backbone Install | 22/03/2021 | 07/04/2021 | 01/03/2021 | 17/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1830 | TT_Task | Telecom-RNG Fiber CNR buildout | 05/10/2020 | 08/12/2020 | 05/10/2020 | 25/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C3260 | TT_Task | IDF Backbone Install | 22/03/2021 | 07/04/2021 | 03/03/2021 | 19/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C2230 | TT_Task | IDF Backbone Install | 22/03/2021 | 07/04/2021 | 01/03/2021 | 17/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C4260 | TT_Task | IDF Backbone Install | 22/03/2021 | 07/04/2021 | 03/02/2021 | 19/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.E1280 | TT_Mile | AHU - ROJ COLO-1 Cell- 1 | 02/11/2020 | 02/11/2020 | 26/10/2020 | 26/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.E1390 | TT_Mile | AHU - ROJ COLO-1 Cell- 3 | 02/11/2020 | 02/11/2020 | 26/10/2020 | 26/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.E1290 | TT_Mile | AHU - ROJ COLO-1 Cell- 2 | 02/11/2020 | 02/11/2020 | 26/10/2020 | 26/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.E1400 | TT_Mile | AHU - ROJ COLO-1 Cell- 4 | 02/11/2020 | 02/11/2020 | 26/10/2020 | 26/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.E1260 | TT_Mile | AHU - ROJ COLO-2 Cell- 1 | 02/01/2021 | 02/01/2021 | 19/11/2020 | 19/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.E1320 | TT_Mile | MSFT Delivery -AHU - ROJ COLO-2 Cell- 3 | 01/03/2021 | 01/03/2021 | 16/02/2021 | 16/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.E1270 | TT_Mile | AHU - ROJ COLO-2 Cell- 2 | 02/01/2021 | 02/01/2021 | 19/11/2020 | 19/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.E1330 | TT_Mile | AHU - ROJ COLO-2 Cell- 4 | 02/01/2021 | 02/01/2021 | 19/11/2020 | 19/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.E1140 | TT_Mile | AHU - ROJ COLO-3 Cell- 1 | 02/01/2021 | 02/01/2021 | 28/12/2020 | 28/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.E1300 | TT_Mile | AHU - ROJ COLO-3 Cell- 3 | 02/01/2021 | 02/01/2021 | 28/12/2020 | 28/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.E1150 | TT_Mile | AHU - ROJ COLO-3 Cell- 2 | 02/01/2021 | 02/01/2021 | 28/12/2020 | 28/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.E1310 | TT_Mile | AHU - ROJ COLO-3 Cell- 4 | 08/01/2021 | 08/01/2021 | 28/12/2020 | 28/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.E1280 | TT_Mile | MSFT Delivery -AHU - ROJ COLO-4 Cell- 1 | 22/03/2021 | 22/03/2021 | 09/03/2021 | 09/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.E1320 | TT_Mile | AHU - ROJ COLO-4 Cell- 3 | 01/06/2021 | 01/06/2021 | 10/03/2021 | 10/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.E1290 | TT_Mile | AHU - ROJ COLO-4 Cell- 2 | 15/05/2021 | 15/05/2021 | 20/02/2021 | 20/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.E1330 | TT_Mile | AHU - ROJ COLO-4 Cell- 4 | 01/06/2021 | 01/06/2021 | 09/03/2021 | 09/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.E1300 | TT_Mile | MSFT Delivery -AHU - ROJ COLO-1 Cell- 1(11/2/20) | 30/11/2020 | 30/11/2020 | 17/11/2020 | 17/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.E1410 | TT_Mile | MSFT Delivery -AHU - ROJ COLO-1 Cell- 3 | 30/11/2020 | 30/11/2020 | 25/11/2020 | 25/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.E1310 | TT_Mile | MSFT Delivery -AHU - ROJ COLO-1 Cell- 2 (11/2/20) | 30/11/2020 | 30/11/2020 | 17/11/2020 | 17/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.E1420 | TT_Mile | MSFT Delivery -AHU - ROJ COLO-1 Cell- 4 | 21/12/2020 | 21/12/2020 | 07/12/2020 | 07/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.E1280 | TT_Mile | MSFT Delivery -AHU - ROJ COLO-2 Cell- 1 | 01/03/2021 | 01/03/2021 | 03/02/2021 | 03/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.E1340 | TT_Mile | AHU - ROJ COLO-2 Cell- 3 | 07/01/2021 | 07/01/2021 | 19/11/2020 | 19/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.E1290 | TT_Mile | MSFT Delivery -AHU - ROJ COLO-2 Cell- 2 | 01/03/2021 | 01/03/2021 | 16/02/2021 | 16/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.E1350 | TT_Mile | MSFT Delivery -AHU - ROJ COLO-2 Cell- 4 | 01/03/2021 | 01/03/2021 | 22/02/2021 | 22/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.E1160 | TT_Mile | MSFT Delivery -AHU - ROJ COLO-3 Cell- 1 | 06/03/2021 | 06/03/2021 | 24/02/2021 | 24/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.E1320 | TT_Mile | MSFT Delivery -AHU - ROJ COLO-3 Cell- 3 | 22/03/2021 | 22/03/2021 | 05/03/2021 | 05/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.E1170 | TT_Mile | MSFT Delivery -AHU - ROJ COLO-3 Cell- 2 | 22/03/2021 | 22/03/2021 | 01/03/2021 | 01/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.E1330 | TT_Mile | MSFT Delivery -AHU - ROJ COLO-3 Cell- 4 | 22/03/2021 | 22/03/2021 | 08/03/2021 | 08/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.E1300 | TT_Mile | AHU - ROJ COLO-4 Cell- 1 | 15/05/2021 | 15/05/2021 | 06/03/2021 | 06/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.E1340 | TT_Mile | MSFT Delivery -AHU - ROJ COLO-4 Cell- 3 | 22/03/2021 | 22/03/2021 | 17/03/2021 | 17/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.E1310 | TT_Mile | MSFT Delivery -AHU - ROJ COLO-4 Cell- 2 | 22/03/2021 | 22/03/2021 | 16/03/2021 | 16/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.E1350 | TT_Mile | MSFT Delivery -AHU - ROJ COLO-4 Cell- 4 | 31/03/2021 | 31/03/2021 | 19/03/2021 | 19/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.E1000 | TT_Mile | UPM ROJ COLO-1 Cell-1 | 28/09/2020 | 28/09/2020 | 24/09/2020 | 24/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.E1010 | TT_Mile | MSFT Delivery -UPM ROJ COLO-1 Cell-1 (PSR ROJ -9/19/2020) | 21/12/2020 | 21/12/2020 | 08/12/2020 | 08/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.E1080 | TT_Mile | UPM ROJ COLO-1 Cell-3 | 02/11/2020 | 02/11/2020 | 09/10/2020 | 09/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.E1090 | TT_Mile | MSFT Delivery -UPM ROJ COLO-1 Cell-3 (PSR ROJ -9/28/2020) | 30/11/2020 | 30/11/2020 | 24/11/2020 | 24/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.E1020 | TT_Mile | MSFT Delivery -UPM ROJ COLO-1 Cell-2 (PSR ROJ -10/13/2020) | 30/11/2020 | 30/11/2020 | 24/11/2020 | 24/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.E1030 | TT_Mile | UPM ROJ COLO-1 Cell-2 | 02/11/2020 | 02/11/2020 | 19/10/2020 | 19/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.E1100 | TT_Mile | UPM ROJ COLO-1 Cell-4 | 02/11/2020 | 02/11/2020 | 19/10/2020 | 19/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.E1110 | TT_Mile | MSFT Delivery -UPM ROJ COLO-1 Cell-4 (PSR ROJ -10/28/2020) | 30/11/2020 | 30/11/2020 | 24/11/2020 | 24/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.E1000 | TT_Mile | UPM - ROJ - COLO2- Cell-1 | 30/11/2020 | 30/11/2020 | 13/11/2020 | 13/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.E1010 | TT_Mile | MSFT Delivery -UPM - ROJ - COLO2- Cell-1 (11/25/2020) | 21/12/2020 | 21/12/2020 | 08/12/2020 | 08/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.E1080 | TT_Mile | UPM - ROJ - COLO2- Cell-3 | 30/11/2020 | 30/11/2020 | 13/11/2020 | 13/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.E1090 | TT_Mile | MSFT Delivery -UPM - ROJ - COLO2- Cell-3 (11/25/2020) | 21/12/2020 | 21/12/2020 | 16/12/2020 | 16/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.E1020 | TT_Mile | MSFT Delivery -UPM - ROJ - COLO2- Cell-2 (11/25/2020) | 21/12/2020 | 21/12/2020 | 10/12/2020 | 10/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.E1030 | TT_Mile | UPM - ROJ - COLO2- Cell-2 | 30/11/2020 | 30/11/2020 | 04/11/2020 | 04/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.E1100 | TT_Mile | UPM - ROJ - COLO2- Cell-4 | 30/11/2020 | 30/11/2020 | 05/11/2020 | 05/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.E1110 | TT_Mile | MSFT Delivery -UPM - ROJ - COLO2- Cell-4 (11/25/2020) | 21/12/2020 | 21/12/2020 | 10/12/2020 | 10/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.E1000 | TT_Mile | UPM - ROJ - COLO3- Cell-1 | 02/01/2021 | 02/01/2021 | 02/12/2020 | 02/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.E1010 | TT_Mile | MSFT Delivery -UPM - ROJ - COLO3- Cell-1 (11/23/2020) | 29/12/2020 | 29/12/2020 | 29/12/2020 | 29/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.E1080 | TT_Mile | UPM - ROJ - COLO3- Cell-3 | 02/01/2021 | 02/01/2021 | 09/12/2020 | 09/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.E1090 | TT_Mile | MSFTDelivery -UPM - ROJ - COLO3- Cell-3 (11/23/2020) | 11/01/2021 | 11/01/2021 | 04/01/2021 | 04/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.E1020 | TT_Mile | UPM - ROJ - COLO3- Cell-2 | 02/01/2021 | 02/01/2021 | 02/12/2020 | 02/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.E1030 | TT_Mile | MSFT Delivery -UPM - ROJ - COLO3- Cell-2 (11/23/2020) | 07/01/2021 | 07/01/2021 | 18/12/2020 | 18/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.E1100 | TT_Mile | UPM - ROJ - COLO3- Cell-4 | 02/01/2021 | 02/01/2021 | 09/12/2020 | 09/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.E1110 | TT_Mile | MSFT Delivery -UPM - ROJ - COLO3- Cell-4 (11/23/2020) | 11/01/2021 | 11/01/2021 | 04/01/2021 | 04/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.E1000 | TT_Mile | UPM - ROJ - COLO-4 Cell- 1 | 02/01/2021 | 02/01/2021 | 04/12/2020 | 04/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.E1010 | TT_Mile | MSFT Delivery -UPM - ROJ - COLO-4 Cell- 1 (12/7/2020) | 09/01/2021 | 09/01/2021 | 30/12/2020 | 30/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.E1080 | TT_Mile | UPM - ROJ - COLO-4 Cell- 3 | 02/01/2021 | 02/01/2021 | 04/12/2020 | 04/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.E1090 | TT_Mile | MSFT Delivery -UPM - ROJ - COLO-4 Cell- 3 (12/18/2020) | 11/01/2021 | 11/01/2021 | 04/01/2021 | 04/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.E1020 | TT_Mile | MSFT Delivery -UPM - ROJ - COLO-4 Cell- 2 (12/7/2020) | 12/01/2021 | 12/01/2021 | 17/12/2020 | 17/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.E1030 | TT_Mile | UPM - ROJ - COLO-4 Cell- 2 | 02/01/2021 | 02/01/2021 | 16/12/2020 | 16/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.E1100 | TT_Mile | UPM - ROJ - COLO-4 Cell- 4 | 02/01/2021 | 02/01/2021 | 16/12/2020 | 16/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.E1110 | TT_Mile | MSFT Delivery -UPM - ROJ - COLO-4 Cell- 4 (12/18/2020) | 11/01/2021 | 11/01/2021 | 04/01/2021 | 04/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.E1120 | TT_Mile | Fluid Cooler - ROJ COLO -1 Cell- 1 | 30/11/2020 | 30/11/2020 | 12/11/2020 | 12/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.E1130 | TT_Mile | MSFT Delivery -Fluid Cooler - ROJ COLO -1 Cell- 1 | 19/09/2020 | 19/09/2020 | 07/07/2020 | 07/07/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.E1260 | TT_Mile | Fluid Cooler - ROJ COLO -1 Cell- 3 | 30/11/2020 | 30/11/2020 | 12/11/2020 | 12/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.E1270 | TT_Mile | MSFT Delivery -Fluid Cooler - ROJ COLO -1 Cell- 3 | 15/10/2020 | 15/10/2020 | 21/07/2020 | 21/07/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.E1160 | TT_Mile | Fluid Cooler - ROJ COLO -1 Cell- 2 | 30/11/2020 | 30/11/2020 | 13/11/2020 | 13/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.E1170 | TT_Mile | MSFT Delivery -Fluid Cooler - ROJ COLO -1 Cell- 2 | 26/09/2020 | 26/09/2020 | 14/07/2020 | 14/07/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.E1240 | TT_Mile | Fluid Cooler - ROJ COLO -1 Cell- 4 | 30/11/2020 | 30/11/2020 | 12/11/2020 | 12/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.E1250 | TT_Mile | MSFT Delivery -Fluid Cooler - ROJ COLO -1 Cell- 4 | 12/10/2020 | 12/10/2020 | 28/07/2020 | 28/07/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.E1140 | TT_Mile | Fluid Cooler - ROJ COLO -2 Cell-1 | 01/02/2021 | 01/02/2021 | 06/01/2021 | 06/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.E1150 | TT_Mile | MSFT Delivery -Fluid Cooler - ROJ COLO -2 Cell-1 | 02/11/2020 | 02/11/2020 | 23/09/2020 | 23/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.E1220 | TT_Mile | Fluid Cooler - ROJ COLO -2 Cell-3 | 01/02/2021 | 01/02/2021 | 06/01/2021 | 06/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.E1230 | TT_Mile | MSFT Delivery -Fluid Cooler - ROJ COLO -2 Cell-3 | 02/11/2020 | 02/11/2020 | 24/09/2020 | 24/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.E1240 | TT_Mile | Fluid Cooler - ROJ COLO -2 Cell-2 | 01/02/2021 | 01/02/2021 | 06/01/2021 | 06/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.E1250 | TT_Mile | MSFT Delivery -Fluid Cooler - ROJ COLO -2 Cell-2 | 02/11/2020 | 02/11/2020 | 30/11/2020 | 30/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.E1180 | TT_Mile | Fluid Cooler - ROJ COLO -3 Cell-1 | 31/03/2021 | 31/03/2021 | 30/12/2020 | 30/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.E1190 | TT_Mile | MSFT Delivery -Fluid Cooler - ROJ COLO -3 Cell-1 | 30/11/2020 | 30/11/2020 | 11/11/2020 | 11/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.E1200 | TT_Mile | Fluid Cooler - ROJ COLO -3 Cell-2 | 01/02/2021 | 01/02/2021 | 15/01/2021 | 15/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.E1210 | TT_Mile | MSFT Delivery -Fluid Cooler - ROJ COLO -3 Cell-2 | 30/11/2020 | 30/11/2020 | 23/11/2020 | 23/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.E1280 | TT_Mile | MSFT Delivery -Fluid Cooler - ROJ COLO -3 Cell-4 | 30/11/2020 | 30/11/2020 | 18/11/2020 | 18/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.E1290 | TT_Mile | Fluid Cooler - ROJ COLO -3 Cell-4 | 01/02/2021 | 01/02/2021 | 15/01/2021 | 15/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.E1140 | TT_Mile | Fluid Cooler - ROJ COLO -4 Cell-1 | 06/05/2021 | 06/05/2021 | 05/02/2021 | 05/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.E1150 | TT_Mile | MSFT Delivery -Fluid Cooler - ROJ COLO -4 Cell-1 | 21/12/2020 | 21/12/2020 | 12/12/2020 | 12/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.E1240 | TT_Mile | Fluid Cooler - ROJ COLO -4 Cell-3 | 30/04/2021 | 30/04/2021 | 05/02/2021 | 05/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.E1250 | TT_Mile | MSFT Delivery -Fluid Cooler - ROJ COLO -4 Cell-3 | 23/12/2020 | 23/12/2020 | 17/12/2020 | 17/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.E1160 | TT_Mile | Fluid Cooler - ROJ COLO -4 Cell-2 | 30/04/2021 | 30/04/2021 | 05/02/2021 | 05/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.E1170 | TT_Mile | MSFT Delivery -Fluid Cooler - ROJ COLO -4 Cell-2 | 21/12/2020 | 21/12/2020 | 17/12/2020 | 17/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.E1260 | TT_Mile | Fluid Cooler - ROJ COLO -4 Cell-4 | 30/04/2021 | 30/04/2021 | 05/02/2021 | 05/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.E1270 | TT_Mile | MSFT Delivery -Fluid Cooler - ROJ COLO -4 Cell-4 | 02/01/2021 | 02/01/2021 | 20/12/2020 | 20/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.E1040 | TT_Mile | Generator ROJ COLO 1- Cell-1 | 30/11/2020 | 30/11/2020 | 10/10/2020 | 10/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.E1050 | TT_Mile | MSFT Delivery -Generator ROJ COLO 1- Cell-1 | 02/11/2020 | 02/11/2020 | 15/10/2020 | 15/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.E1180 | TT_Mile | Generator ROJ COLO 1- Cell-3 | 30/11/2020 | 30/11/2020 | 14/10/2020 | 14/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.E1190 | TT_Mile | MSFT Delivery -Generator ROJ COLO 1- Cell-3 | 16/11/2020 | 16/11/2020 | 13/11/2020 | 13/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.E1060 | TT_Mile | Generator ROJ COLO 1- Cell-2 | 30/11/2020 | 30/11/2020 | 02/10/2020 | 02/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.E1070 | TT_Mile | MSFT Delivery -Generator ROJ COLO 1- Cell-2 | 02/11/2020 | 02/11/2020 | 02/11/2020 | 02/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.E1200 | TT_Mile | Generator ROJ COLO 1- Cell-4 | 30/11/2020 | 30/11/2020 | 21/10/2020 | 21/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.E1210 | TT_Mile | MSFT Delivery -Generator ROJ COLO 1- Cell-4 | 06/11/2020 | 06/11/2020 | 22/10/2020 | 22/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.E1040 | TT_Mile | MSFT Delivery -Generator ROJ COLO 2- Cell - 1 | 09/01/2021 | 09/01/2021 | 29/12/2020 | 29/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.E1050 | TT_Mile | Generator ROJ COLO 2- Cell - 1 | 30/11/2020 | 30/11/2020 | 17/11/2020 | 17/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.E1160 | TT_Mile | Generator ROJ COLO 2- Cell - 3 | 30/11/2020 | 30/11/2020 | 19/11/2020 | 19/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.E1170 | TT_Mile | MSFT Delivery -Generator ROJ COLO 2- Cell - 3 | 01/02/2021 | 01/02/2021 | 19/01/2021 | 19/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.E1060 | TT_Mile | Generator ROJ COLO 2- Cell - 2 | 30/11/2020 | 30/11/2020 | 03/11/2020 | 03/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.E1070 | TT_Mile | MSFT Delivery -Generator ROJ COLO 2- Cell - 2 | 19/01/2021 | 19/01/2021 | 09/01/2021 | 09/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.E1180 | TT_Mile | Generator ROJ COLO 2- Cell - 4 | 30/11/2020 | 30/11/2020 | 05/11/2020 | 05/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.E1190 | TT_Mile | MSFT Delivery -Generator ROJ COLO 2- Cell - 4 | 01/02/2021 | 01/02/2021 | 22/01/2021 | 22/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.E1040 | TT_Mile | Generator ROJ COLO 3- Cell - 1 | 02/01/2021 | 02/01/2021 | 30/11/2020 | 30/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.E1050 | TT_Mile | MSFT Delivery -Generator ROJ COLO 3- Cell - 1 | 01/03/2021 | 01/03/2021 | 18/03/2021 | 18/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.E1220 | TT_Mile | Generator ROJ COLO 3- Cell - 3 | 02/01/2021 | 02/01/2021 | 04/12/2020 | 04/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.E1230 | TT_Mile | MSFT Delivery -Generator ROJ COLO 3- Cell - 3 | 22/03/2021 | 22/03/2021 | 05/03/2021 | 05/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.E1060 | TT_Mile | Generator ROJ COLO 3- Cell - 2 | 02/01/2021 | 02/01/2021 | 11/12/2020 | 11/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.E1070 | TT_Mile | MSFT Delivery -Generator ROJ COLO 3- Cell - 2 | 01/03/2021 | 01/03/2021 | 19/02/2021 | 19/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.E1240 | TT_Mile | Generator ROJ COLO 3- Cell - 4 | 02/01/2021 | 02/01/2021 | 11/12/2020 | 11/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.E1250 | TT_Mile | MSFT Delivery -Generator ROJ COLO 3- Cell - 4 | 01/03/2021 | 01/03/2021 | 26/02/2021 | 26/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.E1180 | TT_Mile | Generator ROJ COLO 4- Cell - 3 | 02/01/2021 | 02/01/2021 | 10/12/2020 | 10/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.E1190 | TT_Mile | MSFT Delivery -Generator ROJ COLO 4- Cell - 3 | 26/04/2021 | 26/04/2021 | 02/04/2021 | 02/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.E1040 | TT_Mile | Generator ROJ COLO 4- Cell - 2 | 02/01/2021 | 02/01/2021 | 16/12/2020 | 16/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.E1050 | TT_Mile | MSFT Delivery -Generator ROJ COLO 4- Cell - 2 | 22/03/2021 | 22/03/2021 | 12/03/2021 | 12/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.E1200 | TT_Mile | Generator ROJ COLO 4- Cell - 4 | 02/01/2021 | 02/01/2021 | 16/12/2020 | 16/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.E1210 | TT_Mile | MSFT Delivery -Generator ROJ COLO 4- Cell - 4 | 31/03/2021 | 31/03/2021 | 26/03/2021 | 26/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.E1060 | TT_Mile | Generator ROJ COLO 4- Cell - 1 | 02/01/2021 | 02/01/2021 | 10/12/2020 | 10/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.E1070 | TT_Mile | MSFT Delivery -Generator ROJ COLO 4- Cell - 1 | 26/04/2021 | 26/04/2021 | 16/04/2021 | 16/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.E1340 | TT_Mile | PDU ROJ COLO-1 Cell-1 | 01/03/2021 | 01/03/2021 | 04/02/2021 | 04/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.E1350 | TT_Mile | MSFT Delivery -PDU ROJ COLO-1 Cell-1 | 30/11/2020 | 30/11/2020 | 16/11/2020 | 16/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.E1430 | TT_Mile | PDU ROJ COLO-1 Cell-3 | 09/03/2021 | 09/03/2021 | 24/02/2021 | 24/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.E1440 | TT_Mile | MSFT Delivery -PDU ROJ COLO-1 Cell-3 | 30/11/2020 | 30/11/2020 | 20/11/2020 | 20/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.E1360 | TT_Mile | PDU ROJ COLO-1 Cell-2 | 01/03/2021 | 01/03/2021 | 04/02/2021 | 04/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.E1370 | TT_Mile | MSFT Delivery -PDU ROJ COLO-1 Cell-2 | 30/11/2020 | 30/11/2020 | 16/11/2020 | 16/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.E1450 | TT_Mile | PDU ROJ COLO-1 Cell-4 | 10/03/2021 | 10/03/2021 | 24/02/2021 | 24/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.E1460 | TT_Mile | MSFT Delivery -PDU ROJ COLO-1 Cell-4 | 21/12/2020 | 21/12/2020 | 05/12/2020 | 05/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.E1370 | TT_Mile | PDU ROJ COLO-2 Cell-1 | 31/03/2021 | 31/03/2021 | 20/03/2021 | 20/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.E1380 | TT_Mile | MSFT Delivery -PDU ROJ COLO-2 Cell-1 | 11/01/2021 | 11/01/2021 | 11/01/2021 | 11/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.E1420 | TT_Mile | PDU ROJ COLO-2 Cell-3 | 30/04/2021 | 30/04/2021 | 15/03/2021 | 15/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.E1430 | TT_Mile | MSFT Delivery -PDU ROJ COLO-2 Cell-3 | 11/01/2021 | 11/01/2021 | 14/01/2021 | 14/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.E1390 | TT_Mile | PDU ROJ COLO-2 Cell-2 | 31/03/2021 | 31/03/2021 | 20/03/2021 | 20/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.E1400 | TT_Mile | MSFT Delivery -PDU ROJ COLO-2 Cell-2 | 11/01/2021 | 11/01/2021 | 11/01/2021 | 11/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.E1440 | TT_Mile | PDU ROJ COLO-2 Cell-4 | 30/04/2021 | 30/04/2021 | 08/04/2021 | 08/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.E1450 | TT_Mile | MSFT Delivery -PDU ROJ COLO-2 Cell-4 | 15/01/2021 | 15/01/2021 | 16/01/2021 | 16/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.E1380 | TT_Mile | PDU ROJ COLO-3 Cell-1 | 30/04/2021 | 30/04/2021 | 02/03/2021 | 02/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.E1390 | TT_Mile | MSFT Delivery -PDU ROJ COLO-3 Cell-1 | 22/03/2021 | 22/03/2021 | 02/03/2021 | 02/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.E1420 | TT_Mile | PDU ROJ COLO-3 Cell-3 | 07/05/2021 | 07/05/2021 | 04/03/2021 | 04/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.E1430 | TT_Mile | MSFT Delivery -PDU ROJ COLO-3 Cell-3 | 02/04/2021 | 02/04/2021 | 15/03/2021 | 15/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.E1400 | TT_Mile | PDU ROJ COLO-3 Cell-2 | 07/05/2021 | 07/05/2021 | 15/03/2021 | 15/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.E1410 | TT_Mile | MSFT Delivery -PDU ROJ COLO-3 Cell-2 | 22/03/2021 | 22/03/2021 | 04/03/2021 | 04/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.E1440 | TT_Mile | PDU ROJ COLO-3 Cell-4 | 13/05/2021 | 13/05/2021 | 19/03/2021 | 19/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.E1450 | TT_Mile | MSFT Delivery -PDU ROJ COLO-3 Cell-4 | 02/04/2021 | 02/04/2021 | 19/03/2021 | 19/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.E1400 | TT_Mile | PDU ROJ COLO-4 Cell-1 | 13/05/2021 | 13/05/2021 | 29/03/2021 | 29/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.E1410 | TT_Mile | MSFT Delivery -PDU ROJ COLO-4 Cell-1 | 31/03/2021 | 31/03/2021 | 29/03/2021 | 29/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.E1440 | TT_Mile | PDU ROJ COLO-4 Cell-3 | 21/05/2021 | 21/05/2021 | 26/04/2021 | 26/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.E1450 | TT_Mile | MSFT Delivery -PDU ROJ COLO-4 Cell-3 | 30/04/2021 | 30/04/2021 | 26/04/2021 | 26/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.E1420 | TT_Mile | PDU ROJ COLO-4 Cell-2 | 19/05/2021 | 19/05/2021 | 12/04/2021 | 12/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.E1430 | TT_Mile | MSFT Delivery -PDU ROJ COLO-4 Cell-2 | 30/04/2021 | 30/04/2021 | 12/04/2021 | 12/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.E1460 | TT_Mile | PDU ROJ COLO-4 Cell-4 | 07/06/2021 | 07/06/2021 | 29/04/2021 | 29/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.E1470 | TT_Mile | MSFT Delivery -PDU ROJ COLO-4 Cell-4 | 30/04/2021 | 30/04/2021 | 30/04/2021 | 30/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2503 | TT_Mile | UMS - ROJ | 30/11/2020 | 30/11/2020 | 07/11/2020 | 07/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2504 | TT_Mile | URS - ROJ | 30/11/2020 | 30/11/2020 | 06/11/2020 | 06/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2505 | TT_Mile | ATS- ROJ | 29/06/2020 | 29/06/2020 | 27/06/2020 | 27/06/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2506 | TT_Mile | MSB - ROJ | 30/11/2020 | 30/11/2020 | 06/11/2020 | 06/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2507 | TT_Mile | TCP - ROJ | 30/11/2020 | 30/11/2020 | 06/11/2020 | 06/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2508 | TT_Mile | UPS- ROJ | 30/11/2020 | 30/11/2020 | 06/11/2020 | 06/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2509 | TT_Mile | MSFT Delivery -UMS - ROJ | 21/12/2020 | 21/12/2020 | 11/12/2020 | 11/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2510 | TT_Mile | MSFTDelivery -URS - ROJ | 02/11/2020 | 02/11/2020 | 02/11/2020 | 02/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2511 | TT_Mile | MSFT Delivery -ATS- ROJ | 29/06/2020 | 29/06/2020 | 27/06/2020 | 27/06/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2512 | TT_Mile | MSFT Delivery -MSB - ROJ | 02/11/2020 | 02/11/2020 | 02/11/2020 | 02/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2513 | TT_Mile | MSFT Delivery -TCP - ROJ | 28/10/2020 | 28/10/2020 | 17/08/2020 | 17/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2514 | TT_Mile | MSFT Delivery -UPS- ROJ | 02/11/2020 | 02/11/2020 | 01/10/2020 | 01/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-C1.P2200 | TT_FinMile | IST Admin/COLO 1 | 13/11/2021 | 13/11/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.Cx4020 | TT_Task | Punch List COLO-2 | 27/12/2021 | 09/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.Cx4020 | TT_Task | Punch List COLO-3 | 09/02/2022 | 22/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH.06.M6010 | TT_FinMile | Project Completion | 23/04/2022 | 23/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1860 | TT_Task | Plant shutdown for winter | 30/11/2020 | 06/04/2021 | 23/11/2020 | 30/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.Cx4020 | TT_Task | Punch List COLO-4 | 21/03/2022 | 02/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-C2.P2200 | TT_FinMile | IST COLO 2 | 15/01/2022 | 15/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-C3.P2200 | TT_FinMile | IST COLO 3 | 23/02/2022 | 23/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-C4.P2200 | TT_FinMile | IST COLO 4 | 04/04/2022 | 04/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-2527 | TT_FinMile | MSFT Delivery -OFCI submittal release | 01/03/2021 | 01/03/2021 | 20/02/2021 | 20/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2529 | TT_FinMile | Weather Tight | 02/11/2020 | 02/11/2020 | 13/10/2020 | 13/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-C1.P2000 | TT_FinMile | Construction Server- COLO-1 | 28/07/2021 | 28/07/2021 | 07/05/2021 | 07/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-C2.P2000 | TT_FinMile | Construction Server- COLO-2 | 06/10/2021 | 06/10/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-C3.P2000 | TT_FinMile | Construction Server- COLO-3 | 30/10/2021 | 30/10/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-C4.P2000 | TT_FinMile | Construction Server- COLO-4 | 06/12/2021 | 06/12/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-C1.P2100 | TT_FinMile | Ready for Network Install | 29/10/2021 | 29/10/2021 |  |  | 1 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-C2.P2100 | TT_FinMile | Ready for Network Install | 27/12/2021 | 27/12/2021 |  |  | 1 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-C3.P2100 | TT_FinMile | Ready for Network Install | 08/02/2022 | 08/02/2022 |  |  | 1 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-C4.P2100 | TT_FinMile | Ready for Network Install | 21/03/2022 | 21/03/2022 |  |  | 1 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.Cx4000 | TT_Task | Security Commissioning (level2 with Corp net after IST) | 27/12/2021 | 10/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.Cx4010 | TT_Task | Security Commissioning (level2 with Corp net after IST) | 30/10/2021 | 08/11/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.Cx4010 | TT_Task | Security Commissioning (level2 with Corp net after IST) | 09/02/2022 | 18/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.Cx4010 | TT_Task | Security Commissioning (level2 with Corp net after IST) | 21/03/2022 | 30/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.D1.S1010 | TT_Mile | NOPC Letter #2- Late OFCI Vendor Approved Submittals | 10/08/2020 | 10/08/2020 | 13/07/2020 | 13/07/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D1.S1030 | TT_Task | URS/UMS Concrete Anchor and Vault Design | 10/08/2020 | 26/08/2020 | 05/08/2020 | 28/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D1.S1040 | TT_Task | URS/UMS Vault Submiital Review by EOR | 14/09/2020 | 18/09/2020 | 29/08/2020 | 25/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C1.C1010 | TT_Task | Fluid Cooler RI prefabrication | 02/11/2020 | 07/11/2020 | 31/10/2020 | 31/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D1.S1020 | TT_FinMile | MSFT - Soft release on unapproved URS submittal | 14/08/2020 | 14/08/2020 | 05/08/2020 | 05/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2535 | TT_FinMile | MSFT Delivery - PDU submittal release | 21/12/2020 | 21/12/2020 | 05/08/2020 | 05/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2536 | TT_FinMile | MSFT Delivery - Admin Gen submittal release | 21/12/2020 | 21/12/2020 | 20/10/2020 | 20/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2537 | TT_FinMile | MSFT Delivery - COLO-1 Gen submittal release | 21/12/2020 | 21/12/2020 | 19/10/2020 | 19/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2538 | TT_FinMile | MSFT Delivery - COLO-2,3,4 Gen submittal approval | 01/03/2021 | 01/03/2021 | 20/02/2021 | 20/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2539 | TT_FinMile | MSFT Delivery - UPM submittal release | 21/12/2020 | 21/12/2020 | 06/11/2020 | 06/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2540 | TT_FinMile | MSFT Delivery - MER submittal COLO-1 | 01/03/2021 | 01/03/2021 | 21/12/2020 | 21/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2541 | TT_Mile | MSFT Delivery -ADMIN- GEN- ROJ | 02/11/2020 | 02/11/2020 | 02/11/2020 | 02/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C1.C1020 | TT_Task | Fluid Cooler Panel installation | 01/03/2021 | 03/03/2021 | 09/02/2021 | 11/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C1.C1030 | TT_Task | Fluid Cooler RI in place | 01/02/2021 | 08/02/2021 | 01/02/2021 | 20/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C1.C1040 | TT_Task | Fluid Cooler Wire install and Term | 05/03/2021 | 11/03/2021 | 09/02/2021 | 20/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C1.C1050 | TT_Task | Fluid Cooler QAQC and Cx | 01/03/2021 | 02/03/2021 | 28/02/2021 | 28/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C1.C3010 | TT_Task | Fluid Cooler RI prefabrication | 02/11/2020 | 07/11/2020 | 31/10/2020 | 31/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C1.C3020 | TT_Task | Fluid Cooler Panel installation | 23/03/2021 | 25/03/2021 | 22/02/2021 | 24/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C1.C3030 | TT_Task | Fluid Cooler RI in place | 18/03/2021 | 25/03/2021 | 29/01/2021 | 02/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C1.C3040 | TT_Task | Fluid Cooler Wire install and Term | 01/03/2021 | 06/03/2021 | 25/02/2021 | 27/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C1.C3050 | TT_Task | Fluid Cooler QAQC and Cx | 10/03/2021 | 11/03/2021 | 28/02/2021 | 28/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C1.C2010 | TT_Task | Fluid Cooler RI prefabrication | 02/11/2020 | 07/11/2020 | 31/10/2020 | 31/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C1.C2020 | TT_Task | Fluid Cooler Panel installation | 15/03/2021 | 17/03/2021 | 18/02/2021 | 20/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C1.C2030 | TT_Task | Fluid Cooler RI in place | 19/02/2021 | 25/02/2021 | 22/02/2021 | 25/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C1.C2040 | TT_Task | Fluid Cooler Wire install and Term | 18/03/2021 | 25/03/2021 | 26/02/2021 | 06/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C1.C2050 | TT_Task | Fluid Cooler QAQC and Cx | 01/03/2021 | 02/03/2021 | 28/02/2021 | 28/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C1.C4000 | TT_Task | Fluid Cooler RI prefabrication | 02/11/2020 | 07/11/2020 | 31/10/2020 | 31/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C1.C4010 | TT_Task | Fluid Cooler Panel installation | 18/03/2021 | 22/03/2021 | 15/02/2021 | 17/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C1.C4020 | TT_Task | Fluid Cooler RI in place | 01/03/2021 | 06/03/2021 | 22/02/2021 | 27/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C1.C4030 | TT_Task | Fluid Cooler Wire install and Term | 22/03/2021 | 27/03/2021 | 01/03/2021 | 06/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C1.C4040 | TT_Task | Fluid Cooler QAQC and Cx | 08/03/2021 | 09/03/2021 | 28/02/2021 | 28/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C2.C1000 | TT_Task | Fluid Cooler RI prefabrication | 02/11/2020 | 07/11/2020 | 31/10/2020 | 31/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C2.C1010 | TT_Task | Fluid Cooler Panel installation | 29/03/2021 | 31/03/2021 | 04/03/2021 | 08/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C2.C1020 | TT_Task | Fluid Cooler RI in place | 25/03/2021 | 31/03/2021 | 04/03/2021 | 13/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C2.C1030 | TT_Task | Fluid Cooler Wire install and Term | 01/04/2021 | 07/04/2021 | 13/03/2021 | 18/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C2.C1040 | TT_Task | Fluid Cooler QAQC and Cx | 18/03/2021 | 19/03/2021 | 28/02/2021 | 28/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C2.C3010 | TT_Task | Fluid Cooler RI prefabrication | 02/11/2020 | 07/11/2020 | 31/10/2020 | 31/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C2.C3020 | TT_Task | Fluid Cooler Panel installation | 31/03/2021 | 02/04/2021 | 18/03/2021 | 22/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C2.C3030 | TT_Task | Fluid Cooler RI in place | 31/03/2021 | 06/04/2021 | 22/03/2021 | 24/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C2.C3040 | TT_Task | Fluid Cooler Wire install and Term | 07/04/2021 | 14/04/2021 | 24/03/2021 | 26/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C2.C3050 | TT_Task | Fluid Cooler QAQC and Cx | 26/03/2021 | 27/03/2021 | 28/02/2021 | 28/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C2.C2010 | TT_Task | Fluid Cooler RI prefabrication | 30/11/2020 | 07/12/2020 | 31/10/2020 | 31/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C2.C2020 | TT_Task | Fluid Cooler Panel installation | 01/04/2021 | 03/04/2021 | 24/03/2021 | 27/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C2.C2030 | TT_Task | Fluid Cooler RI in place | 31/03/2021 | 06/04/2021 | 29/03/2021 | 31/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C2.C2040 | TT_Task | Fluid Cooler Wire install and Term | 26/04/2021 | 29/04/2021 | 31/03/2021 | 03/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C2.C2050 | TT_Task | Fluid Cooler QAQC and Cx | 02/04/2021 | 03/04/2021 | 28/02/2021 | 28/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C3.C1010 | TT_Task | Fluid Cooler RI prefabrication | 10/12/2020 | 16/12/2020 | 31/10/2020 | 31/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C3.C1020 | TT_Task | Fluid Cooler Panel installation | 04/05/2021 | 06/05/2021 | 07/04/2021 | 09/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C3.C1030 | TT_Task | Fluid Cooler RI in place | 07/05/2021 | 13/05/2021 | 12/04/2021 | 17/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C3.C1040 | TT_Task | Fluid Cooler Wire install and Term | 14/05/2021 | 20/05/2021 | 19/04/2021 | 24/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C3.C1050 | TT_Task | Fluid Cooler QAQC and Cx | 06/04/2021 | 07/04/2021 | 28/02/2021 | 28/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C3.C2010 | TT_Task | Fluid Cooler RI prefabrication | 16/12/2020 | 22/12/2020 | 31/10/2020 | 31/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C3.C2020 | TT_Task | Fluid Cooler Panel installation | 17/05/2021 | 17/05/2021 | 30/04/2021 | 04/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C3.C2030 | TT_Task | Fluid Cooler RI in place | 20/05/2021 | 20/05/2021 | 05/05/2021 | 11/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C3.C2040 | TT_Task | Fluid Cooler Wire install and Term | 28/05/2021 | 28/05/2021 | 12/05/2021 | 18/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C3.C2050 | TT_Task | Fluid Cooler QAQC and Cx | 14/04/2021 | 15/04/2021 | 28/02/2021 | 28/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C3.C4010 | TT_Task | Fluid Cooler RI prefabrication | 23/12/2020 | 04/01/2021 | 31/10/2020 | 31/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C3.C4020 | TT_Task | Fluid Cooler Panel installation | 01/06/2021 | 03/06/2021 | 08/05/2021 | 11/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C3.C4030 | TT_Task | Fluid Cooler RI in place | 04/06/2021 | 10/06/2021 | 12/05/2021 | 18/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C3.C4040 | TT_Task | Fluid Cooler Wire install and Term | 11/06/2021 | 18/06/2021 | 19/05/2021 | 26/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C3.C4050 | TT_Task | Fluid Cooler QAQC and Cx | 21/04/2021 | 22/04/2021 | 28/02/2021 | 28/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C4.C1010 | TT_Task | Fluid Cooler RI prefabrication | 07/01/2021 | 13/01/2021 | 31/10/2020 | 31/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C4.C1020 | TT_Task | Fluid Cooler Panel installation | 08/06/2021 | 10/06/2021 | 08/05/2021 | 11/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C4.C1030 | TT_Task | Fluid Cooler RI in place | 11/06/2021 | 18/06/2021 | 12/05/2021 | 18/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C4.C1040 | TT_Task | Fluid Cooler Wire install and Term | 19/06/2021 | 25/06/2021 | 19/05/2021 | 26/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C4.C1050 | TT_Task | Fluid Cooler QAQC and Cx | 14/04/2021 | 15/04/2021 | 28/02/2021 | 28/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C4.C3010 | TT_Task | Fluid Cooler RI prefabrication | 22/01/2021 | 28/01/2021 | 31/10/2020 | 31/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C4.C3020 | TT_Task | Fluid Cooler Panel installation | 11/06/2021 | 15/06/2021 | 12/05/2021 | 14/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C4.C3030 | TT_Task | Fluid Cooler RI in place | 19/06/2021 | 25/06/2021 | 19/05/2021 | 26/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C4.C3040 | TT_Task | Fluid Cooler Wire install and Term | 26/06/2021 | 02/07/2021 | 27/05/2021 | 03/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C4.C3050 | TT_Task | Fluid Cooler QAQC and Cx | 21/04/2021 | 22/04/2021 | 28/02/2021 | 28/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C4.C2010 | TT_Task | Fluid Cooler RI prefabrication | 14/01/2021 | 21/01/2021 | 31/10/2020 | 31/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C4.C2020 | TT_Task | Fluid Cooler Panel installation | 30/06/2021 | 02/07/2021 | 12/05/2021 | 14/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C4.C2030 | TT_Task | Fluid Cooler RI in place | 06/07/2021 | 12/07/2021 | 19/05/2021 | 26/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C4.C2040 | TT_Task | Fluid Cooler Wire install and Term | 13/07/2021 | 19/07/2021 | 27/05/2021 | 03/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C4.C2050 | TT_Task | Fluid Cooler QAQC and Cx | 28/04/2021 | 29/04/2021 | 28/02/2021 | 28/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C4.C4010 | TT_Task | Fluid Cooler RI prefabrication | 26/01/2021 | 01/02/2021 | 31/10/2020 | 31/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C4.C4020 | TT_Task | Fluid Cooler Panel installation | 06/07/2021 | 08/07/2021 | 15/05/2021 | 18/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C4.C4030 | TT_Task | Fluid Cooler RI in place | 13/07/2021 | 19/07/2021 | 27/05/2021 | 03/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C4.C4040 | TT_Task | Fluid Cooler Wire install and Term | 20/07/2021 | 27/07/2021 | 04/06/2021 | 10/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D3.C4.C4050 | TT_Task | Fluid Cooler QAQC and Cx | 06/05/2021 | 07/05/2021 | 28/02/2021 | 28/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2621 | TT_Mile | MSFT Delivery - ADMIN - UPM - ROJ | 30/11/2020 | 30/11/2020 | 24/11/2020 | 24/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2622 | TT_Mile | Admin Gen- ROJ | 30/11/2020 | 30/11/2020 | 25/09/2020 | 25/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C1135 | TT_Task | Set Gen Stack / Exhaust duct | 30/04/2021 | 04/05/2021 | 06/04/2021 | 06/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C1135 | TT_Task | Set Gen Stack / Exhaust duct | 01/02/2021 | 03/02/2021 | 19/01/2021 | 19/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C3135 | TT_Task | Set Gen Stack / Exhaust duct | 01/02/2021 | 03/02/2021 | 22/01/2021 | 22/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C2135 | TT_Task | Set Gen Stack / Exhaust duct | 01/02/2021 | 03/02/2021 | 22/01/2021 | 22/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C4135 | TT_Task | Set Gen Stack / Exhaust duct | 01/02/2021 | 03/02/2021 | 22/01/2021 | 22/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C2135 | TT_Task | Set Gen Stack / Exhaust duct | 30/04/2021 | 04/05/2021 | 06/04/2021 | 06/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C3135 | TT_Task | Set Gen Stack / Exhaust duct | 30/04/2021 | 04/05/2021 | 06/04/2021 | 06/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C4135 | TT_Task | Set Gen Stack / Exhaust duct | 01/06/2021 | 03/06/2021 | 01/05/2021 | 04/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C1135 | TT_Task | Set Gen Stack / Exhaust duct | 30/04/2021 | 04/05/2021 | 06/04/2021 | 06/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C3135 | TT_Task | Set Gen Stack / Exhaust duct | 30/04/2021 | 04/05/2021 | 07/04/2021 | 07/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C2135 | TT_Task | Set Gen Stack / Exhaust duct | 26/04/2021 | 28/04/2021 | 06/04/2021 | 06/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C4135 | TT_Task | Set Gen Stack / Exhaust duct | 30/04/2021 | 04/05/2021 | 07/04/2021 | 07/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C1135 | TT_Task | Set Gen Stack / Exhaust duct | 30/06/2021 | 02/07/2021 | 30/04/2021 | 04/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C3135 | TT_Task | Set Gen Stack / Exhaust duct | 30/06/2021 | 02/07/2021 | 30/04/2021 | 05/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C2135 | TT_Task | Set Gen Stack / Exhaust duct | 30/06/2021 | 02/07/2021 | 31/03/2021 | 02/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C4135 | TT_Task | Set Gen Stack / Exhaust duct | 30/06/2021 | 02/07/2021 | 30/04/2021 | 04/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.AD.A1135 | TT_Task | Set Gen Stack / Exhaust duct | 01/02/2021 | 03/02/2021 | 22/01/2021 | 22/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.CS1120 | TT_Task | Erect Interior Structural Steel | 07/11/2020 | 12/11/2020 | 26/10/2020 | 16/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.CS1120 | TT_Task | Erect Interior Structural Steel | 21/12/2020 | 29/12/2020 | 07/12/2020 | 12/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.CS1120 | TT_Task | Erect Interior Structural Steel | 23/11/2020 | 01/12/2020 | 16/11/2020 | 20/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2624 | TT_Mile | UPM - ROJ | 30/11/2020 | 30/11/2020 | 25/11/2020 | 25/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D4.S1010 | TT_Mile | DRB#2 Approval | 19/10/2020 | 19/10/2020 | 28/09/2020 | 28/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D4.S1020 | TT_Task | ADMIN Overhead Rough-in (DRB#2) | 05/02/2021 | 12/02/2021 | 07/01/2021 | 14/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D4.S1030 | TT_Task | ADMIN Electrical Room Build out (DRB#2) | 01/02/2021 | 04/02/2021 | 15/01/2021 | 21/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D4.S1040 | TT_Task | ADMIN Lighting installation (DRB#2) | 17/05/2021 | 20/05/2021 | 30/04/2021 | 05/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D4.C1.C1010 | TT_Task | Overhead Rough-in Additional Lighting and Branch (DRB#2) | 22/10/2020 | 22/10/2020 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D4.C1.C1030 | TT_Task | COLO Lighting installation (DRB#2) | 23/01/2021 | 23/01/2021 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D4.C1.C1020 | TT_Task | COLO Fluid Cooler Heat Trace Installation (DRB#2) | 17/12/2020 | 17/12/2020 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D4.C1.C3010 | TT_Task | Overhead Rough-in Additional Lighting and Branch (DRB#2) | 04/11/2020 | 04/11/2020 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D4.C1.C3030 | TT_Task | COLO Lighting installation (DRB#2) | 04/02/2021 | 04/02/2021 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D4.C1.C3020 | TT_Task | COLO Fluid Cooler Heat Trace Installation (DRB#2) | 17/12/2020 | 17/12/2020 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D4.C1.C2010 | TT_Task | Overhead Rough-in Additional Lighting and Branch (DRB#2) | 22/10/2020 | 22/10/2020 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D4.C1.C2030 | TT_Task | COLO Lighting installation (DRB#2) | 23/01/2021 | 23/01/2021 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D4.C1.C2020 | TT_Task | COLO Fluid Cooler Heat Trace Installation (DRB#2) | 17/12/2020 | 17/12/2020 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D4.C1.C4010 | TT_Task | Overhead Rough-in Additional Lighting and Branch (DRB#2) | 04/11/2020 | 04/11/2020 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D4.C1.C4030 | TT_Task | COLO Lighting installation (DRB#2) | 08/02/2021 | 08/02/2021 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D4.C1.C4020 | TT_Task | COLO Fluid Cooler Heat Trace Installation (DRB#2) | 17/12/2020 | 17/12/2020 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D4.C2.C1020 | TT_Task | Overhead Rough-in Additional Lighting and Branch (DRB#2) | 02/12/2020 | 02/12/2020 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D4.C2.C1030 | TT_Task | COLO Lighting installation (DRB#2) | 11/03/2021 | 11/03/2021 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D4.C2.C1010 | TT_Task | COLO Fluid Cooler Heat Trace Installation (DRB#2) | 17/12/2020 | 17/12/2020 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D4.C2.C3020 | TT_Task | Overhead Rough-in Additional Lighting and Branch (DRB#2) | 15/12/2020 | 15/12/2020 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D4.C2.C3030 | TT_Task | COLO Lighting installation (DRB#2) | 26/03/2021 | 26/03/2021 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D4.C2.C3010 | TT_Task | COLO Fluid Cooler Heat Trace Installation (DRB#2) | 18/12/2020 | 18/12/2020 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D4.C2.C2020 | TT_Task | Overhead Rough-in Additional Lighting and Branch (DRB#2) | 02/12/2020 | 02/12/2020 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D4.C2.C2040 | TT_Task | COLO Lighting installation (DRB#2) | 11/03/2021 | 11/03/2021 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D4.C2.C2010 | TT_Task | COLO Fluid Cooler Heat Trace Installation (DRB#2) | 29/12/2020 | 29/12/2020 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D4.C2.C4010 | TT_Task | Overhead Rough-in Additional Lighting and Branch (DRB#2) | 15/12/2020 | 15/12/2020 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D4.C2.C4020 | TT_Task | COLO Lighting installation (DRB#2) | 26/03/2021 | 26/03/2021 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D4.C3.C1020 | TT_Task | Overhead Rough-in Additional Lighting and Branch (DRB#2) | 30/01/2021 | 30/01/2021 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D4.C3.C1030 | TT_Task | COLO Lighting installation (DRB#2) | 27/04/2021 | 27/04/2021 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D4.C3.C1010 | TT_Task | COLO Fluid Cooler Heat Trace Installation (DRB#2) | 07/01/2021 | 07/01/2021 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D4.C3.C3010 | TT_Task | Overhead Rough-in Additional Lighting and Branch (DRB#2) | 12/02/2021 | 12/02/2021 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D4.C3.C3020 | TT_Task | COLO Lighting installation (DRB#2) | 12/05/2021 | 12/05/2021 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D4.C3.C2020 | TT_Task | Overhead Rough-in Additional Lighting and Branch (DRB#2) | 30/01/2021 | 30/01/2021 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D4.C3.C2030 | TT_Task | COLO Lighting installation (DRB#2) | 03/05/2021 | 03/05/2021 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D4.C3.C2010 | TT_Task | COLO Fluid Cooler Heat Trace Installation (DRB#2) | 14/01/2021 | 14/01/2021 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D4.C3.C4020 | TT_Task | Overhead Rough-in Additional Lighting and Branch (DRB#2) | 12/02/2021 | 12/02/2021 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D4.C3.C4030 | TT_Task | COLO Lighting installation (DRB#2) | 12/05/2021 | 12/05/2021 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D4.C3.C4010 | TT_Task | COLO Fluid Cooler Heat Trace Installation (DRB#2) | 29/01/2021 | 29/01/2021 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D4.C4.C1020 | TT_Task | Overhead Rough-in Additional Lighting and Branch (DRB#2) | 09/03/2021 | 09/03/2021 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D4.C4.C1030 | TT_Task | COLO Lighting installation (DRB#2) | 09/06/2021 | 09/06/2021 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D4.C4.C1010 | TT_Task | COLO Fluid Cooler Heat Trace Installation (DRB#2) | 05/02/2021 | 05/02/2021 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D4.C4.C3020 | TT_Task | Overhead Rough-in Additional Lighting and Branch (DRB#2) | 22/03/2021 | 22/03/2021 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D4.C4.C3030 | TT_Task | COLO Lighting installation (DRB#2) | 19/06/2021 | 19/06/2021 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D4.C4.C3010 | TT_Task | COLO Fluid Cooler Heat Trace Installation (DRB#2) | 20/02/2021 | 20/02/2021 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D4.C4.C2020 | TT_Task | Overhead Rough-in Additional Lighting and Branch (DRB#2) | 09/03/2021 | 09/03/2021 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D4.C4.C2030 | TT_Task | COLO Lighting installation (DRB#2) | 04/06/2021 | 04/06/2021 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D4.C4.C2010 | TT_Task | COLO Fluid Cooler Heat Trace Installation (DRB#2) | 05/02/2021 | 05/02/2021 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D4.C4.C4020 | TT_Task | Overhead Rough-in Additional Lighting and Branch (DRB#2) | 22/03/2021 | 22/03/2021 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D4.C4.C4030 | TT_Task | COLO Lighting installation (DRB#2) | 19/06/2021 | 19/06/2021 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D4.C4.C4010 | TT_Task | COLO Fluid Cooler Heat Trace Installation (DRB#2) | 20/02/2021 | 20/02/2021 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2677 | TT_Task | Term COLO -1 Cell-4 UPM | 01/02/2021 | 03/02/2021 | 25/01/2021 | 26/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2678 | TT_Task | Term COLO -2 Cell-4 UPM | 01/02/2021 | 03/02/2021 | 28/01/2021 | 06/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2679 | TT_Task | Term COLO -3 Cell-4 UPM | 01/03/2021 | 03/03/2021 | 11/02/2021 | 17/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2680 | TT_Task | Term COLO -4 Cell-4 UPM | 05/03/2021 | 08/03/2021 | 18/02/2021 | 20/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2681 | TT_Task | Term COLO -1 Cell-3 UPM | 01/02/2021 | 03/02/2021 | 26/01/2021 | 29/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2682 | TT_Task | Term COLO -2 Cell-3 UPM | 04/03/2021 | 06/03/2021 | 03/02/2021 | 06/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2683 | TT_Task | Term COLO -3 Cell-3 UPM | 01/03/2021 | 03/03/2021 | 06/02/2021 | 12/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2684 | TT_Task | Term COLO -4 Cell-3 UPM | 05/03/2021 | 08/03/2021 | 06/02/2021 | 10/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2685 | TT_Task | Term Admin - UPM | 01/02/2021 | 03/02/2021 | 21/01/2021 | 25/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D2.S1010 | TT_Task | Delay in UPM Delivery (Duration = Colo1 Cell-1 PSR (9/19) to MSFT delivery) | 28/09/2020 | 15/12/2020 | 19/09/2020 | 08/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D5.S1000 | TT_Task | Water Treatmant Skid Fabrication | 14/09/2020 | 07/12/2020 | 25/08/2020 | 28/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D5.S1010 | TT_Task | LI approval process | 14/09/2020 | 13/10/2020 | 25/08/2020 | 16/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D5.S1020 | TT_Mile | Start of LI Process / MSFT direction to proceed with Fabrication | 14/09/2020 | 14/09/2020 | 24/08/2020 | 24/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D5.S1030 | TT_Task | Water treatment delivery COLO-1 | 21/12/2020 | 27/12/2020 | 28/11/2020 | 04/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-2686 | TT_Task | Set Electrical Equipment-UPM | 30/11/2020 | 03/12/2020 | 24/11/2020 | 24/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-1961.1 | TT_Task | Exterior Equipment Pads - for UPM's | 16/11/2020 | 19/11/2020 | 18/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C1.C1120 | TT_Task | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | 02/01/2021 | 02/01/2021 | 14/12/2020 | 15/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C1.C1130 | TT_Task | Install added DRB#3 Tray and conduit | 01/02/2021 | 03/02/2021 | 04/01/2021 | 08/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C1.C1140 | TT_Task | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | 06/03/2021 | 10/03/2021 | 08/02/2021 | 13/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C1.C1180 | TT_Task | Install Roxtec block sealing and install added tray cable (DRB#3) | 01/06/2021 | 07/06/2021 | 04/05/2021 | 10/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C1.C1150 | TT_Task | Install additional Cable bus (DRB#3) | 13/02/2021 | 13/02/2021 | 18/01/2021 | 19/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C1.C1170 | TT_Task | Install additional Cable bus feeder (DRB#3) | 05/03/2021 | 05/03/2021 | 08/02/2021 | 13/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C1.C1100 | TT_Task | Install Added Overhead Rough In MER MECH EQ (DRB#3) | 28/09/2020 | 05/10/2020 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C1.C1160 | TT_Task | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | 31/03/2021 | 31/03/2021 | 19/03/2021 | 19/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.S1000 | TT_Mile | DRB#3 Approval-Part B- MEP | 19/10/2020 | 19/10/2020 | 08/10/2020 | 08/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.S1010 | TT_Task | Submit and approve Shop drawings for UPM junstion box | 19/10/2020 | 08/11/2020 | 09/10/2020 | 14/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.S1030 | TT_Task | Lead time for junction box | 02/11/2020 | 13/12/2020 | 15/10/2020 | 23/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.S1020 | TT_Task | Submit and approve shop drawing for PEMB penetrations | 19/10/2020 | 08/11/2020 | 31/10/2020 | 31/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C1.C1110 | TT_Task | Sure steel - PEMB MER penetration framing | 30/11/2020 | 03/12/2020 | 16/11/2020 | 18/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.S1040 | TT_Task | Fabrication and Delivery of PEMB pentrations support steel | 09/11/2020 | 13/11/2020 | 23/10/2020 | 29/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C1.C2120 | TT_Task | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | 01/03/2021 | 01/03/2021 | 14/12/2020 | 15/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C1.C2130 | TT_Task | Install added DRB#3 Tray and conduit | 02/03/2021 | 04/03/2021 | 04/01/2021 | 08/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C1.C2140 | TT_Task | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | 06/03/2021 | 10/03/2021 | 25/01/2021 | 05/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C1.C2180 | TT_Task | Install Roxtec block sealing and install added tray cable (DRB#3) | 01/06/2021 | 07/06/2021 | 12/05/2021 | 18/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C1.C2150 | TT_Task | Install additional Cable bus (DRB#3) | 01/03/2021 | 01/03/2021 | 20/01/2021 | 21/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C1.C2170 | TT_Task | Install additional Cable bus feeder (DRB#3) | 06/03/2021 | 06/03/2021 | 08/02/2021 | 13/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C1.C2100 | TT_Task | Install Added Overhead Rough In MER MECH EQ (DRB#3) | 28/09/2020 | 05/10/2020 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C1.C2160 | TT_Task | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | 31/03/2021 | 31/03/2021 | 19/03/2021 | 19/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C1.C2110 | TT_Task | Sure steel - PEMB MER penetration framing | 30/11/2020 | 03/12/2020 | 16/11/2020 | 18/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C1.C3120 | TT_Task | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | 02/01/2021 | 02/01/2021 | 21/12/2020 | 22/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C1.C3130 | TT_Task | Install added DRB#3 Tray and conduit | 08/02/2021 | 11/02/2021 | 15/01/2021 | 23/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C1.C3140 | TT_Task | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | 06/03/2021 | 10/03/2021 | 01/02/2021 | 04/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C1.C3180 | TT_Task | Install Roxtec block sealing and install added tray cable (DRB#3) | 01/06/2021 | 07/06/2021 | 21/05/2021 | 28/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C1.C3150 | TT_Task | Install additional Cable bus (DRB#3) | 01/03/2021 | 01/03/2021 | 25/01/2021 | 26/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C1.C3170 | TT_Task | Install additional Cable bus feeder (DRB#3) | 02/03/2021 | 02/03/2021 | 15/02/2021 | 16/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C1.C3100 | TT_Task | Install Added Overhead Rough In MER MECH EQ (DRB#3) | 28/09/2020 | 05/10/2020 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C1.C3160 | TT_Task | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | 31/03/2021 | 31/03/2021 | 31/03/2021 | 31/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C1.C3110 | TT_Task | Sure steel - PEMB MER penetration framing | 30/11/2020 | 03/12/2020 | 16/11/2020 | 18/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C1.C4120 | TT_Task | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | 01/03/2021 | 01/03/2021 | 21/01/2021 | 22/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C1.C4130 | TT_Task | Install added DRB#3 Tray and conduit | 02/03/2021 | 04/03/2021 | 15/01/2021 | 23/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C1.C4140 | TT_Task | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | 01/03/2021 | 04/03/2021 | 22/02/2021 | 27/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C1.C4180 | TT_Task | Install Roxtec block sealing and install added tray cable (DRB#3) | 07/06/2021 | 14/06/2021 | 24/05/2021 | 28/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C1.C4150 | TT_Task | Install additional Cable bus (DRB#3) | 03/03/2021 | 03/03/2021 | 05/02/2021 | 06/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C1.C4170 | TT_Task | Install additional Cable bus feeder (DRB#3) | 04/03/2021 | 04/03/2021 | 15/02/2021 | 16/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C1.C4100 | TT_Task | Install Added Overhead Rough In MER MECH EQ (DRB#3) | 28/09/2020 | 05/10/2020 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C1.C4160 | TT_Task | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | 31/03/2021 | 31/03/2021 | 31/03/2021 | 31/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C1.C4110 | TT_Task | Sure steel - PEMB MER penetration framing | 04/12/2020 | 09/12/2020 | 16/11/2020 | 18/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C2.C1110 | TT_Task | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | 05/02/2021 | 05/02/2021 | 07/01/2021 | 08/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C2.C1120 | TT_Task | Install added DRB#3 Tray and conduit | 01/03/2021 | 03/03/2021 | 06/02/2021 | 11/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C2.C1130 | TT_Task | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | 31/03/2021 | 03/04/2021 | 04/03/2021 | 09/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C2.C1180 | TT_Task | Install Roxtec block sealing and install added tray cable (DRB#3) | 30/06/2021 | 08/07/2021 | 17/06/2021 | 23/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C2.C1150 | TT_Task | Install additional Cable bus (DRB#3) | 31/03/2021 | 31/03/2021 | 13/03/2021 | 13/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C2.C1160 | TT_Task | Install additional Cable bus feeder (DRB#3) | 30/04/2021 | 30/04/2021 | 17/04/2021 | 17/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C2.C1140 | TT_Task | Install Added Overhead Rough In MER MECH EQ (DRB#3) | 28/09/2020 | 05/10/2020 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C2.C1170 | TT_Task | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | 02/06/2021 | 02/06/2021 | 11/05/2021 | 11/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C2.C1100 | TT_Task | Sure steel - PEMB MER penetration framing | 01/02/2021 | 04/02/2021 | 02/01/2021 | 06/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C2.C2110 | TT_Task | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | 05/02/2021 | 05/02/2021 | 08/01/2021 | 09/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C2.C2120 | TT_Task | Install added DRB#3 Tray and conduit | 31/03/2021 | 02/04/2021 | 01/03/2021 | 09/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C2.C2130 | TT_Task | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | 31/03/2021 | 03/04/2021 | 30/03/2021 | 05/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C2.C2180 | TT_Task | Install Roxtec block sealing and install added tray cable (DRB#3) | 30/06/2021 | 08/07/2021 | 18/06/2021 | 26/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C2.C2150 | TT_Task | Install additional Cable bus (DRB#3) | 03/05/2021 | 03/05/2021 | 01/04/2021 | 01/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C2.C2170 | TT_Task | Install additional Cable bus feeder (DRB#3) | 04/05/2021 | 04/05/2021 | 17/04/2021 | 17/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C2.C2140 | TT_Task | Install Added Overhead Rough In MER MECH EQ (DRB#3) | 28/09/2020 | 05/10/2020 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C2.C2160 | TT_Task | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | 02/06/2021 | 02/06/2021 | 11/05/2021 | 11/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C2.C2100 | TT_Task | Sure steel - PEMB MER penetration framing | 01/02/2021 | 04/02/2021 | 04/01/2021 | 08/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C2.C3110 | TT_Task | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | 11/02/2021 | 11/02/2021 | 11/01/2021 | 12/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C2.C3120 | TT_Task | Install added DRB#3 Tray and conduit | 26/03/2021 | 29/03/2021 | 27/02/2021 | 04/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C2.C3130 | TT_Task | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | 31/03/2021 | 03/04/2021 | 31/03/2021 | 03/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C2.C3180 | TT_Task | Install Roxtec block sealing and install added tray cable (DRB#3) | 30/06/2021 | 08/07/2021 | 22/06/2021 | 29/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C2.C3150 | TT_Task | Install additional Cable bus (DRB#3) | 31/03/2021 | 31/03/2021 | 25/03/2021 | 25/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C2.C3160 | TT_Task | Install additional Cable bus feeder (DRB#3) | 30/04/2021 | 30/04/2021 | 26/04/2021 | 26/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C2.C3140 | TT_Task | Install Added Overhead Rough In MER MECH EQ (DRB#3) | 28/09/2020 | 05/10/2020 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C2.C3170 | TT_Task | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | 02/06/2021 | 02/06/2021 | 26/05/2021 | 26/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C2.C3100 | TT_Task | Sure steel - PEMB MER penetration framing | 05/02/2021 | 10/02/2021 | 07/01/2021 | 11/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C2.C4110 | TT_Task | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | 11/02/2021 | 11/02/2021 | 11/01/2021 | 12/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C2.C4120 | TT_Task | Install added DRB#3 Tray and conduit | 02/04/2021 | 05/04/2021 | 19/03/2021 | 24/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C2.C4130 | TT_Task | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | 07/05/2021 | 11/05/2021 | 02/04/2021 | 07/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C2.C4180 | TT_Task | Install Roxtec block sealing and install added tray cable (DRB#3) | 30/06/2021 | 08/07/2021 | 25/06/2021 | 01/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C2.C4150 | TT_Task | Install additional Cable bus (DRB#3) | 30/04/2021 | 30/04/2021 | 09/04/2021 | 09/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C2.C4160 | TT_Task | Install additional Cable bus feeder (DRB#3) | 04/05/2021 | 04/05/2021 | 30/04/2021 | 30/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C2.C4140 | TT_Task | Install Added Overhead Rough In MER MECH EQ (DRB#3) | 28/09/2020 | 05/10/2020 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C2.C4170 | TT_Task | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | 08/06/2021 | 08/06/2021 | 25/05/2021 | 25/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C2.C4100 | TT_Task | Sure steel - PEMB MER penetration framing | 05/02/2021 | 10/02/2021 | 07/01/2021 | 11/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C3.C1110 | TT_Task | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | 01/03/2021 | 01/03/2021 | 15/02/2021 | 17/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C3.C1120 | TT_Task | Install added DRB#3 Tray and conduit | 30/04/2021 | 04/05/2021 | 20/04/2021 | 23/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C3.C1130 | TT_Task | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | 01/06/2021 | 04/06/2021 | 30/04/2021 | 05/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C3.C1140 | TT_Task | Install Roxtec block sealing and Install added tray cable (DRB#3) | 17/08/2021 | 23/08/2021 | 20/07/2021 | 27/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C3.C1150 | TT_Task | Install additional Cable bus (DRB#3) | 18/05/2021 | 18/05/2021 | 03/05/2021 | 03/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C3.C1180 | TT_Task | Install additional Cable bus feeder (DRB#3) | 01/06/2021 | 01/06/2021 | 01/06/2021 | 02/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C3.C1160 | TT_Task | Install Added Overhead Rough In MER MECH EQ (DRB#3) | 28/09/2020 | 05/10/2020 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C3.C1170 | TT_Task | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | 30/06/2021 | 30/06/2021 | 21/06/2021 | 21/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C3.C1100 | TT_Task | Sure steel - PEMB MER penetration framing | 01/02/2021 | 04/02/2021 | 11/01/2021 | 15/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C3.C2110 | TT_Task | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | 05/02/2021 | 05/02/2021 | 25/01/2021 | 27/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C3.C2120 | TT_Task | Install added DRB#3 Tray and conduit | 30/04/2021 | 04/05/2021 | 28/04/2021 | 03/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C3.C2130 | TT_Task | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | 03/06/2021 | 07/06/2021 | 05/05/2021 | 08/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C3.C2180 | TT_Task | Install Roxtec block sealing and install added tray cable (DRB#3) | 09/08/2021 | 16/08/2021 | 21/07/2021 | 28/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C3.C2140 | TT_Task | Install additional Cable bus (DRB#3) | 29/05/2021 | 29/05/2021 | 13/05/2021 | 13/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C3.C2170 | TT_Task | Install additional Cable bus feeder (DRB#3) | 30/06/2021 | 30/06/2021 | 10/06/2021 | 11/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C3.C2150 | TT_Task | Install Added Overhead Rough In MER MECH EQ (DRB#3) | 28/09/2020 | 05/10/2020 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C3.C2160 | TT_Task | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | 30/06/2021 | 30/06/2021 | 23/06/2021 | 23/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C3.C2100 | TT_Task | Sure steel - PEMB MER penetration framing | 01/02/2021 | 04/02/2021 | 11/01/2021 | 15/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C3.C3110 | TT_Task | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | 01/03/2021 | 01/03/2021 | 15/02/2021 | 17/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C3.C3120 | TT_Task | Install added DRB#3 Tray and conduit | 01/06/2021 | 03/06/2021 | 04/05/2021 | 07/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C3.C3130 | TT_Task | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | 01/06/2021 | 04/06/2021 | 27/04/2021 | 03/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C3.C3180 | TT_Task | Install Roxtec block sealing and install added tray cable (DRB#3) | 03/09/2021 | 11/09/2021 | 20/08/2021 | 26/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C3.C3140 | TT_Task | Install additional Cable bus (DRB#3) | 01/06/2021 | 01/06/2021 | 31/05/2021 | 31/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C3.C3150 | TT_Task | Install additional Cable bus feeder (DRB#3) | 02/07/2021 | 02/07/2021 | 14/06/2021 | 14/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C3.C3160 | TT_Task | Install Added Overhead Rough In MER MECH EQ (DRB#3) | 28/09/2020 | 05/10/2020 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C3.C3170 | TT_Task | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | 31/08/2021 | 31/08/2021 | 14/08/2021 | 14/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C3.C3100 | TT_Task | Sure steel - PEMB MER penetration framing | 05/02/2021 | 10/02/2021 | 11/01/2021 | 15/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C3.C4110 | TT_Task | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | 01/03/2021 | 01/03/2021 | 15/02/2021 | 17/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C3.C4120 | TT_Task | Install added DRB#3 Tray and conduit | 01/06/2021 | 03/06/2021 | 24/05/2021 | 27/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C3.C4130 | TT_Task | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | 07/06/2021 | 10/06/2021 | 28/05/2021 | 02/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C3.C4180 | TT_Task | Install Roxtec block sealing and install added tray cable (DRB#3) | 31/08/2021 | 08/09/2021 | 16/08/2021 | 21/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C3.C4140 | TT_Task | Install additional Cable bus (DRB#3) | 05/06/2021 | 05/06/2021 | 31/05/2021 | 31/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C3.C4160 | TT_Task | Install additional Cable bus feeder (DRB#3) | 31/07/2021 | 31/07/2021 | 16/07/2021 | 16/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C3.C4150 | TT_Task | Install Added Overhead Rough In MER MECH EQ (DRB#3) | 28/09/2020 | 05/10/2020 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C3.C4170 | TT_Task | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | 06/07/2021 | 06/07/2021 | 30/06/2021 | 30/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C3.C4100 | TT_Task | Sure steel - PEMB MER penetration framing | 05/02/2021 | 10/02/2021 | 11/01/2021 | 15/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C4.C1110 | TT_Task | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | 01/06/2021 | 01/06/2021 | 30/04/2021 | 30/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C4.C1120 | TT_Task | Install added DRB#3 Tray and conduit | 06/07/2021 | 08/07/2021 | 17/06/2021 | 13/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C4.C1130 | TT_Task | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | 08/07/2021 | 12/07/2021 | 11/06/2021 | 16/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C4.C1180 | TT_Task | Install Roxtec block sealing and install added tray cable (DRB#3) | 22/09/2021 | 29/09/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C4.C1140 | TT_Task | Install additional Cable bus (DRB#3) | 31/07/2021 | 31/07/2021 | 25/06/2021 | 26/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C4.C1160 | TT_Task | Install additional Cable bus feeder (DRB#3) | 31/07/2021 | 31/07/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C4.C1170 | TT_Task | Install Added Overhead Rough In MER MECH EQ (DRB#3) | 28/09/2020 | 05/10/2020 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C4.C1150 | TT_Task | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | 31/08/2021 | 31/08/2021 | 25/08/2021 | 25/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C4.C1100 | TT_Task | Sure steel - PEMB MER penetration framing | 11/02/2021 | 15/02/2021 | 18/01/2021 | 22/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C4.C2110 | TT_Task | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | 01/06/2021 | 01/06/2021 | 30/04/2021 | 30/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C4.C2120 | TT_Task | Install added DRB#3 Tray and conduit | 31/07/2021 | 03/08/2021 | 30/06/2021 | 02/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C4.C2130 | TT_Task | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | 06/08/2021 | 10/08/2021 | 08/07/2021 | 12/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C4.C2180 | TT_Task | Install Roxtec block sealing and install added tray cable (DRB#3) | 22/09/2021 | 29/09/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C4.C2140 | TT_Task | Install additional Cable bus (DRB#3) | 30/06/2021 | 30/06/2021 | 28/07/2021 | 28/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C4.C2160 | TT_Task | Install additional Cable bus feeder (DRB#3) | 31/08/2021 | 31/08/2021 | 13/08/2021 | 16/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C4.C2170 | TT_Task | Install Added Overhead Rough In MER MECH EQ (DRB#3) | 28/09/2020 | 05/10/2020 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C4.C2150 | TT_Task | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | 31/08/2021 | 31/08/2021 | 25/08/2021 | 25/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C4.C2100 | TT_Task | Sure steel - PEMB MER penetration framing | 11/02/2021 | 15/02/2021 | 18/01/2021 | 22/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C4.C3110 | TT_Task | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | 01/06/2021 | 01/06/2021 | 30/04/2021 | 30/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C4.C3120 | TT_Task | Install added DRB#3 Tray and conduit | 31/07/2021 | 03/08/2021 | 06/07/2021 | 13/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C4.C3130 | TT_Task | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | 31/07/2021 | 04/08/2021 | 12/07/2021 | 15/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C4.C3180 | TT_Task | Install Roxtec block sealing and install added tray cable (DRB#3) | 02/10/2021 | 08/10/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C4.C3140 | TT_Task | Install additional Cable bus (DRB#3) | 31/07/2021 | 31/07/2021 | 17/07/2021 | 17/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C4.C3160 | TT_Task | Install additional Cable bus feeder (DRB#3) | 31/08/2021 | 31/08/2021 | 04/08/2021 | 04/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C4.C3170 | TT_Task | Install Added Overhead Rough In MER MECH EQ (DRB#3) | 28/09/2020 | 05/10/2020 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C4.C3150 | TT_Task | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | 03/09/2021 | 03/09/2021 |  |  | 400 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C4.C3100 | TT_Task | Sure steel - PEMB MER penetration framing | 16/02/2021 | 19/02/2021 | 18/01/2021 | 22/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C4.C4110 | TT_Task | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | 01/06/2021 | 01/06/2021 | 30/04/2021 | 30/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C4.C4120 | TT_Task | Install added DRB#3 Tray and conduit | 31/07/2021 | 03/08/2021 | 06/07/2021 | 08/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C4.C4130 | TT_Task | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | 06/08/2021 | 10/08/2021 | 12/07/2021 | 15/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C4.C4180 | TT_Task | Install Roxtec block sealing and install added tray cable (DRB#3) | 22/09/2021 | 29/09/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C4.C4140 | TT_Task | Install additional Cable bus (DRB#3) | 31/07/2021 | 31/07/2021 | 28/07/2021 | 28/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C4.C4150 | TT_Task | Install additional Cable bus feeder (DRB#3) | 31/08/2021 | 31/08/2021 | 24/08/2021 | 25/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C4.C4170 | TT_Task | Install Added Overhead Rough In MER MECH EQ (DRB#3) | 28/09/2020 | 05/10/2020 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C4.C4160 | TT_Task | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | 31/08/2021 | 31/08/2021 | 25/08/2021 | 25/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.C4.C4100 | TT_Task | Sure steel - PEMB MER penetration framing | 16/02/2021 | 19/02/2021 | 18/01/2021 | 22/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.Cx4030 | TT_Task | MST Ready for Network Install | 02/10/2021 | 14/10/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.Cx4050 | TT_Task | Final Clean/ ready for lock down | 13/11/2021 | 22/11/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-C1.P2300 | TT_FinMile | TCO Admin/COLO 1 | 12/11/2021 | 12/11/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-C1.P2400 | TT_FinMile | Substantial Completion Admin/COLO 1 | 02/12/2021 | 02/12/2021 |  |  | 1136 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-C1.P2500 | TT_FinMile | Lock down Admin/COLO 1 | 22/11/2021 | 22/11/2021 |  |  | 1216 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-C2.P2300. | TT_FinMile | TCO COLO 2 | 10/01/2022 | 10/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-C2.P2400 | TT_FinMile | Substantial Completion COLO 2 | 03/02/2022 | 03/02/2022 |  |  | 632 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-C2.P2500 | TT_FinMile | Lock down COLO 2 | 21/01/2022 | 21/01/2022 |  |  | 736 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-C3.P2300 | TT_FinMile | TCO COLO 3 | 22/02/2022 | 22/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-C3.P2400 | TT_FinMile | Substantial Completion COLO 3 | 14/03/2022 | 14/03/2022 |  |  | 320 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-C3.P2500 | TT_FinMile | Lock down COLO 3 | 06/03/2022 | 06/03/2022 |  |  | 384 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-C4.P2300 | TT_FinMile | TCO COLO 4 | 02/04/2022 | 02/04/2022 |  |  | 168 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-C4.P2400 | TT_FinMile | Substantial Completion COLO 4 | 23/04/2022 | 23/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-C4.P2500 | TT_FinMile | Lock down COLO 4 | 13/04/2022 | 13/04/2022 |  |  | 80 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.Cx4030 | TT_Task | MST Ready for Network Install | 04/12/2021 | 09/12/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.Cx4050 | TT_Task | Final Clean/ ready for lock down | 10/01/2022 | 21/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.Cx4030 | TT_Task | MST Ready for Network Install | 19/01/2022 | 25/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.Cx4050 | TT_Task | Final Clean/ ready for lock down | 23/02/2022 | 06/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.Cx4030 | TT_Task | MST Ready for Network Install | 28/02/2022 | 06/03/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.Cx4050 | TT_Task | Final Clean/ ready for lock down | 03/04/2022 | 13/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
NEW1 | TT_Task | URS Vault design and Approval | 31/08/2020 | 31/08/2020 | 29/08/2020 | 29/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.E.1130 | TT_Task | Set- COLO-1 UMS | 31/08/2020 | 31/08/2020 | 29/08/2020 | 29/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.E.1140 | TT_Task | Set- COLO-2 UMS | 31/08/2020 | 31/08/2020 | 29/08/2020 | 29/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.E.1150 | TT_Task | Set- COLO-3 UMS | 31/08/2020 | 31/08/2020 | 29/08/2020 | 29/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.E.1160 | TT_Task | Set- COLO-4 UMS | 31/08/2020 | 31/08/2020 | 29/08/2020 | 29/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.E.1050 | TT_Task | PAD- COLO-1 UMS | 31/08/2020 | 31/08/2020 | 29/08/2020 | 29/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.E.1060 | TT_Task | PAD- COLO-2 UMS | 31/08/2020 | 31/08/2020 | 29/08/2020 | 29/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.E.1070 | TT_Task | PAD- COLO-3 UMS | 31/08/2020 | 31/08/2020 | 29/08/2020 | 29/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.E.1080 | TT_Task | PAD- COLO-4 UMS | 31/08/2020 | 31/08/2020 | 29/08/2020 | 29/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.E.1010 | TT_Task | Duct Bank - UMS01 to UPM COLO-1 Cell-1 | 31/08/2020 | 31/08/2020 | 29/08/2020 | 29/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.E.1020 | TT_Task | Duct Bank - UMS02 to UPM COLO-2 Cell-1 | 31/08/2020 | 31/08/2020 | 29/08/2020 | 29/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.E.1030 | TT_Task | Duct Bank - UMS03 to UPM COLO-3 Cell-1 | 31/08/2020 | 31/08/2020 | 29/08/2020 | 29/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.E.1040 | TT_Task | Duct Bank - UMS04 to UPM COLO-4 Cell-1 | 31/08/2020 | 31/08/2020 | 29/08/2020 | 29/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.E.1090 | TT_Task | Pull- UMS01- UPM COLO-1 Cell-1 | 31/08/2020 | 31/08/2020 | 29/08/2020 | 29/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.E.1100 | TT_Task | Pull- UMS02- UPM COLO-2 Cell-1 | 31/08/2020 | 31/08/2020 | 29/08/2020 | 29/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.E.1110 | TT_Task | Pull- UMS03- UPM COLO-3 Cell-1 | 31/08/2020 | 31/08/2020 | 29/08/2020 | 29/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.E.1120 | TT_Task | Pull- UMS04- UPM COLO-4 Cell-1 | 31/08/2020 | 31/08/2020 | 29/08/2020 | 29/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.E.1260 | TT_Task | Term- UMS01- Load side | 31/08/2020 | 31/08/2020 | 29/08/2020 | 29/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.E.1270 | TT_Task | Term- UMS02- Load side | 31/08/2020 | 31/08/2020 | 29/08/2020 | 29/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.E.1280 | TT_Task | Term- UMS03- Load side | 31/08/2020 | 31/08/2020 | 29/08/2020 | 29/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.E.1290 | TT_Task | Term- UMS04- Load side | 31/08/2020 | 31/08/2020 | 29/08/2020 | 29/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.E.1300 | TT_Task | Yellow Tagging for UMS01 | 31/08/2020 | 31/08/2020 | 29/08/2020 | 29/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.E.1310 | TT_Task | Yellow Tagging for UMS02 | 31/08/2020 | 31/08/2020 | 29/08/2020 | 29/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.E.1320 | TT_Task | Yellow Tagging for UMS03 | 31/08/2020 | 31/08/2020 | 29/08/2020 | 29/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.E.1330 | TT_Task | Yellow Tagging for UMS04 | 31/08/2020 | 31/08/2020 | 29/08/2020 | 29/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C3121 | TT_Task | Set Exterior Water Treatment equipment | 01/02/2021 | 02/02/2021 | 19/01/2021 | 19/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C2171 | TT_Task | Set Exterior Water Treatment equipment | 01/02/2021 | 02/02/2021 | 26/01/2021 | 26/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C1161 | TT_Task | Set Exterior Water Treatment equipment | 31/03/2021 | 01/04/2021 | 03/03/2021 | 03/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C2161 | TT_Task | Set Exterior Water Treatment equipment | 26/04/2021 | 27/04/2021 | 09/04/2021 | 12/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.C4131 | TT_Task | Set Exterior Water Treatment equipment | 30/04/2021 | 03/05/2021 | 12/04/2021 | 12/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C1111 | TT_Task | Set Exterior Water Treatment equipment | 31/03/2021 | 01/04/2021 | 03/03/2021 | 03/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C3111 | TT_Task | Set Exterior Water Treatment equipment | 30/06/2021 | 01/07/2021 | 30/04/2021 | 03/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C2111 | TT_Task | Set Exterior Water Treatment equipment | 30/06/2021 | 01/07/2021 | 30/04/2021 | 03/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.C4111 | TT_Task | Set Exterior Water Treatment equipment | 30/06/2021 | 01/07/2021 | 30/04/2021 | 03/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.C1121 | TT_Task | Set Exterior Water Treatment equipment | 01/02/2021 | 02/02/2021 | 19/01/2021 | 19/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9708 | TT_Task | UMS - ROJ COLO-2 | 31/08/2020 | 31/08/2020 | 29/08/2020 | 29/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9709 | TT_Task | UMS - ROJ COLO-3 | 31/08/2020 | 31/08/2020 | 29/08/2020 | 29/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9710 | TT_Task | UMS - ROJ COLO-4 | 31/08/2020 | 31/08/2020 | 29/08/2020 | 29/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9711 | TT_Task | MSFT Delivery -UMS -COLO 4 ROJ | 31/08/2020 | 31/08/2020 | 29/08/2020 | 29/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9712 | TT_Task | MSFT Delivery -UMS -COLO 3 ROJ | 31/08/2020 | 31/08/2020 | 29/08/2020 | 29/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9713 | TT_Task | MSFT Delivery -UMS -COLO 2 ROJ | 31/08/2020 | 31/08/2020 | 29/08/2020 | 29/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-C2.P2300 | TT_Task | TCO COLO 2 | 31/08/2020 | 31/08/2020 | 29/08/2020 | 29/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-P2529 | TT_Task | Weather Tight | 31/08/2020 | 31/08/2020 | 29/08/2020 | 29/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.E.1190 | TT_Task | Term COLO -1 Cell-4 UPM | 31/08/2020 | 31/08/2020 | 29/08/2020 | 29/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.E.1200 | TT_Task | Term COLO -2 Cell-4 UPM | 31/08/2020 | 31/08/2020 | 29/08/2020 | 29/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.E.1220 | TT_Task | Term COLO -3 Cell-4 UPM | 31/08/2020 | 31/08/2020 | 29/08/2020 | 29/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.E.1240 | TT_Task | Term COLO -4 Cell-4 UPM | 31/08/2020 | 31/08/2020 | 29/08/2020 | 29/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.E.1180 | TT_Task | Term COLO -1 Cell-3 UPM | 31/08/2020 | 31/08/2020 | 29/08/2020 | 29/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.E.1210 | TT_Task | Term COLO -2 Cell-3 UPM | 31/08/2020 | 31/08/2020 | 29/08/2020 | 29/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.E.1230 | TT_Task | Term COLO -3 Cell-3 UPM | 31/08/2020 | 31/08/2020 | 29/08/2020 | 29/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.E.1250 | TT_Task | Term COLO -4 Cell-3 UPM | 31/08/2020 | 31/08/2020 | 29/08/2020 | 29/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.E.1170 | TT_Task | Term Admin - UPM | 31/08/2020 | 31/08/2020 | 29/08/2020 | 29/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C1111 | TT_Task | Set Exterior Water Treatment equipment | 02/01/2021 | 04/01/2021 | 05/12/2020 | 07/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C3131 | TT_Task | Set Exterior Water Treatment equipment | 07/12/2020 | 08/12/2020 | 23/11/2020 | 08/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C2121 | TT_Task | Set Exterior Water Treatment equipment | 02/01/2021 | 04/01/2021 | 07/12/2020 | 08/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.C4121 | TT_Task | Set Exterior Water Treatment equipment | 02/01/2021 | 04/01/2021 | 07/12/2020 | 09/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9714 | TT_Mile | Void Activities start | 01/09/2020 | 01/09/2020 | 29/08/2020 | 29/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9715 | TT_FinMile | Void Activities finish | 31/08/2020 | 31/08/2020 | 26/09/2020 | 26/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1031 | TT_Task | Remaining Site Sanitary | 11/05/2020 | 24/07/2020 | 11/08/2020 | 11/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1041 | TT_Task | Remaining IWW System | 26/05/2020 | 08/08/2020 | 11/08/2020 | 11/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9716 | TT_Task | Site Shut Down - 9/9/2020 | 14/09/2020 | 14/09/2020 | 09/09/2020 | 09/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9717 | TT_Task | Site Shut Down - 9/10/2020 | 15/09/2020 | 15/09/2020 | 10/09/2020 | 10/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9718 | TT_Task | Site Shut Down - 9/11/2020 | 16/09/2020 | 16/09/2020 | 11/09/2020 | 11/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9719 | TT_Task | Site Shut Down - 9/12/2020 | 17/09/2020 | 17/09/2020 | 12/09/2020 | 12/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9720 | TT_Task | Site Shut Down - 9/14/2020 | 28/09/2020 | 28/09/2020 | 14/09/2020 | 14/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9721 | TT_Task | Site Shut Down - 9/15/2020 | 29/09/2020 | 29/09/2020 | 15/09/2020 | 15/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9722 | TT_Task | Site Shut Down - 9/16/2020 | 30/09/2020 | 30/09/2020 | 16/09/2020 | 16/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.D6.S1000.1 | TT_Mile | DRB#3 Approval-Part A- CSA | 19/10/2020 | 19/10/2020 | 11/09/2020 | 11/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9724 | TT_Task | Complete Remaining IWW piping to tie-in point | 28/09/2020 | 29/10/2020 | 21/09/2020 | 28/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9725 | TT_Task | Clayco Waiting on Overhead Powerlines to be grounded | 14/09/2020 | 19/10/2020 | 12/09/2020 | 17/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9726 | TT_Task | Complete Remaining Sanitary piping to tie-in point | 21/09/2020 | 20/10/2020 | 21/09/2020 | 28/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9727 | TT_Task | Clayco Waiting on Overhead Powerlines to be grounded | 14/09/2020 | 19/10/2020 | 12/09/2020 | 17/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9728 | TT_Task | Complete Remaining ITW piping to tie-in point | 21/09/2020 | 20/10/2020 | 21/09/2020 | 30/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9729 | TT_Task | Clayco Waiting on Overhead Powerlines to be grounded | 14/09/2020 | 19/10/2020 | 12/09/2020 | 17/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9731 | TT_Task | Complete Remaining Fire Main piping to tie-in point | 21/09/2020 | 20/10/2020 | 21/09/2020 | 30/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9730 | TT_Task | Clayco Waiting on Overhead Powerlines to be grounded | 14/09/2020 | 19/10/2020 | 12/09/2020 | 17/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9732 | TT_Task | Complete Remaining Telecom Duct Back (excluding Tie-in) | 21/09/2020 | 20/10/2020 | 21/09/2020 | 17/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9733 | TT_Task | Clayco Waiting on Overhead Powerlines to be grounded | 14/09/2020 | 19/10/2020 | 12/09/2020 | 17/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9734 | TT_Task | Delay in COLO-1- Cell-1 MER Delivery (Duration = COLO1 Cell-1 PSR(11/6/20) to MSFT delivery) | 21/12/2020 | 30/01/2021 | 06/11/2020 | 16/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9735 | TT_Mile | MSFT decision to Bid Fluid cooler scope to Stetner | 28/09/2020 | 28/09/2020 | 22/09/2020 | 22/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9736 | TT_Task | Review Fluid Cooler wiring and devices buyout with Stetner | 28/09/2020 | 01/10/2020 | 23/09/2020 | 09/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9737 | TT_Task | Change order release for fluid cooler wiring devices | 19/10/2020 | 20/10/2020 | 10/10/2020 | 26/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9738 | TT_Task | Temp Power/ Telecom duct bank | 28/09/2020 | 01/10/2020 | 27/08/2020 | 22/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9739 | TT_Task | Delay in UPM Delivery (Duration = Colo1 Cell-2 PSR(10/13) to MSFT delivery) | 02/11/2020 | 12/12/2020 | 13/10/2020 | 23/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9740 | TT_Task | Delay in UPM Delivery (Duration = Colo1 Cell-3 PSR(9/28) to MSFT delivery) | 02/11/2020 | 28/12/2020 | 28/09/2020 | 23/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9741 | TT_Task | Delay in UPM Delivery (Duration = Colo1 Cell-4 PSR (10/28) to MSFT delivery) | 02/11/2020 | 27/11/2020 | 28/10/2020 | 23/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9742 | TT_Task | Delay in COLO-1- Cell-2 MER Delivery (Duration = COLO1 Cell-2 PSR(11/13/20) to MSFT delivery) | 21/12/2020 | 29/01/2021 | 13/11/2020 | 22/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9743 | TT_Task | Delay in COLO-1- Cell-3 MER Delivery (Duration = COLO1 Cell-3 PSR(11/20/20) to MSFT delivery) | 21/12/2020 | 04/02/2021 | 20/11/2020 | 05/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9744 | TT_Task | Hang Wall Partitions | 16/11/2020 | 10/12/2020 | 02/11/2020 | 09/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9745 | TT_Task | Remaining MER raceway across Mech chase | 01/12/2020 | 10/12/2020 | 05/01/2021 | 20/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9746 | TT_Task | Delay in COLO-2- Cell-1 MER Delivery (Duration = Colo1 Cell-1 PSR(12/15/20) to MSFT delivery) | 21/12/2020 | 11/02/2021 | 15/12/2020 | 03/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9747 | TT_Task | Delay in COLO-2- Cell-2 MER Delivery (Duration = COLO 2 Cell-2 PSR(12/22/20) to MSFT delivery) | 01/02/2021 | 25/03/2021 | 22/12/2020 | 17/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9748 | TT_Task | Delay in COLO-2- Cell-3 MER Delivery (Duration = COLO 2- Cell-3 PSR(12/28/20) to MSFT delivery) | 01/02/2021 | 27/03/2021 | 28/12/2020 | 22/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9749 | TT_Task | Delay in COLO-3- Cell-1 MER Delivery (Duration = COLO-3 Cell-1 PSR(1/29/21) to MSFT delivery) | 31/01/2021 | 03/04/2021 | 29/01/2021 | 02/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9750 | TT_Task | Delay in COLO-3- Cell-2 MER Delivery (Duration = COLO-3 Cell-2 PSR(2/5/21) to MSFT delivery) | 28/02/2021 | 30/04/2021 | 05/02/2021 | 08/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9751 | TT_Task | Delay in COLO-3 Cell-3 MER Delivery (Duration = COLO-3 Cell-3 PSR(2/12/21) to MSFT delivery) | 28/02/2021 | 29/04/2021 | 12/02/2021 | 14/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9752 | TT_Task | Delay in COLO-4- Cell-1 MER Delivery (Duration= COLO-4 Cell-1 PSR(3/12/21) to MSFT delivery) | 26/04/2021 | 09/06/2021 | 12/03/2021 | 26/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9753 | TT_Task | Delay in COLO-4- Cell-2 MER Delivery (Duration = COLO-4 Cell-2 PSR(3/19/21) to MSFT delivery) | 26/04/2021 | 09/06/2021 | 19/03/2021 | 03/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9754 | TT_Task | Delay in COLO-4- Cell-3 MER Delivery (Duration = COLO-4 Cell-3 PSR(3/26/21) to MSFT delivery) | 26/04/2021 | 29/05/2021 | 26/03/2021 | 29/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9755 | TT_Task | Remaining MER raceway across Mech chase | 01/02/2021 | 10/02/2021 | 15/01/2021 | 29/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9756 | TT_Task | Remaining MER raceway across Mech chase | 01/12/2020 | 10/12/2020 | 05/01/2021 | 16/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9757 | TT_Task | Remaining MER raceway across Mech chase | 05/02/2021 | 15/02/2021 | 15/01/2021 | 29/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9758 | TT_Task | Remaining Post MER raceway across Mech chase | 22/03/2021 | 05/04/2021 | 22/02/2021 | 09/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9759 | TT_Task | Remaining MER raceway across Mech chase | 25/03/2021 | 08/04/2021 | 10/03/2021 | 17/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9760 | TT_Task | Remaining MER raceway across Mech chase | 22/03/2021 | 05/04/2021 | 22/02/2021 | 09/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9761 | TT_Task | Remaining MER raceway across Mech chase | 22/03/2021 | 05/04/2021 | 12/03/2021 | 24/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9762 | TT_Task | Remaining MER raceway across Mech chase | 03/05/2021 | 03/05/2021 | 30/04/2021 | 15/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9763 | TT_Task | Remaining MER raceway across Mech chase | 17/06/2021 | 01/07/2021 | 17/05/2021 | 01/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9764 | TT_Task | Remaining MER raceway across Mech chase | 03/05/2021 | 17/05/2021 | 30/04/2021 | 15/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9765 | TT_Task | Remaining MER raceway across Mech chase | 17/06/2021 | 01/07/2021 | 17/05/2021 | 01/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9766 | TT_Task | Remaining MER raceway across Mech chase | 01/06/2021 | 16/06/2021 | 01/06/2021 | 18/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9767 | TT_Task | Remaining MER raceway across Mech chase | 01/06/2021 | 16/06/2021 | 01/06/2021 | 22/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9768 | TT_Task | Remaining MER raceway across Mech chase | 01/06/2021 | 16/06/2021 | 01/06/2021 | 16/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9769 | TT_Task | Remaining MER raceway across Mech chase | 30/06/2021 | 16/07/2021 | 21/06/2021 | 07/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9770 | TT_Task | Delay in COLO-1- Cell-4 MER Delivery (Duration = COLO1 Cell-4 PSR(11/30/20) to MSFT delivery) | 01/02/2021 | 09/03/2021 | 30/11/2020 | 07/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9771 | TT_Task | Delay in COLO-2- Cell-4 MER Delivery (Duration = COLO 2- Cell-4 PSR(1/5/21) to MSFT delivery) | 01/02/2021 | 02/04/2021 | 05/01/2021 | 08/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9772 | TT_Task | Delay in COLO-3 Cell-4 MER Delivery (Duration = COLO-3 Cell-4 PSR(2/19/21) to MSFT delivery) | 28/02/2021 | 30/04/2021 | 19/02/2021 | 22/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9773 | TT_Task | Delay in COLO-4- Cell-4 MER Delivery (Duration = COLO-4 Cell-4 PSR(4/2/21) to MSFT delivery) | 26/04/2021 | 01/06/2021 | 02/04/2021 | 09/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9775 | TT_Task | Below Ceiling Branch Conduit Rough-in | 31/03/2021 | 06/04/2021 | 15/03/2021 | 19/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9776 | TT_Task | Below Ceiling Branch Conduit Rough-in | 15/04/2021 | 21/04/2021 | 15/03/2021 | 20/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9777 | TT_Task | Below Ceiling Branch Conduit Rough-in | 07/04/2021 | 14/04/2021 | 15/03/2021 | 20/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9778 | TT_Task | Below Ceiling Branch Conduit Rough-in | 22/04/2021 | 28/04/2021 | 22/03/2021 | 26/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9779 | TT_Task | Below Ceiling Branch Conduit Rough-in | 01/06/2021 | 07/06/2021 | 01/06/2021 | 07/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9780 | TT_Task | Below Ceiling Branch Conduit Rough-in | 30/06/2021 | 08/07/2021 | 08/05/2021 | 14/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9782 | TT_Task | Below Ceiling Branch Conduit Rough-in | 31/07/2021 | 06/08/2021 | 01/07/2021 | 09/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9783 | TT_Task | Below Ceiling Branch Conduit Rough-in | 09/07/2021 | 15/07/2021 | 15/05/2021 | 21/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9784 | TT_Task | Below Ceiling Branch Conduit Rough-in | 16/07/2021 | 22/07/2021 | 24/05/2021 | 29/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9785 | TT_Task | Below Ceiling Branch Conduit Rough-in | 16/07/2021 | 22/07/2021 | 15/05/2021 | 21/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9786 | TT_Task | Below Ceiling Branch Conduit Rough-in | 23/07/2021 | 30/07/2021 | 24/05/2021 | 29/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9787 | TT_Task | Below Ceiling Branch Conduit Rough-in | 31/07/2021 | 06/08/2021 | 14/06/2021 | 18/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9788 | TT_Task | Wire Mesh Procurement | 16/11/2020 | 23/12/2020 | 24/09/2020 | 24/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9789 | TT_Task | Wire Mesh Submittal Approval | 16/11/2020 | 19/11/2020 | 16/09/2020 | 23/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9790 | TT_Task | Wire Mesh Procurement Delay | 16/11/2020 | 19/11/2020 | 24/10/2020 | 24/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9791 | TT_Task | Sprinkler Test | 21/12/2020 | 22/12/2020 | 30/11/2020 | 30/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-01-FND-S | TT_Mile | Foundation Start | 30/11/2020 | 30/11/2020 | 22/04/2020 | 22/04/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-01-FND-F | TT_FinMile | Foundation Complete | 30/11/2020 | 30/11/2020 | 05/06/2020 | 05/06/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-01-UGU-F | TT_FinMile | Completion of U/G Utilities (No Elec) | 30/11/2020 | 30/11/2020 | 22/08/2020 | 22/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-01-SUP-S | TT_Mile | Start Superstructure | 30/11/2020 | 30/11/2020 | 26/06/2020 | 26/06/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-01-SOG-F | TT_FinMile | Slab on Grade Complete | 30/11/2020 | 30/11/2020 | 22/09/2020 | 22/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-01-DRY-F | TT_FinMile | Weather Tight | 30/11/2020 | 30/11/2020 | 22/09/2020 | 22/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-01-UGE-F | TT_FinMile | Completion of Utility/MV UG Electrical | 01/03/2021 | 01/03/2021 | 20/02/2021 | 20/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-01-L1CX-S | TT_Mile | Start of L1 CX | 30/01/2021 | 30/01/2021 | 27/06/2020 | 27/06/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-01-L3CX-S | TT_Mile | L3 CX Start | 05/08/2021 | 05/08/2021 | 06/07/2021 | 06/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-01-UPW-F | TT_FinMile | Utility Power-ON UMS | 17/05/2021 | 17/05/2021 | 25/05/2021 | 25/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-01-GEN-F | TT_FinMile | Generators Ready for Fuel | 30/04/2021 | 30/04/2021 | 28/04/2021 | 28/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-01-MEQ-S | TT_Mile | Mechanical Equipment Start-up | 31/07/2021 | 31/07/2021 | 23/07/2021 | 23/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-01-MER-F | TT_FinMile | MEP Rough-in Complete | 30/11/2020 | 30/11/2020 | 31/10/2020 | 31/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-01-LHP-F | TT_FinMile | Landscaping, Hardscaping Complete | 12/11/2021 | 12/11/2021 |  |  | 80 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-01-L2CX-F | TT_FinMile | L2 CX Complete (Yellow Tag) | 31/08/2021 | 31/08/2021 | 12/08/2021 | 12/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-01-L1CX-F | TT_FinMile | Completion of all Red Tags (All ROJ) | 31/07/2021 | 31/07/2021 | 02/06/2021 | 02/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-01-INT-F | TT_FinMile | Interior Finishes/CSA Complete | 28/06/2021 | 28/06/2021 | 01/06/2021 | 01/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-01-SEC-F | TT_FinMile | Security System Complete | 13/11/2021 | 13/11/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-01-L3CX-F | TT_FinMile | L3 CX Complete (Green Tag) | 02/10/2021 | 02/10/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-01-BAS-F | TT_FinMile | BAS SAT Complete | 31/08/2021 | 31/08/2021 | 28/08/2021 | 28/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-01-EPM-F | TT_FinMile | EPMS SAT Complete | 01/09/2021 | 01/09/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-01-FLS-F | TT_FinMile | Fire Alarm Complete | 20/05/2021 | 20/05/2021 | 30/04/2021 | 30/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-01-IST-F | TT_FinMile | L4 L5 Complete (White Tag) (Clayco- NIC) | 29/10/2021 | 29/10/2021 |  |  | 250 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-02-FND-S | TT_Mile | Foundation Start | 30/11/2020 | 30/11/2020 | 04/05/2020 | 04/05/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-02-FND-F | TT_FinMile | Foundation Complete | 30/11/2020 | 30/11/2020 | 12/06/2020 | 12/06/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-02-UGU-F | TT_FinMile | Completion of U/G Utilities (No Elec) | 30/11/2020 | 30/11/2020 | 21/09/2020 | 21/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-02-SUP-S | TT_Mile | Start Superstructure | 30/11/2020 | 30/11/2020 | 07/07/2020 | 07/07/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-02-SOG-F | TT_FinMile | Slab on Grade Complete | 30/11/2020 | 30/11/2020 | 07/10/2020 | 07/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-02-DRY-F | TT_FinMile | Weather Tight | 30/11/2020 | 30/11/2020 | 07/10/2020 | 07/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-02-UGE-F | TT_FinMile | Completion of Utility/MV UG Electrical | 30/11/2020 | 30/11/2020 | 07/10/2020 | 07/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-02-L1CX-S | TT_Mile | Start of L1 CX | 03/02/2021 | 03/02/2021 | 23/09/2020 | 23/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-02-L3CX-S | TT_Mile | L3 CX Start | 07/10/2021 | 07/10/2021 |  |  | 450 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-02-UPW-F | TT_FinMile | Utility Power-ON | 19/05/2021 | 19/05/2021 | 19/05/2021 | 19/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-02-GEN-F | TT_FinMile | Generators Ready for Fuel | 30/04/2021 | 30/04/2021 | 29/04/2021 | 29/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-02-MEQ-S | TT_Mile | Mechanical Equipment Start-up | 07/10/2021 | 07/10/2021 |  |  | 450 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-02-MER-F | TT_FinMile | MEP Rough-in Complete | 02/01/2021 | 02/01/2021 | 09/12/2020 | 09/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-02-LHP-F | TT_FinMile | Landscaping, Hardscaping Complete | 10/01/2022 | 10/01/2022 |  |  | 109 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-02-L2CX-F | TT_FinMile | L2 CX Complete (Yellow Tag) | 25/10/2021 | 25/10/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-02-L1CX-F | TT_FinMile | Completion of all Red Tags (All ROJ) | 31/08/2021 | 31/08/2021 | 06/08/2021 | 06/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-02-INT-F | TT_FinMile | Interior Finishes/CSA Complete | 31/07/2021 | 31/07/2021 | 19/07/2021 | 19/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-02-SEC-F | TT_FinMile | Security System Complete | 15/01/2022 | 15/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-02-L3CX-F | TT_FinMile | L3 CX Complete (Green Tag) | 04/12/2021 | 04/12/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-02-BAS-F | TT_FinMile | BAS SAT Complete | 30/10/2021 | 30/10/2021 |  |  | 130 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-02-EPM-F | TT_FinMile | EPMS SAT Complete | 07/10/2021 | 07/10/2021 |  |  | 140 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-02-FLS-F | TT_FinMile | Fire Alarm Complete | 28/06/2021 | 28/06/2021 | 01/06/2021 | 01/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-02-IST-F | TT_FinMile | L4 L5 Complete (White Tag) (Clayco- NIC) | 27/12/2021 | 27/12/2021 |  |  | 300 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-03-FND-S | TT_Mile | Foundation Start | 30/11/2020 | 30/11/2020 | 16/06/2020 | 16/06/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-03-FND-F | TT_FinMile | Foundation Complete | 30/11/2020 | 30/11/2020 | 18/07/2020 | 18/07/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-03-UGU-F | TT_FinMile | Completion of U/G Utilities (No Elec) | 30/11/2020 | 30/11/2020 | 15/10/2020 | 15/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-03-SUP-S | TT_Mile | Start Superstructure | 30/11/2020 | 30/11/2020 | 23/07/2020 | 23/07/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-03-SOG-F | TT_FinMile | Slab on Grade Complete | 30/11/2020 | 30/11/2020 | 28/10/2020 | 28/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-03-DRY-F | TT_FinMile | Weather Tight | 30/11/2020 | 30/11/2020 | 28/10/2020 | 28/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-03-UGE-F | TT_FinMile | Completion of Utility/MV UG Electrical | 30/11/2020 | 30/11/2020 | 31/10/2020 | 31/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-03-L1CX-S | TT_Mile | Start of L1 CX | 28/06/2021 | 28/06/2021 | 01/06/2021 | 01/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-03-L3CX-S | TT_Mile | L3 CX Start | 18/10/2021 | 18/10/2021 |  |  | 700 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-03-UPW-F | TT_FinMile | Utility Power-ON | 01/06/2021 | 01/06/2021 | 19/05/2021 | 19/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-03-GEN-F | TT_FinMile | Generators Ready for Fuel | 01/07/2021 | 01/07/2021 | 01/07/2021 | 01/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-03-MEQ-S | TT_Mile | Mechanical Equipment Start-up | 01/11/2021 | 01/11/2021 |  |  | 580 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-03-MER-F | TT_FinMile | MEP Rough-in Complete | 28/06/2021 | 28/06/2021 | 01/06/2021 | 01/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-03-LHP-F | TT_FinMile | Landscaping, Hardscaping Complete | 22/02/2022 | 22/02/2022 |  |  | 100 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-03-L2CX-F | TT_Mile | L2 CX Complete (Yellow Tag) | 20/11/2021 | 20/11/2021 |  |  | 120 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-03-L1CX-F | TT_FinMile | Completion of all Red Tags (All ROJ) | 01/09/2021 | 01/09/2021 | 30/08/2021 | 30/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-03-INT-F | TT_FinMile | Interior Finishes/CSA Complete | 31/08/2021 | 31/08/2021 | 12/08/2021 | 12/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-03-SEC-F | TT_FinMile | Security System Complete | 23/02/2022 | 23/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-03-L3CX-F | TT_FinMile | L3 CX Complete (Green Tag) | 19/01/2022 | 19/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-03-BAS-F | TT_FinMile | BAS SAT Complete | 24/11/2021 | 24/11/2021 |  |  | 260 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-03-EPM-F | TT_FinMile | EPMS SAT Complete | 27/10/2021 | 27/10/2021 |  |  | 310 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-03-FLS-F | TT_FinMile | Fire Alarm Complete | 08/02/2022 | 08/02/2022 |  |  | 290 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-03-IST-F | TT_FinMile | L4 L5 Complete (White Tag) (Clayco- NIC) | 08/02/2022 | 08/02/2022 |  |  | 290 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-04-FND-S | TT_Mile | Foundation Start | 30/11/2020 | 30/11/2020 | 23/06/2020 | 23/06/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-04-FND-F | TT_FinMile | Foundation Complete | 30/11/2020 | 30/11/2020 | 30/07/2020 | 30/07/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-04-UGU-F | TT_FinMile | Completion of U/G Utilities (No Elec) | 30/11/2020 | 30/11/2020 | 15/10/2020 | 15/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-04-SUP-S | TT_Mile | Start Superstructure | 30/11/2020 | 30/11/2020 | 08/08/2020 | 08/08/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-04-SOG-F | TT_FinMile | Slab on Grade Complete | 30/11/2020 | 30/11/2020 | 04/11/2020 | 04/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-04-DRY-F | TT_FinMile | Weather Tight | 30/11/2020 | 30/11/2020 | 04/11/2020 | 04/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-04-UGE-F | TT_FinMile | Completion of Utility/MV UG Electrical | 30/11/2020 | 30/11/2020 | 07/11/2020 | 07/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-04-L1CX-S | TT_Mile | Start of L1 CX | 11/02/2021 | 11/02/2021 | 12/12/2020 | 12/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-04-L3CX-S | TT_Mile | L3 CX Start | 19/11/2021 | 19/11/2021 |  |  | 760 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-04-UPW-F | TT_FinMile | Utility Power-ON | 01/06/2021 | 01/06/2021 | 19/05/2021 | 19/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-04-GEN-F | TT_FinMile | Generators Ready for Fuel | 31/08/2021 | 31/08/2021 |  |  | 1100 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-04-MEQ-S | TT_Mile | Mechanical Equipment Start-up | 07/12/2021 | 07/12/2021 |  |  | 640 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-04-MER-F | TT_FinMile | MEP Rough-in Complete | 31/07/2021 | 31/07/2021 | 07/07/2021 | 07/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-04-LHP-F | TT_FinMile | Landscaping, Hardscaping Complete | 22/02/2022 | 22/02/2022 |  |  | 430 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-04-L2CX-F | TT_Mile | L2 CX Complete (Yellow Tag) | 03/01/2022 | 03/01/2022 |  |  | 160 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-04-L1CX-F | TT_FinMile | Completion of all Red Tags (All ROJ) | 01/10/2021 | 01/10/2021 |  |  | 1160 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-04-INT-F | TT_FinMile | Interior Finishes/CSA Complete | 07/10/2021 | 07/10/2021 |  |  | 1580 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-04-SEC-F | TT_FinMile | Security System Complete | 04/04/2022 | 04/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-04-L3CX-F | TT_FinMile | L3 CX Complete (Green Tag) | 28/02/2022 | 28/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-04-BAS-F | TT_FinMile | BAS SAT Complete | 04/01/2022 | 04/01/2022 |  |  | 320 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-04-EPM-F | TT_FinMile | EPMS SAT Complete | 10/12/2021 | 10/12/2021 |  |  | 300 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-04-FLS-F | TT_FinMile | Fire Alarm Complete | 31/08/2021 | 31/08/2021 |  |  | 1880 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-04-IST-F | TT_FinMile | L4 L5 Complete (White Tag) (Clayco- NIC) | 21/03/2022 | 21/03/2022 |  |  | 300 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-9888 | TT_Task | Complete Remaining Telecom Duct Back tie-in Install to MWH02 | 21/12/2020 | 12/01/2021 | 01/12/2020 | 20/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9889 | TT_Task | Clayco waiting on MSOW Approval | 16/11/2020 | 19/11/2020 | 19/10/2020 | 01/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9890 | TT_Task | Clayco MSOW Submited for approval | 16/11/2020 | 17/11/2020 | 16/10/2020 | 19/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9891 | TT_Task | Delay in UPM Delivery (Duration = Colo2 Cell-1 11/25 to MSFT delivery) | 28/09/2020 | 09/10/2020 | 25/11/2020 | 07/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9892 | TT_Task | Delay in UPM Delivery (Duration = Colo2 Cell-2 11/25 to MSFT delivery) | 02/11/2020 | 15/11/2020 | 25/11/2020 | 09/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9894 | TT_Task | Delay in UPM Delivery (Duration = Colo2 Cell-3 11/25 to MSFT delivery) | 02/11/2020 | 15/11/2020 | 25/11/2020 | 16/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9893 | TT_Task | Delay in UPM Delivery (Duration = Colo2 Cell-4 11/25 to MSFT delivery) | 02/11/2020 | 06/11/2020 | 25/11/2020 | 10/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9895 | TT_Task | Delay in UPM Delivery (Duration = Colo3 Cell-1 PSR 11/23 to MSFT delivery) | 28/09/2020 | 14/10/2020 | 23/11/2020 | 18/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9896 | TT_Task | Delay in UPM Delivery (Duration = Colo3 Cell-2 11/23 to MSFT delivery) | 02/11/2020 | 12/11/2020 | 23/11/2020 | 18/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9898 | TT_Task | Delay in UPM Delivery (Duration = Colo3 Cell-3 11/23 to MSFT delivery) | 02/11/2020 | 18/11/2020 | 23/11/2020 | 03/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9897 | TT_Task | Delay in UPM Delivery (Duration = Colo3 Cell-4 11/23 to MSFT delivery) | 02/11/2020 | 11/11/2020 | 23/11/2020 | 03/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9899 | TT_Task | Delay in UPM Delivery (Duration = Colo4 Cell-1 12/7 to MSFT delivery) | 09/01/2021 | 09/01/2021 | 07/12/2020 | 18/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9900 | TT_Task | Delay in UPM Delivery (Duration = Colo4 Cell-2 12/7 to MSFT delivery) | 05/01/2021 | 05/01/2021 | 07/12/2020 | 17/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9902 | TT_Task | Delay in UPM Delivery (Duration = Colo4 Cell-3 12/18 to MSFT delivery) | 14/01/2021 | 14/01/2021 | 18/12/2020 | 04/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9901 | TT_Task | Delay in UPM Delivery (Duration = Colo4 Cell-4 12/18 to MSFT delivery) | 09/01/2021 | 09/01/2021 | 18/12/2020 | 04/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-01-L2CX-S | TT_Mile | Start of L2 CX | 01/06/2021 | 01/06/2021 | 13/05/2021 | 13/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-02-L2CX-S | TT_Mile | Start of L2 CX | 31/08/2021 | 31/08/2021 | 21/07/2021 | 21/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-04-L2CX-S | TT_Mile | Start of L2 CX | 13/10/2021 | 13/10/2021 |  |  | 100 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-03-L2CX-S | TT_Mile | Start of L2 CX | 31/08/2021 | 31/08/2021 |  |  | 100 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-9903 | TT_Task | Delay in UMS delivery (Duration = (9/19) to MSFT delivery) | 28/09/2020 | 19/10/2020 | 19/11/2020 | 11/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9904 | TT_Mile | Linx Mobilization to Admin/COLO-1 | 01/02/2021 | 01/02/2021 | 25/01/2021 | 25/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9905 | TT_Task | Delay In COLO-2 Cell-1 Generator (Duration= COLO-2 Cell-1 PSR(10/12/20) to MSFT delivery) | 21/12/2020 | 07/03/2021 | 12/10/2020 | 28/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9908 | TT_Task | Delay In COLO-2 Cell-2 Generator (Duration= COLO-2 Cell-2 PSR(11/6/20) to MSFT delivery) | 21/12/2020 | 21/02/2021 | 06/11/2020 | 08/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9909 | TT_Task | Delay In COLO-2 Cell-4 Generator (Duration= COLO-2 Cell-4 PSR(11/21/20) to MSFT delivery) | 21/12/2020 | 19/02/2021 | 21/11/2020 | 21/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9910 | TT_Task | Delay In COLO-2 Cell-3 Generator (Duration= COLO-2 Cell-3 PSR(10/22/20) to MSFT delivery) | 21/12/2020 | 18/03/2021 | 22/10/2020 | 18/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9911 | TT_Task | MSFT Stand down/ Additional Hydro excavation | 21/12/2020 | 12/01/2021 | 08/12/2020 | 19/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9913 | TT_Task | Electrical OH Below Mechanical Piping | 20/01/2021 | 28/01/2021 | 07/01/2021 | 15/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9914 | TT_Task | #1. Rain And High Winds- 10/13/2020(half day only) | 02/01/2021 | 02/01/2021 | 13/10/2020 | 13/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9915 | TT_Task | #2. Snow -12/30/20 (one full day) | 02/01/2021 | 02/01/2021 | 30/12/2020 | 30/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9916 | TT_Task | Electrical OH Below Mechanical Piping | 04/01/2021 | 12/01/2021 | 11/12/2020 | 28/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9917 | TT_Task | Electrical OH Below Mechanical Piping | 20/01/2021 | 28/01/2021 | 07/01/2021 | 15/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9930 | TT_Task | Electrical OH Below Mechanical Piping | 02/01/2021 | 11/01/2021 | 11/12/2020 | 28/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9931 | TT_Task | COLO-1 Cell-1 WA State LI onsite inspection Approval to Connect to MER | 11/01/2021 | 15/01/2021 | 08/01/2021 | 19/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9932 | TT_Task | COLO-1 CELL-3 WA State LI onsite inspection Approval to Connect to MER | 01/02/2021 | 05/02/2021 | 20/01/2021 | 25/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9933 | TT_Task | COLO-1 CELL-2 WA State LI onsite inspection Approval to Connect to MER | 23/01/2021 | 28/01/2021 | 11/01/2021 | 20/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9934 | TT_Task | COLO-1 CELL-4 WA State LI onsite inspection Approval to Connect to MER | 01/02/2021 | 05/02/2021 | 25/01/2021 | 05/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9935 | TT_Task | COLO-2 Cell-1 WA State LI onsite inspection Approval to Connect to MER | 12/03/2021 | 17/03/2021 | 11/02/2021 | 23/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9937 | TT_Task | COLO-2 Cell-3 WA State LI onsite inspection Approval to Connect to MER | 31/03/2021 | 05/04/2021 | 17/03/2021 | 24/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9936 | TT_Task | COLO-2 Cell-2 WA State LI onsite inspection Approval to Connect to MER | 23/03/2021 | 27/03/2021 | 15/03/2021 | 22/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9938 | TT_Task | COLO-2 Cell-4 WA State LI onsite inspection Approval to Connect to MER | 09/04/2021 | 15/04/2021 | 23/03/2021 | 01/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9939 | TT_Task | COLO-3 Cell-1 WA State LI onsite inspection Approval to Connect to MER | 08/05/2021 | 13/05/2021 | 13/04/2021 | 19/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9941 | TT_Task | COLO-3 Cell-3 WA State LI onsite inspection Approval to Connect to MER | 17/05/2021 | 21/05/2021 | 05/05/2021 | 07/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9940 | TT_Task | COLO-3 Cell-2 WA State LI onsite inspection Approval to Connect to MER | 14/05/2021 | 19/05/2021 | 21/04/2021 | 27/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9942 | TT_Task | COLO-3 Cell-4 WA State LI onsite inspection Approval to Connect to MER | 01/06/2021 | 05/06/2021 | 08/05/2021 | 27/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9943 | TT_Task | COLO-4 Cell-1 WA State LI onsite inspection Approval to Connect to MER | 01/06/2021 | 05/06/2021 | 14/05/2021 | 04/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9945 | TT_Task | COLO-4 Cell-3 WA State LI onsite inspection Approval to Connect to MER | 01/06/2021 | 05/06/2021 | 19/05/2021 | 23/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9944 | TT_Task | COLO-4 Cell-2 WA State LI onsite inspection Approval to Connect to MER | 19/06/2021 | 24/06/2021 | 08/05/2021 | 15/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9946 | TT_Task | COLO-4 Cell-4 WA State LI onsite inspection Approval to Connect to MER | 01/06/2021 | 05/06/2021 | 29/05/2021 | 30/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9947 | TT_Task | Delay In COLO-3 Cell-1 Generator (Duration= COLO-3 Cell-1 PSR(10/12/20) to MSFT delivery) | 31/12/2020 | 08/05/2021 | 09/11/2020 | 18/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9948 | TT_Task | Delay In COLO-3 Cell-2 Generator (Duration= COLO-3 Cell-2 PSR(11/6/20) to MSFT delivery) | 31/12/2020 | 30/03/2021 | 21/11/2020 | 19/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9949 | TT_Task | Delay In COLO-3 Cell-4 Generator (Duration= COLO-3 Cell-4 PSR(11/21/20) to MSFT delivery) | 31/12/2020 | 18/03/2021 | 09/12/2020 | 25/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9950 | TT_Task | Delay In COLO-3 Cell-3 Generator (Duration= COLO-3 Cell-3 PSR(10/22/20) to MSFT delivery) | 31/12/2020 | 29/04/2021 | 05/11/2020 | 04/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9951 | TT_Task | Delay In COLO-4 Cell-1 Generator (Duration= COLO-4 Cell-1 PSR(10/12/20) to MSFT delivery) | 31/12/2020 | 05/06/2021 | 09/11/2020 | 15/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9952 | TT_Task | Delay In COLO-4 Cell-2 Generator (Duration= COLO-4 Cell-2 PSR(11/6/20) to MSFT delivery) | 31/12/2020 | 01/04/2021 | 09/12/2020 | 11/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9953 | TT_Task | Delay In COLO-4 Cell-4 Generator (Duration= COLO-4 Cell-4 PSR(11/21/20) to MSFT delivery) | 21/12/2020 | 14/04/2021 | 30/11/2020 | 25/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9954 | TT_Task | Delay In COLO-4 Cell-3 Generator (Duration= COLO-4 Cell-3 PSR(10/22/20) to MSFT delivery) | 31/12/2020 | 11/05/2021 | 20/11/2020 | 01/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9955 | TT_Task | Delay In COLO-1 Cell-1 Generator (Duration= COLO-1 Cell-1 PSR(9/15/20) to MSFT delivery) | 21/12/2020 | 19/01/2021 | 15/09/2020 | 15/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9956 | TT_Task | Delay In COLO-1 Cell-2 Generator (Duration= COLO-1 Cell-2 PSR(9/15/20) to MSFT delivery) | 21/12/2020 | 06/02/2021 | 15/09/2020 | 02/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9957 | TT_Task | Delay In COLO-1 Cell-4 Generator (Duration= COLO-1 Cell-4 PSR(9/29/20) to MSFT delivery) | 21/12/2020 | 12/01/2021 | 29/09/2020 | 22/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-9958 | TT_Task | Delay In COLO-1 Cell-3 Generator (Duration= COLO-1 Cell-3 PSR(9/29/20) to MSFT delivery) | 21/12/2020 | 03/02/2021 | 29/09/2020 | 13/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.Cx2005 | TT_Task | Control Power Available | 30/06/2021 | 13/07/2021 | 22/06/2021 | 02/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1851 | TT_Task | UMS Control Power Available CYT | 10/02/2021 | 17/02/2021 | 01/02/2021 | 18/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.S.1841 | TT_Task | URS Control Power Available CYT | 10/02/2021 | 16/02/2021 | 01/02/2021 | 18/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10030 | TT_Task | Power available for Start up | 06/07/2021 | 09/07/2021 | 06/07/2021 | 09/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10031 | TT_Task | GEN SCR testing and Burnins | 14/07/2021 | 31/07/2021 | 14/07/2021 | 13/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10032 | TT_Task | Admin GEN SCR testing and Burnins | 10/07/2021 | 15/07/2021 | 10/07/2021 | 15/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10033 | TT_Task | Control Power Available | 30/04/2021 | 12/05/2021 | 30/04/2021 | 28/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10034 | TT_Task | Power available for Start up | 30/06/2021 | 06/07/2021 | 30/06/2021 | 06/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10035 | TT_Task | OFCI Lvl 3 Testing Start up (Electrical Equipment) | 10/07/2021 | 29/07/2021 | 10/07/2021 | 29/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10036 | TT_Task | OFCI Lvl 3 Testing Start up (Mechanical Equipment) | 10/07/2021 | 23/07/2021 | 10/07/2021 | 26/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10037 | TT_FinMile | Utility Power-ON URS | 17/05/2021 | 17/05/2021 | 25/05/2021 | 25/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10038 | TT_Task | Control Power Available | 30/06/2021 | 13/07/2021 | 22/06/2021 | 02/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10039 | TT_Task | Power available for Start up | 31/07/2021 | 04/08/2021 | 06/07/2021 | 09/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10040 | TT_Task | Control Power Available | 30/06/2021 | 13/07/2021 | 22/06/2021 | 02/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10041 | TT_Task | Power available for Start up | 06/07/2021 | 09/07/2021 | 06/07/2021 | 09/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10042 | TT_Task | Control Power Available | 22/06/2021 | 02/07/2021 | 22/06/2021 | 02/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10043 | TT_Task | Power available for Start up | 06/07/2021 | 09/07/2021 | 06/07/2021 | 09/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10044 | TT_Task | Control Power Available | 31/08/2021 | 13/09/2021 | 18/08/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
MWH06-10045 | TT_Task | Power available for Start up | 11/09/2021 | 15/09/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10046 | TT_Task | Control Power Available | 31/08/2021 | 13/09/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10047 | TT_Task | Power available for Start up | 14/09/2021 | 17/09/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10048 | TT_Task | Control Power Available | 31/08/2021 | 13/09/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10049 | TT_Task | Power available for Start up | 14/09/2021 | 17/09/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10050 | TT_Task | Control Power Available | 31/08/2021 | 13/09/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10051 | TT_Task | Power available for Start up | 14/09/2021 | 17/09/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10052 | TT_Task | Control Power Available | 09/09/2021 | 20/09/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10053 | TT_Task | Power available for Start up | 21/09/2021 | 24/09/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10054 | TT_Task | Control Power Available | 21/09/2021 | 02/10/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10055 | TT_Task | Power available for Start up | 04/10/2021 | 07/10/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10056 | TT_Task | Control Power Available | 09/09/2021 | 20/09/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10057 | TT_Task | Power available for Start up | 21/09/2021 | 24/09/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10058 | TT_Task | Control Power Available | 21/09/2021 | 02/10/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10059 | TT_Task | Power available for Start up | 04/10/2021 | 07/10/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10060 | TT_Task | Control Power Available | 21/10/2021 | 01/11/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10061 | TT_Task | Control Power Available | 02/11/2021 | 13/11/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10062 | TT_Task | Power available for Start up | 15/11/2021 | 18/11/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10063 | TT_Task | Power available for Start up | 02/11/2021 | 05/11/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10064 | TT_Task | Control Power Available | 21/10/2021 | 01/11/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10065 | TT_Task | Power available for Start up | 02/11/2021 | 05/11/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10066 | TT_Task | Control Power Available | 02/11/2021 | 13/11/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10067 | TT_Task | Power available for Start up | 15/11/2021 | 18/11/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10068 | TT_Task | GEN SCR testing and Burnins | 18/09/2021 | 06/10/2021 |  |  | 150 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10069 | TT_Task | GEN SCR testing and Burnins | 08/10/2021 | 26/10/2021 |  |  | 320 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10070 | TT_Task | GEN SCR testing and Burnins | 19/11/2021 | 09/12/2021 |  |  | 310 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10071 | TT_Task | Concrete interior - Create Punch list | 02/01/2021 | 04/01/2021 | 04/01/2021 | 11/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10072 | TT_Task | Concrete interior - Complete Punch List | 01/02/2021 | 08/02/2021 | 12/01/2021 | 20/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10073 | TT_Task | Garco Steel (Mezz steel, Yard) - Create Punch list | 31/07/2021 | 02/08/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10074 | TT_Task | Garco Steel (Mezz steel, Yard) - Complete Punch List | 03/08/2021 | 09/08/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10075 | TT_Task | Sure Steel (Building, Mezz, Ceiling) - Create Punch list | 02/01/2021 | 04/01/2021 | 21/12/2020 | 23/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10076 | TT_Task | Sure Steel (Building, Mezz, Ceiling) - Complete Punch List | 01/02/2021 | 08/02/2021 | 18/01/2021 | 29/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10077 | TT_Task | Advantage - Create Punch list | 31/07/2021 | 02/08/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10078 | TT_Task | Advantage - Complete Punch List | 03/08/2021 | 09/08/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10079 | TT_Task | PCI - Create Punch list | 31/07/2021 | 02/08/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10080 | TT_Task | PCI - Complete Punch List | 03/08/2021 | 09/08/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10081 | TT_Task | VECA - Create Punch list | 07/09/2021 | 08/09/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10082 | TT_Task | VECA - Complete Punch List | 09/09/2021 | 15/09/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10083 | TT_Task | LINX - Create Punch list | 31/07/2021 | 02/08/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10084 | TT_Task | LINX - Complete Punch List | 03/08/2021 | 09/08/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10085 | TT_Task | Convergent - Create Punch list | 31/07/2021 | 02/08/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10086 | TT_Task | Convergent - Complete Punch List | 03/08/2021 | 09/08/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10087 | TT_Task | TCM- Create Punch list | 31/07/2021 | 02/08/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10088 | TT_Task | TCM - Complete Punch List | 03/08/2021 | 09/08/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10089 | TT_Task | Cascade- Create Punch list | 26/04/2021 | 27/04/2021 | 11/01/2021 | 12/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10090 | TT_Task | Cascade - Complete Punch List | 28/04/2021 | 05/05/2021 | 18/01/2021 | 30/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10091 | TT_Task | Submit GC Punch List to A/E | 21/09/2021 | 21/09/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10092 | TT_Task | A/E Owner-Rep Punchlist Walk | 22/09/2021 | 29/09/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10093 | TT_Task | Complete A/E Punchlist | 30/09/2021 | 13/10/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10094 | TT_Task | PCI - Create Punch list | 31/07/2021 | 02/08/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10095 | TT_Task | PCI - Complete Punch List | 03/08/2021 | 09/08/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10096 | TT_Task | VECA - Create Punch list | 29/10/2021 | 30/10/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10097 | TT_Task | VECA - Complete Punch List | 01/11/2021 | 08/11/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10098 | TT_Task | LINX - Create Punch list | 16/08/2021 | 17/08/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10099 | TT_Task | LINX - Complete Punch List | 18/08/2021 | 24/08/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10100 | TT_Task | Convergent - Create Punch list | 31/07/2021 | 02/08/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10101 | TT_Task | Convergent - Complete Punch List | 03/08/2021 | 09/08/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10102 | TT_Task | TCM- Create Punch list | 22/09/2021 | 23/09/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10103 | TT_Task | TCM - Complete Punch List | 24/09/2021 | 01/10/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10104 | TT_Task | Cascade- Create Punch list | 31/07/2021 | 02/08/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10105 | TT_Task | Cascade - Complete Punch List | 03/08/2021 | 09/08/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10106 | TT_Task | Submit GC Punch List to A/E | 09/11/2021 | 09/11/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10107 | TT_Task | A/E Owner-Rep Punchlist Walk | 10/11/2021 | 16/11/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10108 | TT_Task | Complete A/E Punchlist | 17/11/2021 | 03/12/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10109 | TT_Task | PCI - Create Punch list | 31/07/2021 | 02/08/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10110 | TT_Task | PCI - Complete Punch List | 03/08/2021 | 09/08/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10111 | TT_Task | VECA - Create Punch list | 14/12/2021 | 15/12/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10112 | TT_Task | VECA - Complete Punch List | 16/12/2021 | 23/12/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10113 | TT_Task | LINX - Create Punch list | 13/10/2021 | 14/10/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10114 | TT_Task | LINX - Complete Punch List | 15/10/2021 | 22/10/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10115 | TT_Task | Convergent - Create Punch list | 31/07/2021 | 02/08/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10116 | TT_Task | Convergent - Complete Punch List | 03/08/2021 | 09/08/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10117 | TT_Task | TCM- Create Punch list | 22/09/2021 | 23/09/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10118 | TT_Task | TCM - Complete Punch List | 24/09/2021 | 01/10/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10119 | TT_Task | Cascade- Create Punch list | 31/07/2021 | 02/08/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10120 | TT_Task | Cascade - Complete Punch List | 03/08/2021 | 09/08/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10121 | TT_Task | Submit GC Punch List to A/E | 27/12/2021 | 27/12/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10122 | TT_Task | A/E Owner-Rep Punchlist Walk | 28/12/2021 | 05/01/2022 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10123 | TT_Task | Complete A/E Punchlist | 06/01/2022 | 20/01/2022 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10124 | TT_Task | PCI - Create Punch list | 31/07/2021 | 31/07/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10125 | TT_Task | PCI - Complete Punch List | 31/07/2021 | 06/08/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10126 | TT_Task | VECA - Create Punch list | 28/01/2022 | 31/01/2022 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10127 | TT_Task | VECA - Complete Punch List | 01/02/2022 | 07/02/2022 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10128 | TT_Task | LINX - Create Punch list | 19/11/2021 | 20/11/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10129 | TT_Task | LINX - Complete Punch List | 22/11/2021 | 01/12/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10130 | TT_Task | Convergent - Create Punch list | 31/07/2021 | 02/08/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10131 | TT_Task | Convergent - Complete Punch List | 03/08/2021 | 09/08/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10132 | TT_Task | TCM- Create Punch list | 04/11/2021 | 05/11/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10133 | TT_Task | TCM - Complete Punch List | 08/11/2021 | 13/11/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10134 | TT_Task | Cascade- Create Punch list | 31/07/2021 | 02/08/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10135 | TT_Task | Cascade - Complete Punch List | 03/08/2021 | 09/08/2021 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10136 | TT_Task | Submit GC Punch List to A/E | 08/02/2022 | 08/02/2022 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10137 | TT_Task | A/E Owner-Rep Punchlist Walk | 09/02/2022 | 15/02/2022 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10138 | TT_Task | Complete A/E Punchlist | 16/02/2022 | 01/03/2022 | 30/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10139 | TT_Task | UPM Yellow tagging - Admin COLO-1 CELL-1 | 31/03/2021 | 12/04/2021 | 31/03/2021 | 15/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10140 | TT_Task | Yellow Tagging for COLO-2 UPM's | 29/01/2021 | 10/02/2021 | 30/01/2021 | 30/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10141 | TT_Task | Yellow Tagging for COLO-3 UPM's | 30/01/2021 | 30/01/2021 | 30/01/2021 | 30/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10142 | TT_Task | Yellow Tagging for COLO-4 UPM's | 30/01/2021 | 30/01/2021 | 30/01/2021 | 30/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10143 | TT_Task | Mechanical Equipment Yellow Tag | 01/06/2021 | 11/06/2021 | 29/05/2021 | 10/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10145 | TT_Task | COLO1 CELL1 MER Security/Telecom Missing Raceway installation | 31/03/2021 | 09/04/2021 | 01/03/2021 | 10/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10146 | TT_Task | #3. Snow- 1/27/2021(one full day) | 01/02/2021 | 01/02/2021 | 27/01/2021 | 27/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10148 | TT_Task | Security Devices Trim | 17/05/2021 | 08/06/2021 | 30/04/2021 | 21/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10149 | TT_Task | COLO-1 Cell-1 Rearrange Roxtec blocks per coordination layout | 01/02/2021 | 04/02/2021 | 25/01/2021 | 29/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10150 | TT_Task | COLO1 CELL1 Interior MER conduit installation utility side | 05/03/2021 | 10/03/2021 | 05/02/2021 | 01/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10151 | TT_Task | COLO-1 Cell-1 Interior MER conduit installation building side Complete March1st (MER discovery Corrections Signoff) | 01/03/2021 | 13/03/2021 | 01/02/2021 | 27/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10152 | TT_Task | Safety Stop work due to failed Starline Hangers | 01/02/2021 | 01/02/2021 | 26/01/2021 | 28/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10153 | TT_Mile | SE directs VECA to start Flex Conduit fixes | 01/03/2021 | 01/03/2021 | 01/02/2021 | 01/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10154 | TT_Mile | SE directs VECA to start Roxtec fixes | 01/02/2021 | 01/02/2021 | 22/01/2021 | 22/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10155 | TT_Task | COLO-1 Cell-1 MER Flex Conduit fixes | 02/03/2021 | 08/03/2021 | 16/02/2021 | 27/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10156 | TT_Task | Lead time for replacement hangers from Starline | 01/02/2021 | 07/02/2021 | 29/01/2021 | 04/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10157 | TT_Task | COLO-1 Cell-1 Remove/ Replace busway hangers | 01/03/2021 | 04/03/2021 | 04/02/2021 | 10/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10158 | TT_Task | COLO-1 Cell-3 Remove/ Replace busway hangers | 05/03/2021 | 09/03/2021 | 10/02/2021 | 15/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10159 | TT_Task | COLO-1 Cell-2 Remove/ Replace busway hangers | 01/03/2021 | 04/03/2021 | 04/02/2021 | 10/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10160 | TT_Task | COLO-1 Cell-4 Remove/ Replace busway hangers | 05/03/2021 | 09/03/2021 | 10/02/2021 | 15/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10161 | TT_Task | Generator Term | 05/03/2021 | 09/03/2021 | 23/02/2021 | 28/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10162 | TT_Task | Lead time for missing Admin Gen Bussing | 01/02/2021 | 04/02/2021 | 11/01/2021 | 01/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10163 | TT_Task | Admin Gen Bussing Install | 01/03/2021 | 04/03/2021 | 18/02/2021 | 22/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10164 | TT_Task | COLO-1 Cell-3 MER Flex Conduit fixes | 01/03/2021 | 06/03/2021 | 16/02/2021 | 01/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10165 | TT_Task | COLO-1 Cell-2 MER Flex Conduit fixes | 02/03/2021 | 08/03/2021 | 16/02/2021 | 27/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10166 | TT_Task | COLO-1 Cell-4 MER Flex Conduit fixes | 01/03/2021 | 06/03/2021 | 16/02/2021 | 01/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10167 | TT_Task | COLO1 CELL3 MER Security/Telecom Missing Raceway installation | 31/03/2021 | 09/04/2021 | 03/03/2021 | 12/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10168 | TT_Task | COLO1 CELL2 MER Security/Telecom Missing Raceway installation | 31/03/2021 | 09/04/2021 | 01/03/2021 | 10/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10169 | TT_Task | COLO1 CELL4 MER Security/Telecom Missing Raceway installation | 31/03/2021 | 09/04/2021 | 03/03/2021 | 12/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10170 | TT_Task | COLO-1 CELL3 Rearrange Roxtec blocks per coordination layout | 01/02/2021 | 04/02/2021 | 25/01/2021 | 29/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10171 | TT_Task | COLO1 CELL3 Interior MER conduit installation utility side | 31/03/2021 | 31/03/2021 | 01/03/2021 | 08/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10172 | TT_Task | COLO-1 CELL3 Interior MER conduit installation building side | 02/03/2021 | 15/03/2021 | 01/02/2021 | 02/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10173 | TT_Mile | SE directs VECA to start Roxtec fixes | 01/02/2021 | 01/02/2021 | 22/01/2021 | 22/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10174 | TT_Task | COLO-1 CELL2 Rearrange Roxtec blocks per coordination layout | 01/02/2021 | 04/02/2021 | 25/01/2021 | 29/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10175 | TT_Task | COLO1 CELL2 Interior MER conduit installation utility side | 06/03/2021 | 11/03/2021 | 08/02/2021 | 01/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10176 | TT_Task | COLO-1 CELL2 Interior MER conduit installation building side | 01/03/2021 | 13/03/2021 | 01/02/2021 | 27/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10177 | TT_Mile | SE directs VECA to start Roxtec fixes | 01/02/2021 | 01/02/2021 | 22/01/2021 | 22/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10178 | TT_Task | COLO-1 CELL4 Rearrange Roxtec blocks per coordination layout | 01/02/2021 | 04/02/2021 | 25/01/2021 | 29/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10179 | TT_Task | COLO1 CELL4 Interior MER conduit installation utility side | 31/03/2021 | 05/04/2021 | 01/03/2021 | 05/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10180 | TT_Task | COLO-1 CELL4 Interior MER conduit installation building side | 01/03/2021 | 13/03/2021 | 01/02/2021 | 02/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10181 | TT_Mile | SE directs VECA to start Roxtec fixes | 01/02/2021 | 01/02/2021 | 22/01/2021 | 22/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10183 | TT_Task | SE- Completed L2 QC Checklist | 01/06/2021 | 11/06/2021 | 30/04/2021 | 09/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10184 | TT_Mile | Start of Vendor Lvl-2 | 01/03/2021 | 01/03/2021 | 22/02/2021 | 22/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10185 | TT_Task | Security Devices Trim | 07/06/2021 | 28/06/2021 | 24/05/2021 | 15/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10186 | TT_Task | Security Devices Trim | 17/05/2021 | 08/06/2021 | 30/04/2021 | 21/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10187 | TT_Task | Security Devices Trim | 30/06/2021 | 22/07/2021 | 01/06/2021 | 22/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10188 | TT_Task | SE- Completed L2 QC Checklist | 14/06/2021 | 24/06/2021 | 30/04/2021 | 23/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10189 | TT_Task | Mechanical Equipment Yellow Tag | 13/07/2021 | 23/07/2021 | 11/06/2021 | 30/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10190 | TT_Task | UPM Yellow tagging - COLO-1 CELL-3 | 31/03/2021 | 12/04/2021 | 31/03/2021 | 15/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10191 | TT_Task | SE- Completed L2 QC Checklist | 01/06/2021 | 11/06/2021 | 30/04/2021 | 17/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10192 | TT_Task | Mechanical Equipment Yellow Tag | 30/06/2021 | 13/07/2021 | 01/06/2021 | 11/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10193 | TT_Task | UPM Yellow tagging - COLO-1 CELL-2 | 31/03/2021 | 12/04/2021 | 31/03/2021 | 15/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10194 | TT_Task | SE- Completed L2 QC Checklist | 14/06/2021 | 24/06/2021 | 30/04/2021 | 23/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10195 | TT_Task | Mechanical Equipment Yellow Tag | 02/07/2021 | 15/07/2021 | 14/06/2021 | 30/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10196 | TT_Task | UPM Yellow tagging - COLO-1 CELL-4 | 31/03/2021 | 12/04/2021 | 31/03/2021 | 15/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10197 | TT_Task | SE- Completed L2 QC Checklist | 30/06/2021 | 13/07/2021 | 09/06/2021 | 02/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10198 | TT_Task | Mechanical Equipment Yellow Tag | 31/07/2021 | 11/08/2021 | 01/07/2021 |  | 20 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
MWH06-10199 | TT_Task | UPM Yellow tagging -COLO-2 CELL-1 | 31/07/2021 | 04/08/2021 | 30/07/2021 | 11/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10200 | TT_Task | SE- Completed L2 QC Checklist | 14/07/2021 | 26/07/2021 | 15/06/2021 | 02/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10201 | TT_Task | Mechanical Equipment Yellow Tag | 31/07/2021 | 11/08/2021 | 01/07/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
MWH06-10202 | TT_Task | UPM Yellow tagging -COLO-2 CELL-3 | 12/05/2021 | 12/05/2021 | 30/07/2021 | 11/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10203 | TT_Task | SE- Completed L2 QC Checklist | 30/06/2021 | 13/07/2021 | 30/07/2021 | 02/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10204 | TT_Task | Mechanical Equipment Yellow Tag | 31/07/2021 | 11/08/2021 | 01/07/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
MWH06-10205 | TT_Task | UPM Yellow tagging - COLO-2 CELL-2 | 12/05/2021 | 12/05/2021 | 12/05/2021 | 11/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10206 | TT_Task | SE- Completed L2 QC Checklist | 14/07/2021 | 26/07/2021 | 28/06/2021 | 02/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10207 | TT_Task | Mechanical Equipment Yellow Tag | 31/07/2021 | 11/08/2021 | 01/07/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
MWH06-10208 | TT_Task | UPM Yellow tagging -COLO-2 CELL-4 | 30/06/2021 | 13/07/2021 | 30/07/2021 | 11/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10209 | TT_Task | SE- Completed L2 QC Checklist | 31/08/2021 | 13/09/2021 | 06/08/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
MWH06-10210 | TT_Task | Mechanical Equipment Yellow Tag | 22/09/2021 | 04/10/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10211 | TT_Task | UPM Yellow tagging -COLO-3 CELL-1 | 31/08/2021 | 13/09/2021 |  |  | 60 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10212 | TT_Task | SE- Completed L2 QC Checklist | 07/09/2021 | 17/09/2021 |  |  | 60 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10213 | TT_Task | Mechanical Equipment Yellow Tag | 05/10/2021 | 15/10/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10214 | TT_Task | UPM Yellow tagging -COLO-3 CELL-3 | 31/08/2021 | 13/09/2021 |  |  | 160 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10215 | TT_Task | SE- Completed L2 QC Checklist | 31/08/2021 | 13/09/2021 | 10/08/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
MWH06-10216 | TT_Task | Mechanical Equipment Yellow Tag | 14/09/2021 | 24/09/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10217 | TT_Task | UPM Yellow tagging -COLO-3 CELL-2 | 31/08/2021 | 13/09/2021 |  |  | 60 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10218 | TT_Task | SE- Completed L2 QC Checklist | 31/08/2021 | 13/09/2021 |  |  | 100 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10219 | TT_Task | Mechanical Equipment Yellow Tag | 27/09/2021 | 07/10/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10220 | TT_Task | UPM Yellow tagging COLO-3 CELL-4 | 31/08/2021 | 13/09/2021 |  |  | 160 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10221 | TT_Task | SE- Completed L2 QC Checklist | 13/10/2021 | 25/10/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10222 | TT_Task | Mechanical Equipment Yellow Tag | 18/10/2021 | 28/10/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10223 | TT_Task | UPM Yellow tagging -COLO-4 CELL-1 | 31/08/2021 | 13/09/2021 | 31/07/2021 | 11/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10224 | TT_Task | SE- Completed L2 QC Checklist | 23/10/2021 | 03/11/2021 |  |  | 20 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10225 | TT_Task | Mechanical Equipment Yellow Tag | 29/10/2021 | 10/11/2021 |  |  | 70 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10226 | TT_Task | UPM Yellow tagging -COLO-4 CELL-3 | 31/08/2021 | 13/09/2021 | 04/08/2021 | 16/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10227 | TT_Task | SE- Completed L2 QC Checklist | 13/10/2021 | 25/10/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10228 | TT_Task | Mechanical Equipment Yellow Tag | 08/10/2021 | 20/10/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10229 | TT_Task | UPM Yellow tagging -COLO-4 CELL-2 | 31/08/2021 | 13/09/2021 | 13/08/2021 | 26/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10230 | TT_Task | SE- Completed L2 QC Checklist | 13/10/2021 | 25/10/2021 |  |  | 100 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10231 | TT_Task | Mechanical Equipment Yellow Tag | 21/10/2021 | 01/11/2021 |  |  | 140 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10232 | TT_Task | UPM Yellow tagging -COLO-4 CELL-4 | 31/08/2021 | 13/09/2021 | 24/08/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
MWH06-10233 | TT_Task | Install MER Supply duct | 01/03/2021 | 05/03/2021 | 01/02/2021 | 05/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10234 | TT_Task | Install MER Supply duct | 01/03/2021 | 05/03/2021 | 25/01/2021 | 29/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10235 | TT_Task | Install MER Supply duct | 01/03/2021 | 05/03/2021 | 18/01/2021 | 23/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10236 | TT_Task | Install MER Supply duct | 01/03/2021 | 05/03/2021 | 04/02/2021 | 06/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10237 | TT_Task | Install MER Supply duct | 31/03/2021 | 05/04/2021 | 24/02/2021 | 03/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10238 | TT_Task | Install MER Supply duct | 31/03/2021 | 05/04/2021 | 09/03/2021 | 09/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10239 | TT_Task | Install MER Supply duct | 31/03/2021 | 05/04/2021 | 22/03/2021 | 27/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10240 | TT_Task | Install MER Supply duct | 30/04/2021 | 06/05/2021 | 10/03/2021 | 15/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10241 | TT_Task | Install MER Supply duct | 30/04/2021 | 06/05/2021 | 20/04/2021 | 24/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10242 | TT_Task | Install MER Supply duct | 24/05/2021 | 28/05/2021 | 22/04/2021 | 26/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10243 | TT_Task | Install MER Supply duct | 17/05/2021 | 21/05/2021 | 28/04/2021 | 04/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10244 | TT_Task | Install MER Supply duct | 01/06/2021 | 05/06/2021 | 21/05/2021 | 27/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10245 | TT_Task | Install MER Supply duct | 30/06/2021 | 07/07/2021 | 05/06/2021 | 10/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10246 | TT_Task | Install MER Supply duct | 31/07/2021 | 05/08/2021 | 06/07/2021 | 10/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10247 | TT_Task | Install MER Supply duct | 31/07/2021 | 05/08/2021 | 30/06/2021 | 07/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10248 | TT_Task | Install MER Supply duct | 31/07/2021 | 05/08/2021 | 06/07/2021 | 10/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
A1180 | TT_Task | ATS Equipment Yellow Tagging (S2 from MER) | 17/05/2021 | 21/05/2021 | 12/05/2021 | 24/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10249 | TT_Task | COLO-1 Cell-1 SE Install UPS batteries in cabinet | 01/03/2021 | 04/03/2021 | 16/02/2021 | 20/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
A1190 | TT_Task | COLO-1 Cell-4 SE Install UPS batteries in cabinet | 31/03/2021 | 06/04/2021 | 09/03/2021 | 13/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
A1200 | TT_Task | COLO-1 Cell-3 SE Install UPS batteries in cabinet | 31/03/2021 | 06/04/2021 | 08/03/2021 | 11/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
A1210 | TT_Task | COLO-1 Cell-2 SE Install UPS batteries in cabinet | 31/03/2021 | 06/04/2021 | 01/03/2021 | 04/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10250 | TT_Task | Battery Station Yellow tagging / EPMS Checkouts | 01/03/2021 | 12/03/2021 | 01/03/2021 | 10/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10251 | TT_Task | 6.1.36 Rework for Addtional circuits for UMS URS Battery charger feed upsize | 01/02/2021 | 04/02/2021 | 12/02/2021 | 01/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10252 | TT_Task | 6.1.34.1 COLO-1 Cell-1 Rework on ATS Input conductors | 01/03/2021 | 03/03/2021 | 24/02/2021 | 01/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10253 | TT_Task | COLO-2 CEll-2 Awaiting SE Revised tool Come along for MER Lift Set | 01/03/2021 | 04/03/2021 | 18/02/2021 | 28/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10254 | TT_Task | All Construction activities -Safety Standown due to Admin Gen unplanned Energization | 01/03/2021 | 02/03/2021 | 01/02/2021 | 02/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10255 | TT_Task | COLO-2 Cell-1 Install Tube steel Cable tray transition per RFI#432 | 22/03/2021 | 25/03/2021 | 02/03/2021 | 04/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10256 | TT_Task | Awaiting DCE approval of Non NEMA standard Lugs | 01/03/2021 | 04/03/2021 | 02/02/2021 | 17/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10257 | TT_Task | Determined Startline hanger Design Issue Approve replacement hangers | 01/03/2021 | 04/03/2021 | 19/01/2021 | 28/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10258 | TT_Task | NETA test validation Inpections- VECA-EPS-RTS COLO-1 Cell-1 | 17/04/2021 | 20/04/2021 | 15/03/2021 | 24/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10259 | TT_Task | COLO-2 CEll-3 Awaiting SE Revised tool Come along for MER Lift Set | 01/03/2021 | 04/03/2021 | 18/02/2021 | 01/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10260 | TT_Task | Admin - NETA test validation Inpections- VECA-EPS-RTS Admin | 01/03/2021 | 03/03/2021 | 11/03/2021 | 12/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10261 | TT_Task | 6.1.34.2 COLO-1 Cell-2 Rework on ATS Input conductors | 01/03/2021 | 03/03/2021 | 24/02/2021 | 01/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10262 | TT_Task | 6.1.34.3 COLO-1 Cell-3 Rework on ATS Input conductors | 01/03/2021 | 03/03/2021 | 27/02/2021 | 03/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10263 | TT_Task | 6.1.34.4 COLO-1 Cell-4 Rework on ATS Input conductors | 01/03/2021 | 03/03/2021 | 27/02/2021 | 03/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10265 | TT_Task | 6.1.01.0 Awaiting MER 10A HRG's (lead time= 8 weeks from 2/2/2021) | 01/03/2021 | 12/04/2021 | 02/02/2021 | 30/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10266 | TT_Task | 6.1.09 Awaiting Rev-D for Coordination study (DRB3/SCCS/ Submittal Breaker verification) | 01/03/2021 | 04/03/2021 | 19/01/2021 | 01/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10267 | TT_Task | 6.1.11 Awaiting BAS Backplanes from Siemens to VECA for Installation | 01/03/2021 | 04/03/2021 | 01/02/2021 | 13/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10269 | TT_Task | 6.1.26.1 L2/L3 Scripts SE MER overall Script | 01/03/2021 | 04/03/2021 | 10/02/2021 | 23/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10270 | TT_Task | 6.1.33 URS UMS Ground Buss hole Pattern | 01/03/2021 | 04/03/2021 | 08/02/2021 | 26/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10271 | TT_Task | 6.1.35 UPS battery IR Scanning | 01/03/2021 | 04/03/2021 | 10/02/2021 | 01/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10273 | TT_Task | 6.1.37- 6.2.01- Ground Fault setting on COLO-2 Gen MCB01 | 01/03/2021 | 04/03/2021 | 23/02/2021 | 28/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10274 | TT_Task | 6.1.38 PDU MCB01 LOTO Provisions | 01/03/2021 | 04/03/2021 | 01/03/2021 | 04/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10275 | TT_Task | 6.1.26.2 L2/L3 Scripts Siemens BAS SAT Scripts | 01/03/2021 | 04/03/2021 | 09/02/2021 | 22/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10276 | TT_Task | COLO-2 Cell-1 Remove/ Replace busway hangers | 22/03/2021 | 25/03/2021 | 08/03/2021 | 10/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10277 | TT_Task | COLO-2 Cell-2 Remove/ Replace busway hangers | 22/03/2021 | 25/03/2021 | 08/03/2021 | 10/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10278 | TT_Task | Generator Utility Power Term | 01/02/2021 | 10/02/2021 | 19/02/2021 | 26/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10279 | TT_Task | COLO-1 Cell-1 Field Modification of tray | 01/03/2021 | 27/03/2021 | 18/01/2021 | 15/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10280 | TT_Task | COLO-1 Cell-2 Field Modification of tray | 01/03/2021 | 31/03/2021 | 21/01/2021 | 22/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10281 | TT_Task | COLO-2 Cell-1 Rearrange Roxtec blocks per coordination layout | 31/03/2021 | 03/04/2021 | 01/03/2021 | 04/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10282 | TT_Task | COLO2 CELL1 Interior MER conduit installation utility side | 31/03/2021 | 05/04/2021 | 01/03/2021 | 05/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10283 | TT_Task | COLO-2 Cell-1 Interior MER conduit installation building side | 05/04/2021 | 19/04/2021 | 05/03/2021 | 18/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10284 | TT_Mile | SE directs VECA to start Roxtec fixes | 31/03/2021 | 31/03/2021 | 01/03/2021 | 01/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10285 | TT_Task | COLO-2 CELL3 Rearrange Roxtec blocks per coordination layout | 31/03/2021 | 31/03/2021 | 30/03/2021 | 30/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10286 | TT_Task | COLO2 CELL3 Interior MER conduit installation utility side | 06/04/2021 | 06/04/2021 | 26/03/2021 | 30/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10287 | TT_Task | COLO-2 CELL3 Interior MER conduit installation building side | 20/04/2021 | 20/04/2021 | 30/03/2021 | 30/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10288 | TT_Mile | SE directs VECA to start Roxtec fixes | 31/03/2021 | 31/03/2021 | 26/03/2021 | 26/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10289 | TT_Task | COLO-2 Cell2 Rearrange Roxtec blocks per coordination layout (delete) | 01/06/2021 | 01/06/2021 | 30/05/2021 | 30/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10290 | TT_Task | COLO2 CELL2 Interior MER conduit installation utility side(delete) | 01/06/2021 | 01/06/2021 | 30/05/2021 | 30/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10291 | TT_Task | COLO-2 CELL2 Interior MER conduit installation building (delete) | 01/06/2021 | 01/06/2021 | 30/04/2021 | 30/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10292 | TT_Mile | SE directs VECA to start Roxtec fixes(delete) | 01/06/2021 | 01/06/2021 | 30/05/2021 | 30/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10293 | TT_Task | COLO-2 Cell-4 Rearrange Roxtec blocks per coordination layout | 01/06/2021 | 01/06/2021 | 31/03/2021 | 31/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10294 | TT_Task | COLO2 CELL4 Interior MER conduit installation utility side | 01/06/2021 | 01/06/2021 | 31/03/2021 | 31/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10295 | TT_Task | COLO2 CELL4 Interior MER conduit installation building side | 01/06/2021 | 01/06/2021 | 31/03/2021 | 31/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10296 | TT_Mile | SE directs VECA to start Roxtec fixes | 01/06/2021 | 01/06/2021 | 30/03/2021 | 30/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10297 | TT_Mile | SE directs VECA to start Flex Conduit fixes | 31/03/2021 | 31/03/2021 | 01/03/2021 | 01/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10298 | TT_Task | COLO-2 Cell-1 MER Flex Conduit fixes | 01/06/2021 | 01/06/2021 | 31/03/2021 | 31/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10300 | TT_Task | COLO-2 Cell-3 MER Flex Conduit fixes | 01/06/2021 | 01/06/2021 | 31/03/2021 | 31/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10299 | TT_Task | COLO-2 Cell-2 MER Flex Conduit fixes | 01/06/2021 | 01/06/2021 | 31/03/2021 | 31/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10301 | TT_Task | COLO-2 Cell-4 MER Flex Conduit fixes | 01/06/2021 | 01/06/2021 | 31/03/2021 | 31/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10302 | TT_Task | COLO2 CELL1 MER Security/Telecom Missing Raceway installation | 01/06/2021 | 01/06/2021 | 31/03/2021 | 31/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10304 | TT_Task | COLO2 CELL3 MER Security/Telecom Missing Raceway installation | 01/06/2021 | 01/06/2021 | 31/03/2021 | 31/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10303 | TT_Task | COLO2 CELL2 MER Security/Telecom Missing Raceway installation | 01/06/2021 | 01/06/2021 | 31/03/2021 | 31/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10305 | TT_Task | COLO2 CELL4 MER Security/Telecom Missing Raceway installation | 01/06/2021 | 01/06/2021 | 31/03/2021 | 31/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10306 | TT_Task | RFI#432 | 01/03/2021 | 04/03/2021 | 22/02/2021 | 24/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10307 | TT_Task | Lead time for tube steel | 01/03/2021 | 10/03/2021 | 02/02/2021 | 03/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10308 | TT_Task | COLO-2 Cell-3 Install Tube steel Cable tray transition per RFI#432 | 02/03/2021 | 05/03/2021 | 02/03/2021 | 04/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10309 | TT_Task | COLO-2 Cell-2 Install Tube steel Cable tray transition per RFI#432 | 01/04/2021 | 05/04/2021 | 02/03/2021 | 04/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10310 | TT_Task | COLO-2 Cell-4 Install Tube steel Cable tray transition per RFI#432 | 02/03/2021 | 05/03/2021 | 02/03/2021 | 04/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10311 | TT_Task | COLO-3 Cell-1 Install Tube steel Cable tray transition per RFI#432 | 07/05/2021 | 07/05/2021 | 10/04/2021 | 10/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10312 | TT_Task | COLO-3 Cell-3 Install Tube steel Cable tray transition per RFI#432 | 19/05/2021 | 19/05/2021 | 19/05/2021 | 19/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10313 | TT_Task | COLO-3 Cell-2 Install Tube steel Cable tray transition per RFI#432 | 13/05/2021 | 13/05/2021 | 13/05/2021 | 13/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10314 | TT_Task | COLO-3 Cell-4 Install Tube steel Cable tray transition per RFI#432 | 26/05/2021 | 26/05/2021 | 26/05/2021 | 26/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10315 | TT_Task | COLO-4 Cell-1 Install Tube steel Cable tray transition per RFI#432 | 02/06/2021 | 02/06/2021 | 07/05/2021 | 07/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10316 | TT_Task | COLO-4 Cell-3 Install Tube steel Cable tray transition per RFI#432 | 07/06/2021 | 07/06/2021 | 07/05/2021 | 07/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10317 | TT_Task | COLO-4 Cell-2 Install Tube steel Cable tray transition per RFI#432 | 08/06/2021 | 08/06/2021 | 07/05/2021 | 07/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10318 | TT_Task | COLO-4 Cell-4 Install Tube steel Cable tray transition per RFI#432 | 14/06/2021 | 14/06/2021 | 15/05/2021 | 15/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10319 | TT_Task | COLO-2 Cell-1 SE Install UPS batteries in cabinet | 31/03/2021 | 06/04/2021 | 29/03/2021 | 03/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10322 | TT_Task | COLO-2 Cell-4 SE Install UPS batteries in cabinet | 15/05/2021 | 21/05/2021 | 20/04/2021 | 26/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10321 | TT_Task | COLO-2 Cell-3 SE Install UPS batteries in cabinet | 08/05/2021 | 14/05/2021 | 13/04/2021 | 19/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10320 | TT_Task | COLO-2 Cell-2 SE Install UPS batteries in cabinet | 30/04/2021 | 07/05/2021 | 05/04/2021 | 12/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10323 | TT_Task | COLO-3 Cell-1 SE Install UPS batteries in cabinet | 17/05/2021 | 24/05/2021 | 30/04/2021 | 07/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10326 | TT_Task | COLO-3 Cell-4 SE Install UPS batteries in cabinet | 08/06/2021 | 15/06/2021 | 28/05/2021 | 04/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10325 | TT_Task | COLO-3 Cell-3 SE Install UPS batteries in cabinet | 01/06/2021 | 07/06/2021 | 19/05/2021 | 27/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10324 | TT_Task | COLO-3 Cell-2 SE Install UPS batteries in cabinet | 25/05/2021 | 01/06/2021 | 08/05/2021 | 14/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10327 | TT_Task | COLO-4 Cell-1 SE Install UPS batteries in cabinet | 14/09/2021 | 20/09/2021 | 12/08/2021 | 19/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10330 | TT_Task | COLO-4 Cell-4 SE Install UPS batteries in cabinet | 21/09/2021 | 28/09/2021 | 20/08/2021 | 26/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10329 | TT_Task | COLO-4 Cell-3 SE Install UPS batteries in cabinet | 07/09/2021 | 13/09/2021 | 05/08/2021 | 11/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10328 | TT_Task | COLO-4 Cell-2 SE Install UPS batteries in cabinet | 29/09/2021 | 05/10/2021 | 27/08/2021 |  | 320 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
MWH06-10331 | TT_Task | Awaiting Phase conductor lugs from NC power as per RFI#412 | 01/03/2021 | 04/03/2021 | 23/02/2021 | 05/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10332 | TT_Task | 6.1.01.1 MER 10A HRG Retrofit COLO-1 Cell-1 | 01/06/2021 | 05/06/2021 | 15/05/2021 | 10/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10333 | TT_Task | 6.1.01.4 MER 10A HRG Retrofit COLO-1 Cell-4 | 01/06/2021 | 05/06/2021 | 01/06/2021 | 10/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10334 | TT_Task | 6.1.01.3 MER 10A HRG Retrofit COLO-1 Cell-3 | 01/06/2021 | 05/06/2021 | 01/06/2021 | 10/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10335 | TT_Task | 6.1.01.2 MER 10A HRG Retrofit COLO-1 Cell-2 | 01/06/2021 | 05/06/2021 | 01/06/2021 | 10/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10336 | TT_Task | MER shipping split connection Safety Standown RCA Review | 01/03/2021 | 04/03/2021 | 05/02/2021 | 17/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10337 | TT_Task | NETA test validation Inpections- VECA-EPS-RTS COLO-1 Cell-3 | 01/06/2021 | 03/06/2021 | 12/05/2021 | 14/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10338 | TT_Task | NETA test validation Inpections- VECA-EPS-RTS COLO-1 Cell-2 | 01/06/2021 | 03/06/2021 | 03/05/2021 | 05/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10339 | TT_Task | NETA test validation Inpections- VECA-EPS-RTS COLO-1 Cell-4 | 30/06/2021 | 02/07/2021 | 01/06/2021 | 03/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10340 | TT_Task | NETA test validation Inpections- VECA-EPS-RTS COLO-2 Cell-1 | 31/07/2021 | 03/08/2021 | 27/07/2021 | 29/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10341 | TT_Task | NETA test validation Inpections- VECA-EPS-RTS COLO-2 Cell-3 | 31/07/2021 | 03/08/2021 | 27/07/2021 | 29/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10342 | TT_Task | NETA test validation Inpections- VECA-EPS-RTS COLO-2 Cell-2 | 31/07/2021 | 03/08/2021 | 27/07/2021 | 29/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10343 | TT_Task | NETA test validation Inpections- VECA-EPS-RTS COLO-2 Cell-4 | 31/07/2021 | 03/08/2021 | 27/07/2021 | 29/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10344 | TT_Task | NETA test validation Inpections- VECA-EPS-RTS COLO-3 Cell-1 | 31/08/2021 | 02/09/2021 | 31/07/2021 | 03/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10345 | TT_Task | NETA test validation Inpections- VECA-EPS-RTS COLO-3 Cell-3 | 31/08/2021 | 02/09/2021 | 24/08/2021 | 26/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10346 | TT_Task | NETA test validation Inpections- VECA-EPS-RTS COLO-3 Cell-2 | 31/08/2021 | 02/09/2021 | 31/07/2021 | 03/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10347 | TT_Task | NETA test validation Inpections- VECA-EPS-RTS COLO-3 Cell-4 | 31/08/2021 | 02/09/2021 | 03/08/2021 | 05/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10348 | TT_Task | NETA test validation Inpections- VECA-EPS-RTS COLO-4 Cell-1 | 17/09/2021 | 20/09/2021 |  |  | 180 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10349 | TT_Task | NETA test validation Inpections- VECA-EPS-RTS COLO-4 Cell-3 | 28/09/2021 | 30/09/2021 |  |  | 200 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10350 | TT_Task | NETA test validation Inpections- VECA-EPS-RTS COLO-4 Cell-2 | 17/09/2021 | 20/09/2021 |  |  | 180 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10351 | TT_Task | NETA test validation Inpections- VECA-EPS-RTS COLO-4 Cell-4 | 18/09/2021 | 21/09/2021 |  |  | 270 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10352 | TT_Task | Generator Utility Power Pull | 28/07/2021 | 31/07/2021 | 26/06/2021 | 15/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10353 | TT_Task | Generator Utility Power Pull | 31/07/2021 | 04/08/2021 | 19/07/2021 | 22/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10354 | TT_Task | Generator Utility Power Pull | 31/07/2021 | 04/08/2021 | 29/07/2021 | 05/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10355 | TT_Task | Generator Utility Power Pull | 06/08/2021 | 10/08/2021 | 29/07/2021 | 05/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10356 | TT_Task | Generator Utility Power Pull | 01/06/2021 | 04/06/2021 | 25/06/2021 | 30/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10357 | TT_Task | Generator Utility Power Pull | 01/06/2021 | 04/06/2021 | 18/05/2021 | 24/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10358 | TT_Task | Generator Utility Power Pull | 01/06/2021 | 04/06/2021 | 19/06/2021 | 24/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10359 | TT_Task | Generator Utility Power Pull | 19/05/2021 | 24/05/2021 | 08/05/2021 | 13/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10360 | TT_Task | Generator Utility Power Pull | 13/05/2021 | 17/05/2021 | 09/04/2021 | 15/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10361 | TT_Task | Generator Utility Power Pull | 26/03/2021 | 31/03/2021 | 26/03/2021 | 31/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10362 | TT_Task | Generator Utility Power Pull | 11/05/2021 | 14/05/2021 | 07/04/2021 | 13/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10363 | TT_Task | Generator Utility Power Pull | 30/04/2021 | 05/05/2021 | 25/03/2021 | 30/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10364 | TT_Task | Generator Utility Power Pull | 01/03/2021 | 03/03/2021 | 24/02/2021 | 27/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10365 | TT_Task | Generator Utility Power Pull | 02/02/2021 | 05/02/2021 | 22/01/2021 | 26/02/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10366 | TT_Task | Generator Utility Power Test-Term | 22/03/2021 | 30/03/2021 | 01/03/2021 | 08/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10367 | TT_Task | 6.1.39.1- COLO-3 CEll-1 GEN Belly tank Failed pressure test | 15/03/2021 | 09/04/2021 | 11/02/2021 | 17/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10369 | TT_Task | 6.1.39.2- COLO-3 Cell-1 Replace Belly Tank and Set GEN | 22/03/2021 | 26/03/2021 | 17/03/2021 | 18/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10370 | TT_Task | 6.1.40- 480V house power to Gen Enclousure is Fed OH vs UG | 15/03/2021 | 17/04/2021 | 08/03/2021 | 08/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10371 | TT_Task | 6.1.41 - Incorrect Lugs for Admin Gen Main Bussing | 31/03/2021 | 03/04/2021 | 22/03/2021 | 20/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10372 | TT_Task | COLO-2 Cell-1 Install Missing Raceway Bussing within generator | 31/03/2021 | 03/04/2021 | 29/12/2020 | 01/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10373 | TT_Task | 6.1.43- Updates to Rev D SCCS - Reprint Arc Flash Labels | 15/03/2021 | 17/04/2021 | 15/03/2021 | 22/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10374 | TT_Task | 6.1.43- Updates to Rev D SCCS - Reprint Arc Flash Labels- 2weeks- fab and ship | 06/04/2021 | 06/04/2021 | 23/03/2021 | 05/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10375 | TT_Task | 6.1.43- Updates to Rev D SCCS - Reprint Arc Flash Labels- 1 week to install | 07/04/2021 | 14/04/2021 | 06/04/2021 | 09/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10376 | TT_Task | 6.1.44- MER Battery Monitoring Software � Constraint to EPMS checkouts/Point � Point(needed by 4/23) | 15/03/2021 | 07/06/2021 | 15/03/2021 | 07/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10378 | TT_Task | GCPUD NORTH Mobile substation maintance Mobile Sub re-energization 4/1 � 4/3 | 01/02/2021 | 24/02/2021 | 15/03/2021 | 16/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10380 | TT_Task | GCPUD SOUTH Mobile substation maintance Mobile Sub re-energization 4/1 � 4/3 | 01/02/2021 | 24/02/2021 | 15/03/2021 | 16/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10381 | TT_Task | 6.1.46- Site UPM Inspections | 15/03/2021 | 17/04/2021 | 22/03/2021 | 09/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10382 | TT_Task | 6.1.47- COLO-1 Cell-2 UPS01- Factory Test thermal event | 15/03/2021 | 02/04/2021 | 23/03/2021 | 21/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10383 | TT_Task | COLO-1 Cell-1 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | 22/03/2021 | 06/04/2021 | 09/03/2021 | 18/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10384 | TT_Task | COLO-1 Cell-3 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | 05/04/2021 | 21/04/2021 | 15/03/2021 | 31/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10385 | TT_Task | COLO-1 Cell-2 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | 31/03/2021 | 16/04/2021 | 09/03/2021 | 18/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10386 | TT_Task | COLO-1 Cell-4 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | 31/03/2021 | 16/04/2021 | 29/03/2021 | 13/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10393 | TT_Task | COLO-2 Cell-1 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | 30/04/2021 | 17/05/2021 | 23/04/2021 | 10/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10394 | TT_Task | COLO-2 Cell-3 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | 17/05/2021 | 03/06/2021 | 03/05/2021 | 25/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10396 | TT_Task | COLO-2 Cell-2 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | 17/05/2021 | 03/06/2021 | 26/04/2021 | 10/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10395 | TT_Task | COLO-2 Cell-4 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | 03/05/2021 | 18/05/2021 | 03/05/2021 | 24/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10397 | TT_Task | COLO-3 Cell-1 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | 30/06/2021 | 17/07/2021 | 01/06/2021 | 18/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10398 | TT_Task | COLO-3 Cell-3 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | 30/06/2021 | 17/07/2021 | 14/06/2021 | 16/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10400 | TT_Task | COLO-3 Cell-2 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | 30/06/2021 | 22/07/2021 | 07/06/2021 | 22/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10399 | TT_Task | COLO-3 Cell-4 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | 30/06/2021 | 17/07/2021 | 14/06/2021 | 29/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10401 | TT_Task | COLO-4 Cell-1 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | 09/09/2021 | 24/09/2021 | 07/08/2021 | 24/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10402 | TT_Task | COLO-4 Cell-3 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | 31/08/2021 | 17/09/2021 | 18/08/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
MWH06-10404 | TT_Task | COLO-4 Cell-2 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | 31/08/2021 | 17/09/2021 | 07/08/2021 | 24/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10403 | TT_Task | COLO-4 Cell-4 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | 31/08/2021 | 17/09/2021 | 07/08/2021 | 24/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10417 | TT_Task | COLO-2 Cell-2 Install Missing Raceway Bussing within generator | 31/03/2021 | 03/04/2021 | 10/01/2021 | 01/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10418 | TT_Task | COLO-2 Cell-3 Install Missing Raceway Bussing within generator | 31/03/2021 | 03/04/2021 | 20/01/2021 | 02/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10419 | TT_Task | COLO-2 Cell-4 Install Missing Raceway Bussing within generator | 31/03/2021 | 03/04/2021 | 23/01/2021 | 02/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10420 | TT_Task | COLO-3 Cell-1 Install Missing Raceway Bussing within generator | 26/04/2021 | 28/04/2021 | 05/04/2021 | 08/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10421 | TT_Task | COLO-3 Cell-2 Install Missing Raceway Bussing within generator | 29/04/2021 | 03/05/2021 | 09/04/2021 | 14/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10422 | TT_Task | COLO-3 Cell-3 Install Missing Raceway Bussing within generator | 07/05/2021 | 10/05/2021 | 20/04/2021 | 23/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10423 | TT_Task | COLO-3 Cell-4 Install Missing Raceway Bussing within generator | 04/05/2021 | 06/05/2021 | 15/04/2021 | 19/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10424 | TT_Task | COLO-4 Cell-1 Install Missing Raceway Bussing within generator | 25/05/2021 | 27/05/2021 | 08/05/2021 | 11/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10425 | TT_Task | COLO-4 Cell-2 Install Missing Raceway Bussing within generator | 11/05/2021 | 13/05/2021 | 26/04/2021 | 29/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10426 | TT_Task | COLO-4 Cell-3 Install Missing Raceway Bussing within generator | 20/05/2021 | 24/05/2021 | 05/05/2021 | 07/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10427 | TT_Task | COLO-4 Cell-4 Install Missing Raceway Bussing within generator | 17/05/2021 | 19/05/2021 | 30/04/2021 | 04/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10428 | TT_Task | 6.2.03- Replace ADP01 faulty trip units | 31/03/2021 | 03/04/2021 | 06/04/2021 | 07/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10429 | TT_Task | 6.2.03- Replace Damaged UPM in COLO-4 Cell-4 | 06/05/2021 | 08/05/2021 | 26/04/2021 | 29/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10431 | TT_Task | Downtime awaiting solution for safety space constraint | 26/04/2021 | 13/05/2021 | 01/04/2021 | 20/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10432 | TT_Task | NOPC-18 Remove COLO-1 Cell-1 transformer | 26/04/2021 | 26/04/2021 | 20/04/2021 | 20/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10433 | TT_Task | NOPC-18 Remove COLO-1 Cell-2 transformer | 26/04/2021 | 26/04/2021 | 21/04/2021 | 21/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10434 | TT_Task | NOPC-18 Remove COLO-1 Cell-3 transformer | 26/04/2021 | 26/04/2021 | 26/04/2021 | 26/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10435 | TT_Task | NOPC-18 Remove COLO-1 Cell-4 transformer | 17/05/2021 | 17/05/2021 | 14/05/2021 | 15/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10436 | TT_Task | 6.1.51-COLO-1 Cell-1,2 Factory conductors not terminated per drawings | 30/04/2021 | 05/05/2021 | 20/04/2021 | 27/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-02-MOB-S | TT_Mile | Start Mobilization | 27/04/2020 | 27/04/2020 | 06/04/2020 | 06/04/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10438 | TT_Mile | Start Foundation | 27/04/2020 | 27/04/2020 | 22/04/2020 | 22/04/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10439 | TT_FinMile | Complete Foundation | 26/05/2020 | 26/05/2020 | 17/06/2020 | 17/06/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10444 | TT_Task | NOPC-18 Remove COLO-2 Cell-1 transformer | 01/06/2021 | 23/07/2021 | 11/05/2021 | 08/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10445 | TT_Task | NOPC-18 Remove COLO-2 Cell-2 transformer | 02/06/2021 | 08/07/2021 | 11/05/2021 | 17/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10446 | TT_Task | NOPC-18 Remove COLO-2 Cell-3 transformer | 01/06/2021 | 01/06/2021 | 26/05/2021 | 14/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10447 | TT_Task | NOPC-18 Remove COLO-2 Cell-4 transformer | 01/06/2021 | 01/06/2021 | 25/05/2021 | 26/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10453 | TT_Task | NOPC-18 Remove COLO-4 Cell-1 transformer | 18/09/2021 | 18/09/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10454 | TT_Task | NOPC-18 Remove COLO-4 Cell-2 transformer | 18/09/2021 | 18/09/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10455 | TT_Task | NOPC-18 Remove COLO-4 Cell-3 transformer | 29/09/2021 | 29/09/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10456 | TT_Task | NOPC-18 Remove COLO-4 Cell-4 transformer | 18/09/2021 | 18/09/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10462 | TT_Task | NOPC-18 Remove COLO-3 Cell-1 transformer | 12/08/2021 | 12/08/2021 | 16/07/2021 | 16/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10463 | TT_Task | NOPC-18 Remove COLO-3 Cell-2 transformer | 31/07/2021 | 31/07/2021 | 24/07/2021 | 24/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10464 | TT_Task | NOPC-18 Remove COLO-3 Cell-3 transformer | 31/08/2021 | 31/08/2021 | 19/08/2021 | 19/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10465 | TT_Task | NOPC-18 Remove COLO-3 Cell-4 transformer | 31/08/2021 | 31/08/2021 | 04/08/2021 | 04/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10470 | TT_Task | PDU termination crew downtime due to COVID-19 | 24/04/2021 | 06/05/2021 | 13/04/2021 | 24/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10471 | TT_Task | Rubicon MSB inspection complete (ready for transformer reinstall) | 26/04/2021 | 30/04/2021 | 26/04/2021 | 03/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10472 | TT_Task | MSB inspection complete (ready for transformer reinstall) | 17/05/2021 | 21/05/2021 | 26/04/2021 | 03/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10473 | TT_Task | MSB inspection complete (ready for transformer reinstall) | 17/05/2021 | 21/05/2021 | 06/05/2021 | 12/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10474 | TT_Task | MSB inspection complete (ready for transformer reinstall) | 01/06/2021 | 05/06/2021 | 21/05/2021 | 27/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10475 | TT_Task | 6.1.55-COLO-1 - FC Factoy Re-wire (RFI-502) | 26/04/2021 | 29/04/2021 | 23/04/2021 | 28/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10476 | TT_Task | 6.1.55-COLO-2 - FC Factoy Re-wire (RFI-502) | 01/06/2021 | 04/06/2021 | 24/05/2021 | 28/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10477 | TT_Task | 6.1.55-COLO-3 - FC Factoy Re-wire (RFI-502) | 05/06/2021 | 09/06/2021 | 24/05/2021 | 28/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10478 | TT_Task | 6.1.55-COLO-4 - FC Factoy Re-wire (RFI-502) | 10/06/2021 | 15/06/2021 | 24/05/2021 | 28/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10479 | TT_Task | 6.1.54- TCM Awaiting Admin Siemens Break tank parts | 17/05/2021 | 29/05/2021 | 30/04/2021 | 12/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10480 | TT_Task | 6.1.54- Install Breaktank parts | 26/04/2021 | 29/04/2021 | 21/04/2021 | 12/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10481 | TT_Task | 6.1.11 Awaiting Liftstation #3 BAS Backplanes from Siemens to VECA for Installation | 01/03/2021 | 04/03/2021 | 01/02/2021 | 29/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10482 | TT_Task | 6.1.11 Liftstation #3 BAS Install / Pull wire / term Backplanes | 17/05/2021 | 28/05/2021 | 30/04/2021 | 17/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10483 | TT_Task | 6.1.49 - COLO-1 Cell-1 Awaiting Ground Lug solution, procurement, installation of labelling ATS 01-06 | 30/04/2021 | 22/06/2021 | 14/04/2021 | 16/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10484 | TT_Task | 6.1.50- ADP01- FCB23/FCB24 Two wire circuit design change and potential SCCS change | 30/04/2021 | 05/05/2021 | 20/04/2021 | 09/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10485 | TT_Task | 6.1.50- ADP01- FCB23/FCB24 Two wire circuit design change and potential SCCS change(delete) | 30/04/2021 | 05/05/2021 | 20/04/2021 | 15/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10486 | TT_Task | 6.1.57 -Awaiting revised coordination study #9 | 30/04/2021 | 06/05/2021 | 29/04/2021 | 20/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10487 | TT_Task | Reprint revised panel 3,4 Arc flash labels | 01/06/2021 | 05/06/2021 | 21/05/2021 | 28/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10488 | TT_Task | Print new DC Arc flash labels for Admin ELP | 01/06/2021 | 05/06/2021 | 21/05/2021 | 28/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10489 | TT_Task | Remaining Mechanical Equipment (ADP01) Termimations | 18/03/2021 | 23/03/2021 | 28/04/2021 | 03/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10490 | TT_Task | Remaining Mechanical Equipment (ADP01) Termimations | 22/03/2021 | 14/04/2021 | 28/04/2021 | 03/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10491 | TT_Task | 6.1.53-COLO-1 Cell-1,2 UPS01, PNL01 awaiting missing breakers | 30/04/2021 | 05/05/2021 | 21/04/2021 | 27/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10492 | TT_Task | 6.1.53-COLO-1 Cell-1,2,3,4 UPS01, PNL01 Install/ term Missing breakers | 30/04/2021 | 05/05/2021 | 21/04/2021 | 14/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10496 | TT_Task | 6.1.01.1 MER 10A HRG Retrofit COLO-2 Cell-1 | 30/06/2021 | 07/07/2021 | 26/06/2021 | 09/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10499 | TT_Task | 6.1.01.4 MER 10A HRG Retrofit COLO-2 Cell-4 | 06/07/2021 | 10/07/2021 | 13/07/2021 | 19/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10498 | TT_Task | 6.1.01.3 MER 10A HRG Retrofit COLO-2 Cell-3 | 30/06/2021 | 07/07/2021 | 30/06/2021 | 07/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10497 | TT_Task | 6.1.01.2 MER 10A HRG Retrofit COLO-2 Cell-2 | 30/06/2021 | 07/07/2021 | 30/06/2021 | 07/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10500 | TT_Task | 6.1.01.1 MER 10A HRG Retrofit COLO-3 Cell-1 | 31/08/2021 | 07/09/2021 | 24/08/2021 | 28/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10501 | TT_Task | 6.1.01.4 MER 10A HRG Retrofit COLO-3 Cell-4 | 07/09/2021 | 11/09/2021 |  |  | 10 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10502 | TT_Task | 6.1.01.3 MER 10A HRG Retrofit COLO-3 Cell-3 | 07/09/2021 | 11/09/2021 |  |  | 10 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10503 | TT_Task | 6.1.01.2 MER 10A HRG Retrofit COLO-3 Cell-2 | 09/09/2021 | 14/09/2021 | 25/08/2021 | 30/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10504 | TT_Task | 6.1.01.1 MER 10A HRG Retrofit COLO-4 Cell-1 | 07/10/2021 | 12/10/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10505 | TT_Task | 6.1.01.4 MER 10A HRG Retrofit COLO-4 Cell-4 | 07/10/2021 | 12/10/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10506 | TT_Task | 6.1.01.3 MER 10A HRG Retrofit COLO-4 Cell-3 | 18/10/2021 | 22/10/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10507 | TT_Task | 6.1.01.2 MER 10A HRG Retrofit COLO-4 Cell-2 | 07/10/2021 | 12/10/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-02-BFA-F | TT_FinMile | Complete Beneficial Use - Facilities Operations Centre (FOC) | 21/01/2022 | 21/01/2022 |  |  | 780 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-02-BND-F | TT_FinMile | Complete Beneficial Use - Intermediate Distribution Frame (IDF) | 14/10/2021 | 14/10/2021 |  |  | 1520 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-02-BNF-F | TT_FinMile | Complete Beneficial Use - Facility Cable Room (FCR) | 14/10/2021 | 14/10/2021 |  |  | 1520 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-02-BNM-F | TT_FinMile | Complete Beneficial Use - Meet Me Rooms or Entry Rooms (MMR/ER) | 14/10/2021 | 14/10/2021 |  |  | 1520 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-2-BNS-F | TT_FinMile | Complete Beneficial Use - Security Equipment Room (SER) | 14/10/2021 | 14/10/2021 |  |  | 1520 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-02-BNU-F | TT_FinMile | Complete Beneficial Use | 22/11/2021 | 22/11/2021 |  |  | 1210 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-02-BRN-F | TT_FinMile | Complete Beneficial Use - Regional Network Gateway (RNG) | 14/10/2021 | 14/10/2021 |  |  | 1520 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-02-BSS-F | TT_FinMile | Complete Beneficial Use - Secure Storage | 14/10/2021 | 14/10/2021 |  |  | 1520 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-02-CO-F | TT_FinMile | Complete Certificate of Occupancy | 13/04/2022 | 13/04/2022 |  |  | 90 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-02-CSA-F | TT_FinMile | Complete Interior Finishes/CSA | 31/07/2021 | 31/07/2021 | 19/07/2021 | 19/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-02-EPMS-F | TT_FinMile | Complete EPMS Testing Complete | 03/12/2021 | 03/12/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-02-EW-F | TT_FinMile | Complete Earthworks (Clayco- NIC) | 30/04/2021 | 30/04/2021 | 22/04/2020 | 22/04/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-02-EW-S | TT_Mile | Start Earthworks (Clayco- NIC) | 30/04/2021 | 30/04/2021 | 06/04/2020 | 06/04/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-02-FC-F | TT_FinMile | Final Completion � | 21/01/2022 | 21/01/2022 |  |  | 780 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-02-FIR-F | TT_FinMile | Complete Fire Alarm | 03/12/2021 | 03/12/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-02-L4CX-F | TT_FinMile | Complete L4 Cx (Blue Tag) (Clayco- NIC) | 27/12/2021 | 27/12/2021 |  |  | 1 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-02-L5CX-F | TT_FinMile | Complete L5/IST (White Tag)� (Clayco- NIC) | 27/12/2021 | 27/12/2021 |  |  | 1 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-02-MEP-F | TT_FinMile | Complete MEP Rough-in | 30/04/2021 | 30/04/2021 | 09/12/2020 | 09/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-02-PAD-F | TT_FinMile | Complete Building Footprint Pad Ready (Clayco- NIC) | 30/04/2021 | 30/04/2021 | 22/04/2020 | 22/04/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-02-POW-F | TT_FinMile | Complete Utility Power-ON | 01/06/2021 | 01/06/2021 | 19/05/2021 | 19/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-02-RNI-F | TT_FinMile | Complete Ready for Network Install | 09/12/2021 | 09/12/2021 |  |  | 111 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-02-ROJ-F | TT_FinMile | Complete Last ROJ Arrival | 30/04/2021 | 30/04/2021 | 08/03/2021 | 08/03/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-02-ROJ-S | TT_Mile | Start First ROJ Arrival | 30/04/2021 | 30/04/2021 | 23/09/2020 | 23/09/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-02-SC-F | TT_FinMile | Complete Substantial Completion | 10/01/2022 | 10/01/2022 |  |  | 1 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-02-SSC-F | TT_FinMile | Complete Security System | 15/01/2022 | 15/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-01-BFA-F | TT_FinMile | Complete Beneficial Use - Facilities Operations Centre (FOC) | 22/11/2021 | 22/11/2021 |  |  | 1210 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-01-BND-F | TT_FinMile | Complete Beneficial Use - Intermediate Distribution Frame (IDF) | 14/10/2021 | 14/10/2021 |  |  | 1520 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-01-BNF-F | TT_FinMile | Complete Beneficial Use - Facility Cable Room (FCR) | 14/10/2021 | 14/10/2021 |  |  | 1520 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-01-BNM-F | TT_FinMile | Complete Beneficial Use - Meet Me Rooms or Entry Rooms (MMR/ER) | 14/10/2021 | 14/10/2021 |  |  | 1520 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-01-BNS-F | TT_FinMile | Complete Beneficial Use - Security Equipment Room (SER) | 14/10/2021 | 14/10/2021 |  |  | 1520 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-01-BNU-F | TT_FinMile | Complete Beneficial Use | 22/11/2021 | 22/11/2021 |  |  | 1210 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-01-BRN-F | TT_FinMile | Complete Beneficial Use - Regional Network Gateway (RNG) | 14/10/2021 | 14/10/2021 |  |  | 1520 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-01-BSS-F | TT_FinMile | Complete Beneficial Use - Secure Storage | 14/10/2021 | 14/10/2021 |  |  | 1520 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-01-CO-F | TT_FinMile | Complete Certificate of Occupancy | 13/04/2022 | 13/04/2022 |  |  | 90 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-01-CSA-F | TT_FinMile | Complete Interior Finishes/CSA | 28/06/2021 | 28/06/2021 | 01/06/2021 | 01/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-01-EPMS-F | TT_FinMile | Complete EPMS Testing Complete | 01/10/2021 | 01/10/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-01-EW-F | TT_FinMile | Complete Earthworks (Clayco- NIC) | 30/04/2021 | 30/04/2021 | 22/04/2020 | 22/04/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-01-EW-S | TT_Mile | Start Earthworks (Clayco- NIC) | 30/04/2021 | 30/04/2021 | 06/04/2020 | 06/04/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-01-FC-F | TT_FinMile | Final Completion � | 22/11/2021 | 22/11/2021 |  |  | 1210 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-01-FIR-F | TT_FinMile | Complete Fire Alarm | 01/10/2021 | 01/10/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-01-L4CX-F | TT_FinMile | Complete L4 Cx (Blue Tag) (Clayco- NIC) | 29/10/2021 | 29/10/2021 |  |  | 1 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-01-L5CX-F | TT_FinMile | Complete L5/IST (White Tag)� (Clayco- NIC) | 29/10/2021 | 29/10/2021 |  |  | 1 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-01-MEP-F | TT_FinMile | Complete MEP Rough-in | 30/04/2021 | 30/04/2021 | 30/10/2020 | 30/10/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-01-MOB-S | TT_Mile | Start Mobilization | 30/04/2021 | 30/04/2021 | 06/04/2020 | 06/04/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-01-PAD-F | TT_FinMile | Complete Building Footprint Pad Ready (Clayco- NIC) | 30/04/2021 | 30/04/2021 | 22/04/2020 | 22/04/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-01-POW-F | TT_FinMile | Complete Utility Power-ON | 19/05/2021 | 19/05/2021 | 19/05/2021 | 19/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-01-RNI-F | TT_FinMile | Complete Ready for Network Install | 14/10/2021 | 14/10/2021 |  |  | 121 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-01-ROJ-F | TT_FinMile | Complete Last ROJ Arrival | 30/04/2021 | 30/04/2021 | 08/01/2021 | 08/01/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-01-ROJ-S | TT_Mile | Start First ROJ Arrival | 30/04/2021 | 30/04/2021 | 07/07/2020 | 07/07/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-01-SC-F | TT_FinMile | Complete Substantial Completion | 12/11/2021 | 12/11/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-01-SSC-F | TT_FinMile | Complete Security System | 13/11/2021 | 13/11/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-03-BFA-F | TT_FinMile | Complete Beneficial Use - Facilities Operations Centre (FOC) | 08/02/2022 | 08/02/2022 |  |  | 640 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-03-BND-F | TT_FinMile | Complete Beneficial Use - Intermediate Distribution Frame (IDF) | 14/10/2021 | 14/10/2021 |  |  | 1520 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-03-BNF-F | TT_FinMile | Complete Beneficial Use - Facility Cable Room (FCR) | 14/10/2021 | 14/10/2021 |  |  | 1520 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-03-BNM-F | TT_FinMile | Complete Beneficial Use - Meet Me Rooms or Entry Rooms (MMR/ER) | 14/10/2021 | 14/10/2021 |  |  | 1520 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-03-BNS-F | TT_FinMile | Complete Beneficial Use - Security Equipment Room (SER) | 14/10/2021 | 14/10/2021 |  |  | 1520 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-03-BNU-F | TT_FinMile | Complete Beneficial Use | 08/02/2022 | 08/02/2022 |  |  | 640 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-03-BRN-F | TT_FinMile | Complete Beneficial Use - Regional Network Gateway (RNG) | 14/10/2021 | 14/10/2021 |  |  | 1520 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-03-BSS-F | TT_FinMile | Complete Beneficial Use - Secure Storage | 14/10/2021 | 14/10/2021 |  |  | 1520 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-03-CO-F | TT_FinMile | Complete Certificate of Occupancy | 13/04/2022 | 13/04/2022 |  |  | 90 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-03-CSA-F | TT_FinMile | Complete Interior Finishes/CSA | 31/08/2021 | 31/08/2021 | 12/08/2021 | 12/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-03-EPMS-F | TT_FinMile | Complete EPMS Testing Complete | 18/01/2022 | 18/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-03-EW-F | TT_FinMile | Complete Earthworks (Clayco- NIC) | 30/04/2021 | 30/04/2021 | 22/04/2020 | 22/04/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-03-EW-S | TT_Mile | Start Earthworks (Clayco- NIC) | 30/04/2021 | 30/04/2021 | 06/04/2020 | 06/04/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-03-FC-F | TT_FinMile | Final Completion � | 08/02/2022 | 08/02/2022 |  |  | 640 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-03-FIR-F | TT_FinMile | Complete Fire Alarm | 18/01/2022 | 18/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-03-L4CX-F | TT_FinMile | Complete L4 Cx (Blue Tag) (Clayco- NIC) | 08/02/2022 | 08/02/2022 |  |  | 1 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-03-L5CX-F | TT_FinMile | Complete L5/IST (White Tag)� (Clayco- NIC) | 08/02/2022 | 08/02/2022 |  |  | 1 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-03-MEP-F | TT_FinMile | Complete MEP Rough-in | 28/06/2021 | 28/06/2021 | 01/06/2021 | 01/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-03-MOB-S | TT_Mile | Start Mobilization | 30/04/2021 | 30/04/2021 | 06/04/2020 | 06/04/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-03-PAD-F | TT_FinMile | Complete Building Footprint Pad Ready | 30/04/2021 | 30/04/2021 | 22/04/2020 | 22/04/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-03-POW-F | TT_FinMile | Complete Utility Power-ON | 01/06/2021 | 01/06/2021 | 19/05/2021 | 19/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-03-RNI-F | TT_FinMile | Complete Ready for Network Install | 25/01/2022 | 25/01/2022 |  |  | 111 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-03-ROJ-F | TT_FinMile | Complete Last ROJ Arrival | 30/04/2021 | 30/04/2021 | 23/04/2021 | 23/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-03-ROJ-S | TT_Mile | Start First ROJ Arrival | 30/04/2021 | 30/04/2021 | 20/11/2020 | 20/11/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-03-SC-F | TT_FinMile | Complete Substantial Completion | 22/02/2022 | 22/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-03-SSC-F | TT_FinMile | Complete Security System | 23/02/2022 | 23/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-04-BFA-F | TT_FinMile | Complete Beneficial Use - Facilities Operations Centre (FOC) | 13/04/2022 | 13/04/2022 |  |  | 90 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-04-BND-F | TT_FinMile | Complete Beneficial Use - Intermediate Distribution Frame (IDF) | 14/10/2021 | 14/10/2021 |  |  | 1520 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-04-BNF-F | TT_FinMile | Complete Beneficial Use - Facility Cable Room (FCR) | 14/10/2021 | 14/10/2021 |  |  | 1520 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-04-BNM-F | TT_FinMile | Complete Beneficial Use - Meet Me Rooms or Entry Rooms (MMR/ER) | 14/10/2021 | 14/10/2021 |  |  | 1520 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-04-BNS-F | TT_FinMile | Complete Beneficial Use - Security Equipment Room (SER) | 14/10/2021 | 14/10/2021 |  |  | 1520 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-04-BNU-F | TT_FinMile | Complete Beneficial Use | 13/04/2022 | 13/04/2022 |  |  | 90 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-04-BRN-F | TT_FinMile | Complete Beneficial Use - Regional Network Gateway (RNG) | 14/10/2021 | 14/10/2021 |  |  | 1520 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-04-BSS-F | TT_FinMile | Complete Beneficial Use - Secure Storage | 14/10/2021 | 14/10/2021 |  |  | 1520 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-04-CO-F | TT_FinMile | Complete Certificate of Occupancy | 13/04/2022 | 13/04/2022 |  |  | 90 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-04-CSA-F | TT_FinMile | Complete Interior Finishes/CSA | 07/10/2021 | 07/10/2021 |  |  | 1580 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-04-EPMS-F | TT_FinMile | Complete EPMS Testing Complete | 12/02/2022 | 12/02/2022 |  |  | 120 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-04-EW-F | TT_FinMile | Complete Earthworks (Clayco- NIC) | 30/04/2021 | 30/04/2021 | 22/04/2020 | 22/04/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-04-EW-S | TT_Mile | Start Earthworks (Clayco- NIC) | 30/04/2021 | 30/04/2021 | 06/04/2020 | 06/04/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-04-FC-F | TT_FinMile | Final Completion � | 13/04/2022 | 13/04/2022 |  |  | 90 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-04-FIR-F | TT_FinMile | Complete Fire Alarm | 26/02/2022 | 26/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-04-L4CX-F | TT_FinMile | Complete L4 Cx (Blue Tag) (Clayco- NIC) | 21/03/2022 | 21/03/2022 |  |  | 1 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-04-L5CX-F | TT_FinMile | Complete L5/IST (White Tag)� (Clayco- NIC) | 21/03/2022 | 21/03/2022 |  |  | 1 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-04-MEP-F | TT_FinMile | Complete MEP Rough-in | 31/07/2021 | 31/07/2021 | 07/07/2021 | 07/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-04-MOB-S | TT_Mile | Start Mobilization | 30/04/2021 | 30/04/2021 | 06/04/2020 | 06/04/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-04-PAD-F | TT_FinMile | Complete Building Footprint Pad Ready (Clayco- NIC) | 30/04/2021 | 30/04/2021 | 22/04/2020 | 22/04/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-04-POW-F | TT_FinMile | Complete Utility Power-ON | 01/06/2021 | 01/06/2021 | 19/05/2021 | 19/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-04-RNI-F | TT_FinMile | Complete Ready for Network Install | 07/03/2022 | 07/03/2022 |  |  | 121 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-04-ROJ-F | TT_FinMile | Complete Last ROJ Arrival | 31/07/2021 | 31/07/2021 | 10/05/2021 | 10/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-04-ROJ-S | TT_Mile | Start First ROJ Arrival | 30/04/2021 | 30/04/2021 | 12/12/2020 | 12/12/2020 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH-06-04-SC-F | TT_FinMile | Complete Substantial Completion | 02/04/2022 | 02/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH-06-04-SSC-F | TT_FinMile | Complete Security System | 04/04/2022 | 04/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10508 | TT_Task | 6.1.59 (6.1.51 carryover) -COLO-1 Cell-1,2 Factory conductors exertherm corrections | 30/04/2021 | 05/05/2021 | 20/04/2021 | 20/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10509 | TT_Task | NOPC-18 Reinstall COLO-1 Cell-1 transformer | 25/05/2021 | 29/05/2021 | 04/05/2021 | 14/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10510 | TT_Task | NOPC-18 Reinstall COLO-1 Cell-2 transformer | 01/06/2021 | 05/06/2021 | 04/05/2021 | 14/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10511 | TT_Task | NOPC-18 Reinstall COLO-1 Cell-3 transformer | 01/06/2021 | 09/06/2021 | 26/05/2021 | 28/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10512 | TT_Task | NOPC-18 Reinstall COLO-1 Cell-4 transformer | 01/06/2021 | 09/06/2021 | 26/05/2021 | 28/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10513 | TT_Task | NOPC-18 Reinstall COLO-2 Cell-1 transformer | 22/07/2021 | 31/07/2021 | 17/06/2021 | 26/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10514 | TT_Task | NOPC-18 Reinstall COLO-2 Cell-2 transformer | 23/07/2021 | 02/08/2021 | 24/06/2021 | 30/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10515 | TT_Task | NOPC-18 Reinstall COLO-2 Cell-3 transformer | 29/07/2021 | 06/08/2021 | 21/06/2021 | 26/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10516 | TT_Task | NOPC-18 Reinstall COLO-2 Cell-4 transformer | 30/06/2021 | 02/07/2021 | 09/07/2021 | 12/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10517 | TT_Task | NOPC-18 Reinstall COLO-3 Cell-1 transformer | 31/07/2021 | 06/08/2021 | 22/07/2021 | 29/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10518 | TT_Task | NOPC-18 Reinstall COLO-3 Cell-2 transformer | 31/08/2021 | 08/09/2021 | 31/07/2021 | 06/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10519 | TT_Task | NOPC-18 Reinstall COLO-3 Cell-3 transformer | 31/08/2021 | 08/09/2021 | 27/08/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
MWH06-10520 | TT_Task | NOPC-18 Reinstall COLO-3 Cell-4 transformer | 31/08/2021 | 08/09/2021 | 27/08/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
MWH06-10521 | TT_Task | NOPC-18 Reinstall COLO-4 Cell-1 transformer | 30/09/2021 | 06/10/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10522 | TT_Task | NOPC-18 Reinstall COLO-4 Cell-2 transformer | 30/09/2021 | 06/10/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10523 | TT_Task | NOPC-18 Reinstall COLO-4 Cell-3 transformer | 09/10/2021 | 15/10/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10524 | TT_Task | NOPC-18 Reinstall COLO-4 Cell-4 transformer | 30/09/2021 | 06/10/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10525 | TT_Task | 6.1.58-RFI-528- COLO-1 - SF/RF Circuitry terminal block rework | 17/05/2021 | 20/05/2021 | 03/05/2021 | 24/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10527 | TT_Task | 6.1.63- COLO1-UPS01-PNL01 Compass Issues Constraining L3�s | 17/05/2021 | 20/05/2021 | 12/05/2021 | 01/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10530 | TT_Task | All trades stand down | 01/06/2021 | 03/06/2021 | 15/05/2021 | 18/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10531 | TT_Task | Veca standown | 01/06/2021 | 07/06/2021 | 15/05/2021 | 21/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10532 | TT_Task | 6.1.56 - COLO-1 Awaiting MSB/ADP Ground Lug replacements, Installation of labelling | 30/04/2021 | 26/05/2021 | 30/04/2021 | 16/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10534 | TT_Task | 6.1.50- SCCS Revision#10 (RFI-540) | 30/04/2021 | 05/05/2021 | 26/05/2021 | 15/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.Cx4011 | TT_Task | Security Commissioning (level3 DCPS) | 09/11/2021 | 13/11/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C2.Cx4001 | TT_Task | Security Commissioning (level3 DCPS) | 11/01/2022 | 15/01/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C3.Cx4011 | TT_Task | Security Commissioning (level3 DCPS) | 19/02/2022 | 23/02/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06.C4.Cx4011 | TT_Task | Security Commissioning (level3 DCPS) | 31/03/2022 | 04/04/2022 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10535 | TT_Task | COLO-1 Cell-1 MER-UPS Battery Disconnect modifications rework | 16/06/2021 | 19/06/2021 | 16/06/2021 | 21/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10537 | TT_Task | COLO-3 Cell-3 Remove inaccessible tray in MER | 28/06/2021 | 29/06/2021 | 01/06/2021 | 04/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10538 | TT_Task | COLO-3 CEll-3 Reinstall tray in MER | 28/06/2021 | 01/07/2021 | 25/06/2021 | 30/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10539 | TT_Task | COLO-1 Cell-2 MER-UPS Battery Disconnect modifications rework | 28/06/2021 | 01/07/2021 | 16/06/2021 | 21/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10540 | TT_Task | COLO-1 Cell-3 MER-UPS Battery Disconnect modifications rework | 28/06/2021 | 01/07/2021 | 17/06/2021 | 22/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10541 | TT_Task | COLO-1 Cell-4 MER-UPS Battery Disconnect modifications rework | 01/06/2021 | 04/06/2021 | 17/06/2021 | 22/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10542 | TT_Task | RFI-548 COLO MSB to UPS Battery disconnect solution approval | 01/06/2021 | 03/06/2021 | 10/06/2021 | 15/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10543 | TT_Task | ADMIN-UPS Battery Disconnect modifications rework | 16/06/2021 | 19/06/2021 | 24/06/2021 | 09/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10544 | TT_Task | RFI-552 Admin MSB to UPS Battery disconnect solution approval | 01/06/2021 | 07/06/2021 | 16/06/2021 | 23/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10546 | TT_Task | COLO-2 Cell-1 MER-UPS Battery Disconnect modifications rework | 30/06/2021 | 06/07/2021 | 30/06/2021 | 17/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10545 | TT_Task | COLO-2 Cell-2 MER-UPS Battery Disconnect modifications rework | 30/06/2021 | 06/07/2021 | 30/06/2021 | 21/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10547 | TT_Task | COLO-2 Cell-3 MER-UPS Battery Disconnect modifications rework | 01/07/2021 | 07/07/2021 | 01/07/2021 | 17/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10548 | TT_Task | COLO-2 Cell-4 MER-UPS Battery Disconnect modifications rework | 02/07/2021 | 08/07/2021 | 02/07/2021 | 23/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10549 | TT_Task | COLO-3 Cell-1 MER-UPS Battery Disconnect modifications rework | 31/07/2021 | 04/08/2021 | 28/07/2021 | 04/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10550 | TT_Task | COLO-3 Cell-2 MER-UPS Battery Disconnect modifications rework | 31/08/2021 | 03/09/2021 | 05/08/2021 | 09/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10551 | TT_Task | COLO-3 Cell-3 MER-UPS Battery Disconnect modifications rework | 07/09/2021 | 10/09/2021 | 10/08/2021 | 13/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10552 | TT_Task | COLO-3 Cell-4 MER-UPS Battery Disconnect modifications rework | 11/09/2021 | 15/09/2021 | 16/08/2021 | 19/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10553 | TT_Task | COLO-4 Cell-1 MER-UPS Battery Disconnect modifications rework | 16/09/2021 | 20/09/2021 | 20/08/2021 | 24/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10554 | TT_Task | COLO-4 Cell-2 MER-UPS Battery Disconnect modifications rework | 21/09/2021 | 24/09/2021 | 25/08/2021 | 28/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10555 | TT_Task | COLO-4 Cell-3 MER-UPS Battery Disconnect modifications rework | 27/09/2021 | 30/09/2021 | 30/08/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
MWH06-10556 | TT_Task | COLO-4 Cell-4 MER-UPS Battery Disconnect modifications rework | 03/09/2021 | 09/09/2021 |  |  | 270 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10557 | TT_Task | COLO-3 Cell-4 Remove inaccessible tray in MER | 30/06/2021 | 01/07/2021 | 10/06/2021 | 12/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10558 | TT_Task | COLO-3 Cell-4 Reinstall tray in MER | 30/06/2021 | 02/07/2021 | 23/06/2021 | 26/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10560 | TT_Task | COLO-4 Cell-1 Remove inaccessible tray in MER | 12/07/2021 | 13/07/2021 | 10/06/2021 | 12/06/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10561 | TT_Task | COLO-4 Cell-1 Reinstall tray in MER | 03/08/2021 | 05/08/2021 | 16/07/2021 | 19/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10562 | TT_Task | COLO-4 Cell-2 Remove inaccessible tray in MER | 31/07/2021 | 02/08/2021 | 16/07/2021 | 20/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10563 | TT_Task | COLO-4 Cell-2 Reinstall tray in MER | 31/08/2021 | 02/09/2021 | 31/07/2021 | 04/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10564 | TT_Task | COLO-4 Cell-3 Remove inaccessible tray in MER | 31/07/2021 | 02/08/2021 | 15/07/2021 | 17/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10565 | TT_Task | COLO-4 Cell-3 Reinstall tray in MER | 06/08/2021 | 09/08/2021 | 23/07/2021 | 27/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10566 | TT_Task | COLO-4 Cell-4 Remove inaccessible tray in MER4 | 04/08/2021 | 05/08/2021 | 26/07/2021 | 28/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10567 | TT_Task | COLO-4 Cell-4 Reinstall tray in MER | 03/09/2021 | 08/09/2021 | 09/08/2021 | 12/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10568 | TT_Task | COLO-3 Cell-1 Remove inaccessible tray in MER | 28/06/2021 | 30/06/2021 | 20/04/2021 | 23/04/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10569 | TT_Task | COLO-3 CEll-1 Reinstall tray in MER | 28/06/2021 | 30/06/2021 | 14/05/2021 | 19/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10570 | TT_Task | COLO-3 Cell-2 Remove inaccessible tray in MER | 30/06/2021 | 02/07/2021 | 28/04/2021 | 03/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10571 | TT_Task | COLO-3 Cell-2 Reinstall tray in MER | 30/06/2021 | 02/07/2021 | 25/05/2021 | 28/05/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10572 | TT_Task | #4. Extreme Heat - 6/28/21- 7/2/21(Effecting COLO-4 Yard work) | 30/06/2021 | 07/07/2021 | 28/06/2021 | 02/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10573 | TT_Task | CSA Punchlist - COLO-1 | 31/07/2021 | 11/08/2021 | 26/07/2021 | 03/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10574 | TT_Task | #5 Extreme heat -production loss in Yards 7/1/21 through 7/14/21 (11 half days of loss) | 31/07/2021 | 05/08/2021 | 09/07/2021 | 14/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10575 | TT_Task | COLO-3 Cell-3 Conduit rework | 31/07/2021 | 16/08/2021 | 14/07/2021 | 29/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10576 | TT_Task | COLO-4 Cell-1 Conduit rework | 31/07/2021 | 16/08/2021 | 23/07/2021 | 09/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10577 | TT_Task | COLO-4 Cell-2 Conduit rework | 31/07/2021 | 16/08/2021 | 16/07/2021 | 31/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10578 | TT_Task | COLO-4 Cell-3 Conduit rework | 31/08/2021 | 16/09/2021 | 03/08/2021 | 18/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10579 | TT_Task | COLO-4 Cell-4 Conduit rework | 31/07/2021 | 16/08/2021 | 20/07/2021 | 04/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10580 | TT_Task | #6 Extreme heat - Production loss in Yards 7/15/21 through 7/31/21 (3 half days) | 31/07/2021 | 31/07/2021 | 26/07/2021 | 27/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10581 | TT_Task | 6.1-88 COLO-1 MER awaiting updated UPS L3 test script approval | 14/07/2021 | 17/07/2021 | 20/07/2021 | 31/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10582 | TT_Task | 6.1-89 RFI574- COLO-1 Relocating MSB EPMS device to different cabinet | 14/07/2021 | 17/07/2021 | 21/07/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
MWH06-10583 | TT_Task | 6.1-92 COLO-1 SF/ RF startup delay (vendor schedule availability) | 14/07/2021 | 17/07/2021 | 23/07/2021 | 30/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10584 | TT_Task | 6.1-93 COLO-1 HVAC minisplits startup delay (vendor schedule availability) | 14/07/2021 | 17/07/2021 | 23/07/2021 | 29/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10585 | TT_Task | 6.1-95 COLO-1 ATS's L3 startup delay (vendor schedule availability) | 14/07/2021 | 28/07/2021 | 21/07/2021 | 30/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10586 | TT_Task | ATS- Lvl 3 Testing Start up (Electrical Equipment) | 10/07/2021 | 15/07/2021 | 10/07/2021 |  | 100 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
MWH06-10587 | TT_Task | 6.1-96 COLO-1 PDU - EPMS L3 startup delay (vendor schedule availability) | 31/07/2021 | 04/08/2021 | 26/07/2021 | 02/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10588 | TT_Task | 6.2-08 COLO-2 Cell- 1,2 MER equipment Phenolic labelling | 14/07/2021 | 16/08/2021 | 21/06/2021 | 23/07/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10589 | TT_Task | 6.2-08 COLO-2 Cell- 3,4 MER equipment Phenolic labelling | 14/07/2021 | 16/08/2021 | 21/06/2021 | 02/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10590 | TT_Task | 6.2-12 COLO-2 All Cells- Factory connection Torque verification | 14/07/2021 | 21/07/2021 | 26/07/2021 | 02/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10592 | TT_Task | CSA Punchlist - COLO-2 | 08/10/2021 | 20/10/2021 |  |  | 220 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10593 | TT_Task | CSA Punchlist - COLO-3 | 01/11/2021 | 12/11/2021 |  |  | 360 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10594 | TT_Task | CSA Punchlist - COLO-4 | 11/12/2021 | 23/12/2021 |  |  | 380 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10595 | TT_Task | MEP Punchlist - COLO-1 | 07/09/2021 | 17/09/2021 |  |  | 110 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10596 | TT_Task | MEP Punchlist - COLO-2 | 17/11/2021 | 01/12/2021 |  |  | 20 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10597 | TT_Task | MEP Punchlist - COLO-3 | 04/01/2022 | 15/01/2022 |  |  | 20 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10598 | TT_Task | MEP Punchlist - COLO-4 | 14/02/2022 | 24/02/2022 |  |  | 20 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10599 | TT_Task | AE/Owner Punchlist - COLO-1 | 30/10/2021 | 04/11/2021 |  |  | 60 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10600 | TT_Task | AE/Owner Punchlist - COLO-2 | 27/12/2021 | 03/01/2022 |  |  | 41 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10601 | TT_Task | AE/Owner Punchlist - COLO-3 | 09/02/2022 | 14/02/2022 |  |  | 71 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10602 | TT_Task | AE/Owner Punchlist - COLO-4 | 21/03/2022 | 25/03/2022 |  |  | 70 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10603 | TT_Task | COLO-2 Cell-1 UPS PNL01 Compass issues Preventing CYT | 31/08/2021 | 13/09/2021 | 04/08/2021 | 17/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10604 | TT_Task | COLO-2 Cell-2 UPS PNL01 Compass issues Preventing CYT | 31/08/2021 | 13/09/2021 | 04/08/2021 | 17/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10605 | TT_Task | COLO-2 Cell-3 UPS PNL01 Compass issues Preventing CYT | 31/08/2021 | 13/09/2021 | 04/08/2021 | 17/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10606 | TT_Task | COLO-2 Cell-4 UPS PNL01 Compass issues Preventing CYT | 31/08/2021 | 13/09/2021 | 04/08/2021 | 17/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06.C1.Cx3020.1 | TT_Task | Additional Go-Back loadbanking (ASCO) | 10/09/2021 | 13/09/2021 |  |  | 0 | TK_NotStart | MWH-06-UP#13_FSW_REV.graphml
MWH06-10607 | TT_Task | 6.1-98 Admin/COLO-1 ASCO EPMS Connectivity Issues | 31/08/2021 | 10/09/2021 | 30/08/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
MWH06-10608 | TT_Task | 6.1-88 Admin/ COLO-1 MER/ADMIN UPS L3 Testing (includes shutdown to move PQM's PQM data post proccessing) | 31/08/2021 | 13/09/2021 | 31/08/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
MWH06-10609 | TT_Task | 6.1-106 COLO-1 Cell-2 UPS01 Power module failure | 31/08/2021 | 13/09/2021 | 27/08/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
MWH06-10610 | TT_Task | COLO-2 Cell-1 Open Issues preventing Yellow tags MER Equipment | 31/08/2021 | 29/09/2021 | 03/08/2021 | 30/08/2021 | 0 | TK_Complete | MWH-06-UP#13_FSW_REV.graphml
MWH06-10611 | TT_Task | COLO-2 Cell-2 Open Issues preventing Yellow tags MER Equipment | 31/08/2021 | 01/10/2021 | 03/08/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
MWH06-10612 | TT_Task | COLO-2 Cell-3 Open Issues preventing Yellow tags MER Equipment | 31/08/2021 | 01/10/2021 | 03/08/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
MWH06-10613 | TT_Task | COLO-2 Cell-4 Open Issues preventing Yellow tags MER Equipment | 31/08/2021 | 01/10/2021 | 03/08/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml
MWH06-10614 | TT_Task | COLO-3 Delay in SE uploading QC Checkilst | 31/08/2021 | 03/09/2021 | 06/08/2021 |  | 0 | TK_Active | MWH-06-UP#13_FSW_REV.graphml